## Pivot Tavble
Sum of Budgeted Units | Column Labels
Row Labels | CONTRB UNIV LBR.CONTRB UNIV LBR | ELEC DES.ELEC DES | ELEC ENG.ELEC ENG | ELEC TECH.ELEC TECH | EXPNS MACHINE SHOP.MSHOP | EXPNS PURCHASD LABOR.PLABOR | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | EXPNS TRAVEL.TRAVEL | MECH DES.MECH DES | MECH ENG.MECH ENG | MECH TECH.MECH TECH | P ELEC TECH.PLABOR | P LABORER.PLABOR | P MECH DES.PLABOR | PD UNIV STAFF.PD UNIV STAFF | PD UNIV STUDNT.PD UNIV STUDNT | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | PRCRMNT<$50K60NESC14.PROCUREMENT<$50K 60 NO ESCALATION FY14 | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | PRCRMNT>$50K69NESC14.PROCUREMENT>$50K 69 NO ESCALATION FY14 | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | SCIENTIST.SCIENTIST | SR STAFF.SR STAFF | VISTNG USERS.VISTNG USERS | Grand Total
1.4.2.2.1.1 SILICON DETECTOR |  |  | 47.5 | 58.5 | [5 empty] | 6.8 | 31.5 |  |  | 0 |  |  | 0 |  | 0 | 0 |  |  | 0 |  |  |  | 91 | 235.3
242211360 | [18 empty] | 0 |  |  |  | 0 |  |  |  |  | 0
242211395 |  |  | 4 | 4 | [23 empty] | 8
242211485 | [9 empty] | 1 | 12 |  |  | 0 | [13 empty] | 13
242211490 |  |  | 1.7 | 1.7 | [22 empty] | 3.4 | 6.8
242211515 | [18 empty] | 0 | [8 empty] | 0
242211520 | [16 empty] | 0 | [10 empty] | 0
242211545 | [9 empty] | 1 | 6 |  |  | 0 | [13 empty] | 7
242211600 |  |  | 4 | 4 | [22 empty] | 8 | 16
242211615 |  |  | 4.5 | 4.5 | [22 empty] | 32 | 41
242211645 |  |  | 4.5 | 9 | [23 empty] | 13.5
242211680 |  |  | 3.7 | 3.7 | [5 empty] | 1.8 | 5.5 | [15 empty] | 6 | 20.7
242211695 | [16 empty] | 0 | [10 empty] | 0
242211700 | [9 empty] | 1 | 4 |  |  | 0 | [13 empty] | 5
242211745 | [16 empty] | 0 | [10 empty] | 0
242211810 | [16 empty] | 0 | [10 empty] | 0
242211815 | [9 empty] | 1 | 2 | [16 empty] | 3
242211825 |  |  |  | 1 | [6 empty] | 0 | [16 empty] | 1
242211830 | [16 empty] | 0 | [10 empty] | 0
242211865 | [16 empty] | 0 | [10 empty] | 0
242211870 | [9 empty] | 1 | 2 |  |  | 0 | [13 empty] | 3
242211876 | [19 empty] | 0 | [7 empty] | 0
242211160w | [22 empty] | 0 |  |  |  |  | 0
242211160w5 | [22 empty] | 0 |  |  |  |  | 0
242211400a |  |  | 4 | 9 | [23 empty] | 13
242211490a |  |  | 20.6 | 20.6 | [22 empty] | 41.6 | 82.8
242211645A |  |  | 0.5 | 1 | [23 empty] | 1.5
1.4.2.2.3.1 CENTRAL TOF |  |  |  | 8 | 0 |  | 0 |  | 18.5 | 6 | 36.4 | [5 empty] | 0 |  |  | 0 |  |  |  |  | 35.1 |  | 12 | 116
242231115 | [6 empty] | 0 |  | 2.5 |  | 2.5 | [13 empty] | 2.5 |  |  | 7.5
242231260 | [8 empty] | 4 | [18 empty] | 4
242231265 | [16 empty] | 0 | [10 empty] | 0
242231270 | [8 empty] | 11.7 | [18 empty] | 11.7
242231272 | [9 empty] | 4 | [17 empty] | 4
242231275 | [19 empty] | 0 | [7 empty] | 0
242231290 | [6 empty] | 0 | [20 empty] | 0
242231295 |  |  |  |  | 0 | [22 empty] | 0
242231300 | [16 empty] | 0 | [10 empty] | 0
242231305 | [16 empty] | 0 | [10 empty] | 0
242231325 | [9 empty] | 0.3 | 0.4 | [13 empty] | 0.3 |  | 0.4 | 1.4
242231335 | [16 empty] | 0 | [7 empty] | 0.6 |  |  | 0.6
242231340 | [10 empty] | 5 | [13 empty] | 1 |  | 1 | 7
242231355 |  |  |  | 3 | [6 empty] | 3 | [13 empty] | 1 |  | 1 | 8
242231360 |  |  |  | 1 | [6 empty] | 2 | [13 empty] | 1 |  |  | 4
242231365 |  |  |  | 2 | [20 empty] | 1 |  | 2 | 5
242231370 |  |  |  | 2 | [20 empty] | 2 |  | 2 | 6
242231385 | [10 empty] | 4.8 | [13 empty] | 4.8 |  |  | 9.6
242231390 | [10 empty] | 2 | [13 empty] | 1 |  |  | 3
242231395 | [10 empty] | 0.6 | [13 empty] | 0.5 |  |  | 1.1
242231400 | [10 empty] | 0.5 | [13 empty] | 0.5 |  |  | 1
242231405 | [10 empty] | 1.1 | [13 empty] | 1.1 |  |  | 2.2
242231410 | [10 empty] | 1 | [13 empty] | 2 |  |  | 3
242231415 | [24 empty] | 2.4 |  |  | 2.4
242231420 | [10 empty] | 0.3 | [13 empty] | 1.6 |  |  | 1.9
242231425 | [10 empty] | 3 | [13 empty] | 3 |  | 3 | 9
242231430 | [6 empty] | 0 | [20 empty] | 0
242231435 | [16 empty] | 0 | [10 empty] | 0
242231440 | [16 empty] | 0 | [10 empty] | 0
242231445 | [16 empty] | 0 | [10 empty] | 0
242231450 | [16 empty] | 0 | [10 empty] | 0
242231455 | [16 empty] | 0 | [10 empty] | 0
242231270A | [8 empty] | 0.3 | [18 empty] | 0.3
242231325A | [9 empty] | 1.7 | 2.6 | [13 empty] | 1.7 |  | 2.6 | 8.6
242231395A | [10 empty] | 2 | [13 empty] | 1.5 |  |  | 3.5
242231400A | [10 empty] | 1.9 | [13 empty] | 1.9 |  |  | 3.8
242231405A | [10 empty] | 3.7 | [13 empty] | 3.7 |  |  | 7.4
1.4.2.2.4.1 HIGH THRESHOLD CC |  |  |  | 2 |  |  |  |  | 0.5 | 0.5 | 47.3 |  |  |  | 4.7 | 7.9 | [8 empty] | 11.4 |  | 16.7 | 91
242241528 |  |  |  | 2 | [6 empty] | 2 | [13 empty] | 0.5 |  | 3 | 7.5
242241610 | [10 empty] | 2 | [16 empty] | 2
242241630 | [10 empty] | 3.5 | [16 empty] | 3.5
242241640 | [8 empty] | 0.5 | 0.5 | 20.5 | [13 empty] | 1.8 |  | 2.7 | 26
242241645 | [14 empty] | 1 | 1 | [8 empty] | 2 |  | 2 | 6
242241450b | [10 empty] | 3 | [16 empty] | 3
242241450ba | [10 empty] | 16.3 | [16 empty] | 16.3
242241647d | [14 empty] | 1.3 | 1.3 | [8 empty] | 0.1 |  | 2 | 4.7
242241647d5 | [14 empty] | 2.4 | 5.6 | [8 empty] | 7 |  | 7 | 22
1.4.2.2.4.2 LOW THRESHOLD CC | 6 |  |  | 4 |  |  | 0 |  |  |  | 72.2 |  |  |  |  | 4 |  |  | 0 | 0 |  |  |  | 0 | 14.2 |  | 8 | 108.4
242242031 | 0.5 | [23 empty] | 0 |  | 0.3 | 0.8
242242040 | [19 empty] | 0 |  |  |  | 0 |  |  |  | 0
242242076 | [6 empty] | 0 |  |  |  | 1 | [16 empty] | 1
242242092 | [19 empty] | 0 |  |  |  | 0 | 1.9 |  |  | 1.9
242242115 | [10 empty] | 0.3 | [13 empty] | 0.1 |  |  | 0.4
242242152 | [18 empty] | 0 | [5 empty] | 0 |  |  | 0
242242155 | [10 empty] | 1 | [13 empty] | 0.2 |  |  | 1.2
242242163 | [19 empty] | 0 |  |  |  |  | 0.6 |  |  | 0.6
242242164 |  |  |  | 3.2 | [20 empty] | 0.9 |  |  | 4.1
242242190 | [10 empty] | 0.5 | [16 empty] | 0.5
242242195 | [10 empty] | 0.2 | [16 empty] | 0.2
242242205 | [10 empty] | 2.3 |  |  |  |  | 3 | [8 empty] | 2 |  | 3 | 10.3
242242215 | [24 empty] | 0.2 |  |  | 0.2
242242222 | [24 empty] | 0.1 |  |  | 0.1
242242223 | [24 empty] | 0.9 |  |  | 0.9
242242225 | [24 empty] | 0.4 |  |  | 0.4
242242230 | [10 empty] | 0.3 | [13 empty] | 0.1 |  |  | 0.4
242242235 | [10 empty] | 3.8 | [16 empty] | 3.8
242242240 | [10 empty] | 1.6 | [13 empty] | 1.4 |  |  | 3
242242280 | [10 empty] | 0.1 | [16 empty] | 0.1
242242305 | [10 empty] | 0.8 | [16 empty] | 0.8
242242315 | [10 empty] | 0.2 | [13 empty] | 0.1 |  |  | 0.3
242242325 | [10 empty] | 0 | [16 empty] | 0
242242330 | [10 empty] | 0.5 | [13 empty] | 0.1 |  |  | 0.6
242242340 | [10 empty] | 8 | [16 empty] | 8
242242350 | [10 empty] | 2 | [16 empty] | 2
242242355 | [10 empty] | 1 | [16 empty] | 1
242242360 | [10 empty] | 1.2 | [16 empty] | 1.2
242242365 | [10 empty] | 7.2 | [16 empty] | 7.2
242242375 | [10 empty] | 2 | [16 empty] | 2
242242380 | [10 empty] | 1 | [16 empty] | 1
242242385 | [10 empty] | 1 | [16 empty] | 1
242242390 | [10 empty] | 7.2 | [16 empty] | 7.2
242242400 | [10 empty] | 0.5 | [16 empty] | 0.5
242242405 | [10 empty] | 1 | [16 empty] | 1
242242410 | [10 empty] | 1 | [16 empty] | 1
242242415 | [10 empty] | 6.4 | [16 empty] | 6.4
242242425 | [10 empty] | 2 | [16 empty] | 2
242242430 | [10 empty] | 1 | [16 empty] | 1
242242435 | [10 empty] | 1 | [16 empty] | 1
242242440 | [10 empty] | 6.4 | [16 empty] | 6.4
242242450 | [10 empty] | 2 | [16 empty] | 2
242242455 | [10 empty] | 1 | [16 empty] | 1
242242460 | [10 empty] | 1 | [16 empty] | 1
242242031a | 5.5 | [23 empty] | 0.3 |  | 3.7 | 9.5
242242220a | [24 empty] | 0.1 |  |  | 0.1
242242220aa | [24 empty] | 0.9 |  |  | 0.9
242242222a | [24 empty] | 1 |  |  | 1
242242280a | [10 empty] | 0.3 | [16 empty] | 0.3
242242325a | [10 empty] | 0.4 | [16 empty] | 0.4
242242092A | [24 empty] | 0.3 |  |  | 0.3
242242092B | [19 empty] | 0 |  |  |  | 0 |  |  |  | 0
242242115A | [10 empty] | 0.1 | [13 empty] | 0 |  |  | 0.1
242242163A | [24 empty] | 0.2 |  |  | 0.2
242242163B | [19 empty] | 0 | [7 empty] | 0
242242164A |  |  |  | 0.8 | [20 empty] | 0.2 |  |  | 1
242242205A | [10 empty] | 0.7 |  |  |  |  | 1 | [8 empty] | 0.6 |  | 1 | 3.3
242242223A | [24 empty] | 0.3 |  |  | 0.3
242242230A | [10 empty] | 0.1 | [13 empty] | 0 |  |  | 0.1
242242235A | [10 empty] | 1.2 | [16 empty] | 1.2
242242240A | [10 empty] | 1.4 | [13 empty] | 1.3 |  |  | 2.7
242242315A | [10 empty] | 0 | [13 empty] | 0 |  |  | 0
242242325B | [10 empty] | 0 | [16 empty] | 0
242242330A | [10 empty] | 0 | [13 empty] | 0 |  |  | 0
242242400A | [10 empty] | 1.5 | [16 empty] | 1.5
1.4.2.3.1 TRIGGER SYSTEM (Scintillators) |  |  | 2 | [13 empty] | 0 |  |  |  | 0 | [6 empty] | 2
24231005 |  |  | 2 | [24 empty] | 2
24231007 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
1.4.2.3.2 DAQ | [16 empty] | 0 |  |  |  | 0 |  |  |  | 8 |  |  | 8
24232022 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24232025 | [24 empty] | 8 |  |  | 8
1.4.2.3.3 ONLINE COMPUTING | [16 empty] | 0 |  |  |  | 0 |  |  |  | 15 |  |  | 15
24233010 | [16 empty] | 0 | [10 empty] | 0
24233015 | [16 empty] | 0 | [10 empty] | 0
24233020 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24233025 | [24 empty] | 4 |  |  | 4
24233030 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24233035 | [24 empty] | 1 |  |  | 1
24233040 | [16 empty] | 0 | [10 empty] | 0
24233045 | [24 empty] | 2 |  |  | 2
24233055 | [24 empty] | 1 |  |  | 1
24233065 | [24 empty] | 7 |  |  | 7
1.4.2.3.5 SLOW CONTROLS | [24 empty] | 44 |  | 88 | 132
24235015 | [24 empty] | 22 |  | 88 | 110
24235010a | [24 empty] | 21.9 |  |  | 21.9
24235010aB | [24 empty] | 0.1 |  |  | 0.1
1.4.2.4.2 TDC AND DISCRIMINATORS | [11 empty] | 0 | [12 empty] | 0 |  |  | 0
24242055 | [11 empty] | 0 | [15 empty] | 0
24242005a | [11 empty] | 0 | [15 empty] | 0
24242030a | [11 empty] | 0 | [12 empty] | 0 |  |  | 0
24242040a | [11 empty] | 0 | [15 empty] | 0
1.4.2.4.3 SCALERS | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24243010 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
1.4.2.4.4 HIGH VOLTAGE | [11 empty] | 0 | [15 empty] | 0
24244030 | [11 empty] | 0 | [15 empty] | 0
1.4.2.4.7 CRATES, RACKS | [11 empty] | 0 | [15 empty] | 0
24247030 | [11 empty] | 0 | [15 empty] | 0
24247045 | [11 empty] | 0 | [15 empty] | 0
24247005a | [11 empty] | 0 | [15 empty] | 0
24247005aB | [11 empty] | 0 | [15 empty] | 0
1.4.2.5.4 BEAMLINE COMPONENTS |  |  | 6.9 | 2 |  |  | 0 |  | 16 | 3 | 36.1 | [5 empty] | 0 |  |  |  | 0 | [6 empty] | 64
24254000 | [6 empty] | 0 | [20 empty] | 0
24254005 |  |  | 1 | 2 | [23 empty] | 3
24254010 | [8 empty] | 1 | [18 empty] | 1
24254015 | [16 empty] | 0 | [10 empty] | 0
24254020 | [10 empty] | 1 | [16 empty] | 1
24254025 | [8 empty] | 4 | 1 | [17 empty] | 5
24254030 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24254035 |  |  | 0.9 | [7 empty] | 7.1 | [16 empty] | 8
24254040 | [8 empty] | 4 | 1 | [17 empty] | 5
24254045 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24254050 | [10 empty] | 8 | [16 empty] | 8
24254055 | [16 empty] | 0 | [10 empty] | 0
24254060 | [10 empty] | 4 | [16 empty] | 4
24254065 | [16 empty] | 0 | [10 empty] | 0
24254070 | [8 empty] | 1 |  | 1 | [16 empty] | 2
24254075 | [16 empty] | 0 | [10 empty] | 0
24254080 |  |  | 2 | [5 empty] | 1 |  | 1 | [16 empty] | 4
24254085 | [16 empty] | 0 | [10 empty] | 0
24254090 | [10 empty] | 9 | [16 empty] | 9
24254095 | [8 empty] | 4 | 1 | [17 empty] | 5
24254100 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24254105 |  |  | 1 | [7 empty] | 4 | [16 empty] | 5
24254110 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
24254115 |  |  | 2 | [5 empty] | 1 |  | 1 | [16 empty] | 4
24254120 | [16 empty] | 0 | [10 empty] | 0
1.4.2.6.4 INSTALLATION |  |  | 13.3 | 28.1 |  | 0 | 0 |  | 47 | 114.5 | 442.2 |  | 0 | 0 |  |  | 0 |  | 0 | [5 empty] | 9.6 | 67.1 |  | 721.8
24264105 | [8 empty] | 4 | [18 empty] | 4
24264110 | [8 empty] | 5 | [18 empty] | 5
24264115 | [8 empty] | 11.3 | [18 empty] | 11.3
24264120 | [9 empty] | 6 | [17 empty] | 6
24264125 | [16 empty] | 0 | [10 empty] | 0
24264145 | [9 empty] | 1 |  |  |  | 0 | [13 empty] | 1
24264160 | [16 empty] | 0 | [10 empty] | 0
24264230 | [16 empty] | 0 | [10 empty] | 0
24264280 | [8 empty] | 6 |  | 12 | [16 empty] | 18
24264281 | [10 empty] | 7 | [16 empty] | 7
24264360 | [10 empty] | 0.6 | [16 empty] | 0.6
24264460 | [10 empty] | 8 | [16 empty] | 8
24264465 | [10 empty] | 1.8 | [16 empty] | 1.8
24264470 | [10 empty] | 2.4 | [13 empty] | 1.2 |  |  | 3.6
24264490 | [10 empty] | 4.8 | [16 empty] | 4.8
24264495 | [10 empty] | 1.8 | [16 empty] | 1.8
24264500 | [10 empty] | 2.4 | [13 empty] | 1.2 |  |  | 3.6
24264517 | [18 empty] | 0 | [8 empty] | 0
24264520 | [10 empty] | 2 | [16 empty] | 2
24264525 | [10 empty] | 1.6 | [16 empty] | 1.6
24264527 | [10 empty] | 4 | [16 empty] | 4
24264529 | [10 empty] | 4 | [16 empty] | 4
24264531 | [10 empty] | 3.2 | [16 empty] | 3.2
24264533 | [10 empty] | 1.6 | [16 empty] | 1.6
24264535 | [10 empty] | 2.4 | [16 empty] | 2.4
24264540 | [10 empty] | 2 | [16 empty] | 2
24264545 |  |  |  | 4 | [23 empty] | 4
24264546 |  |  | 4 | 4 | [23 empty] | 8
24264550 | [10 empty] | 3.2 | [16 empty] | 3.2
24264555 | [10 empty] | 0.8 | [16 empty] | 0.8
24264557 | [10 empty] | 1.2 | [16 empty] | 1.2
24264560 | [10 empty] | 0.8 | [16 empty] | 0.8
24264562 | [10 empty] | 0.6 | [16 empty] | 0.6
24264565 | [10 empty] | 1.2 | [16 empty] | 1.2
24264567 | [10 empty] | 0.6 | [16 empty] | 0.6
24264570 | [10 empty] | 11.7 | [16 empty] | 11.7
24264572 | [10 empty] | 0.6 | [16 empty] | 0.6
24264575 | [10 empty] | 0.6 | [16 empty] | 0.6
24264577 | [10 empty] | 2.4 | [16 empty] | 2.4
24264580 | [10 empty] | 0.6 | [16 empty] | 0.6
24264582 | [10 empty] | 5.4 | [16 empty] | 5.4
24264585 | [10 empty] | 0.4 | [16 empty] | 0.4
24264587 | [10 empty] | 0.6 | [16 empty] | 0.6
24264590 | [10 empty] | 2.4 | [16 empty] | 2.4
24264592 | [10 empty] | 0.6 | [16 empty] | 0.6
24264595 | [10 empty] | 8.1 | [16 empty] | 8.1
24264597 | [10 empty] | 0.4 | [16 empty] | 0.4
24264600 | [10 empty] | 0.6 | [16 empty] | 0.6
24264605 | [10 empty] | 2.4 | [16 empty] | 2.4
24264607 | [10 empty] | 0.6 | [16 empty] | 0.6
24264610 | [10 empty] | 8.1 | [16 empty] | 8.1
24264612 | [10 empty] | 0.4 | [16 empty] | 0.4
24264615 | [10 empty] | 0.6 | [16 empty] | 0.6
24264617 | [10 empty] | 2.4 | [16 empty] | 2.4
24264620 | [10 empty] | 2.4 | [16 empty] | 2.4
24264622 | [10 empty] | 1.2 | [16 empty] | 1.2
24264625 | [10 empty] | 0.6 | [16 empty] | 0.6
24264627 | [10 empty] | 8.1 | [16 empty] | 8.1
24264630 | [10 empty] | 0.4 | [16 empty] | 0.4
24264632 | [10 empty] | 0.6 | [16 empty] | 0.6
24264635 | [10 empty] | 8.1 | [16 empty] | 8.1
24264637 | [10 empty] | 0.4 | [16 empty] | 0.4
24264645 |  |  |  | 2 | [6 empty] | 6 | [16 empty] | 8
24264650 | [10 empty] | 0.8 | [16 empty] | 0.8
24264655 | [10 empty] | 1.6 | [16 empty] | 1.6
24264660 | [10 empty] | 0.4 | [16 empty] | 0.4
24264665 | [10 empty] | 6 | [16 empty] | 6
24264670 | [10 empty] | 3.6 | [16 empty] | 3.6
24264675 | [10 empty] | 9.6 | [16 empty] | 9.6
24264680 | [10 empty] | 3.6 | [16 empty] | 3.6
24264685 | [10 empty] | 2.4 | [16 empty] | 2.4
24264690 |  |  |  | 4.8 | [6 empty] | 4.8 | [16 empty] | 9.6
24264695 | [10 empty] | 7.2 | [16 empty] | 7.2
24264700 |  |  |  | 0.6 | [6 empty] | 1.2 | [16 empty] | 1.8
24264705 | [10 empty] | 4.8 | [16 empty] | 4.8
24264710 | [10 empty] | 3.2 | [16 empty] | 3.2
24264712 | [10 empty] | 30 | [16 empty] | 30
24264715 | [10 empty] | 2.4 | [16 empty] | 2.4
24264717 | [10 empty] | 8 | [16 empty] | 8
24264720 |  |  |  | 0.8 | [6 empty] | 0.8 | [16 empty] | 1.6
24264722 | [10 empty] | 1.2 | [16 empty] | 1.2
24264725 | [10 empty] | 1.8 | [16 empty] | 1.8
24264727 | [10 empty] | 3 | [16 empty] | 3
24264730 | [10 empty] | 0.6 | [16 empty] | 0.6
24264732 | [10 empty] | 7.2 | [16 empty] | 7.2
24264737 |  |  |  | 1 | [6 empty] | 3 | [16 empty] | 4
24264740 | [10 empty] | 0.8 | [16 empty] | 0.8
24264742 | [10 empty] | 2.4 | [16 empty] | 2.4
24264745 | [10 empty] | 1 | [16 empty] | 1
24264747 | [10 empty] | 0.8 | [16 empty] | 0.8
24264750 | [10 empty] | 2 | [16 empty] | 2
24264760 |  |  |  | 0.4 | [5 empty] | 0.4 | 1.8 | [16 empty] | 2.6
24264762 | [9 empty] | 3 | [17 empty] | 3
24264770 | [9 empty] | 3 | 8.2 | [16 empty] | 11.2
24264797 | [16 empty] | 0 | [10 empty] | 0
24264800 |  |  |  | 2 | [5 empty] | 2 | 4 | [16 empty] | 8
24264805 | [10 empty] | 0.8 | [16 empty] | 0.8
24264810 | [10 empty] | 6 |  | 0 | [14 empty] | 6
24264815 |  |  |  | 4 | [23 empty] | 4
24264820 | [10 empty] | 0.4 | [16 empty] | 0.4
24264845 | [10 empty] | 8 | [13 empty] | 2 |  |  | 10
24264850 | [10 empty] | 1.2 | [16 empty] | 1.2
24264855 | [10 empty] | 8 | [13 empty] | 2 |  |  | 10
24264860 | [10 empty] | 1.2 | [16 empty] | 1.2
24264868 | [8 empty] | 3 |  | 6 | [16 empty] | 9
24264870 | [10 empty] | 1 | [16 empty] | 1
24264872 | [10 empty] | 0.5 | [16 empty] | 0.5
24264874 | [10 empty] | 3 | [16 empty] | 3
24264876 | [10 empty] | 1.2 | [13 empty] | 1.2 |  |  | 2.4
24264878 | [10 empty] | 0.8 | [16 empty] | 0.8
24264882 | [5 empty] | 0 |  |  |  |  | 16 | [5 empty] | 0 | [10 empty] | 16
24264884 | [10 empty] | 12 | [16 empty] | 12
24264886 | [10 empty] | 4.8 | [16 empty] | 4.8
24264888 | [10 empty] | 6 | [16 empty] | 6
24264890 | [13 empty] | 0 | [13 empty] | 0
24264895 | [9 empty] | 6 | [17 empty] | 6
24264900 | [16 empty] | 0 | [10 empty] | 0
24264905 | [13 empty] | 0 | [13 empty] | 0
24264910 | [9 empty] | 5 | [17 empty] | 5
24264915 | [16 empty] | 0 | [10 empty] | 0
24264920 | [13 empty] | 0 | [13 empty] | 0
24264925 | [9 empty] | 3 | [17 empty] | 3
24264930 | [16 empty] | 0 | [10 empty] | 0
24264965 | [10 empty] | 13.6 | [16 empty] | 13.6
24264970 | [10 empty] | 6 | [16 empty] | 6
24264975 | [10 empty] | 13.6 | [16 empty] | 13.6
24264980 | [10 empty] | 6 | [16 empty] | 6
24264985 | [10 empty] | 13.6 | [16 empty] | 13.6
24264990 | [10 empty] | 6 | [16 empty] | 6
24264995 |  |  |  | 2 | [20 empty] | 2 |  |  | 4
24264006LOE | [9 empty] | 13.3 | [15 empty] | 23.3 |  | 36.6
24264762A | [10 empty] | 0.4 | [16 empty] | 0.4
24264762B | [6 empty] | 0 |  |  | 4 | [17 empty] | 4
24264762C | [10 empty] | 4 | [16 empty] | 4
24264762D | [10 empty] | 1.6 | [16 empty] | 1.6
24264762F | [10 empty] | 0.4 | [16 empty] | 0.4
24264762G | [10 empty] | 1.6 | [16 empty] | 1.6
24264762H | [10 empty] | 1 | [16 empty] | 1
24264794a | [10 empty] | 2 | [16 empty] | 2
24264115A | [8 empty] | 0.7 | [18 empty] | 0.7
24264547A |  |  | 8.5 | 2.3 |  |  |  |  | 15.5 | 23.2 | 15.5 | [16 empty] | 65
24264547B |  |  | 0.8 | 0.2 |  |  |  |  | 1.5 | 2.3 | 1.5 | [16 empty] | 6.3
24264582A | [10 empty] | 3.6 | [16 empty] | 3.6
24264905A | [13 empty] | 0 | [13 empty] | 0
24264005LOEA | [9 empty] | 42.3 | [15 empty] | 43.8 |  | 86.1
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | [16 empty] | 0 |  |  |  |  | 0 | [5 empty] | 0
24271705 | [21 empty] | 0 | [5 empty] | 0
24271710 | [21 empty] | 0 | [5 empty] | 0
24271715 | [21 empty] | 0 | [5 empty] | 0
24271720 | [21 empty] | 0 | [5 empty] | 0
24271722 | [21 empty] | 0 | [5 empty] | 0
24271695G | [21 empty] | 0 | [5 empty] | 0
24271700B | [21 empty] | 0 | [5 empty] | 0
24271700C | [21 empty] | 0 | [5 empty] | 0
24271700D | [21 empty] | 0 | [5 empty] | 0
24271705A | [21 empty] | 0 | [5 empty] | 0
24271705B | [21 empty] | 0 | [5 empty] | 0
24271705C | [21 empty] | 0 | [5 empty] | 0
24271705D | [21 empty] | 0 | [5 empty] | 0
24271710A | [21 empty] | 0 | [5 empty] | 0
24271710B | [21 empty] | 0 | [5 empty] | 0
24271710C | [21 empty] | 0 | [5 empty] | 0
24271710D | [21 empty] | 0 | [5 empty] | 0
24271715A | [21 empty] | 0 | [5 empty] | 0
24271715B | [21 empty] | 0 | [5 empty] | 0
24271715C | [21 empty] | 0 | [5 empty] | 0
24271715D | [21 empty] | 0 | [5 empty] | 0
24271720A | [21 empty] | 0 | [5 empty] | 0
24271720B | [21 empty] | 0 | [5 empty] | 0
24271720C | [21 empty] | 0 | [5 empty] | 0
24271720D | [21 empty] | 0 | [5 empty] | 0
24271724A | [16 empty] | 0 | [10 empty] | 0
24271724B | [16 empty] | 0 | [10 empty] | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS |  | 45 | 14.8 | 61.6 | [12 empty] | 0 | 0 |  |  | 0 | 0 | [5 empty] | 121.4
242710.1 |  | 35 | 6 | [24 empty] | 41
242710.1005 |  |  | 1 | [24 empty] | 1
242710.101 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242710.1015 |  | 2.8 | 0.3 | [24 empty] | 3.1
242710.102 |  |  | 1 | [24 empty] | 1
242710.1025 | [16 empty] | 0 | [10 empty] | 0
242710.103 |  |  | 2.6 | 27.3 | [23 empty] | 29.9
242710.104 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242710.1045 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242710.105 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242710.1055 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242710.1015a |  | 7.2 | 0.7 | [24 empty] | 7.9
242710.1030A |  |  | 3.2 | 34.3 | [23 empty] | 37.5
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | [17 empty] | 0 |  |  |  | 0 |  | 0 |  | 3.7 |  | 3.7
242711.101 | [21 empty] | 0 |  | 0 |  |  |  | 0
242711.1005F | [21 empty] | 0 | [5 empty] | 0
242711.1010A | [21 empty] | 0 | [5 empty] | 0
242711.1010B | [21 empty] | 0 | [5 empty] | 0
242711.1010C | [21 empty] | 0 | [5 empty] | 0
242711.1010D | [21 empty] | 0 | [5 empty] | 0
242711.1005A | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242711.1005B | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242711.1005C | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242711.1005D | [21 empty] | 0 | [5 empty] | 0
242711.1000A | [25 empty] | 3.7 |  | 3.7
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION |  |  |  | 21 |  |  | 0 | [18 empty] | 10.5 |  | 31.5
242711.3035 |  |  |  | 3 |  |  | 0 | [18 empty] | 1.5 |  | 4.5
242711.304 |  |  |  | 3 |  |  | 0 | [18 empty] | 1.5 |  | 4.5
242711.3045 |  |  |  | 3 |  |  | 0 | [18 empty] | 1.5 |  | 4.5
242711.305 |  |  |  | 3 |  |  | 0 | [18 empty] | 1.5 |  | 4.5
242711.3055 |  |  |  | 3 |  |  | 0 | [18 empty] | 1.5 |  | 4.5
242711.306 |  |  |  | 3 |  |  | 0 | [18 empty] | 1.5 |  | 4.5
242711.3065 |  |  |  | 0.6 |  |  | 0 | [18 empty] | 0.3 |  | 0.9
242711.3065A |  |  |  | 2.4 |  |  | 0 | [18 empty] | 1.2 |  | 3.6
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | [7 empty] | 0 | [8 empty] | 0 |  |  | 0 | 0 |  |  | 0 |  | 6.7 |  | 6.7
242711.5005 | [7 empty] | 0 | [17 empty] | 2 |  | 2
242711.5015 | [7 empty] | 0 | [8 empty] | 0 |  |  |  | 0 |  |  |  |  | 4.7 |  | 4.7
242711.502 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242711.5025 | [20 empty] | 0 | [6 empty] | 0
242711.503 | [20 empty] | 0 | [6 empty] | 0
242711.5010b | [7 empty] | 0 | [11 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | [19 empty] | 0 |  | 0 |  | 0 |  |  |  | 0
24272085 | [19 empty] | 0 |  |  |  | 0 |  |  |  | 0
24272090 | [23 empty] | 0 |  |  |  | 0
24272075k | [21 empty] | 0 | [5 empty] | 0
24272075p | [21 empty] | 0 | [5 empty] | 0
24272075q | [21 empty] | 0 | [5 empty] | 0
24272075r | [21 empty] | 0 | [5 empty] | 0
24272075t | [21 empty] | 0 | [5 empty] | 0
24272075u | [21 empty] | 0 | [5 empty] | 0
24272075v | [21 empty] | 0 | [5 empty] | 0
24272075x | [21 empty] | 0 | [5 empty] | 0
24272075y | [21 empty] | 0 | [5 empty] | 0
24272075z | [21 empty] | 0 | [5 empty] | 0
24272075za | [21 empty] | 0 | [5 empty] | 0
24272075zb | [21 empty] | 0 | [5 empty] | 0
24272075zc | [21 empty] | 0 | [5 empty] | 0
24272075zd | [21 empty] | 0 | [5 empty] | 0
24272075zf | [21 empty] | 0 | [5 empty] | 0
24272075zg | [21 empty] | 0 | [5 empty] | 0
24272075zh | [21 empty] | 0 | [5 empty] | 0
24272075zj | [21 empty] | 0 | [5 empty] | 0
24272075zk | [21 empty] | 0 | [5 empty] | 0
24272075zn | [21 empty] | 0 | [5 empty] | 0
1.4.2.7.3 MAGNET INFRASTRUCTURE | [21 empty] | 0 | [5 empty] | 0
24273060 | [21 empty] | 0 | [5 empty] | 0
24273065 | [21 empty] | 0 | [5 empty] | 0
24273075 | [21 empty] | 0 | [5 empty] | 0
24273085 | [21 empty] | 0 | [5 empty] | 0
1.4.2.7.4.2 PROTOTYPE | [6 empty] | 0 |  |  | 15.8 | 50.2 | [14 empty] | 8 |  | 74
242742065 | [6 empty] | 0 |  |  | 4.7 | 14.9 | [14 empty] | 2.4 |  | 22
242742070 | [6 empty] | 0 |  |  | 6 | 19 | [14 empty] | 3 |  | 28
242742075 | [6 empty] | 0 |  |  | 5.1 | 16.3 | [14 empty] | 2.6 |  | 24
1.4.2.7.4.3 PRODUCTION | [6 empty] | 0 |  |  | 54.8 | 274.9 | [14 empty] | 27.3 |  | 357
242743005 | [6 empty] | 0 |  |  | 5.9 | 13.2 | [14 empty] | 2.9 |  | 22
242743010 | [9 empty] | 4 | 14 | [14 empty] | 2 |  | 20
242743015 | [9 empty] | 1.7 | 7.5 | [14 empty] | 0.8 |  | 10
242743025 | [6 empty] | 0 |  |  | 2.9 | 17.6 | [14 empty] | 1.5 |  | 22
242743030 | [9 empty] | 2 | 17 | [14 empty] | 1 |  | 20
242743035 | [9 empty] | 1.7 | 7.5 | [14 empty] | 0.8 |  | 10
242743045 | [6 empty] | 0 |  |  | 2.9 | 17.6 | [14 empty] | 1.5 |  | 22
242743050 | [9 empty] | 2 | 17 | [14 empty] | 1 |  | 20
242743055 | [9 empty] | 1 | 4.5 | [14 empty] | 0.5 |  | 6
242743065 | [6 empty] | 0 |  |  | 2.9 | 17.6 | [14 empty] | 1.5 |  | 22
242743070 | [9 empty] | 1.2 | 10.2 | [14 empty] | 0.6 |  | 12
242743075 | [9 empty] | 1.7 | 7.5 | [14 empty] | 0.8 |  | 10
242743085 | [6 empty] | 0 |  |  | 1.6 | 9.4 | [14 empty] | 0.8 |  | 11.8
242743090 | [9 empty] | 2 | 17 | [14 empty] | 1 |  | 20
242743095 | [9 empty] | 1.7 | 7.5 | [14 empty] | 0.8 |  | 10
242743105 | [6 empty] | 0 |  |  | 2.9 | 17.6 | [14 empty] | 1.5 |  | 22
242743110 | [9 empty] | 2 | 17 | [14 empty] | 1 |  | 20
242743115 | [9 empty] | 1.7 | 7.5 | [14 empty] | 0.8 |  | 10
242743120 | [9 empty] | 6 | 9 | [14 empty] | 3 |  | 18
242743055A | [9 empty] | 0.7 | 3 | [14 empty] | 0.3 |  | 4
242743070A | [9 empty] | 0.8 | 6.8 | [14 empty] | 0.4 |  | 8
242743085A | [6 empty] | 0 |  |  | 1.4 | 8.2 | [14 empty] | 0.7 |  | 10.3
242743125A | [9 empty] | 4.1 | 20.7 | [14 empty] | 2.1 |  | 26.9
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | [8 empty] | 5.4 | 21.3 | [6 empty] | 0 |  |  |  | 0 | [6 empty] | 26.7
242751170 | [9 empty] | 1 | [17 empty] | 1
242751215 | [8 empty] | 0.5 | [18 empty] | 0.5
242751240 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242751255 | [9 empty] | 1 | [17 empty] | 1
242751260 | [16 empty] | 0 | [10 empty] | 0
242751290 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242751295 | [9 empty] | 1 | [17 empty] | 1
242751300 | [16 empty] | 0 | [10 empty] | 0
242751305 | [9 empty] | 1 | [17 empty] | 1
242751310 | [16 empty] | 0 | [10 empty] | 0
242751325 | [8 empty] | 2 | [18 empty] | 2
242751330 | [9 empty] | 1 | [17 empty] | 1
242751335 | [16 empty] | 0 | [10 empty] | 0
242751360 | [9 empty] | 3 | [17 empty] | 3
242751365 | [9 empty] | 3 | [17 empty] | 3
242751375 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242751380 | [9 empty] | 1 | [17 empty] | 1
242751385 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242751410 | [8 empty] | 2 | [18 empty] | 2
242751415 | [9 empty] | 9.3 | [17 empty] | 9.3
242751440 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242751215a | [8 empty] | 0.9 | [18 empty] | 0.9
1.4.2.7.6.1 CRYO DISTRIBUTION CAN | [9 empty] | 7.1 | [9 empty] | 0 |  |  |  | 0 |  |  |  | 7.1
242761010 | [9 empty] | 0.2 | [17 empty] | 0.2
242761015 | [9 empty] | 2.6 | [17 empty] | 2.6
242761025 | [9 empty] | 2 | [17 empty] | 2
242761030 | [19 empty] | 0 |  |  |  | 0 |  |  |  | 0
242761010a | [9 empty] | 2.3 | [17 empty] | 2.3
1.4.2.7.6.2 CRYO CONTROL CAN |  |  | 1 | [5 empty] | 19 | 27 | [9 empty] | 0 |  |  |  | 0 |  |  |  | 47
242762000 | [9 empty] | 4 | [17 empty] | 4
242762005 | [9 empty] | 2 | [17 empty] | 2
242762010 |  |  | 1 | [24 empty] | 1
242762015 | [8 empty] | 16 | [18 empty] | 16
242762020 | [8 empty] | 3 | [18 empty] | 3
242762025 | [9 empty] | 2 | [17 empty] | 2
242762030 | [9 empty] | 3 | [17 empty] | 3
242762035 | [9 empty] | 3 | [17 empty] | 3
242762040 | [9 empty] | 2 | [17 empty] | 2
242762045 | [19 empty] | 0 |  |  |  | 0 |  |  |  | 0
242762000a | [9 empty] | 11 | [17 empty] | 11
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL |  | 44.2 | 14.7 | 61.6 | [12 empty] | 0 | 0 |  |  | 0 | 0 | [5 empty] | 120.5
242771000 |  | 9.2 | 0.9 | [24 empty] | 10.1
242771005 |  | 35 | 6 | [24 empty] | 41
242771015 |  |  | 1 | [24 empty] | 1
242771020 | [16 empty] | 0 | [10 empty] | 0
242771025 |  |  | 1 | [24 empty] | 1
242771030 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242771035 |  |  | 5.8 | 61.6 | [23 empty] | 67.4
242771050 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242771055 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
242771060 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS |  |  | 5 |  |  |  | 0 |  | 20 | 12 | [9 empty] | 0 |  |  |  |  | 5 | 21.2 |  | 63.2
242781015 |  |  | 5 | [5 empty] | 20 | 10 | [14 empty] | 5 | 5 |  | 45
242781020 | [19 empty] | 0 | [7 empty] | 0
242781025 | [9 empty] | 1.6 | [15 empty] | 3.1 |  | 4.7
242781010LOE | [6 empty] | 0 | [18 empty] | 12.2 |  | 12.2
242781025A | [9 empty] | 0.4 | [15 empty] | 0.9 |  | 1.3
1.4.2.7.9.1 SOLENOID CRYOGENICS | [6 empty] | 0 |  |  | 28.6 | 19.8 | [5 empty] | 0 |  |  |  | 0 | [6 empty] | 48.4
242791010 | [9 empty] | 3 | [17 empty] | 3
242791015 | [9 empty] | 0.6 | [17 empty] | 0.6
242791020 | [9 empty] | 2 | 2 | [16 empty] | 4
242791025 | [9 empty] | 2.3 | 2.3 | [16 empty] | 4.6
242791030 | [9 empty] | 12 | 12 | [16 empty] | 24
242791035 | [9 empty] | 0.2 | [17 empty] | 0.2
242791040 | [9 empty] | 1 | [17 empty] | 1
242791045 | [9 empty] | 2 | [17 empty] | 2
242791050 | [6 empty] | 0 | [9 empty] | 0 |  |  |  | 0 | [6 empty] | 0
242791055 | [9 empty] | 1.5 | 1.5 | [16 empty] | 3
242791060 | [9 empty] | 2 | 2 | [16 empty] | 4
242791040A | [9 empty] | 2 | [17 empty] | 2
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT |  |  | 8 | [8 empty] | 0 |  |  |  | 20.27 | [8 empty] | 67.52 |  | 40.63 | 136.42
28223000 |  |  | 8 | [21 empty] | 8 |  |  | 16
28223025 | [24 empty] | 0.9 |  |  | 0.9
28223030 | [15 empty] | 0.7 | [8 empty] | 0.7 |  | 1.5 | 2.9
28223040 | [11 empty] | 0 | [12 empty] | 16 |  |  | 16
28223025A | [24 empty] | 22.16 |  |  | 22.16
28223025B | [24 empty] | 0.19 |  |  | 0.19
28223030A | [15 empty] | 19.39 | [8 empty] | 19.39 |  | 38.77 | 77.55
28223030B | [15 empty] | 0.18 | [8 empty] | 0.18 |  | 0.36 | 0.72
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 4 |  | 6 | 2 | [5 empty] | 21.4 | 30.9 | [13 empty] | 4 |  |  | 68.3
28226000 |  |  |  | 2 | [5 empty] | 2 | 2 | [16 empty] | 6
28226005 |  |  | 4 | [6 empty] | 10.9 | 15 | [16 empty] | 29.9
28226010 |  |  | 2 | [6 empty] | 5.5 | 6.9 | [16 empty] | 14.4
28226015 | 4 | [9 empty] | 4 | [13 empty] | 4 |  |  | 12
28226020 | [9 empty] | 1.8 | 1.8 | [16 empty] | 3.6
28226025 | [9 empty] | 1.2 | 1.2 | [16 empty] | 2.4
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 25.2 | [8 empty] | 4.2 | 1.4 | [13 empty] | 19.6 |  | 33.6 | 84
2822X000 | 25.2 | [8 empty] | 4.2 | 1.4 | [13 empty] | 19.6 |  | 33.6 | 84
1.4.3.2.8 DETECTOR FRAME | [16 empty] | 0 | [10 empty] | 0
24328010ba | [16 empty] | 0 | [10 empty] | 0
1.4.3.2.3 NOBLE GAS CERENKOV | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
24323005b | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
1.4.3.1.5 MAGNET COMPONENTS PROCURED BY JLAB |  |  | 8.5 | 8.5 | [23 empty] | 17
24315007 |  |  | 8.5 | 8.5 | [23 empty] | 17
1.4.3.1.4 DIPOLE | [7 empty] | 0 | 12 | 12 | 1 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 25
24314P6LOE | [7 empty] | 0 |  | 8 | [17 empty] | 8
24314027 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
24314040 | [8 empty] | 12 | [18 empty] | 12
24314035a | [9 empty] | 2 | 1 | [16 empty] | 3
24314030 | [21 empty] | 0 | [5 empty] | 0
24314035 | [21 empty] | 0 | [5 empty] | 0
24314048 | [7 empty] | 0 |  | 0.5 | [17 empty] | 0.5
24314049 | [7 empty] | 0 |  | 1 | [17 empty] | 1
24314048A | [7 empty] | 0 |  | 0.5 | [17 empty] | 0.5
1.4.3.1.1 HB MAGNET | [7 empty] | 0 | 13.2 | 4 | 0.8 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 18
24311170 | [7 empty] | 0 | 1 | 1 | [17 empty] | 2
243118P6LOE | [7 empty] | 0 |  | 3 | [17 empty] | 3
24311135 | [17 empty] | 0 | [9 empty] | 0
24311150 | [21 empty] | 0 | [5 empty] | 0
24311155 | [21 empty] | 0 | [5 empty] | 0
24311160 | [21 empty] | 0 | [5 empty] | 0
24311165 | [21 empty] | 0 | [5 empty] | 0
24311168 | [21 empty] | 0 | [5 empty] | 0
24311071 | [8 empty] | 5 | [18 empty] | 5
24311077 | [8 empty] | 0.2 |  | 0.8 | [16 empty] | 1
24311071A | [8 empty] | 7 | [18 empty] | 7
1.4.3.1.2 Q-1 QUADRUPOLE | [7 empty] | 0 | 12 | 2.8 | [8 empty] | 0 |  |  | 0 |  |  | 25 |  |  | 39.8
24312060 | [18 empty] | 0 | [8 empty] | 0
24312048 | [21 empty] | 0 | [5 empty] | 0
24312050 | [21 empty] | 0 | [5 empty] | 0
24312050c | [21 empty] | 0 | [5 empty] | 0
24312050d | [8 empty] | 7.7 | [18 empty] | 7.7
24312915LOE | [24 empty] | 22 |  |  | 22
243128P6LOE5 | [7 empty] | 0 |  | 2.8 | [17 empty] | 2.8
24312915LOE5 | [24 empty] | 3 |  |  | 3
24312050dA | [8 empty] | 4.3 | [18 empty] | 4.3
1.4.3.1.3 Q2-3 QUADRUPOLE | [7 empty] | 0 | 12 | 15.8 | [7 empty] | 0 |  |  |  | 0 | [5 empty] | 27.8
24313235 | [7 empty] | 0 | [19 empty] | 0
24313275 | [8 empty] | 12 | [18 empty] | 12
24313017 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
24313230 | [7 empty] | 0 |  | 1 | [17 empty] | 1
24313P6LOE | [7 empty] | 0 |  | 11 | [17 empty] | 11
24313P6LOE5 | [9 empty] | 2.8 | [17 empty] | 2.8
24313285 | [21 empty] | 0 | [5 empty] | 0
24313019 | [17 empty] | 0 |  |  |  | 0 | [5 empty] | 0
24313019a | [21 empty] | 0 | [5 empty] | 0
24313019b | [21 empty] | 0 | [5 empty] | 0
24313220 | [7 empty] | 0 |  | 1 | [17 empty] | 1
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | [7 empty] | 0 |  | 23.8 | [6 empty] | 0 |  |  |  | 0 | [6 empty] | 23.8
243161000 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
243161005 | [20 empty] | 0 | [6 empty] | 0
243161010 | [20 empty] | 0 | [6 empty] | 0
243161015 | [20 empty] | 0 | [6 empty] | 0
243161020 | [20 empty] | 0 | [6 empty] | 0
243161030LOE | [7 empty] | 0 |  | 23.8 | [17 empty] | 23.8
1.4.3.5.3 MAPPING |  |  |  | 5 | 0 |  | 0 | 0 | 5 | 5 | 0.4 | [5 empty] | 0 | [7 empty] | 4 |  |  | 19.4
24353015 |  |  |  | 5 | 0 |  | 0 | 0 | 5 | 5 | 0.4 | [5 empty] | 0 | [7 empty] | 4 |  |  | 19.4
1.4.3.5.4 SCATTERING CHAMBER |  |  |  |  | 0 |  | 0 | 0 | 8 | 2 | 8 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 1 |  |  | 19
24354020 | [6 empty] | 0 |  | 0 | [18 empty] | 0
24354015a |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | [8 empty] | 0 | [7 empty] | 0
24354030 | [6 empty] | 0 | 0 | 2 | 0 | 0 |  |  | 0 | [13 empty] | 2
24354030b | [16 empty] | 0 |  |  | 0 | [7 empty] | 0
24354022 | [8 empty] | 0 | 0 | 4 | [5 empty] | 0 | [10 empty] | 4
24354010 | [8 empty] | 6 | 2 | 0 | [13 empty] | 1 |  |  | 9
24354030b5 | [10 empty] | 4 | [16 empty] | 4
24354015C | [19 empty] | 0 | [7 empty] | 0
24354015B |  |  |  |  | 0 | [22 empty] | 0
24354020A | [6 empty] | 0 |  | 0 | [18 empty] | 0
1.4.3.5.5 BEAM PIPE & STANDS | [7 empty] | 0 | 43.31 | 17.08 | 9 | [5 empty] | 0 |  |  |  | 0 | [6 empty] | 69.39
24355005 | [8 empty] | 4 | 2 | 2 | [5 empty] | 0 | [10 empty] | 8
24355020 | [8 empty] | 6 | 6 | 3 | [9 empty] | 0 | [6 empty] | 15
24355000 | [8 empty] | 19.7 | 4.9 | [17 empty] | 24.6
24355025 | [16 empty] | 0 | [10 empty] | 0
24355030 | [16 empty] | 0 | [10 empty] | 0
24355015 | [7 empty] | 0 | 7 | 2 | 2 | [5 empty] | 0 |  |  |  | 0 | [6 empty] | 11
24355010 | [8 empty] | 6 | 2 | 2 | [5 empty] | 0 | [10 empty] | 10
24355000A | [8 empty] | 0.61 | 0.18 | [17 empty] | 0.79
1.4.3.6.5 VACUUM SYSTEM | [16 empty] | 0 |  | 0 |  | 0 | [6 empty] | 0
24365025 | [18 empty] | 0 | [8 empty] | 0
24365032 | [20 empty] | 0 | [6 empty] | 0
24365040 | [16 empty] | 0 | [10 empty] | 0
1.4.3.6.6 CABLING |  |  |  | 8 | [23 empty] | 8
24366025 |  |  |  | 8 | [23 empty] | 8
1.4.3.6.8 INSTALLATION |  |  | 4.4 | 77.43 | 0 |  | 0 |  | 27.94 | 49 | 259.93 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 30.32 |  | 4 | 453.02
24368350 | [8 empty] | 0.6 |  | 2.4 | [16 empty] | 3
24368110 | [10 empty] | 0.4 | [16 empty] | 0.4
24368450 |  |  |  | 6 | [23 empty] | 6
24368545 |  |  |  |  | 0 |  |  |  |  | 2 | 4.4 | [16 empty] | 6.4
24368465 | [8 empty] | 9 | 3 | [17 empty] | 12
24368490 |  |  |  |  | 0 |  | 0 |  |  |  | 4 | [16 empty] | 4
24368480 |  |  |  |  | 0 |  | 0 |  |  |  | 1 | [16 empty] | 1
24368535 |  |  |  |  | 0 |  | 0 |  | 1 | 1 | 4 | [16 empty] | 6
24368360 | [8 empty] | 0.2 | 0.2 | 4 | [16 empty] | 4.4
24368155 |  |  | 2.6 |  |  |  | 0 |  | 3.5 | 2.6 | 36.4 | [16 empty] | 45.1
24368315 | [8 empty] | 0.2 | 0.2 | 4 | [16 empty] | 4.4
24368325 | [8 empty] | 0.2 | 0.2 | 4 | [16 empty] | 4.4
24368160 |  |  |  | 5 | [12 empty] | 0 | [10 empty] | 5
24368420 |  |  |  | 5.6 | [20 empty] | 2.8 |  |  | 8.4
24368485 |  |  | 1 | 2 | [6 empty] | 5 | [5 empty] | 0 | [10 empty] | 8
24368405 |  |  |  | 2 | [23 empty] | 2
24368400 | [10 empty] | 8 | [16 empty] | 8
24368410 | [26 empty] | 4 | 4
24368540 | [9 empty] | 1 | 4.4 | [16 empty] | 5.4
24368100 | [8 empty] | 1 |  | 4.4 | [16 empty] | 5.4
24368470 | [8 empty] | 3 | 2 | 3 | [16 empty] | 8
24368440 |  |  |  | 2 |  |  |  |  | 1 | 2 | 2 | [16 empty] | 7
24368340 |  |  |  |  | 0 | [5 empty] | 18 | [5 empty] | 0 | [10 empty] | 18
24368305 |  |  |  |  | 0 |  |  |  | 2 | 1 | 26 | [5 empty] | 0 |  |  |  | 0 | [6 empty] | 29
24368295 |  |  |  |  | 0 |  |  |  | 1 |  | 1 | [5 empty] | 0 | [10 empty] | 2
24368430 | [8 empty] | 1 |  | 4 | [16 empty] | 5
24368370 |  |  |  |  | 0 | [5 empty] | 18 | [5 empty] | 0 | [10 empty] | 18
24368290 |  |  |  |  | 0 |  |  |  | 0.6 |  | 11.9 | [5 empty] | 0 | [10 empty] | 12.5
24368520 | [9 empty] | 2 | [17 empty] | 2
24368445 |  |  |  | 10 | 0 | [5 empty] | 12 | [5 empty] | 0 | [10 empty] | 22
24368095 | [8 empty] | 2 |  | 4 | [16 empty] | 6
24368365 | [8 empty] | 0.2 |  | 0.8 | [16 empty] | 1
24368390 | [8 empty] | 0.2 |  | 0.8 | [16 empty] | 1
24368435 |  |  |  | 10 | 0 | [5 empty] | 12 | [5 empty] | 0 | [10 empty] | 22
24368590LOE | [9 empty] | 5 | [14 empty] | 2.1 |  |  | 7.1
24368530 |  |  |  |  | 0 | [5 empty] | 15 | [5 empty] | 0 | [10 empty] | 15
24368310 |  |  |  |  | 0 | [5 empty] | 15 | [5 empty] | 0 | [10 empty] | 15
24368565 |  |  |  | 2 |  |  | 0 |  |  |  | 3 | [5 empty] | 0 | [10 empty] | 5
24368130 |  |  |  | 4 | [16 empty] | 0 | [6 empty] | 4
24368570 | [9 empty] | 4 | 9 | [9 empty] | 0 | [6 empty] | 13
24368300 | [8 empty] | 0.2 |  | 0.8 | [16 empty] | 1
24368560 | [10 empty] | 6 | [16 empty] | 6
24368585LOE | [9 empty] | 22 | [14 empty] | 11 |  |  | 33
24368155A |  |  | 0.8 |  |  |  | 0 |  | 1.04 | 0.8 | 11.23 | [16 empty] | 13.87
24368420A |  |  |  | 28.83 | [20 empty] | 14.42 |  |  | 43.25
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | [9 empty] | 8 | 10 | [5 empty] | 0 |  |  |  | 0 | [6 empty] | 18
26112013 | [9 empty] | 8 | 10 | [16 empty] | 18
26112012 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
1.6.1.1.4 TUNNEL AIR CONDITIONING |  |  | 1 | [5 empty] | 1 | 20 | 13 | [5 empty] | 0 |  |  |  | 0 | [6 empty] | 35
26114005 | [9 empty] | 2 | [17 empty] | 2
26114025 | [9 empty] | 2 | [17 empty] | 2
26114020 |  |  | 1 | [5 empty] | 1 | 16 | 13 | [16 empty] | 31
26114010 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
26114015 | [16 empty] | 0 | [10 empty] | 0
1.8.2.3.1 HALL C HB AND Q1 TESTING | [8 empty] | 2 | 9 | 12.5 | [16 empty] | 23.5
28231000 | [8 empty] | 1 | 4 | 6 | [16 empty] | 11
28231010 | [9 empty] | 1 | 0.5 | [16 empty] | 1.5
28231005 | [8 empty] | 1 | 4 | 6 | [16 empty] | 11
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING |  |  | 2 | [5 empty] | 4.5 | 17 | 25.3 | [16 empty] | 48.8
28236000 | [8 empty] | 2.5 | 1 | 2.5 | [16 empty] | 6
28236005 | [9 empty] | 2 | 2 | [16 empty] | 4
28236030 |  |  | 2 | [6 empty] | 2 | 6 | [16 empty] | 10
28236015 | [9 empty] | 2 | 1.4 | [16 empty] | 3.4
28236025 | [9 empty] | 2 | 1.4 | [16 empty] | 3.4
28236010 | [8 empty] | 1 | 4 | 6 | [16 empty] | 11
28236020 | [8 empty] | 1 | 4 | 6 | [16 empty] | 11
1.8.2.3.X HALL C COMMISSIONG WITH BEAM | 12.6 | [8 empty] | 2.1 | 0.7 | [13 empty] | 9.8 |  | 8.4 | 33.6
2823X000 | 12.6 | [8 empty] | 2.1 | 0.7 | [13 empty] | 9.8 |  | 8.4 | 33.6
1.8.2.4.X HALL D COMMISSIONING WITH BEAM | 36 | [8 empty] | 6.8 | 4 | [13 empty] | 36 |  | 24 | 106.8
2824X000 | 36 | [8 empty] | 6.8 | 4 | [13 empty] | 36 |  | 24 | 106.8
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE |  |  | 30.6 |  |  |  | 0 |  |  | 122.3 | [14 empty] | 12.3 | 155.9 |  | 321.1
2831915LOE |  |  | 16.7 |  |  |  | 0 |  |  | 66.6 | [14 empty] | 6.7 | 84.9 |  | 174.9
2831916LOE |  |  | 13.9 |  |  |  | 0 |  |  | 55.7 | [14 empty] | 5.6 | 71 |  | 146.2
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES |  |  | 9.3 | 9.3 | [5 empty] | 9.3 | 9.3 | [9 empty] | 0 | [6 empty] | 37.2
2812035 |  |  | 1.6 | 1.6 | [5 empty] | 1.6 | 1.6 | [9 empty] | 0 | [6 empty] | 6.4
2812050 |  |  | 4.6 | 4.6 | [5 empty] | 4.6 | 4.6 | [9 empty] | 0 | [6 empty] | 18.4
2812020 |  |  | 3.1 | 3.1 | [5 empty] | 3.1 | 3.1 | [9 empty] | 0 | [6 empty] | 12.4
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING |  |  | 6 | 99.6 | [5 empty] | 6 | 12 | [13 empty] | 18 |  |  | 141.6
2811065 |  |  | 3 | 49.8 | [5 empty] | 3 | 6 | [13 empty] | 9 |  |  | 70.8
2811035 |  |  | 2 | 33.2 | [5 empty] | 2 | 4 | [13 empty] | 6 |  |  | 47.2
2811050 |  |  | 1 | 16.6 | [5 empty] | 1 | 2 | [13 empty] | 3 |  |  | 23.6
1.5.5.3 BEAMLINE COMPONENTS |  |  | 4.5 | 16 |  |  | 0 |  |  | 0.5 | 2 | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0.5 |  |  | 23.5
2553095 |  |  | 0.5 | 1.7 | [23 empty] | 2.2
2553157 | [6 empty] | 0 |  |  | 0.5 | 2 | [13 empty] | 0.5 |  |  | 3
2553010a | [16 empty] | 0 | [10 empty] | 0
2553095a |  |  | 4 | 14.3 | [23 empty] | 18.3
2553010 | [16 empty] | 0 |  |  |  | 0 | [6 empty] | 0
1.7.1 PROJECT OFFICE |  |  | 15.82 |  |  |  | 0 |  |  | 63.37 | [14 empty] | 6.27 | 80.78 |  | 166.24
271915LOE |  |  | 10.65 |  |  |  | 0 |  |  | 42.79 | [14 empty] | 4.24 | 54.57 |  | 112.25
271916LOE |  |  | 5.17 |  |  |  | 0 |  |  | 20.58 | [14 empty] | 2.03 | 26.21 |  | 53.99
Grand Total | 83.8 | 89.2 | 201.32 | 472.63 | 0 | 0 | 0 | 0 | 267.35 | 718.85 | 1410.83 | 0 | 0 | 0 | 4.7 | 32.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376.61 | 381.18 | 326.33 | 4364.97

## Resource Raw Data
WBS Name | Activity ID | Activity Name | Resource ID Name | Budgeted Units
1.4.2.2.1.1 SILICON DETECTOR | 242211810 | Installation MECH GRP - Support and alignment tube - Proc | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211545 | MECH GRP - Mounting and aligning on support structure in lab, R4 - Labor | P MECH DES.PLABOR | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211545 | MECH GRP - Mounting and aligning on support structure in lab, R4 - Labor | MECH TECH.MECH TECH | 6
1.4.2.2.1.1 SILICON DETECTOR | 242211545 | MECH GRP - Mounting and aligning on support structure in lab, R4 - Labor | MECH ENG.MECH ENG | 1
1.4.2.2.1.1 SILICON DETECTOR | 242211815 | Installation MECH GRP - Support and alignment (construction) - Labor | MECH ENG.MECH ENG | 1
1.4.2.2.1.1 SILICON DETECTOR | 242211815 | Installation MECH GRP - Support and alignment (construction) - Labor | MECH TECH.MECH TECH | 2
1.4.2.2.1.1 SILICON DETECTOR | 242211825 | Installation MECH GRP - AC Distribution - proc prep - Labor | MECH TECH.MECH TECH | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211825 | Installation MECH GRP - AC Distribution - proc prep - Labor | ELEC TECH.ELEC TECH | 1
1.4.2.2.1.1 SILICON DETECTOR | 242211865 | Installation MECH GRP - Purging system: installation - Proc | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211160w | FNAL Construction and test (Jlab/FNAL) of R4 production 11 modules | PRCRMNT>$50K69NESC14.PROCUREMENT>$50K 69 NO ESCALATION FY14 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211360 | HBI - Electronics HFCB R1-R4 - Proc | PRCRMNT<$50K60NESC14.PROCUREMENT<$50K 60 NO ESCALATION FY14 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211360 | HBI - Electronics HFCB R1-R4 - Proc | PRCRMNT>$50K69NESC14.PROCUREMENT>$50K 69 NO ESCALATION FY14 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211695 | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: - Proc | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211700 | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: construct & assemble - Labor | P MECH DES.PLABOR | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211700 | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: construct & assemble - Labor | MECH ENG.MECH ENG | 1
1.4.2.2.1.1 SILICON DETECTOR | 242211700 | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: construct & assemble - Labor | MECH TECH.MECH TECH | 4
1.4.2.2.1.1 SILICON DETECTOR | 242211745 | MECH GRP - Environmental Control System - Proc | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211876 | MECH GRP - Module shipping Charges from FNAL to Jlab - Proc | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211490 | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY13 | ELEC ENG.ELEC ENG | 1.7
1.4.2.2.1.1 SILICON DETECTOR | 242211490 | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY13 | ELEC TECH.ELEC TECH | 1.7
1.4.2.2.1.1 SILICON DETECTOR | 242211490 | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY13 | VISTNG USERS.VISTNG USERS | 3.4
1.4.2.2.1.1 SILICON DETECTOR | 242211485 | MECH GRP - Mounting and aligning on support structure in lab, R1-R3 - Labor | P MECH DES.PLABOR | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211485 | MECH GRP - Mounting and aligning on support structure in lab, R1-R3 - Labor | MECH ENG.MECH ENG | 1
1.4.2.2.1.1 SILICON DETECTOR | 242211485 | MECH GRP - Mounting and aligning on support structure in lab, R1-R3 - Labor | MECH TECH.MECH TECH | 12
1.4.2.2.1.1 SILICON DETECTOR | 242211870 | Installation MECH GRP - Purging system: installation in clean room- Labor | P MECH DES.PLABOR | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211870 | Installation MECH GRP - Purging system: installation in clean room- Labor | MECH ENG.MECH ENG | 1
1.4.2.2.1.1 SILICON DETECTOR | 242211870 | Installation MECH GRP - Purging system: installation in clean room- Labor | MECH TECH.MECH TECH | 2
1.4.2.2.1.1 SILICON DETECTOR | 242211515 | HBI - Electronics: HFCB Population - Proc Part A | PRCRMNT<$50K60NESC14.PROCUREMENT<$50K 60 NO ESCALATION FY14 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211830 | Installation MECH GRP - AC Distribution - Proc | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211160w5 | FNAL Construction and test (Jlab/FNAL) of R4 production 11 modules | PRCRMNT>$50K69NESC14.PROCUREMENT>$50K 69 NO ESCALATION FY14 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211395 | HBI - Sloco:Slow controls for monitoring and charge calib system: assemble, test, and debug ADC's- Labor | ELEC ENG.ELEC ENG | 4
1.4.2.2.1.1 SILICON DETECTOR | 242211395 | HBI - Sloco:Slow controls for monitoring and charge calib system: assemble, test, and debug ADC's- Labor | ELEC TECH.ELEC TECH | 4
1.4.2.2.1.1 SILICON DETECTOR | 242211520 | HBI - Electronics: HFCB Population - Proc Part B | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.1.1 SILICON DETECTOR | 242211400a | HBI - Sloco:Slow controls for monitor and charge calib system: develop sloco software (1/2) - Labor | ELEC ENG.ELEC ENG | 4
1.4.2.2.1.1 SILICON DETECTOR | 242211400a | HBI - Sloco:Slow controls for monitor and charge calib system: develop sloco software (1/2) - Labor | ELEC TECH.ELEC TECH | 9
1.4.2.2.1.1 SILICON DETECTOR | 242211600 | HBI - Full system R4, test and burn-in in Cleanroom EEL 121 - Labor | ELEC ENG.ELEC ENG | 4
1.4.2.2.1.1 SILICON DETECTOR | 242211600 | HBI - Full system R4, test and burn-in in Cleanroom EEL 121 - Labor | ELEC TECH.ELEC TECH | 4
1.4.2.2.1.1 SILICON DETECTOR | 242211600 | HBI - Full system R4, test and burn-in in Cleanroom EEL 121 - Labor | VISTNG USERS.VISTNG USERS | 8
1.4.2.2.1.1 SILICON DETECTOR | 242211615 | HBI - Full system R1-R3, test and burn-in in Cleanroom EEL 121 - Labor | ELEC TECH.ELEC TECH | 4.5
1.4.2.2.1.1 SILICON DETECTOR | 242211615 | HBI - Full system R1-R3, test and burn-in in Cleanroom EEL 121 - Labor | ELEC ENG.ELEC ENG | 4.5
1.4.2.2.1.1 SILICON DETECTOR | 242211615 | HBI - Full system R1-R3, test and burn-in in Cleanroom EEL 121 - Labor | VISTNG USERS.VISTNG USERS | 32
1.4.2.2.1.1 SILICON DETECTOR | 242211645 | HBI - Module Reception tests at JLAB - Labor FY14 | ELEC TECH.ELEC TECH | 9
1.4.2.2.1.1 SILICON DETECTOR | 242211645 | HBI - Module Reception tests at JLAB - Labor FY14 | ELEC ENG.ELEC ENG | 4.5
1.4.2.2.1.1 SILICON DETECTOR | 242211680 | MECH GRP - Full system test Integration of SVT R3/R4 - Labor | ELEC ENG.ELEC ENG | 3.7
1.4.2.2.1.1 SILICON DETECTOR | 242211680 | MECH GRP - Full system test Integration of SVT R3/R4 - Labor | ELEC TECH.ELEC TECH | 3.7
1.4.2.2.1.1 SILICON DETECTOR | 242211680 | MECH GRP - Full system test Integration of SVT R3/R4 - Labor | MECH ENG.MECH ENG | 1.8
1.4.2.2.1.1 SILICON DETECTOR | 242211680 | MECH GRP - Full system test Integration of SVT R3/R4 - Labor | MECH TECH.MECH TECH | 5.5
1.4.2.2.1.1 SILICON DETECTOR | 242211680 | MECH GRP - Full system test Integration of SVT R3/R4 - Labor | VISTNG USERS.VISTNG USERS | 6
1.4.2.2.1.1 SILICON DETECTOR | 242211490a | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY14 | ELEC TECH.ELEC TECH | 20.6
1.4.2.2.1.1 SILICON DETECTOR | 242211490a | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY14 | VISTNG USERS.VISTNG USERS | 41.6
1.4.2.2.1.1 SILICON DETECTOR | 242211490a | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY14 | ELEC ENG.ELEC ENG | 20.6
1.4.2.2.1.1 SILICON DETECTOR | 242211645A | HBI - Module Reception tests at JLAB - Labor FY15 | ELEC TECH.ELEC TECH | 1
1.4.2.2.1.1 SILICON DETECTOR | 242211645A | HBI - Module Reception tests at JLAB - Labor FY15 | ELEC ENG.ELEC ENG | 0.5
1.4.2.2.3.1 CENTRAL TOF | 242231270A | Final drawings for counter installation arm - cart and transport rack FY15 | MECH DES.MECH DES | 0.3
1.4.2.2.3.1 CENTRAL TOF | 242231325A | Assemble the Setup for Magnetic Shields Tests FY15 | SCIENTIST.SCIENTIST | 1.7
1.4.2.2.3.1 CENTRAL TOF | 242231325A | Assemble the Setup for Magnetic Shields Tests FY15 | MECH ENG.MECH ENG | 1.7
1.4.2.2.3.1 CENTRAL TOF | 242231325A | Assemble the Setup for Magnetic Shields Tests FY15 | MECH TECH.MECH TECH | 2.6
1.4.2.2.3.1 CENTRAL TOF | 242231325A | Assemble the Setup for Magnetic Shields Tests FY15 | VISTNG USERS.VISTNG USERS | 2.6
1.4.2.2.3.1 CENTRAL TOF | 242231395A | Install shield disks onto the Light guides FY15 | SCIENTIST.SCIENTIST | 1.5
1.4.2.2.3.1 CENTRAL TOF | 242231395A | Install shield disks onto the Light guides FY15 | MECH TECH.MECH TECH | 2
1.4.2.2.3.1 CENTRAL TOF | 242231400A | Install compensation coils and check polarity FY15 | SCIENTIST.SCIENTIST | 1.9
1.4.2.2.3.1 CENTRAL TOF | 242231400A | Install compensation coils and check polarity FY15 | MECH TECH.MECH TECH | 1.9
1.4.2.2.3.1 CENTRAL TOF | 242231405A | Install Middle. Mag. Shields onto PMT FY15 | SCIENTIST.SCIENTIST | 3.7
1.4.2.2.3.1 CENTRAL TOF | 242231405A | Install Middle. Mag. Shields onto PMT FY15 | MECH TECH.MECH TECH | 3.7
1.4.2.2.3.1 CENTRAL TOF | 242231115 | Refurbish Laser Calibration System | SCIENTIST.SCIENTIST | 2.5
1.4.2.2.3.1 CENTRAL TOF | 242231115 | Refurbish Laser Calibration System | MECH DES.MECH DES | 2.5
1.4.2.2.3.1 CENTRAL TOF | 242231115 | Refurbish Laser Calibration System | MECH TECH.MECH TECH | 2.5
1.4.2.2.3.1 CENTRAL TOF | 242231115 | Refurbish Laser Calibration System | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.2.3.1 CENTRAL TOF | 242231265 | CTOF procure support and solenoid harness and interface rings | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231395 | Install shield disks onto the Light guides FY14 | SCIENTIST.SCIENTIST | 0.5
1.4.2.2.3.1 CENTRAL TOF | 242231395 | Install shield disks onto the Light guides FY14 | MECH TECH.MECH TECH | 0.6
1.4.2.2.3.1 CENTRAL TOF | 242231405 | Install Middle. Mag. Shields onto PMT FY14 | SCIENTIST.SCIENTIST | 1.1
1.4.2.2.3.1 CENTRAL TOF | 242231405 | Install Middle. Mag. Shields onto PMT FY14 | MECH TECH.MECH TECH | 1.1
1.4.2.2.3.1 CENTRAL TOF | 242231410 | CTOF in Storage Rack cabling | SCIENTIST.SCIENTIST | 2
1.4.2.2.3.1 CENTRAL TOF | 242231410 | CTOF in Storage Rack cabling | MECH TECH.MECH TECH | 1
1.4.2.2.3.1 CENTRAL TOF | 242231400 | Install compensation coils and check polarity FY14 | SCIENTIST.SCIENTIST | 0.5
1.4.2.2.3.1 CENTRAL TOF | 242231400 | Install compensation coils and check polarity FY14 | MECH TECH.MECH TECH | 0.5
1.4.2.2.3.1 CENTRAL TOF | 242231415 | Assemble the DAQ system | SCIENTIST.SCIENTIST | 2.4
1.4.2.2.3.1 CENTRAL TOF | 242231420 | Standalone CTOF testing/optimizing | SCIENTIST.SCIENTIST | 1.6
1.4.2.2.3.1 CENTRAL TOF | 242231420 | Standalone CTOF testing/optimizing | MECH TECH.MECH TECH | 0.3
1.4.2.2.3.1 CENTRAL TOF | 242231425 | Prepare CTOF-in-Storage-Rack for transportation | VISTNG USERS.VISTNG USERS | 3
1.4.2.2.3.1 CENTRAL TOF | 242231425 | Prepare CTOF-in-Storage-Rack for transportation | MECH TECH.MECH TECH | 3
1.4.2.2.3.1 CENTRAL TOF | 242231425 | Prepare CTOF-in-Storage-Rack for transportation | SCIENTIST.SCIENTIST | 3
1.4.2.2.3.1 CENTRAL TOF | 242231260 | Final Drawings of CTOF Support and Solenoid Harness | MECH DES.MECH DES | 4
1.4.2.2.3.1 CENTRAL TOF | 242231435 | Purchase/Fabricate/Ship Middle Mag. Disks-2 Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231440 | Purchase/Fabricate/Ship Extern. Mag. Disks-1 Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231445 | Purchase/Fabricate/Ship Extern. Mag. Disks-2 Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231450 | Purchase/Fabricate/Ship Inner Mag. Cylinder #1 | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231455 | Purchase/Fabricate/Ship Inner Non-mag. Cylinder #2 | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231275 | CTOF procure installation tooling and transport rack | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231290 | Purchase Coil components and materials | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.2.3.1 CENTRAL TOF | 242231272 | Counter installation arm - cart and transport rack Engineering Analysis | MECH ENG.MECH ENG | 4
1.4.2.2.3.1 CENTRAL TOF | 242231430 | Purchase incidentals/tools/material | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.2.3.1 CENTRAL TOF | 242231390 | Install PMT and check the orientation | SCIENTIST.SCIENTIST | 1
1.4.2.2.3.1 CENTRAL TOF | 242231390 | Install PMT and check the orientation | MECH TECH.MECH TECH | 2
1.4.2.2.3.1 CENTRAL TOF | 242231300 | Fabricate Compensating Coil Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231295 | Fabricate Compensating Coil Machine Shop | EXPNS MACHINE SHOP.MSHOP | 0
1.4.2.2.3.1 CENTRAL TOF | 242231305 | Purchase/Fabricate/Ship Inner Mag. Cylinder Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231325 | Assemble the Setup for Magnetic Shields Tests FY14 | SCIENTIST.SCIENTIST | 0.3
1.4.2.2.3.1 CENTRAL TOF | 242231325 | Assemble the Setup for Magnetic Shields Tests FY14 | MECH ENG.MECH ENG | 0.3
1.4.2.2.3.1 CENTRAL TOF | 242231325 | Assemble the Setup for Magnetic Shields Tests FY14 | MECH TECH.MECH TECH | 0.4
1.4.2.2.3.1 CENTRAL TOF | 242231325 | Assemble the Setup for Magnetic Shields Tests FY14 | VISTNG USERS.VISTNG USERS | 0.4
1.4.2.2.3.1 CENTRAL TOF | 242231335 | Purchase Cables and Connectors | SCIENTIST.SCIENTIST | 0.6
1.4.2.2.3.1 CENTRAL TOF | 242231335 | Purchase Cables and Connectors | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.2.3.1 CENTRAL TOF | 242231340 | Fabricate Cables LV&HV | MECH TECH.MECH TECH | 5
1.4.2.2.3.1 CENTRAL TOF | 242231340 | Fabricate Cables LV&HV | SCIENTIST.SCIENTIST | 1
1.4.2.2.3.1 CENTRAL TOF | 242231340 | Fabricate Cables LV&HV | VISTNG USERS.VISTNG USERS | 1
1.4.2.2.3.1 CENTRAL TOF | 242231355 | Fabricate Patch Panels for LV&HV | MECH TECH.MECH TECH | 3
1.4.2.2.3.1 CENTRAL TOF | 242231355 | Fabricate Patch Panels for LV&HV | SCIENTIST.SCIENTIST | 1
1.4.2.2.3.1 CENTRAL TOF | 242231355 | Fabricate Patch Panels for LV&HV | VISTNG USERS.VISTNG USERS | 1
1.4.2.2.3.1 CENTRAL TOF | 242231355 | Fabricate Patch Panels for LV&HV | ELEC TECH.ELEC TECH | 3
1.4.2.2.3.1 CENTRAL TOF | 242231360 | Fabricate Splitter Parts | ELEC TECH.ELEC TECH | 1
1.4.2.2.3.1 CENTRAL TOF | 242231360 | Fabricate Splitter Parts | SCIENTIST.SCIENTIST | 1
1.4.2.2.3.1 CENTRAL TOF | 242231360 | Fabricate Splitter Parts | MECH TECH.MECH TECH | 2
1.4.2.2.3.1 CENTRAL TOF | 242231365 | Assembling of the CTOF patch panels | ELEC TECH.ELEC TECH | 2
1.4.2.2.3.1 CENTRAL TOF | 242231365 | Assembling of the CTOF patch panels | VISTNG USERS.VISTNG USERS | 2
1.4.2.2.3.1 CENTRAL TOF | 242231365 | Assembling of the CTOF patch panels | SCIENTIST.SCIENTIST | 1
1.4.2.2.3.1 CENTRAL TOF | 242231370 | Assembling of the CTOF splitters | ELEC TECH.ELEC TECH | 2
1.4.2.2.3.1 CENTRAL TOF | 242231370 | Assembling of the CTOF splitters | VISTNG USERS.VISTNG USERS | 2
1.4.2.2.3.1 CENTRAL TOF | 242231370 | Assembling of the CTOF splitters | SCIENTIST.SCIENTIST | 2
1.4.2.2.3.1 CENTRAL TOF | 242231270 | Final drawings for counter installation arm - cart and transport rack FY14 | MECH DES.MECH DES | 11.7
1.4.2.2.3.1 CENTRAL TOF | 242231385 | Testing External magnetic shields | SCIENTIST.SCIENTIST | 4.8
1.4.2.2.3.1 CENTRAL TOF | 242231385 | Testing External magnetic shields | MECH TECH.MECH TECH | 4.8
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241450ba | Assembly of the CV FY14 | MECH TECH.MECH TECH | 16.3
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241450b | Assembly of the CV FY13 | MECH TECH.MECH TECH | 3
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241528 | Assembly of the HTCC Gas System | ELEC TECH.ELEC TECH | 2
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241528 | Assembly of the HTCC Gas System | VISTNG USERS.VISTNG USERS | 3
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241528 | Assembly of the HTCC Gas System | SCIENTIST.SCIENTIST | 0.5
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241528 | Assembly of the HTCC Gas System | MECH TECH.MECH TECH | 2
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241640 | Installation ofthe ellipsoidal mirror - Lab | VISTNG USERS.VISTNG USERS | 2.7
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241640 | Installation ofthe ellipsoidal mirror - Lab | SCIENTIST.SCIENTIST | 1.8
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241640 | Installation ofthe ellipsoidal mirror - Lab | MECH DES.MECH DES | 0.5
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241640 | Installation ofthe ellipsoidal mirror - Lab | MECH TECH.MECH TECH | 20.5
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241640 | Installation ofthe ellipsoidal mirror - Lab | MECH ENG.MECH ENG | 0.5
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241645 | Optical tests of mirror geometry in situ - Lab | VISTNG USERS.VISTNG USERS | 2
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241645 | Optical tests of mirror geometry in situ - Lab | PD UNIV STAFF.PD UNIV STAFF | 1
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241645 | Optical tests of mirror geometry in situ - Lab | PD UNIV STUDNT.PD UNIV STUDNT | 1
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241645 | Optical tests of mirror geometry in situ - Lab | SCIENTIST.SCIENTIST | 2
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241610 | Installation of the composite exit window - Lab | MECH TECH.MECH TECH | 2
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241630 | Installation of a temporary CO2 gas supply system - Lab | MECH TECH.MECH TECH | 3.5
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d | Installation of LMS | SCIENTIST.SCIENTIST | 0.1
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d | Installation of LMS | VISTNG USERS.VISTNG USERS | 2
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d | Installation of LMS | PD UNIV STUDNT.PD UNIV STUDNT | 1.3
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d | Installation of LMS | PD UNIV STAFF.PD UNIV STAFF | 1.3
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d5 | Quality control of the installed items | SCIENTIST.SCIENTIST | 7
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d5 | Quality control of the installed items | VISTNG USERS.VISTNG USERS | 7
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d5 | Quality control of the installed items | PD UNIV STUDNT.PD UNIV STUDNT | 5.6
1.4.2.2.4.1 HIGH THRESHOLD CC | 242241647d5 | Quality control of the installed items | PD UNIV STAFF.PD UNIV STAFF | 2.4
1.4.2.2.4.2 LOW THRESHOLD CC | 242242340 | Sector 2 Box Refurbish | MECH TECH.MECH TECH | 8
1.4.2.2.4.2 LOW THRESHOLD CC | 242242350 | Sector 2 Mirrors Alignment | MECH TECH.MECH TECH | 2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242355 | Sector 2 Windows Installation | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242360 | Sector 2 Gas Leaks Checks | MECH TECH.MECH TECH | 1.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092A | Al/Mg Deposit Procurement WC Labor FY15 | SCIENTIST.SCIENTIST | 0.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092B | Al/Mg Deposit Procurement WC Procurement | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092B | Al/Mg Deposit Procurement WC Procurement | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242115A | Installation of Elliptical mirrors FY15 | MECH TECH.MECH TECH | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242115A | Installation of Elliptical mirrors FY15 | SCIENTIST.SCIENTIST | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242163A | Divider Modifications Labor FY15 | SCIENTIST.SCIENTIST | 0.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242163B | Divider Modifications Procurement | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242164A | Divider Modifications Implementation FY15 | SCIENTIST.SCIENTIST | 0.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242164A | Divider Modifications Implementation FY15 | ELEC TECH.ELEC TECH | 0.8
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205A | Mirrors Laser Alignments FY15 | PD UNIV STUDNT.PD UNIV STUDNT | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205A | Mirrors Laser Alignments FY15 | MECH TECH.MECH TECH | 0.7
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205A | Mirrors Laser Alignments FY15 | SCIENTIST.SCIENTIST | 0.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205A | Mirrors Laser Alignments FY15 | VISTNG USERS.VISTNG USERS | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242223A | Online HV Matching Test FY15 | SCIENTIST.SCIENTIST | 0.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242230A | PMT Installation FY15 | SCIENTIST.SCIENTIST | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242230A | PMT Installation FY15 | MECH TECH.MECH TECH | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242235A | Windows Installation 6 sectors FY15 | MECH TECH.MECH TECH | 1.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242240A | Gas Leak Check 6 sectors FY15 | MECH TECH.MECH TECH | 1.4
1.4.2.2.4.2 LOW THRESHOLD CC | 242242240A | Gas Leak Check 6 sectors FY15 | SCIENTIST.SCIENTIST | 1.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242315A | Patch Panel Installation FY15 | MECH TECH.MECH TECH | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242315A | Patch Panel Installation FY15 | SCIENTIST.SCIENTIST | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242325B | Spine Refusrbish FY15 | MECH TECH.MECH TECH | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242330A | Gas Line Refurbish FY15 | MECH TECH.MECH TECH | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242330A | Gas Line Refurbish FY15 | SCIENTIST.SCIENTIST | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242400A | Sector 4 Mirrors Alignment FY15 | MECH TECH.MECH TECH | 1.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242365 | Sector 3 Box Refurbish | MECH TECH.MECH TECH | 7.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242375 | Sector 3 Mirrors Alignment | MECH TECH.MECH TECH | 2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242380 | Sector 3 Windows Installation | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242385 | Sector 3 Gas Leaks Checks | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242390 | Sector 4 Box Refurbish | MECH TECH.MECH TECH | 7.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242400 | Sector 4 Mirrors Alignment FY14 | MECH TECH.MECH TECH | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242405 | Sector 4 Windows Installation | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242410 | Sector 4 Gas Leaks Checks | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242415 | Sector 5 Box Refurbish | MECH TECH.MECH TECH | 6.4
1.4.2.2.4.2 LOW THRESHOLD CC | 242242425 | Sector 5 Mirrors Alignment | MECH TECH.MECH TECH | 2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242430 | Sector 5 Windows Installation | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242435 | Sector 5 Gas Leaks Checks | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242440 | Sector 6 Box Refurbish | MECH TECH.MECH TECH | 6.4
1.4.2.2.4.2 LOW THRESHOLD CC | 242242450 | Sector 6 Mirrors Alignment | MECH TECH.MECH TECH | 2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242455 | Sector 6 Windows Installation | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242460 | Sector 6 Gas Leaks Checks | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242115 | Installation of Elliptical mirrors FY14 | MECH TECH.MECH TECH | 0.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242115 | Installation of Elliptical mirrors FY14 | SCIENTIST.SCIENTIST | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242155 | Walls Manufacturing and Installation | SCIENTIST.SCIENTIST | 0.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242155 | Walls Manufacturing and Installation | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242190 | Install Gas Line (1S) | MECH TECH.MECH TECH | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242195 | Gas Line Quality Control | MECH TECH.MECH TECH | 0.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205 | Mirrors Laser Alignments FY14 | PD UNIV STUDNT.PD UNIV STUDNT | 3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205 | Mirrors Laser Alignments FY14 | MECH TECH.MECH TECH | 2.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205 | Mirrors Laser Alignments FY14 | SCIENTIST.SCIENTIST | 2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205 | Mirrors Laser Alignments FY14 | VISTNG USERS.VISTNG USERS | 3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242215 | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | SCIENTIST.SCIENTIST | 0.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242225 | Online Calibration Test | SCIENTIST.SCIENTIST | 0.4
1.4.2.2.4.2 LOW THRESHOLD CC | 242242230 | PMT Installation FY14 | SCIENTIST.SCIENTIST | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242230 | PMT Installation FY14 | MECH TECH.MECH TECH | 0.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242235 | Windows Installation 6 sectors FY14 | MECH TECH.MECH TECH | 3.8
1.4.2.2.4.2 LOW THRESHOLD CC | 242242220a | Online Calibration Design FY13 | SCIENTIST.SCIENTIST | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031a | Quality Control of Existing PMTs FY14 | CONTRB UNIV LBR.CONTRB UNIV LBR | 5.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031a | Quality Control of Existing PMTs FY14 | VISTNG USERS.VISTNG USERS | 3.7
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031a | Quality Control of Existing PMTs FY14 | SCIENTIST.SCIENTIST | 0.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242152 | Window Procurement | SCIENTIST.SCIENTIST | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242152 | Window Procurement | PRCRMNT<$50K60NESC14.PROCUREMENT<$50K 60 NO ESCALATION FY14 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242240 | Gas Leak Check 6 sectors FY14 | MECH TECH.MECH TECH | 1.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242240 | Gas Leak Check 6 sectors FY14 | SCIENTIST.SCIENTIST | 1.4
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092 | Al/Mg Deposit Procurement WC Labor FY14 | SCIENTIST.SCIENTIST | 1.9
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092 | Al/Mg Deposit Procurement WC Labor FY14 | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092 | Al/Mg Deposit Procurement WC Labor FY14 | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242220aa | Online Calibration Design FY14 | SCIENTIST.SCIENTIST | 0.9
1.4.2.2.4.2 LOW THRESHOLD CC | 242242222a | Online HV Matching Design FY14 | SCIENTIST.SCIENTIST | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242280a | Frame Support FY14 | MECH TECH.MECH TECH | 0.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242325a | Spine Refurbish FY14 | MECH TECH.MECH TECH | 0.4
1.4.2.2.4.2 LOW THRESHOLD CC | 242242222 | Online HV Matching Design FY13 | SCIENTIST.SCIENTIST | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242223 | Online HV Matching Test FY14 | SCIENTIST.SCIENTIST | 0.9
1.4.2.2.4.2 LOW THRESHOLD CC | 242242076 | Support Frame Fabrication for 1S in TED | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242076 | Support Frame Fabrication for 1S in TED | MECH TECH.MECH TECH | 1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242040 | Wavelength Shifting Procurement (Temple) | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242040 | Wavelength Shifting Procurement (Temple) | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031 | Quality Control of Existing PMTs FY13 | CONTRB UNIV LBR.CONTRB UNIV LBR | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031 | Quality Control of Existing PMTs FY13 | VISTNG USERS.VISTNG USERS | 0.3
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031 | Quality Control of Existing PMTs FY13 | SCIENTIST.SCIENTIST | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242163 | Divider Modifications Labor FY14 | SCIENTIST.SCIENTIST | 0.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242163 | Divider Modifications Labor FY14 | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242164 | Divider Modifications Implementation FY14 | ELEC TECH.ELEC TECH | 3.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242164 | Divider Modifications Implementation FY14 | SCIENTIST.SCIENTIST | 0.9
1.4.2.2.4.2 LOW THRESHOLD CC | 242242280 | Frame Support FY13 | MECH TECH.MECH TECH | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242305 | Rear Brace Installation | MECH TECH.MECH TECH | 0.8
1.4.2.2.4.2 LOW THRESHOLD CC | 242242315 | Patch Panel Installation FY14 | MECH TECH.MECH TECH | 0.2
1.4.2.2.4.2 LOW THRESHOLD CC | 242242315 | Patch Panel Installation FY14 | SCIENTIST.SCIENTIST | 0.1
1.4.2.2.4.2 LOW THRESHOLD CC | 242242325 | Spine Refurbish FY13 | MECH TECH.MECH TECH | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242330 | Gas Line Refurbish FY14 | MECH TECH.MECH TECH | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242330 | Gas Line Refurbish FY14 | SCIENTIST.SCIENTIST | 0.1
1.4.2.3.1 TRIGGER SYSTEM (Scintillators) | 24231007 | CTP procurement (22 boards) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.3.1 TRIGGER SYSTEM (Scintillators) | 24231007 | CTP procurement (22 boards) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.3.1 TRIGGER SYSTEM (Scintillators) | 24231005 | CTP procurement Prep | ELEC ENG.ELEC ENG | 2
1.4.2.3.2 DAQ | 24232022 | Procure GE VME controllers (53) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.3.2 DAQ | 24232022 | Procure GE VME controllers (53) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.3.2 DAQ | 24232025 | Install GE VME controllers (22) | SCIENTIST.SCIENTIST | 8
1.4.2.3.3 ONLINE COMPUTING | 24233035 | Install 4-port 10GBit Blades for BigIron | SCIENTIST.SCIENTIST | 1
1.4.2.3.3 ONLINE COMPUTING | 24233040 | Procure Ethernet fibers/Cu wires | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.3.3 ONLINE COMPUTING | 24233045 | Install Ethernet fibers/Cu wires | SCIENTIST.SCIENTIST | 2
1.4.2.3.3 ONLINE COMPUTING | 24233055 | Install Terminal servers (Etherlite32) (10) | SCIENTIST.SCIENTIST | 1
1.4.2.3.3 ONLINE COMPUTING | 24233065 | Install daq/online computers | SCIENTIST.SCIENTIST | 7
1.4.2.3.3 ONLINE COMPUTING | 24233010 | Ethernet wiring inside Hall B (10Gbit) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.3.3 ONLINE COMPUTING | 24233015 | Trigger system fibers wiring | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.3.3 ONLINE COMPUTING | 24233020 | Procure CISCO 2960S switches (24 Cu ports) (15) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.3.3 ONLINE COMPUTING | 24233020 | Procure CISCO 2960S switches (24 Cu ports) (15) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.3.3 ONLINE COMPUTING | 24233025 | Install CISCO 2960S switches (24 Cu ports) (15) | SCIENTIST.SCIENTIST | 4
1.4.2.3.3 ONLINE COMPUTING | 24233030 | Procure 4-port 10GBit Blades for BigIron | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.3.3 ONLINE COMPUTING | 24233030 | Procure 4-port 10GBit Blades for BigIron | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.3.5 SLOW CONTROLS | 24235010a | SLOW CNTL (EPICS device drivers development) FY14 | SCIENTIST.SCIENTIST | 21.9
1.4.2.3.5 SLOW CONTROLS | 24235015 | SLOW CNTL (EPICS software development) | SCIENTIST.SCIENTIST | 22
1.4.2.3.5 SLOW CONTROLS | 24235015 | SLOW CNTL (EPICS software development) | VISTNG USERS.VISTNG USERS | 88
1.4.2.3.5 SLOW CONTROLS | 24235010aB | SLOW CNTL (EPICS device drivers development) FY15 | SCIENTIST.SCIENTIST | 0.1
1.4.2.4.2 TDC AND DISCRIMINATORS | 24242005a | CAEN v1190 (1) and v1290N (7) TDC's installation (SF) | P ELEC TECH.PLABOR | 0
1.4.2.4.2 TDC AND DISCRIMINATORS | 24242030a | JLab TDC Fanout (2) test/install (SF) | SCIENTIST.SCIENTIST | 0
1.4.2.4.2 TDC AND DISCRIMINATORS | 24242030a | JLab TDC Fanout (2) test/install (SF) | P ELEC TECH.PLABOR | 0
1.4.2.4.2 TDC AND DISCRIMINATORS | 24242055 | ORTEC 935F Discriminators (24) Test/Install (SF) | P ELEC TECH.PLABOR | 0
1.4.2.4.2 TDC AND DISCRIMINATORS | 24242040a | JLab Discriminator (12) and Flash FADC (12) test/install (SF) | P ELEC TECH.PLABOR | 0
1.4.2.4.3 SCALERS | 24243010 | SCALERS - Procurement/Install (SF) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.4.3 SCALERS | 24243010 | SCALERS - Procurement/Install (SF) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.4.4 HIGH VOLTAGE | 24244030 | CAEN 1527 HV mainframes install (12) (FC), (2) (SF)installation | P ELEC TECH.PLABOR | 0
1.4.2.4.7 CRATES, RACKS | 24247045 | Re-locate existing UPS to Hall B | P ELEC TECH.PLABOR | 0
1.4.2.4.7 CRATES, RACKS | 24247005a | Wiener VME64x crates install (2) (SF) FY14 | P ELEC TECH.PLABOR | 0
1.4.2.4.7 CRATES, RACKS | 24247030 | NIM crates (2) install (SF) | P ELEC TECH.PLABOR | 0
1.4.2.4.7 CRATES, RACKS | 24247005aB | Wiener VME64x crates install (2) (SF) FY15 | P ELEC TECH.PLABOR | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254015 | Downstream Viewer Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254015 | Downstream Viewer Procurement | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254020 | Downstream Viewer Assembly | MECH TECH.MECH TECH | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254035 | Moller polarimeter upgrade Installation | MECH TECH.MECH TECH | 7.1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254035 | Moller polarimeter upgrade Installation | ELEC ENG.ELEC ENG | 0.9
1.4.2.5.4 BEAMLINE COMPONENTS | 24254045 | Moller Shielding Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254045 | Moller Shielding Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254050 | Moller Shielding Installation | MECH TECH.MECH TECH | 8
1.4.2.5.4 BEAMLINE COMPONENTS | 24254060 | Downstream Vacuum System Installation | MECH TECH.MECH TECH | 4
1.4.2.5.4 BEAMLINE COMPONENTS | 24254080 | Beam Offset Monitor Installation | MECH DES.MECH DES | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254080 | Beam Offset Monitor Installation | MECH TECH.MECH TECH | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254080 | Beam Offset Monitor Installation | ELEC ENG.ELEC ENG | 2
1.4.2.5.4 BEAMLINE COMPONENTS | 24254075 | Beam Offset Monitor Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254090 | 2C24 girder move Labor | MECH TECH.MECH TECH | 9
1.4.2.5.4 BEAMLINE COMPONENTS | 24254085 | 2C24 girder move Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254100 | Upstream beam blocker and vacuum box Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254100 | Upstream beam blocker and vacuum box Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254095 | Upstream beam blocker and vacuum box Manufacturing Design | MECH DES.MECH DES | 4
1.4.2.5.4 BEAMLINE COMPONENTS | 24254095 | Upstream beam blocker and vacuum box Manufacturing Design | MECH ENG.MECH ENG | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254105 | Upstream beam blocker and vacuum box Installation | MECH TECH.MECH TECH | 4
1.4.2.5.4 BEAMLINE COMPONENTS | 24254105 | Upstream beam blocker and vacuum box Installation | ELEC ENG.ELEC ENG | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254115 | Upstream Shielding Wall Installation | MECH DES.MECH DES | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254115 | Upstream Shielding Wall Installation | MECH TECH.MECH TECH | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254115 | Upstream Shielding Wall Installation | ELEC ENG.ELEC ENG | 2
1.4.2.5.4 BEAMLINE COMPONENTS | 24254110 | Upstream Shielding Wall Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254110 | Upstream Shielding Wall Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254110 | Upstream Shielding Wall Procurement | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254110 | Upstream Shielding Wall Procurement | PRCRMNT>$50K69NESC16.PROCUREMENT>$50K 69 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254120 | Procurement of Beamline Devices | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254120 | Procurement of Beamline Devices | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254000 | Faraday Cup Materials | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254030 | Moller polarimeter upgrade Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254030 | Moller polarimeter upgrade Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254030 | Moller polarimeter upgrade Procurement | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254030 | Moller polarimeter upgrade Procurement | PRCRMNT>$50K69NESC16.PROCUREMENT>$50K 69 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254025 | Moller polarimeter upgrade Manufacturing Design | MECH DES.MECH DES | 4
1.4.2.5.4 BEAMLINE COMPONENTS | 24254025 | Moller polarimeter upgrade Manufacturing Design | MECH ENG.MECH ENG | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254070 | Upstream Vacuum System Installation | MECH DES.MECH DES | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254070 | Upstream Vacuum System Installation | MECH TECH.MECH TECH | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254040 | Moller Shielding Manufacturing Design | MECH DES.MECH DES | 4
1.4.2.5.4 BEAMLINE COMPONENTS | 24254040 | Moller Shielding Manufacturing Design | MECH ENG.MECH ENG | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254055 | Downstream Vacuum System Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254065 | Upstream Vacuum System Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254005 | Faraday Cup Labor | ELEC ENG.ELEC ENG | 1
1.4.2.5.4 BEAMLINE COMPONENTS | 24254005 | Faraday Cup Labor | ELEC TECH.ELEC TECH | 2
1.4.2.5.4 BEAMLINE COMPONENTS | 24254010 | Downstream Viewer Manufacturing Design | MECH DES.MECH DES | 1
1.4.2.6.4 INSTALLATION | 24264470 | Cable/test/repair LTCC's | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264470 | Cable/test/repair LTCC's | SCIENTIST.SCIENTIST | 1.2
1.4.2.6.4 INSTALLATION | 24264920 | DC - design maintenance platforms | P MECH DES.PLABOR | 0
1.4.2.6.4 INSTALLATION | 24264925 | DC - maintenance platforms Engineering Analysis | MECH ENG.MECH ENG | 3
1.4.2.6.4 INSTALLATION | 24264930 | DC - procure maintenance platforms | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264527 | Distribution Can - Connect cold piping with fittings and welding | MECH TECH.MECH TECH | 4
1.4.2.6.4 INSTALLATION | 24264529 | Distribution Can - Connect Instrumentation and valves | MECH TECH.MECH TECH | 4
1.4.2.6.4 INSTALLATION | 24264531 | Distribution Can - leak test system | MECH TECH.MECH TECH | 3.2
1.4.2.6.4 INSTALLATION | 24264533 | Distribution Can - pressure test system | MECH TECH.MECH TECH | 1.6
1.4.2.6.4 INSTALLATION | 24264535 | Distribution Can - final leak test system | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264540 | Distribution Can - purify system | MECH TECH.MECH TECH | 2
1.4.2.6.4 INSTALLATION | 24264805 | Install Solenoid cart | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264810 | Assemble Solenoid and Piping | P LABORER.PLABOR | 0
1.4.2.6.4 INSTALLATION | 24264810 | Assemble Solenoid and Piping | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264517 | Modify Space Frame For Cryo Can | PRCRMNT<$50K60NESC14.PROCUREMENT<$50K 60 NO ESCALATION FY14 | 0
1.4.2.6.4 INSTALLATION | 24264797 | Solenoid - procure cart | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264650 | Install cold to warm supports | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264645 | Pressure/leak test. Electrical test. | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264645 | Pressure/leak test. Electrical test. | ELEC TECH.ELEC TECH | 2
1.4.2.6.4 INSTALLATION | 24264655 | Insulate cold to warm supports | MECH TECH.MECH TECH | 1.6
1.4.2.6.4 INSTALLATION | 24264660 | Complete shields on hex and hub | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264665 | Install MLI on hex beam to coil connections | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264670 | Complete 4K and 80K shields on coil-to-coil gaps at hub | MECH TECH.MECH TECH | 3.6
1.4.2.6.4 INSTALLATION | 24264675 | Install U-shape vacumm jacket sections, skip weld | MECH TECH.MECH TECH | 9.6
1.4.2.6.4 INSTALLATION | 24264680 | Install plates to complete vacuum jacket at hub, skip weld | MECH TECH.MECH TECH | 3.6
1.4.2.6.4 INSTALLATION | 24264685 | Survey assembly for symmetry | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264690 | Route instrumentation wires, make electrical connections at feedthroughs | ELEC TECH.ELEC TECH | 4.8
1.4.2.6.4 INSTALLATION | 24264690 | Route instrumentation wires, make electrical connections at feedthroughs | MECH TECH.MECH TECH | 4.8
1.4.2.6.4 INSTALLATION | 24264695 | Install brackets to complete vacuum jacket welding | MECH TECH.MECH TECH | 7.2
1.4.2.6.4 INSTALLATION | 24264700 | Final leak check, final electrical tests | ELEC TECH.ELEC TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264700 | Final leak check, final electrical tests | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264705 | Install and tack weld closure plates on hex | MECH TECH.MECH TECH | 4.8
1.4.2.6.4 INSTALLATION | 24264710 | Install LN2 Thermosiphon Jumpers | MECH TECH.MECH TECH | 3.2
1.4.2.6.4 INSTALLATION | 24264712 | Complete all welding to finsih vacuum jacket | MECH TECH.MECH TECH | 30
1.4.2.6.4 INSTALLATION | 24264715 | Orient assembly, survey, and lock rotation | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264717 | Construct legs in Hall B | MECH TECH.MECH TECH | 8
1.4.2.6.4 INSTALLATION | 24264740 | Final pressure test | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264750 | Pump down vacuum | MECH TECH.MECH TECH | 2
1.4.2.6.4 INSTALLATION | 24264770 | Install mounting adapters for drift chambers | MECH TECH.MECH TECH | 8.2
1.4.2.6.4 INSTALLATION | 24264770 | Install mounting adapters for drift chambers | MECH ENG.MECH ENG | 3
1.4.2.6.4 INSTALLATION | 24264762A | Cut Back the warm piping | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264762H | Purify Entire System | MECH TECH.MECH TECH | 1
1.4.2.6.4 INSTALLATION | 24264762B | Procure warm gas valves and fittings | MECH ENG.MECH ENG | 4
1.4.2.6.4 INSTALLATION | 24264762B | Procure warm gas valves and fittings | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.6.4 INSTALLATION | 24264762C | Install New warm gas Piping | MECH TECH.MECH TECH | 4
1.4.2.6.4 INSTALLATION | 24264762G | Final Leak Test system | MECH TECH.MECH TECH | 1.6
1.4.2.6.4 INSTALLATION | 24264762D | Leak Test new warm Piping | MECH TECH.MECH TECH | 1.6
1.4.2.6.4 INSTALLATION | 24264762F | Pressure Test warm Piping | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264732 | Torus Cryotower - Connect cold piping with fittings and welding | MECH TECH.MECH TECH | 7.2
1.4.2.6.4 INSTALLATION | 24264745 | Pump vacuum | MECH TECH.MECH TECH | 1
1.4.2.6.4 INSTALLATION | 24264737 | Leak check, electrical tests | MECH TECH.MECH TECH | 3
1.4.2.6.4 INSTALLATION | 24264737 | Leak check, electrical tests | ELEC TECH.ELEC TECH | 1
1.4.2.6.4 INSTALLATION | 24264747 | Leak tests while pumping | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264742 | Close 1-8" holes, close vacuum jacket | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264762 | Design Warm Gas Panel and Piping | MECH ENG.MECH ENG | 3
1.4.2.6.4 INSTALLATION | 24264730 | Locate/install cryotower | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264577 | Install Coil C, survey & align | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264580 | Rotate Assembly, Sector 4 to bottom, prep. | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264550 | Install Spit in Hall B | MECH TECH.MECH TECH | 3.2
1.4.2.6.4 INSTALLATION | 24264546 | Install Torus Control System | ELEC TECH.ELEC TECH | 4
1.4.2.6.4 INSTALLATION | 24264546 | Install Torus Control System | ELEC ENG.ELEC ENG | 4
1.4.2.6.4 INSTALLATION | 24264555 | Mount Hub to Spit | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264557 | Align Spit to Beamline | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264560 | Attach Coil A to Hub | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264562 | Rotate Assembly, attach Sector 3 beams | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264565 | Install Coil B, survey & align | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264567 | Rotate Assembly, Sector 3 to bottom, prep. | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264570 | Install hardware on Sector 3 US beam | MECH TECH.MECH TECH | 11.7
1.4.2.6.4 INSTALLATION | 24264572 | Install hardware on Sector 3 DS beam | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264575 | Rotate Assembly, attach Sector 4 beams | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264632 | Rotate Assembly, Sector 2 to bottom, prep. | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264635 | Install hardware on Sector 2 US beam | MECH TECH.MECH TECH | 8.1
1.4.2.6.4 INSTALLATION | 24264720 | Run Wires, Connect instruments, verify OOPS operation | ELEC TECH.ELEC TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264720 | Run Wires, Connect instruments, verify OOPS operation | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264722 | Pre-load vertical supports | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264725 | Adjust OOPS loads | MECH TECH.MECH TECH | 1.8
1.4.2.6.4 INSTALLATION | 24264637 | Install hardware on Sector 2 DS beam | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264727 | Using threaded holes adjust coil locations | MECH TECH.MECH TECH | 3
1.4.2.6.4 INSTALLATION | 24264760 | IInstall Vacuum pumping system | MECH TECH.MECH TECH | 1.8
1.4.2.6.4 INSTALLATION | 24264760 | IInstall Vacuum pumping system | MECH ENG.MECH ENG | 0.4
1.4.2.6.4 INSTALLATION | 24264760 | IInstall Vacuum pumping system | ELEC TECH.ELEC TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264582 | Install hardware on Sector 4 US beam FY14 | MECH TECH.MECH TECH | 5.4
1.4.2.6.4 INSTALLATION | 24264585 | Install hardware on Sector 4 DS beam | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264587 | Rotate Assembly, attach Sector 5 beams | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264590 | Install Coil D, survey & align | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264592 | Rotate Assembly, Sector 5 to bottom, prep. | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264595 | Install hardware on Sector 5 US beam | MECH TECH.MECH TECH | 8.1
1.4.2.6.4 INSTALLATION | 24264597 | Install hardware on Sector 5 DS beam | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264600 | Rotate Assembly, attach Sector 6 beams | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264605 | Install Coil E, survey & align | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264607 | Rotate Assembly, Sector 6 to bottom, prep. | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264610 | Install hardware on Sector 6 US beam | MECH TECH.MECH TECH | 8.1
1.4.2.6.4 INSTALLATION | 24264612 | Install hardware on Sector 6 DS beam | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264615 | Rotate Assembly, attach Sector 1 beams | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264617 | Install Coil F, survey & align | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264620 | Rotate Assembly, attach Sector 2 beams | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264622 | Survey and align entire assembly | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264625 | Rotate Assembly, Sector 1 to bottom, prep. | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264627 | Install hardware on Sector 1 US beam | MECH TECH.MECH TECH | 8.1
1.4.2.6.4 INSTALLATION | 24264630 | Install hardware on Sector 1 DS beam | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264230 | Subway Level 1 addition wiring Power Dist. | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264105 | SVT - Design mounts for SVT to cart | MECH DES.MECH DES | 4
1.4.2.6.4 INSTALLATION | 24264110 | SVT - Design Insertion/service cart and installation arm | MECH DES.MECH DES | 5
1.4.2.6.4 INSTALLATION | 24264280 | Modify LTCC gas piping | MECH DES.MECH DES | 6
1.4.2.6.4 INSTALLATION | 24264280 | Modify LTCC gas piping | MECH TECH.MECH TECH | 12
1.4.2.6.4 INSTALLATION | 24264115 | SVT - Design transportation cart/skid FY14 | MECH DES.MECH DES | 11.3
1.4.2.6.4 INSTALLATION | 24264120 | SVT - Cart/Skid Engineering analysis | MECH ENG.MECH ENG | 6
1.4.2.6.4 INSTALLATION | 24264125 | SVT - Procure SVT mounts and cart | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264360 | Align Goni and Moeller Quads | MECH TECH.MECH TECH | 0.6
1.4.2.6.4 INSTALLATION | 24264006LOE | Installation Engineering Oversight FY16 | SR STAFF.SR STAFF | 23.3
1.4.2.6.4 INSTALLATION | 24264006LOE | Installation Engineering Oversight FY16 | MECH ENG.MECH ENG | 13.3
1.4.2.6.4 INSTALLATION | 24264845 | Mount, assemble and cable CTOF system | SCIENTIST.SCIENTIST | 2
1.4.2.6.4 INSTALLATION | 24264845 | Mount, assemble and cable CTOF system | MECH TECH.MECH TECH | 8
1.4.2.6.4 INSTALLATION | 24264855 | Mount, cable and check SVT system | SCIENTIST.SCIENTIST | 2
1.4.2.6.4 INSTALLATION | 24264855 | Mount, cable and check SVT system | MECH TECH.MECH TECH | 8
1.4.2.6.4 INSTALLATION | 24264860 | Align SVT | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264850 | Align CTOF | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264870 | Rig and Transport HTCC to Hall | MECH TECH.MECH TECH | 1
1.4.2.6.4 INSTALLATION | 24264872 | Install HTCC cart | MECH TECH.MECH TECH | 0.5
1.4.2.6.4 INSTALLATION | 24264874 | Install HTCC | MECH TECH.MECH TECH | 3
1.4.2.6.4 INSTALLATION | 24264876 | HTCC verify mirror alignment and align detector to beam | SCIENTIST.SCIENTIST | 1.2
1.4.2.6.4 INSTALLATION | 24264876 | HTCC verify mirror alignment and align detector to beam | MECH TECH.MECH TECH | 1.2
1.4.2.6.4 INSTALLATION | 24264878 | Cable HTCC | MECH TECH.MECH TECH | 0.8
1.4.2.6.4 INSTALLATION | 24264965 | Install Region 2 Drift Chamber | MECH TECH.MECH TECH | 13.6
1.4.2.6.4 INSTALLATION | 24264970 | Survey/align R2 Drift chambers | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264975 | Install Region 1 Drift Chamber | MECH TECH.MECH TECH | 13.6
1.4.2.6.4 INSTALLATION | 24264980 | Survey/align R1 Drift chambers | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264985 | Install Region 3 Drift Chamber | MECH TECH.MECH TECH | 13.6
1.4.2.6.4 INSTALLATION | 24264990 | Survey/align R3 Drift chambers | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264995 | Connect / Cable Drift Chambers | ELEC TECH.ELEC TECH | 2
1.4.2.6.4 INSTALLATION | 24264995 | Connect / Cable Drift Chambers | SCIENTIST.SCIENTIST | 2
1.4.2.6.4 INSTALLATION | 24264281 | Install new gas lines from gas sched to the hall | MECH TECH.MECH TECH | 7
1.4.2.6.4 INSTALLATION | 24264895 | DC - mounts and adjusters Engineering Analysis | MECH ENG.MECH ENG | 6
1.4.2.6.4 INSTALLATION | 24264900 | DC - procure mounts and adjusters for DC to Torus | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264905 | DC - design cable trays and gas system mounts FY14 | P MECH DES.PLABOR | 0
1.4.2.6.4 INSTALLATION | 24264910 | DC - cable trays and gas system mounts Engineering Analysis | MECH ENG.MECH ENG | 5
1.4.2.6.4 INSTALLATION | 24264915 | DC - procure cable trays and gas system mounts | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264460 | Transport and Install LTCC | MECH TECH.MECH TECH | 8
1.4.2.6.4 INSTALLATION | 24264465 | Survey (as found location) LTCC positions | MECH TECH.MECH TECH | 1.8
1.4.2.6.4 INSTALLATION | 24264490 | Transport and Install TOF Panel 2 and align relative to panel 1a | MECH TECH.MECH TECH | 4.8
1.4.2.6.4 INSTALLATION | 24264495 | Final Survey TOF panel 2's Positions | MECH TECH.MECH TECH | 1.8
1.4.2.6.4 INSTALLATION | 24264500 | Cable/test/repair Panel 2 TOFs | MECH TECH.MECH TECH | 2.4
1.4.2.6.4 INSTALLATION | 24264500 | Cable/test/repair Panel 2 TOFs | SCIENTIST.SCIENTIST | 1.2
1.4.2.6.4 INSTALLATION | 24264520 | Modify Space Frame Level 3 deck For Torus Cryo | MECH TECH.MECH TECH | 2
1.4.2.6.4 INSTALLATION | 24264525 | Distribution Can - Transport and position distribution box | MECH TECH.MECH TECH | 1.6
1.4.2.6.4 INSTALLATION | 24264545 | Install and wire up Torus PS | ELEC TECH.ELEC TECH | 4
1.4.2.6.4 INSTALLATION | 24264145 | HTCC - design transport cart | P MECH DES.PLABOR | 0
1.4.2.6.4 INSTALLATION | 24264145 | HTCC - design transport cart | MECH ENG.MECH ENG | 1
1.4.2.6.4 INSTALLATION | 24264160 | HTCC - procure transport cart | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264794a | Solenoid - Install motion system | MECH TECH.MECH TECH | 2
1.4.2.6.4 INSTALLATION | 24264868 | Design and install HTCC gas system | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264868 | Design and install HTCC gas system | MECH DES.MECH DES | 3
1.4.2.6.4 INSTALLATION | 24264888 | Reroute DC gas lines to the distribution panel | MECH TECH.MECH TECH | 6
1.4.2.6.4 INSTALLATION | 24264815 | Solenoid instrumentation and current leads | ELEC TECH.ELEC TECH | 4
1.4.2.6.4 INSTALLATION | 24264820 | Align Solenoid | MECH TECH.MECH TECH | 0.4
1.4.2.6.4 INSTALLATION | 24264800 | Receive and inspect solenoid magnet from Vendor | MECH TECH.MECH TECH | 4
1.4.2.6.4 INSTALLATION | 24264800 | Receive and inspect solenoid magnet from Vendor | MECH ENG.MECH ENG | 2
1.4.2.6.4 INSTALLATION | 24264800 | Receive and inspect solenoid magnet from Vendor | ELEC TECH.ELEC TECH | 2
1.4.2.6.4 INSTALLATION | 24264882 | Install DC signal cable trays and gas lines | MECH TECH.MECH TECH | 16
1.4.2.6.4 INSTALLATION | 24264882 | Install DC signal cable trays and gas lines | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.6.4 INSTALLATION | 24264882 | Install DC signal cable trays and gas lines | EXPNS PURCHASD LABOR.PLABOR | 0
1.4.2.6.4 INSTALLATION | 24264882 | Install DC signal cable trays and gas lines | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.6.4 INSTALLATION | 24264884 | Route DC Signal Cables | MECH TECH.MECH TECH | 12
1.4.2.6.4 INSTALLATION | 24264886 | Install DC HV/LV Racks and cable trays | MECH TECH.MECH TECH | 4.8
1.4.2.6.4 INSTALLATION | 24264890 | DC - design mounts and adjusters for DC to Torus | P MECH DES.PLABOR | 0
1.4.2.6.4 INSTALLATION | 24264115A | SVT - Design transportation cart/skid FY15 | MECH DES.MECH DES | 0.7
1.4.2.6.4 INSTALLATION | 24264547A | Labor to Support The Torus Installation, Cooldown and Test FY15 | ELEC TECH.ELEC TECH | 2.3
1.4.2.6.4 INSTALLATION | 24264547A | Labor to Support The Torus Installation, Cooldown and Test FY15 | ELEC ENG.ELEC ENG | 8.5
1.4.2.6.4 INSTALLATION | 24264547A | Labor to Support The Torus Installation, Cooldown and Test FY15 | MECH TECH.MECH TECH | 15.5
1.4.2.6.4 INSTALLATION | 24264547A | Labor to Support The Torus Installation, Cooldown and Test FY15 | MECH ENG.MECH ENG | 23.2
1.4.2.6.4 INSTALLATION | 24264547A | Labor to Support The Torus Installation, Cooldown and Test FY15 | MECH DES.MECH DES | 15.5
1.4.2.6.4 INSTALLATION | 24264547B | Labor to Support The Torus Installation, Cooldown and Test FY16 | ELEC TECH.ELEC TECH | 0.2
1.4.2.6.4 INSTALLATION | 24264547B | Labor to Support The Torus Installation, Cooldown and Test FY16 | ELEC ENG.ELEC ENG | 0.8
1.4.2.6.4 INSTALLATION | 24264547B | Labor to Support The Torus Installation, Cooldown and Test FY16 | MECH TECH.MECH TECH | 1.5
1.4.2.6.4 INSTALLATION | 24264547B | Labor to Support The Torus Installation, Cooldown and Test FY16 | MECH ENG.MECH ENG | 2.3
1.4.2.6.4 INSTALLATION | 24264547B | Labor to Support The Torus Installation, Cooldown and Test FY16 | MECH DES.MECH DES | 1.5
1.4.2.6.4 INSTALLATION | 24264582A | Install hardware on Sector 4 US beam FY15 | MECH TECH.MECH TECH | 3.6
1.4.2.6.4 INSTALLATION | 24264905A | DC - design cable trays and gas system mounts FY15 | P MECH DES.PLABOR | 0
1.4.2.6.4 INSTALLATION | 24264005LOEA | Installation Engineering Oversight FY15-B | SR STAFF.SR STAFF | 43.8
1.4.2.6.4 INSTALLATION | 24264005LOEA | Installation Engineering Oversight FY15-B | MECH ENG.MECH ENG | 42.3
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271710C | FNAL: Impregnate, cure and clean-up for CCM#4 (FNAL CCM #6) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271710D | FNAL:Pot coil in case and ship for CCM#4 (FNAL CCM #6) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271715 | FNAL: Transfer and Clean Cable for CCM#5 (FNAL CCM #7) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271715A | FNAL: Wind, Test and Compress for CCM#5 (FNAL CCM #7) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271715B | FNAL: Solder Copper Shields for CCM#5 (FNAL CCM #7) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271715C | FNAL: Impregnate, cure and clean-up for CCM#5 (FNAL CCM #7) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271715D | FNAL:Pot coil in case and ship for CCM#5 (FNAL CCM #7) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271720 | FNAL: Transfer and Clean Cable for CCM#6 (FNAL CCM #8) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271720A | FNAL: Wind, Test and Compress for CCM#6 (FNAL CCM #8) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271720B | FNAL: Solder Copper Shields for CCM#6 (FNAL CCM #8) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271720C | FNAL: Impregnate, cure and clean-up for CCM#6 (FNAL CCM #8) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271720D | FNAL:Pot coil in case and ship for CCM#6 (FNAL CCM #8) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271722 | FNAL:Break down tooling and ship to JLab | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271724A | Shipping of First 4 CCMs | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271724B | Shipping of Last 4 CCMs | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271695G | FNAL:Pot coil in case and ship for CCM#1 (FNAL CCM #3) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271700B | FNAL: Solder Copper Shields for CCM#2 (FNAL CCM #4) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271700C | FNAL: Impregnate, cure and clean-up for CCM#2 (FNAL CCM #4) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271700D | FNAL:Pot coil in case and ship for CCM#2 (FNAL CCM #4) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271705 | FNAL: Transfer and Clean Cable for CCM#3 (FNAL CCM #5) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271705A | FNAL: Wind, Test and Compress for CCM#3 (FNAL CCM #5) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271705B | FNAL: Solder Copper Shields for CCM#3 (FNAL CCM #5) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271705C | FNAL: Impregnate, cure and clean-up for CCM#3 (FNAL CCM #5) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271705D | FNAL:Pot coil in case and ship for CCM#3 (FNAL CCM #5) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271710 | FNAL: Transfer and Clean Cable for CCM#4 (FNAL CCM #6) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271710A | FNAL: Wind, Test and Compress for CCM#4 (FNAL CCM #6) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.1 TOROIDAL MAGNET NEW VENDOR | 24271710B | FNAL: Solder Copper Shields for CCM#4 (FNAL CCM #6) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1030A | Solenoid - Instrumentation Controls Assembly FY15 | ELEC ENG.ELEC ENG | 3.2
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1030A | Solenoid - Instrumentation Controls Assembly FY15 | ELEC TECH.ELEC TECH | 34.3
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.104 | Solenoid - Vend Fab Power Supply - Peg Point #2 - Materials Received and Inspected at Vendor/Fabrication Start | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.104 | Solenoid - Vend Fab Power Supply - Peg Point #2 - Materials Received and Inspected at Vendor/Fabrication Start | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1045 | Solenoid - Vend Fab Power Supply - Peg Point #3 - Factory Test Completed and Accepted/Shipment | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1045 | Solenoid - Vend Fab Power Supply - Peg Point #3 - Factory Test Completed and Accepted/Shipment | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.105 | Solenoid - Vend Fab Power Supply - Peg Point #4 - Acceptance Test at JLab | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.105 | Solenoid - Vend Fab Power Supply - Peg Point #4 - Acceptance Test at JLab | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1055 | Solenoid - Vend Fab Power Supply - Peg Point #5 - Receipt of Spares | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1055 | Solenoid - Vend Fab Power Supply - Peg Point #5 - Receipt of Spares | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.103 | Solenoid - Instrumentation Controls Assembly FY14 | ELEC ENG.ELEC ENG | 2.6
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.103 | Solenoid - Instrumentation Controls Assembly FY14 | ELEC TECH.ELEC TECH | 27.3
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1005 | Solenoid - Instrumentation Magnet Protection System Procurement Prep | ELEC ENG.ELEC ENG | 1
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.101 | Solenoid - Instrumentation Magnet Protection System Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.101 | Solenoid - Instrumentation Magnet Protection System Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1 | Solenoid - Instrumentation Magnet Protection System Design | ELEC ENG.ELEC ENG | 6
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1 | Solenoid - Instrumentation Magnet Protection System Design | ELEC DES.ELEC DES | 35
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1015a | Solenoid - Instrumentation Controls Design FY14 | ELEC ENG.ELEC ENG | 0.7
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1015a | Solenoid - Instrumentation Controls Design FY14 | ELEC DES.ELEC DES | 7.2
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.102 | Solenoid - Instrumentation Controls Procurement Prep | ELEC ENG.ELEC ENG | 1
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1025 | Solenoid - Instrumentation Controls Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1015 | Solenoid - Instrumentation Controls Design FY13 | ELEC ENG.ELEC ENG | 0.3
1.4.2.7.10.1 SOLENOID INSTRUMENTATION AND CONTROLS | 242710.1015 | Solenoid - Instrumentation Controls Design FY13 | ELEC DES.ELEC DES | 2.8
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1000A | Additional FNAL Oversight FY15 | SR STAFF.SR STAFF | 3.7
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.101 | FNAL: Transfer and Clean Cable for CCM#7 (FNAL CCM #9) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.101 | FNAL: Transfer and Clean Cable for CCM#7 (FNAL CCM #9) | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1010A | FNAL: Wind, Test and Compress for CCM#7 (FNAL CCM #9) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1010B | FNAL: Solder Copper Shields for CCM#7 (FNAL CCM #9) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1010C | FNAL: Impregnate, cure and clean-up for CCM#7 (FNAL CCM #9) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1010D | FNAL:Pot coil in case and ship for CCM#7 (FNAL CCM #9) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005A | FNAL: Transfer and Clean Cable for CCM #8 (FNAL CCM #10) | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005A | FNAL: Transfer and Clean Cable for CCM #8 (FNAL CCM #10) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005B | FNAL: Wind, Test and Compress for CCM #8 (FNAL CCM #10) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005B | FNAL: Wind, Test and Compress for CCM #8 (FNAL CCM #10) | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005C | FNAL: Solder Copper Shields for CCM #8 (FNAL CCM #10) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005C | FNAL: Solder Copper Shields for CCM #8 (FNAL CCM #10) | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005D | FNAL: Impregnate, cure and clean-up for CCM #8 (FNAL CCM #10) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005F | FNAL:Pot coil in case and ship for Prototype CCM (FNAL CCM #10) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3065 | LN2 TEST - LN2 Testing of CCM #7 FY14 | ELEC TECH.ELEC TECH | 0.6
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3065 | LN2 TEST - LN2 Testing of CCM #7 FY14 | SR STAFF.SR STAFF | 0.3
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3065 | LN2 TEST - LN2 Testing of CCM #7 FY14 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3065A | LN2 TEST - LN2 Testing of CCM #7 FY15 | ELEC TECH.ELEC TECH | 2.4
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3065A | LN2 TEST - LN2 Testing of CCM #7 FY15 | SR STAFF.SR STAFF | 1.2
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3065A | LN2 TEST - LN2 Testing of CCM #7 FY15 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3035 | LN2 TEST - LN2 Testing of CCM #1 | ELEC TECH.ELEC TECH | 3
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3035 | LN2 TEST - LN2 Testing of CCM #1 | SR STAFF.SR STAFF | 1.5
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3035 | LN2 TEST - LN2 Testing of CCM #1 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.304 | LN2 TEST - LN2 Testing of CCM #2 | ELEC TECH.ELEC TECH | 3
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.304 | LN2 TEST - LN2 Testing of CCM #2 | SR STAFF.SR STAFF | 1.5
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.304 | LN2 TEST - LN2 Testing of CCM #2 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3045 | LN2 TEST - LN2 Testing of CCM #3 | ELEC TECH.ELEC TECH | 3
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3045 | LN2 TEST - LN2 Testing of CCM #3 | SR STAFF.SR STAFF | 1.5
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3045 | LN2 TEST - LN2 Testing of CCM #3 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.305 | LN2 TEST - LN2 Testing of CCM #4 | ELEC TECH.ELEC TECH | 3
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.305 | LN2 TEST - LN2 Testing of CCM #4 | SR STAFF.SR STAFF | 1.5
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.305 | LN2 TEST - LN2 Testing of CCM #4 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3055 | LN2 TEST - LN2 Testing of CCM #5 | ELEC TECH.ELEC TECH | 3
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3055 | LN2 TEST - LN2 Testing of CCM #5 | SR STAFF.SR STAFF | 1.5
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.3055 | LN2 TEST - LN2 Testing of CCM #5 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.306 | LN2 TEST - LN2 Testing of CCM #6 | SR STAFF.SR STAFF | 1.5
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.306 | LN2 TEST - LN2 Testing of CCM #6 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.11.3 COIL LN2 TESTING FOR TORUS RISK MITIGATION | 242711.306 | LN2 TEST - LN2 Testing of CCM #6 | ELEC TECH.ELEC TECH | 3
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5025 | DUMMY | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.503 | DUMMY | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5010b | Cold Tests - Planning Package FY14 | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5010b | Cold Tests - Planning Package FY14 | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5010b | Cold Tests - Planning Package FY14 | SR STAFF.SR STAFF | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5010b | Cold Tests - Planning Package FY14 | EXPNS TRAVEL.TRAVEL | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5015 | Cold Tests - Planning Package FY15 | SR STAFF.SR STAFF | 4.7
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5015 | Cold Tests - Planning Package FY15 | EXPNS TRAVEL.TRAVEL | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5015 | Cold Tests - Planning Package FY15 | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5015 | Cold Tests - Planning Package FY15 | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.502 | DUMMY | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.502 | DUMMY | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5005 | Cold Tests - Kickoff Meeting | SR STAFF.SR STAFF | 2
1.4.2.7.11.5 COIL COLD TESTING FOR TORUS RISK MITIGATION | 242711.5005 | Cold Tests - Kickoff Meeting | EXPNS TRAVEL.TRAVEL | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zb | Vend Fab Solenoid - Line Item #24 - Intermediate Coils Wound & Potted | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zg | Vend Fab Solenoid - Line Item #28 - Solenoid Magnet Final Assembly Complete | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zc | Vend Fab Solenoid - Line Item #25 - Shield Coil Wound & Potted | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zf | Vend Fab Solenoid - Line Item #27 - Correction Coils Wound & Potted | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zn | Vend Fab Solenoid - Line Item #32 - Final Documentation Package Acceptance | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zk | Vend Fab Solenoid - Line Item #31 - Final Acceptance Complete at Jefferson Lab | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zj | Vend Fab Solenoid - Line Item #30 - Solenoid Magnet Received on-site at Jefferson Lab | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272090 | Purchase Additional Trim Coils | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272085 | Solenoid Outside Consulting FY14 | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272085 | Solenoid Outside Consulting FY14 | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075k | Vend Fab Solenoid - Line Item #10 - Correction Coil Design & Analysis Complete | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075p | Vend Fab Solenoid - Line Item #12 - Practice Winding Complete (1/2 height - Inner Coil) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075q | Vend Fab Solenoid - Line Item #13 - Pre-MRR (Review manufacturing and QA for prototype coil winding) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075r | Vend Fab Solenoid - Line Item #14 - Prototype Inner Coil Winding Setup (PSMM) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075u | Vend Fab Solenoid - Line Item #17 - QA/QC Plan Acceptance | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075t | Vend Fab Solenoid - Line Item #16 - Materials for Cold Mass Received (Bobbin, Coils, Thermal Shield, etc.) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zd | Vend Fab Solenoid - Line Item #26 - Cold Mass Assembly Complete (Bobbin, Coils, Thermal Shield, etc.) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075v | Vend Fab Solenoid - Line Item #18 - Prototype Inner Coil Winding Complete (PSMM) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075z | Vend Fab Solenoid - Line Item #22 - Inner Coils Wound & Potted | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075x | Vend Fab Solenoid - Line Item #20 - Materials for Final Assembly Received | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075y | Vend Fab Solenoid - Line Item #21 - Winding and Potting Tooling - Intermediate Coils | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075zh | Vend Fab Solenoid - Line Item #29 - Solenoid Magnet Acceptance Testing Complete at ETI | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.2 SOLENOID MAGNET NEW VENDOR | 24272075za | Vend Fab Solenoid - Line Item #23 - Winding and Potting Tooling - Shield Coil | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.3 MAGNET INFRASTRUCTURE | 24273060 | Vend Fab Solder of Solenoid Conductor Peg Point #8-Delivery of 4th set of Solenoid Conductor Lengths 1-9 | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.3 MAGNET INFRASTRUCTURE | 24273065 | Vend Fab Solder of Longer Solenoid Conductor Peg Point #9 | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.3 MAGNET INFRASTRUCTURE | 24273075 | Vend Fab Post Cleaning/Buffing of Conductor Peg Point #14 | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.3 MAGNET INFRASTRUCTURE | 24273085 | Vend Fab Solder of Torus Conductor - Delivery of Torus Coil T9 - Peg Point #19 | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.4.2 PROTOTYPE | 242742065 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Receive, QA and Pre-assembly) | MECH ENG.MECH ENG | 4.7
1.4.2.7.4.2 PROTOTYPE | 242742065 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Receive, QA and Pre-assembly) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.2 PROTOTYPE | 242742065 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Receive, QA and Pre-assembly) | MECH TECH.MECH TECH | 14.9
1.4.2.7.4.2 PROTOTYPE | 242742065 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Receive, QA and Pre-assembly) | SR STAFF.SR STAFF | 2.4
1.4.2.7.4.2 PROTOTYPE | 242742070 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (MLI and LN2 shield assembly) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.2 PROTOTYPE | 242742070 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (MLI and LN2 shield assembly) | MECH TECH.MECH TECH | 19
1.4.2.7.4.2 PROTOTYPE | 242742070 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (MLI and LN2 shield assembly) | SR STAFF.SR STAFF | 3
1.4.2.7.4.2 PROTOTYPE | 242742070 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (MLI and LN2 shield assembly) | MECH ENG.MECH ENG | 6
1.4.2.7.4.2 PROTOTYPE | 242742075 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Vac jacket weld up) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.2 PROTOTYPE | 242742075 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Vac jacket weld up) | MECH TECH.MECH TECH | 16.3
1.4.2.7.4.2 PROTOTYPE | 242742075 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Vac jacket weld up) | SR STAFF.SR STAFF | 2.6
1.4.2.7.4.2 PROTOTYPE | 242742075 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Vac jacket weld up) | MECH ENG.MECH ENG | 5.1
1.4.2.7.4.3 PRODUCTION | 242743055A | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY15 | MECH TECH.MECH TECH | 3
1.4.2.7.4.3 PRODUCTION | 242743055A | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY15 | SR STAFF.SR STAFF | 0.3
1.4.2.7.4.3 PRODUCTION | 242743055A | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY15 | MECH ENG.MECH ENG | 0.7
1.4.2.7.4.3 PRODUCTION | 242743070A | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY15 | MECH TECH.MECH TECH | 6.8
1.4.2.7.4.3 PRODUCTION | 242743070A | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY15 | SR STAFF.SR STAFF | 0.4
1.4.2.7.4.3 PRODUCTION | 242743070A | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY15 | MECH ENG.MECH ENG | 0.8
1.4.2.7.4.3 PRODUCTION | 242743085A | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY15 | MECH ENG.MECH ENG | 1.4
1.4.2.7.4.3 PRODUCTION | 242743085A | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY15 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.3 PRODUCTION | 242743085A | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY15 | MECH TECH.MECH TECH | 8.2
1.4.2.7.4.3 PRODUCTION | 242743085A | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY15 | SR STAFF.SR STAFF | 0.7
1.4.2.7.4.3 PRODUCTION | 242743125A | Cryostat Factory - Rework FY15 | MECH ENG.MECH ENG | 4.1
1.4.2.7.4.3 PRODUCTION | 242743125A | Cryostat Factory - Rework FY15 | MECH TECH.MECH TECH | 20.7
1.4.2.7.4.3 PRODUCTION | 242743125A | Cryostat Factory - Rework FY15 | SR STAFF.SR STAFF | 2.1
1.4.2.7.4.3 PRODUCTION | 242743095 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Vac jacket weld up) | MECH TECH.MECH TECH | 7.5
1.4.2.7.4.3 PRODUCTION | 242743095 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Vac jacket weld up) | SR STAFF.SR STAFF | 0.8
1.4.2.7.4.3 PRODUCTION | 242743095 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Vac jacket weld up) | MECH ENG.MECH ENG | 1.7
1.4.2.7.4.3 PRODUCTION | 242743105 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Receive, QA and Pre-assembly) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.3 PRODUCTION | 242743105 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Receive, QA and Pre-assembly) | MECH TECH.MECH TECH | 17.6
1.4.2.7.4.3 PRODUCTION | 242743105 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Receive, QA and Pre-assembly) | SR STAFF.SR STAFF | 1.5
1.4.2.7.4.3 PRODUCTION | 242743105 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Receive, QA and Pre-assembly) | MECH ENG.MECH ENG | 2.9
1.4.2.7.4.3 PRODUCTION | 242743110 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (MLI and LN2 shield assembly) | SR STAFF.SR STAFF | 1
1.4.2.7.4.3 PRODUCTION | 242743110 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (MLI and LN2 shield assembly) | MECH ENG.MECH ENG | 2
1.4.2.7.4.3 PRODUCTION | 242743110 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (MLI and LN2 shield assembly) | MECH TECH.MECH TECH | 17
1.4.2.7.4.3 PRODUCTION | 242743115 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Vac jacket weld up) | MECH TECH.MECH TECH | 7.5
1.4.2.7.4.3 PRODUCTION | 242743115 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Vac jacket weld up) | SR STAFF.SR STAFF | 0.8
1.4.2.7.4.3 PRODUCTION | 242743115 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Vac jacket weld up) | MECH ENG.MECH ENG | 1.7
1.4.2.7.4.3 PRODUCTION | 242743090 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (MLI and LN2 shield assembly) | MECH TECH.MECH TECH | 17
1.4.2.7.4.3 PRODUCTION | 242743090 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (MLI and LN2 shield assembly) | SR STAFF.SR STAFF | 1
1.4.2.7.4.3 PRODUCTION | 242743090 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (MLI and LN2 shield assembly) | MECH ENG.MECH ENG | 2
1.4.2.7.4.3 PRODUCTION | 242743005 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Receive, QA and Pre-assembly) | MECH ENG.MECH ENG | 5.9
1.4.2.7.4.3 PRODUCTION | 242743005 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Receive, QA and Pre-assembly) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.3 PRODUCTION | 242743005 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Receive, QA and Pre-assembly) | MECH TECH.MECH TECH | 13.2
1.4.2.7.4.3 PRODUCTION | 242743005 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Receive, QA and Pre-assembly) | SR STAFF.SR STAFF | 2.9
1.4.2.7.4.3 PRODUCTION | 242743070 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY14 | MECH TECH.MECH TECH | 10.2
1.4.2.7.4.3 PRODUCTION | 242743070 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY14 | SR STAFF.SR STAFF | 0.6
1.4.2.7.4.3 PRODUCTION | 242743070 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY14 | MECH ENG.MECH ENG | 1.2
1.4.2.7.4.3 PRODUCTION | 242743075 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Vac jacket weld up) | MECH TECH.MECH TECH | 7.5
1.4.2.7.4.3 PRODUCTION | 242743075 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Vac jacket weld up) | SR STAFF.SR STAFF | 0.8
1.4.2.7.4.3 PRODUCTION | 242743075 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Vac jacket weld up) | MECH ENG.MECH ENG | 1.7
1.4.2.7.4.3 PRODUCTION | 242743085 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY14 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.3 PRODUCTION | 242743085 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY14 | MECH TECH.MECH TECH | 9.4
1.4.2.7.4.3 PRODUCTION | 242743085 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY14 | SR STAFF.SR STAFF | 0.8
1.4.2.7.4.3 PRODUCTION | 242743085 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY14 | MECH ENG.MECH ENG | 1.6
1.4.2.7.4.3 PRODUCTION | 242743120 | Cryostat Factory - Clean up And ship to site | MECH ENG.MECH ENG | 6
1.4.2.7.4.3 PRODUCTION | 242743120 | Cryostat Factory - Clean up And ship to site | MECH TECH.MECH TECH | 9
1.4.2.7.4.3 PRODUCTION | 242743120 | Cryostat Factory - Clean up And ship to site | SR STAFF.SR STAFF | 3
1.4.2.7.4.3 PRODUCTION | 242743010 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (MLI and LN2 shield assembly) | MECH TECH.MECH TECH | 14
1.4.2.7.4.3 PRODUCTION | 242743010 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (MLI and LN2 shield assembly) | SR STAFF.SR STAFF | 2
1.4.2.7.4.3 PRODUCTION | 242743010 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (MLI and LN2 shield assembly) | MECH ENG.MECH ENG | 4
1.4.2.7.4.3 PRODUCTION | 242743015 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Vac jacket weld up) | MECH TECH.MECH TECH | 7.5
1.4.2.7.4.3 PRODUCTION | 242743015 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Vac jacket weld up) | SR STAFF.SR STAFF | 0.8
1.4.2.7.4.3 PRODUCTION | 242743015 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Vac jacket weld up) | MECH ENG.MECH ENG | 1.7
1.4.2.7.4.3 PRODUCTION | 242743025 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Receive, QA and Pre-assembly) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.3 PRODUCTION | 242743025 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Receive, QA and Pre-assembly) | MECH TECH.MECH TECH | 17.6
1.4.2.7.4.3 PRODUCTION | 242743025 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Receive, QA and Pre-assembly) | SR STAFF.SR STAFF | 1.5
1.4.2.7.4.3 PRODUCTION | 242743025 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Receive, QA and Pre-assembly) | MECH ENG.MECH ENG | 2.9
1.4.2.7.4.3 PRODUCTION | 242743030 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (MLI and LN2 shield assembly) | MECH TECH.MECH TECH | 17
1.4.2.7.4.3 PRODUCTION | 242743030 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (MLI and LN2 shield assembly) | SR STAFF.SR STAFF | 1
1.4.2.7.4.3 PRODUCTION | 242743030 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (MLI and LN2 shield assembly) | MECH ENG.MECH ENG | 2
1.4.2.7.4.3 PRODUCTION | 242743035 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Vac jacket weld up) | MECH TECH.MECH TECH | 7.5
1.4.2.7.4.3 PRODUCTION | 242743035 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Vac jacket weld up) | SR STAFF.SR STAFF | 0.8
1.4.2.7.4.3 PRODUCTION | 242743035 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Vac jacket weld up) | MECH ENG.MECH ENG | 1.7
1.4.2.7.4.3 PRODUCTION | 242743045 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Receive, QA and Pre-assembly) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.3 PRODUCTION | 242743045 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Receive, QA and Pre-assembly) | MECH TECH.MECH TECH | 17.6
1.4.2.7.4.3 PRODUCTION | 242743045 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Receive, QA and Pre-assembly) | SR STAFF.SR STAFF | 1.5
1.4.2.7.4.3 PRODUCTION | 242743045 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Receive, QA and Pre-assembly) | MECH ENG.MECH ENG | 2.9
1.4.2.7.4.3 PRODUCTION | 242743050 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (MLI and LN2 shield assembly) | MECH TECH.MECH TECH | 17
1.4.2.7.4.3 PRODUCTION | 242743050 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (MLI and LN2 shield assembly) | SR STAFF.SR STAFF | 1
1.4.2.7.4.3 PRODUCTION | 242743050 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (MLI and LN2 shield assembly) | MECH ENG.MECH ENG | 2
1.4.2.7.4.3 PRODUCTION | 242743055 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY14 | MECH ENG.MECH ENG | 1
1.4.2.7.4.3 PRODUCTION | 242743055 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY14 | MECH TECH.MECH TECH | 4.5
1.4.2.7.4.3 PRODUCTION | 242743055 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY14 | SR STAFF.SR STAFF | 0.5
1.4.2.7.4.3 PRODUCTION | 242743065 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Receive, QA and Pre-assembly) | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.4.3 PRODUCTION | 242743065 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Receive, QA and Pre-assembly) | MECH TECH.MECH TECH | 17.6
1.4.2.7.4.3 PRODUCTION | 242743065 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Receive, QA and Pre-assembly) | SR STAFF.SR STAFF | 1.5
1.4.2.7.4.3 PRODUCTION | 242743065 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Receive, QA and Pre-assembly) | MECH ENG.MECH ENG | 2.9
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751260 | Torus - Upstream Hex MLI Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751295 | Torus - Downstream Hex MLI Procurement Prep | MECH ENG.MECH ENG | 1
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751300 | Torus - Downstream Hex MLI Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751305 | Torus - Misc Hex MLI Procurement Prep | MECH ENG.MECH ENG | 1
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751215a | Torus - Upstream Hex - Splice design and tooling design FY14 | MECH DES.MECH DES | 0.9
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751290 | Torus - Downstream Hex Assembly Parts Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751290 | Torus - Downstream Hex Assembly Parts Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751310 | Torus - Misc Hex MLI Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751325 | Torus - Supply-Return Header to DS ring - Modeling/Drafting | MECH DES.MECH DES | 2
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751330 | Torus - Supply-Return Header Procurement Prep | MECH ENG.MECH ENG | 1
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751335 | Torus - Supply-Return Header Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751360 | Torus - Main Cold mass support system - Attachment to Floor Engineering | MECH ENG.MECH ENG | 3
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751365 | Torus - Main Cold mass support system - Attachment to Floor Modeling and Drafting | MECH ENG.MECH ENG | 3
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751380 | Torus - Torus Support to Hall floor Assembly Procurement Prep | MECH ENG.MECH ENG | 1
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751385 | Torus - Torus Support to Hall floor Assembly Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751385 | Torus - Torus Support to Hall floor Assembly Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751375 | Torus - CM Support Assembly Parts Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751375 | Torus - CM Support Assembly Parts Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751410 | Torus - Installation Design - Develop Scaffolding Design | MECH DES.MECH DES | 2
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751415 | Torus - Installation Design - Develop procedures and safety documentation | MECH ENG.MECH ENG | 9.3
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751440 | Torus - Installation Parts Procurement (90K Accounted for Cryo Jumpers) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751440 | Torus - Installation Parts Procurement (90K Accounted for Cryo Jumpers) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751170 | Torus - Cold Hub - Hub shield final drafting | MECH ENG.MECH ENG | 1
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751215 | Torus - Upstream Hex - Splice design and tooling design FY13 | MECH DES.MECH DES | 0.5
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751240 | Torus - Upstream Hex Assembly Parts Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751240 | Torus - Upstream Hex Assembly Parts Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.5.1 TORUS MAGNET DESIGN/PARTS | 242751255 | Torus - Upstream Hex MLI Procurement Prep | MECH ENG.MECH ENG | 1
1.4.2.7.6.1 CRYO DISTRIBUTION CAN | 242761015 | Hall B - Distribution Can - QA | MECH ENG.MECH ENG | 2.6
1.4.2.7.6.1 CRYO DISTRIBUTION CAN | 242761025 | Hall B - Distribution Can - Bid and select vendor | MECH ENG.MECH ENG | 2
1.4.2.7.6.1 CRYO DISTRIBUTION CAN | 242761030 | Hall B - Distribution Can Procurement | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.7.6.1 CRYO DISTRIBUTION CAN | 242761030 | Hall B - Distribution Can Procurement | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.7.6.1 CRYO DISTRIBUTION CAN | 242761010a | Hall B - Distribution Can - ProjectMgt FY14 | MECH ENG.MECH ENG | 2.3
1.4.2.7.6.1 CRYO DISTRIBUTION CAN | 242761010 | Hall B - Distribution Can - ProjectMgt FY13 | MECH ENG.MECH ENG | 0.2
1.4.2.7.6.2 CRYO CONTROL CAN | 242762035 | Torus - Cryogenic Tower - Write Specs | MECH ENG.MECH ENG | 3
1.4.2.7.6.2 CRYO CONTROL CAN | 242762040 | Torus - Cryogenic Tower - Bid and select vendor | MECH ENG.MECH ENG | 2
1.4.2.7.6.2 CRYO CONTROL CAN | 242762000 | Torus - Cryogenic Tower - Mechanical Engineering FY13 | MECH ENG.MECH ENG | 4
1.4.2.7.6.2 CRYO CONTROL CAN | 242762045 | Torus - Cryogenic Tower Procurement | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.7.6.2 CRYO CONTROL CAN | 242762045 | Torus - Cryogenic Tower Procurement | PRCRMNT>$50K69NESC15.PROCUREMENT>$50K 69 NO ESCALATION FY15 | 0
1.4.2.7.6.2 CRYO CONTROL CAN | 242762000a | Torus - Cryogenic Tower - Mechanical Engineering FY14 | MECH ENG.MECH ENG | 11
1.4.2.7.6.2 CRYO CONTROL CAN | 242762005 | Torus - Cryogenic Tower - Structural Engineering | MECH ENG.MECH ENG | 2
1.4.2.7.6.2 CRYO CONTROL CAN | 242762010 | Torus - Cryogenic Tower - Electrical/Instrumentation Engineering | ELEC ENG.ELEC ENG | 1
1.4.2.7.6.2 CRYO CONTROL CAN | 242762015 | Torus - Cryogenic Tower - Drafting Mechanical | MECH DES.MECH DES | 16
1.4.2.7.6.2 CRYO CONTROL CAN | 242762020 | Torus - Cryogenic Tower - Drafting Structural | MECH DES.MECH DES | 3
1.4.2.7.6.2 CRYO CONTROL CAN | 242762025 | Torus - Cryogenic Tower - ProjectMgt | MECH ENG.MECH ENG | 2
1.4.2.7.6.2 CRYO CONTROL CAN | 242762030 | Torus - Cryogenic Tower - Drawing review and sign-off | MECH ENG.MECH ENG | 3
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771050 | Torus - Vend Fab Power Supply - Peg Point #3 - Factory Test Completed and Accepted/Shipment | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771050 | Torus - Vend Fab Power Supply - Peg Point #3 - Factory Test Completed and Accepted/Shipment | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771055 | Torus - Vend Fab Power Supply - Peg Point #4 - Acceptance Test at JLab | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771055 | Torus - Vend Fab Power Supply - Peg Point #4 - Acceptance Test at JLab | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771060 | Torus - Vend Fab Power Supply - Peg Point #5 - Receipt of Spares | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771060 | Torus - Vend Fab Power Supply - Peg Point #5 - Receipt of Spares | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771015 | Torus - Instrumentation Controls Procurement Prep | ELEC ENG.ELEC ENG | 1
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771020 | Torus - Instrumentation Controls Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771035 | Torus - Instrumentation Controls Assembly | ELEC ENG.ELEC ENG | 5.8
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771035 | Torus - Instrumentation Controls Assembly | ELEC TECH.ELEC TECH | 61.6
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771030 | Torus - Instrumentation Magnet Protection System Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771030 | Torus - Instrumentation Magnet Protection System Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771005 | Torus - Instrumentation Magnet Protection System Design | ELEC ENG.ELEC ENG | 6
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771005 | Torus - Instrumentation Magnet Protection System Design | ELEC DES.ELEC DES | 35
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771000 | Torus - Instrumentation Controls Design | ELEC ENG.ELEC ENG | 0.9
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771000 | Torus - Instrumentation Controls Design | ELEC DES.ELEC DES | 9.2
1.4.2.7.7.1 TORUS INSTUMENTATION AND CONTROL | 242771025 | Torus - Instrumentation Magnet Protection System Procurement Prep | ELEC ENG.ELEC ENG | 1
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781025A | Solenoid Commissioning - Design & Documentation FY15 | SR STAFF.SR STAFF | 0.9
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781025A | Solenoid Commissioning - Design & Documentation FY15 | MECH ENG.MECH ENG | 0.4
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781010LOE | Solenoid - Technical Support & Oversite FY15 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781010LOE | Solenoid - Technical Support & Oversite FY15 | SR STAFF.SR STAFF | 12.2
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781015 | Solenoid - Magent Installation Design | ELEC ENG.ELEC ENG | 5
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781015 | Solenoid - Magent Installation Design | SCIENTIST.SCIENTIST | 5
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781015 | Solenoid - Magent Installation Design | SR STAFF.SR STAFF | 5
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781015 | Solenoid - Magent Installation Design | MECH DES.MECH DES | 20
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781015 | Solenoid - Magent Installation Design | MECH ENG.MECH ENG | 10
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781020 | Solenoid - Magent Installation Procurements | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781025 | Solenoid Commissioning - Design & Documentation FY14 | SR STAFF.SR STAFF | 3.1
1.4.2.7.8.1 SOLENOID MAGNET DESIGN/PARTS | 242781025 | Solenoid Commissioning - Design & Documentation FY14 | MECH ENG.MECH ENG | 1.6
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791040A | Solenoid Cryogenics - Write Specifications FY15 | MECH ENG.MECH ENG | 2
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791040 | Solenoid Cryogenics - Write Specifications FY14 | MECH ENG.MECH ENG | 1
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791055 | Solenoid cryogenics - Installation and Commissioning | MECH ENG.MECH ENG | 1.5
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791055 | Solenoid cryogenics - Installation and Commissioning | MECH TECH.MECH TECH | 1.5
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791010 | Solenoid - Cryogenic Modes of Operation | MECH ENG.MECH ENG | 3
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791015 | Solenoid - PDR | MECH ENG.MECH ENG | 0.6
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791020 | Solenoid - Evaluation of Process Components | MECH ENG.MECH ENG | 2
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791020 | Solenoid - Evaluation of Process Components | MECH TECH.MECH TECH | 2
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791025 | Solenoid - Current Leads | MECH ENG.MECH ENG | 2.3
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791025 | Solenoid - Current Leads | MECH TECH.MECH TECH | 2.3
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791030 | Solenoid - Mechanical Design of the cryogenic can | MECH ENG.MECH ENG | 12
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791030 | Solenoid - Mechanical Design of the cryogenic can | MECH TECH.MECH TECH | 12
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791035 | Solenoid - FDR | MECH ENG.MECH ENG | 0.2
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791045 | Solenoid Cryogenics - Bid cycle, review and award | MECH ENG.MECH ENG | 2
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791050 | Solenoid Cryogenics - Procurement | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791050 | Solenoid Cryogenics - Procurement | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791050 | Solenoid Cryogenics - Procurement | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791060 | Solenoid cryogenics - Test of system | MECH ENG.MECH ENG | 2
1.4.2.7.9.1 SOLENOID CRYOGENICS | 242791060 | Solenoid cryogenics - Test of system | MECH TECH.MECH TECH | 2
1.4.3.1.1 HB MAGNET | 24311170 | HB- Factory Mag Test of HB Mag | MECH ENG.MECH ENG | 1
1.4.3.1.1 HB MAGNET | 24311170 | HB- Factory Mag Test of HB Mag | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.1 HB MAGNET | 24311170 | HB- Factory Mag Test of HB Mag | MECH DES.MECH DES | 1
1.4.3.1.1 HB MAGNET | 243118P6LOE | HB Contract Mngmnt for HB Mag | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.1 HB MAGNET | 243118P6LOE | HB Contract Mngmnt for HB Mag | MECH ENG.MECH ENG | 3
1.4.3.1.1 HB MAGNET | 24311135 | Vend Fab HB Magnet Peg Point #15 Finish Vac Wall & Support Links | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.3.1.1 HB MAGNET | 24311150 | Vend Fab HB Magnet Peg Point #18 Connect Leads, Instr. He Vessel, Leak Check Cryo, Finish Shield Conn. | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.1 HB MAGNET | 24311155 | Vend Fab HB Magnet Peg Point #19 Finish Insul & Vac; Leak Check; Fab shipping structure | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.1 HB MAGNET | 24311160 | Vend Fab HB Magnet Peg Point #20 Crate & Deliver HB Magnet to JLab | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.1 HB MAGNET | 24311165 | Vend Fab HB Magnet Peg Point #21 Acceptance, Setup, Testing, and Mapping at JLab | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.1 HB MAGNET | 24311168 | Vend Fab HB Magnet Contract Closeout | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.1 HB MAGNET | 24311071A | HB Drawing Validation FY15 | MECH DES.MECH DES | 7
1.4.3.1.1 HB MAGNET | 24311071 | HB Drawing Validation FY14 | MECH DES.MECH DES | 5
1.4.3.1.1 HB MAGNET | 24311077 | Finducialize Magnet CL of SHMS HB Magnet | MECH DES.MECH DES | 0.2
1.4.3.1.1 HB MAGNET | 24311077 | Finducialize Magnet CL of SHMS HB Magnet | MECH TECH.MECH TECH | 0.8
1.4.3.1.2 Q-1 QUADRUPOLE | 24312050dA | Q1 Drawing Validation FY15 | MECH DES.MECH DES | 4.3
1.4.3.1.2 Q-1 QUADRUPOLE | 24312060 | Q1 Schedule Acceleration Incentives | PRCRMNT<$50K60NESC14.PROCUREMENT<$50K 60 NO ESCALATION FY14 | 0
1.4.3.1.2 Q-1 QUADRUPOLE | 24312048 | Vend Fab Q1 Completion of Factory Tests by Vendor | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.2 Q-1 QUADRUPOLE | 24312050 | Vend Fab Q1 Magnet System Delivery | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.2 Q-1 QUADRUPOLE | 24312050c | Vend Fab Q1 Magnet Acceptance | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.2 Q-1 QUADRUPOLE | 24312050d | Q1 Drawing Validation FY14 | MECH DES.MECH DES | 7.7
1.4.3.1.2 Q-1 QUADRUPOLE | 24312915LOE | Q1- FY15 Proj Mngmnt H-C upgrade | SCIENTIST.SCIENTIST | 22
1.4.3.1.2 Q-1 QUADRUPOLE | 243128P6LOE5 | Q1- P-7 Contract Mngmnt for Q1 | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.2 Q-1 QUADRUPOLE | 243128P6LOE5 | Q1- P-7 Contract Mngmnt for Q1 | MECH ENG.MECH ENG | 2.8
1.4.3.1.2 Q-1 QUADRUPOLE | 24312915LOE5 | Q1- FY16 Proj Mngmnt H-C upgrade | SCIENTIST.SCIENTIST | 3
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313235 | Q2 and Q3 witness Pressure Tests | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313275 | Q2&Q3 Drawing Validation | MECH DES.MECH DES | 12
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313017 | Vend Fab Q2&3 Peg Point #3 Cryostat Component Complete | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313017 | Vend Fab Q2&3 Peg Point #3 Cryostat Component Complete | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313230 | Q2 and Q3- Insp Cold Mass | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313230 | Q2 and Q3- Insp Cold Mass | MECH ENG.MECH ENG | 1
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313P6LOE | Q2&3- P-6 Contract Mngmnt for Q2-3 | MECH ENG.MECH ENG | 11
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313P6LOE | Q2&3- P-6 Contract Mngmnt for Q2-3 | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313P6LOE5 | Q2&3- P-7 Contract Mngmnt for Q2-3 | MECH ENG.MECH ENG | 2.8
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313285 | Q2/Q3 portion of consolodation equipment and processing | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313019 | Vend Fab Q2&3 Peg Point #4 Cold Mass Fiducialitzation | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313019 | Vend Fab Q2&3 Peg Point #4 Cold Mass Fiducialitzation | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313019a | Vend Fab Q2&3 Peg Point #5 Shipment | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313019b | Vend Fab Q2&3 Peg Point #6 Final Acceptance | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313220 | Q2 and Q3 Coil Inspection | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.3 Q2-3 QUADRUPOLE | 24313220 | Q2 and Q3 Coil Inspection | MECH ENG.MECH ENG | 1
1.4.3.1.4 DIPOLE | 24314P6LOE | Dipole- P-6 Contract Mngmnt for Dipole | MECH ENG.MECH ENG | 8
1.4.3.1.4 DIPOLE | 24314P6LOE | Dipole- P-6 Contract Mngmnt for Dipole | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.4 DIPOLE | 24314027 | Vend Fab Dipole Outer Vessel Completed Peg Point #5 (F-12) | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.3.1.4 DIPOLE | 24314027 | Vend Fab Dipole Outer Vessel Completed Peg Point #5 (F-12) | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.4 DIPOLE | 24314040 | Dipole Drawing Validation | MECH DES.MECH DES | 12
1.4.3.1.4 DIPOLE | 24314035a | Dipole HC Test | MECH TECH.MECH TECH | 1
1.4.3.1.4 DIPOLE | 24314035a | Dipole HC Test | MECH ENG.MECH ENG | 2
1.4.3.1.4 DIPOLE | 24314030 | Vend Fab Dipole Factory Test Completed Peg Point #6 | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.4 DIPOLE | 24314035 | Vend Fab Dipole Magnet Accepted Peg Point #7 | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.1.4 DIPOLE | 24314048 | Dipole Inspect Cold Mass FY14 | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.4 DIPOLE | 24314048 | Dipole Inspect Cold Mass FY14 | MECH ENG.MECH ENG | 0.5
1.4.3.1.4 DIPOLE | 24314049 | Dipole Witness Final Factory Tests | MECH ENG.MECH ENG | 1
1.4.3.1.4 DIPOLE | 24314049 | Dipole Witness Final Factory Tests | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.4 DIPOLE | 24314048A | Dipole Inspect Cold Mass FY15 | EXPNS TRAVEL.TRAVEL | 0
1.4.3.1.4 DIPOLE | 24314048A | Dipole Inspect Cold Mass FY15 | MECH ENG.MECH ENG | 0.5
1.4.3.1.5 MAGNET COMPONENTS PROCURED BY JLAB | 24315007 | Test & Integrate DC Pwr Sys for all magnets | ELEC TECH.ELEC TECH | 8.5
1.4.3.1.5 MAGNET COMPONENTS PROCURED BY JLAB | 24315007 | Test & Integrate DC Pwr Sys for all magnets | ELEC ENG.ELEC ENG | 8.5
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161000 | Vendor wind Spare Q2/Q3 Coil | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161000 | Vendor wind Spare Q2/Q3 Coil | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161005 | Vendor Prepare Tooling to wind Spare Dipole Coil | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161010 | Vendor wind Spare Dipole Coil | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161015 | Vendor storage of Spare Coils | PRCRMNT>$50K69NESC16.PROCUREMENT>$50K 69 NO ESCALATION FY16 | 0
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161015 | Vendor storage of Spare Coils | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161020 | Vendor ship spare coils to JLab | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161030LOE | Oversight of Spare Coil Winding | MECH ENG.MECH ENG | 23.8
1.4.3.1.6.1 CONSTRUCTION HALL C SPARE COILS | 243161030LOE | Oversight of Spare Coil Winding | EXPNS TRAVEL.TRAVEL | 0
1.4.3.2.3 NOBLE GAS CERENKOV | 24323005b | Fab Noble Gas Cerenkov Procurement | PRCRMNT>$50K 69NOESC.PROCUREMENT>$50K 69 NO ESCALATION | 0
1.4.3.2.3 NOBLE GAS CERENKOV | 24323005b | Fab Noble Gas Cerenkov Procurement | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0
1.4.3.2.8 DETECTOR FRAME | 24328010ba | Rigging Fixtures for individual Detctr's Procurement Part B | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | MECH TECH.MECH TECH | 0.4
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | MECH DES.MECH DES | 5
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | ELEC TECH.ELEC TECH | 5
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | SCIENTIST.SCIENTIST | 4
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | EXPNS TRAVEL.TRAVEL | 0
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | MECH ENG.MECH ENG | 5
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.5.3 MAPPING | 24353015 | Refurb Existing Harmonic Coil for SHMS Mags | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354020 | Procure Seal Supplies FY14 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354020 | Procure Seal Supplies FY14 | MECH DES.MECH DES | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354015a | Fabricate New Seals / Flanges Expenses FY14 | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354015a | Fabricate New Seals / Flanges Expenses FY14 | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354015a | Fabricate New Seals / Flanges Expenses FY14 | MECH DES.MECH DES | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354015a | Fabricate New Seals / Flanges Expenses FY14 | MECH ENG.MECH ENG | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354015a | Fabricate New Seals / Flanges Expenses FY14 | MECH TECH.MECH TECH | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030 | Specify & Order Valves, Adapters, Flanges, Gauges | MECH DES.MECH DES | 2
1.4.3.5.4 SCATTERING CHAMBER | 24354030 | Specify & Order Valves, Adapters, Flanges, Gauges | MECH ENG.MECH ENG | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030 | Specify & Order Valves, Adapters, Flanges, Gauges | MECH TECH.MECH TECH | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030 | Specify & Order Valves, Adapters, Flanges, Gauges | P MECH DES.PLABOR | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030 | Specify & Order Valves, Adapters, Flanges, Gauges | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030 | Specify & Order Valves, Adapters, Flanges, Gauges | EXPNS TRAVEL.TRAVEL | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030b | Procure Gate Valves, BL Adapters, Gauges, Fittings | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030b | Procure Gate Valves, BL Adapters, Gauges, Fittings | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354022 | Fabricate, Install, Test Seal and Windows | MECH DES.MECH DES | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354022 | Fabricate, Install, Test Seal and Windows | MECH ENG.MECH ENG | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354022 | Fabricate, Install, Test Seal and Windows | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354022 | Fabricate, Install, Test Seal and Windows | MECH TECH.MECH TECH | 4
1.4.3.5.4 SCATTERING CHAMBER | 24354010 | Detail Replacement Seal | MECH ENG.MECH ENG | 2
1.4.3.5.4 SCATTERING CHAMBER | 24354010 | Detail Replacement Seal | MECH DES.MECH DES | 6
1.4.3.5.4 SCATTERING CHAMBER | 24354010 | Detail Replacement Seal | SCIENTIST.SCIENTIST | 1
1.4.3.5.4 SCATTERING CHAMBER | 24354010 | Detail Replacement Seal | MECH TECH.MECH TECH | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354030b5 | Install Valves, Gauges, Fittings on SC | MECH TECH.MECH TECH | 4
1.4.3.5.4 SCATTERING CHAMBER | 24354015C | Fabricate New Seals / Flanges Procurement | PRCRMNT<$50K60NESC15.PROCUREMENT<$50K 60 NO ESCALATION FY15 | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354015B | Fabricate New Seals / Flanges Expenses FY15 | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354020A | Procure Seal Supplies FY15 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354020A | Procure Seal Supplies FY15 | MECH DES.MECH DES | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355005 | Proc 1st Pipe (Beam Pipe) | MECH TECH.MECH TECH | 2
1.4.3.5.5 BEAM PIPE & STANDS | 24355005 | Proc 1st Pipe (Beam Pipe) | MECH DES.MECH DES | 4
1.4.3.5.5 BEAM PIPE & STANDS | 24355005 | Proc 1st Pipe (Beam Pipe) | MECH ENG.MECH ENG | 2
1.4.3.5.5 BEAM PIPE & STANDS | 24355005 | Proc 1st Pipe (Beam Pipe) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355020 | Proc Windows & Window Spool (Beam Pipe) | MECH ENG.MECH ENG | 6
1.4.3.5.5 BEAM PIPE & STANDS | 24355020 | Proc Windows & Window Spool (Beam Pipe) | MECH TECH.MECH TECH | 3
1.4.3.5.5 BEAM PIPE & STANDS | 24355020 | Proc Windows & Window Spool (Beam Pipe) | MECH DES.MECH DES | 6
1.4.3.5.5 BEAM PIPE & STANDS | 24355020 | Proc Windows & Window Spool (Beam Pipe) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355000 | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY14 | MECH DES.MECH DES | 19.7
1.4.3.5.5 BEAM PIPE & STANDS | 24355000 | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY14 | MECH ENG.MECH ENG | 4.9
1.4.3.5.5 BEAM PIPE & STANDS | 24355025 | Proc Beam Stands (Beam Pipe) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355030 | Proc Vac Fittings (Beam Pipe) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355015 | Proc 3rd Section of Beam Pipe (Beam Pipe) | EXPNS TRAVEL.TRAVEL | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355015 | Proc 3rd Section of Beam Pipe (Beam Pipe) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355015 | Proc 3rd Section of Beam Pipe (Beam Pipe) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355015 | Proc 3rd Section of Beam Pipe (Beam Pipe) | MECH ENG.MECH ENG | 2
1.4.3.5.5 BEAM PIPE & STANDS | 24355015 | Proc 3rd Section of Beam Pipe (Beam Pipe) | MECH TECH.MECH TECH | 2
1.4.3.5.5 BEAM PIPE & STANDS | 24355015 | Proc 3rd Section of Beam Pipe (Beam Pipe) | MECH DES.MECH DES | 7
1.4.3.5.5 BEAM PIPE & STANDS | 24355010 | Proc 2nd Section of Beam Pipe (Beam Pipe) | MECH DES.MECH DES | 6
1.4.3.5.5 BEAM PIPE & STANDS | 24355010 | Proc 2nd Section of Beam Pipe (Beam Pipe) | MECH ENG.MECH ENG | 2
1.4.3.5.5 BEAM PIPE & STANDS | 24355010 | Proc 2nd Section of Beam Pipe (Beam Pipe) | MECH TECH.MECH TECH | 2
1.4.3.5.5 BEAM PIPE & STANDS | 24355010 | Proc 2nd Section of Beam Pipe (Beam Pipe) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355000A | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY15 | MECH DES.MECH DES | 0.3
1.4.3.5.5 BEAM PIPE & STANDS | 24355000A | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY15 | MECH ENG.MECH ENG | 0.1
1.4.3.6.5 VACUUM SYSTEM | 24365025 | Proc Valves & Plumbing and Reliefs Part B | PRCRMNT<$50K60NESC14.PROCUREMENT<$50K 60 NO ESCALATION FY14 | 0
1.4.3.6.5 VACUUM SYSTEM | 24365032 | Proc Spool & Bellows for All Magnets Part B | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.6.5 VACUUM SYSTEM | 24365040 | Proc Windows & Flanges Part B | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.6 CABLING | 24366025 | Terminate Cables | ELEC TECH.ELEC TECH | 8
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | ELEC ENG.ELEC ENG | 0.4
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | MECH ENG.MECH ENG | 0.4
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | MECH TECH.MECH TECH | 5.6
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | MECH DES.MECH DES | 0.5
1.4.3.6.8 INSTALLATION | 24368420A | Install Electrnc's (FAST Electrnc's) FY15 | ELEC TECH.ELEC TECH | 14.4
1.4.3.6.8 INSTALLATION | 24368420A | Install Electrnc's (FAST Electrnc's) FY15 | SCIENTIST.SCIENTIST | 7.2
1.4.3.6.8 INSTALLATION | 24368350 | Fiducialize Magnet CL of SHMS Dipole Magnet | MECH DES.MECH DES | 0.6
1.4.3.6.8 INSTALLATION | 24368350 | Fiducialize Magnet CL of SHMS Dipole Magnet | MECH TECH.MECH TECH | 2.4
1.4.3.6.8 INSTALLATION | 24368110 | Install Roof Beams and Wall Blocks in Shield House | MECH TECH.MECH TECH | 0.4
1.4.3.6.8 INSTALLATION | 24368450 | Hot Check-out of Detctr's in Shield House | ELEC TECH.ELEC TECH | 6
1.4.3.6.8 INSTALLATION | 24368545 | Install Sieve Slit Sys | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368545 | Install Sieve Slit Sys | MECH ENG.MECH ENG | 2
1.4.3.6.8 INSTALLATION | 24368545 | Install Sieve Slit Sys | MECH TECH.MECH TECH | 4.4
1.4.3.6.8 INSTALLATION | 24368465 | Install Beam Stands (Beam Pipe) | MECH ENG.MECH ENG | 3
1.4.3.6.8 INSTALLATION | 24368465 | Install Beam Stands (Beam Pipe) | MECH DES.MECH DES | 9
1.4.3.6.8 INSTALLATION | 24368490 | Leak Test Beam Pipe Vac Sys | MECH TECH.MECH TECH | 4
1.4.3.6.8 INSTALLATION | 24368490 | Leak Test Beam Pipe Vac Sys | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.6.8 INSTALLATION | 24368490 | Leak Test Beam Pipe Vac Sys | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368480 | Install Beam Pipe and Vac Fittings | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.6.8 INSTALLATION | 24368480 | Install Beam Pipe and Vac Fittings | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368480 | Install Beam Pipe and Vac Fittings | MECH TECH.MECH TECH | 1
1.4.3.6.8 INSTALLATION | 24368535 | Install Spool & Bellows for All Magnets | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.6.8 INSTALLATION | 24368535 | Install Spool & Bellows for All Magnets | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368535 | Install Spool & Bellows for All Magnets | MECH ENG.MECH ENG | 1
1.4.3.6.8 INSTALLATION | 24368535 | Install Spool & Bellows for All Magnets | MECH DES.MECH DES | 1
1.4.3.6.8 INSTALLATION | 24368535 | Install Spool & Bellows for All Magnets | MECH TECH.MECH TECH | 4
1.4.3.6.8 INSTALLATION | 24368360 | Assemble Upper Iron Yoke & Stands for Q3 magnet | MECH TECH.MECH TECH | 4
1.4.3.6.8 INSTALLATION | 24368360 | Assemble Upper Iron Yoke & Stands for Q3 magnet | MECH DES.MECH DES | 0.2
1.4.3.6.8 INSTALLATION | 24368360 | Assemble Upper Iron Yoke & Stands for Q3 magnet | MECH ENG.MECH ENG | 0.2
1.4.3.6.8 INSTALLATION | 24368155 | Install Cables & Produce Final Drawings (CABLING) FY14 | MECH TECH.MECH TECH | 36.4
1.4.3.6.8 INSTALLATION | 24368155 | Install Cables & Produce Final Drawings (CABLING) FY14 | MECH DES.MECH DES | 3.5
1.4.3.6.8 INSTALLATION | 24368155 | Install Cables & Produce Final Drawings (CABLING) FY14 | ELEC ENG.ELEC ENG | 2.6
1.4.3.6.8 INSTALLATION | 24368155 | Install Cables & Produce Final Drawings (CABLING) FY14 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.6.8 INSTALLATION | 24368155 | Install Cables & Produce Final Drawings (CABLING) FY14 | MECH ENG.MECH ENG | 2.6
1.4.3.6.8 INSTALLATION | 24368315 | Inspect & Assemble Upper Iron Yoke & Stands for Dipole magnet | MECH TECH.MECH TECH | 4
1.4.3.6.8 INSTALLATION | 24368315 | Inspect & Assemble Upper Iron Yoke & Stands for Dipole magnet | MECH ENG.MECH ENG | 0.2
1.4.3.6.8 INSTALLATION | 24368315 | Inspect & Assemble Upper Iron Yoke & Stands for Dipole magnet | MECH DES.MECH DES | 0.2
1.4.3.6.8 INSTALLATION | 24368325 | Assemble Upper Iron Yoke & Stands for Q2 magnet | MECH TECH.MECH TECH | 4
1.4.3.6.8 INSTALLATION | 24368325 | Assemble Upper Iron Yoke & Stands for Q2 magnet | MECH DES.MECH DES | 0.2
1.4.3.6.8 INSTALLATION | 24368325 | Assemble Upper Iron Yoke & Stands for Q2 magnet | MECH ENG.MECH ENG | 0.2
1.4.3.6.8 INSTALLATION | 24368160 | Install Fire Protection and Flamm Gas det. (SHIELD HOUSE) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368160 | Install Fire Protection and Flamm Gas det. (SHIELD HOUSE) | ELEC TECH.ELEC TECH | 5
1.4.3.6.8 INSTALLATION | 24368420 | Install Electrnc's (FAST Electrnc's) FY14 | ELEC TECH.ELEC TECH | 5.6
1.4.3.6.8 INSTALLATION | 24368420 | Install Electrnc's (FAST Electrnc's) FY14 | SCIENTIST.SCIENTIST | 2.8
1.4.3.6.8 INSTALLATION | 24368485 | Connect Additional Quad for Moeller polarimeter | ELEC TECH.ELEC TECH | 2
1.4.3.6.8 INSTALLATION | 24368485 | Connect Additional Quad for Moeller polarimeter | MECH TECH.MECH TECH | 5
1.4.3.6.8 INSTALLATION | 24368485 | Connect Additional Quad for Moeller polarimeter | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368485 | Connect Additional Quad for Moeller polarimeter | ELEC ENG.ELEC ENG | 1
1.4.3.6.8 INSTALLATION | 24368405 | Connect PMTs & Cables (SHOWER COUNTER) | ELEC TECH.ELEC TECH | 2
1.4.3.6.8 INSTALLATION | 24368400 | Stack Calorimeter Blocks (SHOWER COUNTER) | MECH TECH.MECH TECH | 8
1.4.3.6.8 INSTALLATION | 24368410 | Test Calorimeter (SHOWER COUNTER) | VISTNG USERS.VISTNG USERS | 4
1.4.3.6.8 INSTALLATION | 24368540 | Install Slit Controls | MECH TECH.MECH TECH | 4.4
1.4.3.6.8 INSTALLATION | 24368540 | Install Slit Controls | MECH ENG.MECH ENG | 1
1.4.3.6.8 INSTALLATION | 24368100 | Install and Align Detector Frames for DC and Rear Detectors (Assemble Rear Detector Frame) | MECH DES.MECH DES | 1
1.4.3.6.8 INSTALLATION | 24368100 | Install and Align Detector Frames for DC and Rear Detectors (Assemble Rear Detector Frame) | MECH TECH.MECH TECH | 4.4
1.4.3.6.8 INSTALLATION | 24368470 | Install Windows & Flanges | MECH DES.MECH DES | 3
1.4.3.6.8 INSTALLATION | 24368470 | Install Windows & Flanges | MECH TECH.MECH TECH | 3
1.4.3.6.8 INSTALLATION | 24368470 | Install Windows & Flanges | MECH ENG.MECH ENG | 2
1.4.3.6.8 INSTALLATION | 24368440 | Install Shutter Exit Window | MECH ENG.MECH ENG | 2
1.4.3.6.8 INSTALLATION | 24368440 | Install Shutter Exit Window | MECH DES.MECH DES | 1
1.4.3.6.8 INSTALLATION | 24368440 | Install Shutter Exit Window | MECH TECH.MECH TECH | 2
1.4.3.6.8 INSTALLATION | 24368440 | Install Shutter Exit Window | ELEC TECH.ELEC TECH | 2
1.4.3.6.8 INSTALLATION | 24368340 | Mount Q2 on Supprt Carriage | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368340 | Mount Q2 on Supprt Carriage | MECH TECH.MECH TECH | 18
1.4.3.6.8 INSTALLATION | 24368340 | Mount Q2 on Supprt Carriage | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368305 | Final Assemble & Mount Dipole on Supprt Carriage | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368305 | Final Assemble & Mount Dipole on Supprt Carriage | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.6.8 INSTALLATION | 24368305 | Final Assemble & Mount Dipole on Supprt Carriage | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368305 | Final Assemble & Mount Dipole on Supprt Carriage | MECH DES.MECH DES | 2
1.4.3.6.8 INSTALLATION | 24368305 | Final Assemble & Mount Dipole on Supprt Carriage | MECH ENG.MECH ENG | 1
1.4.3.6.8 INSTALLATION | 24368305 | Final Assemble & Mount Dipole on Supprt Carriage | MECH TECH.MECH TECH | 26
1.4.3.6.8 INSTALLATION | 24368295 | Mount HB on Supprt Carriage | MECH DES.MECH DES | 1
1.4.3.6.8 INSTALLATION | 24368295 | Mount HB on Supprt Carriage | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368295 | Mount HB on Supprt Carriage | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368295 | Mount HB on Supprt Carriage | MECH TECH.MECH TECH | 1
1.4.3.6.8 INSTALLATION | 24368430 | Fiducialize SHMS Drift Ch's, Hodoscopes, Cerenkovs, Preshower (front Dets) | MECH TECH.MECH TECH | 4
1.4.3.6.8 INSTALLATION | 24368430 | Fiducialize SHMS Drift Ch's, Hodoscopes, Cerenkovs, Preshower (front Dets) | MECH DES.MECH DES | 1
1.4.3.6.8 INSTALLATION | 24368370 | Mount Q3 on Supprt Carriage | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368370 | Mount Q3 on Supprt Carriage | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368370 | Mount Q3 on Supprt Carriage | MECH TECH.MECH TECH | 18
1.4.3.6.8 INSTALLATION | 24368290 | Mount Q1 on Supprt Carriage | MECH DES.MECH DES | 0.6
1.4.3.6.8 INSTALLATION | 24368290 | Mount Q1 on Supprt Carriage | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368290 | Mount Q1 on Supprt Carriage | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368290 | Mount Q1 on Supprt Carriage | MECH TECH.MECH TECH | 11.9
1.4.3.6.8 INSTALLATION | 24368520 | Prep for Vac & pressure systems Safety Review | MECH ENG.MECH ENG | 2
1.4.3.6.8 INSTALLATION | 24368445 | Install Detctr's in Shield House FWD | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368445 | Install Detctr's in Shield House FWD | ELEC TECH.ELEC TECH | 10
1.4.3.6.8 INSTALLATION | 24368445 | Install Detctr's in Shield House FWD | MECH TECH.MECH TECH | 12
1.4.3.6.8 INSTALLATION | 24368445 | Install Detctr's in Shield House FWD | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368445 | Install Detctr's in Shield House FWD | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.3.6.8 INSTALLATION | 24368095 | Install Doors in Shield House | MECH DES.MECH DES | 2
1.4.3.6.8 INSTALLATION | 24368095 | Install Doors in Shield House | MECH TECH.MECH TECH | 4
1.4.3.6.8 INSTALLATION | 24368365 | Finucialize Magnet CL of SHMS Q2 Magnet | MECH TECH.MECH TECH | 0.8
1.4.3.6.8 INSTALLATION | 24368365 | Finucialize Magnet CL of SHMS Q2 Magnet | MECH DES.MECH DES | 0.2
1.4.3.6.8 INSTALLATION | 24368390 | Finucialize Magnet CL of SHMS Q3 Magnet | MECH TECH.MECH TECH | 0.8
1.4.3.6.8 INSTALLATION | 24368390 | Finucialize Magnet CL of SHMS Q3 Magnet | MECH DES.MECH DES | 0.2
1.4.3.6.8 INSTALLATION | 24368435 | Install Detctr's in Shield House REAR | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368435 | Install Detctr's in Shield House REAR | ELEC TECH.ELEC TECH | 10
1.4.3.6.8 INSTALLATION | 24368435 | Install Detctr's in Shield House REAR | MECH TECH.MECH TECH | 12
1.4.3.6.8 INSTALLATION | 24368435 | Install Detctr's in Shield House REAR | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368590LOE | Installation Management P4 | SCIENTIST.SCIENTIST | 2.1
1.4.3.6.8 INSTALLATION | 24368590LOE | Installation Management P4 | MECH ENG.MECH ENG | 5
1.4.3.6.8 INSTALLATION | 24368530 | Install & Connect Spectrometer Vac system | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368530 | Install & Connect Spectrometer Vac system | MECH TECH.MECH TECH | 15
1.4.3.6.8 INSTALLATION | 24368530 | Install & Connect Spectrometer Vac system | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368310 | Install & Connect Magnet Insulating Vac system | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.6.8 INSTALLATION | 24368310 | Install & Connect Magnet Insulating Vac system | MECH TECH.MECH TECH | 15
1.4.3.6.8 INSTALLATION | 24368310 | Install & Connect Magnet Insulating Vac system | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368565 | Install SHMS Position Readback System | MECH TECH.MECH TECH | 3
1.4.3.6.8 INSTALLATION | 24368565 | Install SHMS Position Readback System | ELEC TECH.ELEC TECH | 2
1.4.3.6.8 INSTALLATION | 24368565 | Install SHMS Position Readback System | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.6.8 INSTALLATION | 24368565 | Install SHMS Position Readback System | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.4.3.6.8 INSTALLATION | 24368130 | Install Fire Protection & Detection Sys of Supprt Struct | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.6.8 INSTALLATION | 24368130 | Install Fire Protection & Detection Sys of Supprt Struct | ELEC TECH.ELEC TECH | 4
1.4.3.6.8 INSTALLATION | 24368130 | Install Fire Protection & Detection Sys of Supprt Struct | PLANT ENG.PLANT ENG | 2
1.4.3.6.8 INSTALLATION | 24368570 | Install Rotation Controls of Supprt Struct | MECH ENG.MECH ENG | 4
1.4.3.6.8 INSTALLATION | 24368570 | Install Rotation Controls of Supprt Struct | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.4.3.6.8 INSTALLATION | 24368570 | Install Rotation Controls of Supprt Struct | MECH TECH.MECH TECH | 9
1.4.3.6.8 INSTALLATION | 24368300 | Fiducialize Magnet CL of SHMS Q1 Magnet | MECH TECH.MECH TECH | 0.8
1.4.3.6.8 INSTALLATION | 24368300 | Fiducialize Magnet CL of SHMS Q1 Magnet | MECH DES.MECH DES | 0.2
1.4.3.6.8 INSTALLATION | 24368560 | Install & Align SHMS Angle Scribe Plates | MECH TECH.MECH TECH | 6
1.4.3.6.8 INSTALLATION | 24368585LOE | Installation Management P3 | SCIENTIST.SCIENTIST | 11
1.4.3.6.8 INSTALLATION | 24368585LOE | Installation Management P3 | MECH ENG.MECH ENG | 22
1.5.5.3 BEAMLINE COMPONENTS | 2553095 | Design Install Feedback System for Active Collimator (Accelerator Grp) FY13 | ELEC TECH.ELEC TECH | 1.7
1.5.5.3 BEAMLINE COMPONENTS | 2553095 | Design Install Feedback System for Active Collimator (Accelerator Grp) FY13 | ELEC ENG.ELEC ENG | 0.5
1.5.5.3 BEAMLINE COMPONENTS | 2553157 | Install polarimeter | MECH ENG.MECH ENG | 0.5
1.5.5.3 BEAMLINE COMPONENTS | 2553157 | Install polarimeter | MECH TECH.MECH TECH | 2
1.5.5.3 BEAMLINE COMPONENTS | 2553157 | Install polarimeter | SCIENTIST.SCIENTIST | 0.5
1.5.5.3 BEAMLINE COMPONENTS | 2553157 | Install polarimeter | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.5.5.3 BEAMLINE COMPONENTS | 2553010a | Thinning-Characterization-Mounting of Radiator Diamond Crystals (BL Compnts) | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.5.5.3 BEAMLINE COMPONENTS | 2553095a | Design Install Feedback System for Active Collimator (Accelerator Grp) FY14 | ELEC TECH.ELEC TECH | 14.3
1.5.5.3 BEAMLINE COMPONENTS | 2553095a | Design Install Feedback System for Active Collimator (Accelerator Grp) FY14 | ELEC ENG.ELEC ENG | 4
1.5.5.3 BEAMLINE COMPONENTS | 2553010 | Thinning-Characterization-Mounting of Radiator Diamond Crystals (BL Compnts) Phase 1 | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.5.5.3 BEAMLINE COMPONENTS | 2553010 | Thinning-Characterization-Mounting of Radiator Diamond Crystals (BL Compnts) Phase 1 | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112013 | Redundant Cooling Towers Construction Management | MECH TECH.MECH TECH | 10
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112013 | Redundant Cooling Towers Construction Management | MECH ENG.MECH ENG | 8
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112013 | Redundant Cooling Towers Construction Management | OFFICE (admn supprt).OFFICE | 2
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112012 | Redundant Cooling Towers Contract Progress | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112012 | Redundant Cooling Towers Contract Progress | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112012 | Redundant Cooling Towers Contract Progress | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112012 | Redundant Cooling Towers Contract Progress | PRCRMNT>$50K69NESC16.PROCUREMENT>$50K 69 NO ESCALATION FY16 | 0
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114005 | Tunnel A/C Award Contract | MECH ENG.MECH ENG | 2
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114025 | Tunnel A/C Beneficial Occupancy | MECH ENG.MECH ENG | 2
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114020 | Tunnel A/C Constrctn Mngmnt | OFFICE (admn supprt).OFFICE | 3
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114020 | Tunnel A/C Constrctn Mngmnt | ELEC ENG.ELEC ENG | 1
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114020 | Tunnel A/C Constrctn Mngmnt | MECH ENG.MECH ENG | 16
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114020 | Tunnel A/C Constrctn Mngmnt | MECH TECH.MECH TECH | 13
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114020 | Tunnel A/C Constrctn Mngmnt | MECH DES.MECH DES | 1
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114010 | Tunnel A/C Constrctn Contract Progress | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114010 | Tunnel A/C Constrctn Contract Progress | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.6.1.1.4 TUNNEL AIR CONDITIONING | 26114015 | Tunnel A/C Bldng Cmmssng | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 0
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | MECH ENG.MECH ENG | 21.4
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | SR STAFF.SR STAFF | 27.3
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | SCIENTIST.SCIENTIST | 2.1
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | DIRECTORATE.DIRECTORATE | 18.7
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | OFFICE (admn supprt).OFFICE | 21.4
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | ELEC ENG.ELEC ENG | 5.3
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | ADMIN.ADMIN | 10.7
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | SR STAFF.SR STAFF | 13.1
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | OFFICE (admn supprt).OFFICE | 10.3
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | ELEC ENG.ELEC ENG | 2.6
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | DIRECTORATE.DIRECTORATE | 9
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | ADMIN.ADMIN | 5.1
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | SCIENTIST.SCIENTIST | 1
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | MECH ENG.MECH ENG | 10.3
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811065 | H-D Beam Cmmssng | ELEC TECH.ELEC TECH | 49.8
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811065 | H-D Beam Cmmssng | MECH ENG.MECH ENG | 3
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811065 | H-D Beam Cmmssng | COMP SCIENT.COMP SCIENT | 6
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811065 | H-D Beam Cmmssng | SCIENTIST.SCIENTIST | 9
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811065 | H-D Beam Cmmssng | ELEC ENG.ELEC ENG | 3
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811065 | H-D Beam Cmmssng | MECH TECH.MECH TECH | 6
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811035 | H-B Beam Cmmssng | ELEC ENG.ELEC ENG | 2
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811035 | H-B Beam Cmmssng | MECH TECH.MECH TECH | 4
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811035 | H-B Beam Cmmssng | ELEC TECH.ELEC TECH | 33.2
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811035 | H-B Beam Cmmssng | MECH ENG.MECH ENG | 2
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811035 | H-B Beam Cmmssng | COMP SCIENT.COMP SCIENT | 4
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811035 | H-B Beam Cmmssng | SCIENTIST.SCIENTIST | 6
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811050 | H-C Beam Cmmssng | ELEC ENG.ELEC ENG | 1
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811050 | H-C Beam Cmmssng | MECH ENG.MECH ENG | 1
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811050 | H-C Beam Cmmssng | COMP SCIENT.COMP SCIENT | 2
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811050 | H-C Beam Cmmssng | MECH TECH.MECH TECH | 2
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811050 | H-C Beam Cmmssng | SCIENTIST.SCIENTIST | 3
1.8.1.1 CONSTRUCTION ACCELERATOR PRE-OPS BEAM COMMISIONING | 2811050 | H-C Beam Cmmssng | ELEC TECH.ELEC TECH | 16.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812035 | H-C Beam Cmmssng (Utilities) | MECH ENG.MECH ENG | 1.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812035 | H-C Beam Cmmssng (Utilities) | ELEC TECH.ELEC TECH | 1.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812035 | H-C Beam Cmmssng (Utilities) | MECH TECH.MECH TECH | 1.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812035 | H-C Beam Cmmssng (Utilities) | ELEC ENG.ELEC ENG | 1.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812035 | H-C Beam Cmmssng (Utilities) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812050 | H-D Beam Cmmssng (Utilities) | MECH ENG.MECH ENG | 4.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812050 | H-D Beam Cmmssng (Utilities) | ELEC ENG.ELEC ENG | 4.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812050 | H-D Beam Cmmssng (Utilities) | ELEC TECH.ELEC TECH | 4.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812050 | H-D Beam Cmmssng (Utilities) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812050 | H-D Beam Cmmssng (Utilities) | MECH TECH.MECH TECH | 4.6
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812020 | H-B Beam Cmmssng (Utilities) | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 0
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812020 | H-B Beam Cmmssng (Utilities) | ELEC TECH.ELEC TECH | 3.1
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812020 | H-B Beam Cmmssng (Utilities) | MECH TECH.MECH TECH | 3.1
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812020 | H-B Beam Cmmssng (Utilities) | ELEC ENG.ELEC ENG | 3.1
1.8.1.2 CONSTRUCTION ACCELERATOR PRE-OPS UTILITIES | 2812020 | H-B Beam Cmmssng (Utilities) | MECH ENG.MECH ENG | 3.1
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223040 | Trigger system commissioning | P ELEC TECH.PLABOR | 0
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223040 | Trigger system commissioning | SCIENTIST.SCIENTIST | 16
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223000 | CTP testing of 22 boards | SCIENTIST.SCIENTIST | 8
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223000 | CTP testing of 22 boards | ELEC ENG.ELEC ENG | 8
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030 | CLAS12 DAQ/online software updates FY14 | SCIENTIST.SCIENTIST | 0.7
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030 | CLAS12 DAQ/online software updates FY14 | VISTNG USERS.VISTNG USERS | 1.5
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030 | CLAS12 DAQ/online software updates FY14 | PD UNIV STUDNT.PD UNIV STUDNT | 0.7
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223025 | DAQ Commissioning FY14 | SCIENTIST.SCIENTIST | 0.9
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223025A | DAQ Commissioning FY15 | SCIENTIST.SCIENTIST | 11.1
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223025B | DAQ Commissioning FY16 | SCIENTIST.SCIENTIST | 0.1
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030A | CLAS12 DAQ/online software updates FY15 | SCIENTIST.SCIENTIST | 9.7
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030A | CLAS12 DAQ/online software updates FY15 | VISTNG USERS.VISTNG USERS | 19.4
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030A | CLAS12 DAQ/online software updates FY15 | PD UNIV STUDNT.PD UNIV STUDNT | 9.7
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030B | CLAS12 DAQ/online software updates FY16 | SCIENTIST.SCIENTIST | 0.1
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030B | CLAS12 DAQ/online software updates FY16 | VISTNG USERS.VISTNG USERS | 0.2
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030B | CLAS12 DAQ/online software updates FY16 | PD UNIV STUDNT.PD UNIV STUDNT | 0.1
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226005 | Cooldown | MECH TECH.MECH TECH | 15
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226005 | Cooldown | MECH ENG.MECH ENG | 10.9
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226005 | Cooldown | ELEC ENG.ELEC ENG | 4
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226010 | Torus Operational Tests | MECH TECH.MECH TECH | 6.9
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226010 | Torus Operational Tests | MECH ENG.MECH ENG | 5.5
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226010 | Torus Operational Tests | ELEC ENG.ELEC ENG | 2
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226015 | Map CLAS12 Torus Field both polarities | MECH TECH.MECH TECH | 4
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226015 | Map CLAS12 Torus Field both polarities | CONTRB UNIV LBR.CONTRB UNIV LBR | 4
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226015 | Map CLAS12 Torus Field both polarities | SCIENTIST.SCIENTIST | 4
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226025 | Solenoid Acceptance Tests and Mapping | MECH TECH.MECH TECH | 1.2
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226025 | Solenoid Acceptance Tests and Mapping | MECH ENG.MECH ENG | 1.2
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226000 | Commission Cryogenic System | MECH ENG.MECH ENG | 2
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226000 | Commission Cryogenic System | MECH TECH.MECH TECH | 2
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226000 | Commission Cryogenic System | ELEC TECH.ELEC TECH | 2
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226020 | Solenoid Cool Down | MECH ENG.MECH ENG | 1.8
1.8.2.2.6 HALL B MAGNET INSTALLATION TESTING | 28226020 | Solenoid Cool Down | MECH TECH.MECH TECH | 1.8
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X000 | H-B PRE-OPS Cmmssn with Beam | MECH ENG.MECH ENG | 4.2
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X000 | H-B PRE-OPS Cmmssn with Beam | CONTRB UNIV LBR.CONTRB UNIV LBR | 25.2
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X000 | H-B PRE-OPS Cmmssn with Beam | VISTNG USERS.VISTNG USERS | 33.6
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X000 | H-B PRE-OPS Cmmssn with Beam | SCIENTIST.SCIENTIST | 19.6
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X000 | H-B PRE-OPS Cmmssn with Beam | MECH TECH.MECH TECH | 1.4
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231000 | HB-Acceptance Test | MECH DES.MECH DES | 1
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231000 | HB-Acceptance Test | MECH ENG.MECH ENG | 4
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231000 | HB-Acceptance Test | MECH TECH.MECH TECH | 6
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231010 | Q1 Harmonic Coil Test | MECH TECH.MECH TECH | 0.5
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231010 | Q1 Harmonic Coil Test | MECH ENG.MECH ENG | 1
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231005 | Q1 Cooldown and Acceptance Test | MECH DES.MECH DES | 1
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231005 | Q1 Cooldown and Acceptance Test | MECH ENG.MECH ENG | 4
1.8.2.3.1 HALL C HB AND Q1 TESTING | 28231005 | Q1 Cooldown and Acceptance Test | MECH TECH.MECH TECH | 6
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236000 | Cool Down Dipole Magnet | MECH TECH.MECH TECH | 2.5
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236000 | Cool Down Dipole Magnet | MECH DES.MECH DES | 2.5
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236000 | Cool Down Dipole Magnet | MECH ENG.MECH ENG | 1
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236005 | Dipole Acceptance Test | MECH TECH.MECH TECH | 2
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236005 | Dipole Acceptance Test | MECH ENG.MECH ENG | 2
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236030 | Power all Magnets together | ELEC ENG.ELEC ENG | 2
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236030 | Power all Magnets together | MECH ENG.MECH ENG | 2
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236030 | Power all Magnets together | MECH TECH.MECH TECH | 6
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236015 | Q2 HC & FF Test | MECH TECH.MECH TECH | 1.4
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236015 | Q2 HC & FF Test | MECH ENG.MECH ENG | 2
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236025 | Q3- HC & FF Test | MECH TECH.MECH TECH | 1.4
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236025 | Q3- HC & FF Test | MECH ENG.MECH ENG | 2
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236010 | Q2 Cooldown and Acceptance Test | MECH DES.MECH DES | 1
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236010 | Q2 Cooldown and Acceptance Test | MECH ENG.MECH ENG | 4
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236010 | Q2 Cooldown and Acceptance Test | MECH TECH.MECH TECH | 6
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236020 | Q3 Cooldown and Acceptance Test | MECH DES.MECH DES | 1
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236020 | Q3 Cooldown and Acceptance Test | MECH ENG.MECH ENG | 4
1.8.2.3.6 HALL C DIPOLE AND Q2Q3 MAGNET TESTING | 28236020 | Q3 Cooldown and Acceptance Test | MECH TECH.MECH TECH | 6
1.8.2.3.X HALL C COMMISSIONG WITH BEAM | 2823X000 | H-C PRE-OPS Cmmssn with Beam | MECH ENG.MECH ENG | 2.1
1.8.2.3.X HALL C COMMISSIONG WITH BEAM | 2823X000 | H-C PRE-OPS Cmmssn with Beam | CONTRB UNIV LBR.CONTRB UNIV LBR | 12.6
1.8.2.3.X HALL C COMMISSIONG WITH BEAM | 2823X000 | H-C PRE-OPS Cmmssn with Beam | MECH TECH.MECH TECH | 0.7
1.8.2.3.X HALL C COMMISSIONG WITH BEAM | 2823X000 | H-C PRE-OPS Cmmssn with Beam | VISTNG USERS.VISTNG USERS | 8.4
1.8.2.3.X HALL C COMMISSIONG WITH BEAM | 2823X000 | H-C PRE-OPS Cmmssn with Beam | SCIENTIST.SCIENTIST | 9.8
1.8.2.4.X HALL D COMMISSIONING WITH BEAM | 2824X000 | H-D PRE-OPS Cmmssn with Beam | CONTRB UNIV LBR.CONTRB UNIV LBR | 36
1.8.2.4.X HALL D COMMISSIONING WITH BEAM | 2824X000 | H-D PRE-OPS Cmmssn with Beam | MECH TECH.MECH TECH | 4
1.8.2.4.X HALL D COMMISSIONING WITH BEAM | 2824X000 | H-D PRE-OPS Cmmssn with Beam | VISTNG USERS.VISTNG USERS | 24
1.8.2.4.X HALL D COMMISSIONING WITH BEAM | 2824X000 | H-D PRE-OPS Cmmssn with Beam | SCIENTIST.SCIENTIST | 36
1.8.2.4.X HALL D COMMISSIONING WITH BEAM | 2824X000 | H-D PRE-OPS Cmmssn with Beam | MECH ENG.MECH ENG | 6.8
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | MECH ENG.MECH ENG | 66.6
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | SR STAFF.SR STAFF | 84.9
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | SCIENTIST.SCIENTIST | 6.7
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | DIRECTORATE.DIRECTORATE | 58.3
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | OFFICE (admn supprt).OFFICE | 66.6
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | ELEC ENG.ELEC ENG | 16.7
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831915LOE | FY15 Pre-Ops Supprt - Proj Office | ADMIN.ADMIN | 33.3
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | MECH ENG.MECH ENG | 55.7
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | SR STAFF.SR STAFF | 71
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | OFFICE (admn supprt).OFFICE | 55.7
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | ELEC ENG.ELEC ENG | 13.9
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | DIRECTORATE.DIRECTORATE | 48.8
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | ADMIN.ADMIN | 27.9
1.8.3.1 PRE-OPS SUPPORT - PROJECT OFFICE | 2831916LOE | FY16 Pre-Ops Supprt - Proj Office | SCIENTIST.SCIENTIST | 5.6
1.4.3.5.4 SCATTERING CHAMBER | 24354015B | Fabricate New Seals / Flanges Expenses FY15 | EXPNS MACHINE SHOP.MSHOP | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354020A | Procure Seal Supplies FY15 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.5.4 SCATTERING CHAMBER | 24354020A | Procure Seal Supplies FY15 | MECH DES.MECH DES | 0
1.4.3.5.5 BEAM PIPE & STANDS | 24355000A | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY15 | MECH DES.MECH DES | 0.31
1.4.3.5.5 BEAM PIPE & STANDS | 24355000A | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY15 | MECH ENG.MECH ENG | 0.08
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | ELEC ENG.ELEC ENG | 0.4
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | MECH ENG.MECH ENG | 0.4
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | MECH TECH.MECH TECH | 5.63
1.4.3.6.8 INSTALLATION | 24368155A | Install Cables & Produce Final Drawings (CABLING) FY15 | MECH DES.MECH DES | 0.54
1.4.3.6.8 INSTALLATION | 24368420A | Install Electrnc's (FAST Electrnc's) FY15 | ELEC TECH.ELEC TECH | 14.43
1.4.3.6.8 INSTALLATION | 24368420A | Install Electrnc's (FAST Electrnc's) FY15 | SCIENTIST.SCIENTIST | 7.22
1.4.3.6.8 INSTALLATION | 24368445 | Install Detctr's in Shield House FWD | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112012 | Redundant Cooling Towers Contract Progress | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.6.1.1.2 NORTH & SOUTH ACCESS BUILDING UTILITIES | 26112012 | Redundant Cooling Towers Contract Progress | PRCRMNT>$50K69NESC16.PROCUREMENT>$50K 69 NO ESCALATION FY16 | 0
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223025A | DAQ Commissioning FY15 | SCIENTIST.SCIENTIST | 11.06
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223025B | DAQ Commissioning FY16 | SCIENTIST.SCIENTIST | 0.09
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030A | CLAS12 DAQ/online software updates FY15 | SCIENTIST.SCIENTIST | 9.69
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030A | CLAS12 DAQ/online software updates FY15 | VISTNG USERS.VISTNG USERS | 19.37
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030A | CLAS12 DAQ/online software updates FY15 | PD UNIV STUDNT.PD UNIV STUDNT | 9.69
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030B | CLAS12 DAQ/online software updates FY16 | SCIENTIST.SCIENTIST | 0.08
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030B | CLAS12 DAQ/online software updates FY16 | VISTNG USERS.VISTNG USERS | 0.16
1.8.2.2.3 HALL B TRIGGER, DAQ AND ONLINE SOFTWARE CHECKOUT | 28223030B | CLAS12 DAQ/online software updates FY16 | PD UNIV STUDNT.PD UNIV STUDNT | 0.08
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | MECH ENG.MECH ENG | 21.39
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | SR STAFF.SR STAFF | 27.27
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | SCIENTIST.SCIENTIST | 2.14
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | DIRECTORATE.DIRECTORATE | 18.71
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | OFFICE (admn supprt).OFFICE | 21.39
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | ELEC ENG.ELEC ENG | 5.35
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.7.1 PROJECT OFFICE | 271915LOE | FY15 Constrctn Proj Office Proj Mngmnt | ADMIN.ADMIN | 10.69
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | SR STAFF.SR STAFF | 13.11
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | OFFICE (admn supprt).OFFICE | 10.28
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | ELEC ENG.ELEC ENG | 2.57
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | DIRECTORATE.DIRECTORATE | 9
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 0
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | ADMIN.ADMIN | 5.14
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | SCIENTIST.SCIENTIST | 1.03
1.7.1 PROJECT OFFICE | 271916LOE | FY16 Constrctn Proj Office Proj Mngmnt | MECH ENG.MECH ENG | 10.28
1.4.2.5.4 BEAMLINE COMPONENTS | 24254015 | Downstream Viewer Procurement | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254030 | Moller polarimeter upgrade Procurement | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254030 | Moller polarimeter upgrade Procurement | PRCRMNT>$50K69NESC16.PROCUREMENT>$50K 69 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254110 | Upstream Shielding Wall Procurement | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254110 | Upstream Shielding Wall Procurement | PRCRMNT>$50K69NESC16.PROCUREMENT>$50K 69 NO ESCALATION FY16 | 0
1.4.2.5.4 BEAMLINE COMPONENTS | 24254120 | Procurement of Beamline Devices | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 0
1.4.2.7.11.1 ADDITIONAL FNAL COILS FOR TORUS RISK MITIGATION | 242711.1005C | FNAL: Solder Copper Shields for CCM #8 (FNAL CCM #10) | PRCRMNT<$50K 60NOESC.PROCUREMENT<$50K 60 NO ESCALATION | 0

## P6 Additional Raw Data
Activity ID | EVMS Reporting Codes | Activity Name | Start | Finish | Physical % Complete | BL Project Material Cost | BL Project Nonlabor Cost | BL Project Total Cost
1-7M | M | CD-4A ( Approve Accelerator Completion & Start of Operations) |  | 31-Jul-14 16:00 A | 100% | 0 | 0 | 0
1-8M | M | CD-4B (Approve Proj Compltn & Start of Operations) |  | 29-Sep-17 16:00* | 0% | 0 | 0 | 0
2-03M | M | Accelerator Commissioned |  | 07-May-14 16:00 A | 100% | 0 | 0 | 0
2-08M | M | Installation of Experimental Equipment into H-A is Completed |  | 18-Nov-13 16:00 A | 100% | 0 | 0 | 0
2-09M | M | Hall-A Beam Commissioning Completed |  | 01-Apr-14 16:00 A | 100% | 0 | 0 | 0
2-12M | M | Hall-D Equipment Installation Completed |  | 2014-10-31 08:00 | 100% | 0 | 0 | 0
2-13M | M | Hall-D Beam Commissioning Completed |  | 21-Nov-14 16:00* | 0% | 0 | 0 | 0
2-25M | M | Box Supply Installtn Comptd |  | 2014-09-15 08:00 | 100% | 0 | 0 | 0
2-26M | M | Accel Installtn Comptd Except for All Power Supplies |  | 08-Apr-14 16:00 A | 100% | 0 | 0 | 0
2-27M | M | Hall C Q1 Magnet Delivered |  | 15-Jan-15 16:00* | 0% | 0 | 0 | 0
2-28M | M | Hall C HB Magnet Delivered |  | 15-May-15 16:00* | 0% | 0 | 0 | 0
2-29M | M | Hall C Dipole Delivered |  | 04-Nov-15 16:00* | 0% | 0 | 0 | 0
2-30M | M | Hall C Q2 Magnet Delivered |  | 18-Nov-15 08:00* | 0% | 0 | 0 | 0
2-31M | M | Hall C Q3 Magnet Delivered |  | 10-Feb-16 16:00* | 0% | 0 | 0 | 0
2-32M | M | Installation of Expermentall Equipment into H-C is Completed |  | 13-Jun-16 16:00* | 0% | 0 | 0 | 0
2-33M | M | Hall C Beam Commissioning Complete |  | 19-Jul-16 16:00* | 0% | 0 | 0 | 0
2-34M | M | Hall B Torus Cold Mass Delivered |  | 17-Apr-15 16:00* | 0% | 0 | 0 | 0
2-35M | M | Hall B Solenoid Cryostated Coil Delivered |  | 03-Mar-16 16:00* | 0% | 0 | 0 | 0
2-36M | M | Installation of Expermentall Equipment into H-B is Completed |  | 16-Aug-16 16:00* | 0% | 0 | 0 | 0
2-37M | M | Hall B Beam Commissioning Complete |  | 27-Sep-16 16:00* | 0% | 0 | 0 | 0
2-38M | M | Conventional Facilt's Comptd |  | 07-Aug-15 16:00* | 0% | 0 | 0 | 0
232111914LOE | E | Proj Admin ongoing (Klystrons) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 1881
232113125 | H | Test and Reinstall SL Circulators | 2013-09-03 08:00 | 06-Sep-13 16:00 A | 100% | 0 | 0 | 763
23213020M | M | Comp Cavity Tests (INSTALL & SYS COMMIS) |  | 20-Jan-14 16:00 A | 100% | 0 | 0 | 0
23221022b | E | Magnet Box Power Supply Contract Oversight FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 1342 | 3687
23221022c | E | Magnet Box Power Supply Contract Oversight FY14 | 2013-10-01 08:00 | 02-Jun-14 16:00 A | 100% | 0 | 6191 | 18212
23221023C | D | Vend Fab Magnet Box Power Supplies Peg Point #4 - ARC 3, 4, 5, 6 and LAM 1 Delivered and accepted at JLab | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 290775 | 0 | 290775
23221023D | D | Vend Fab Magnet Box Power Supplies Peg Point #4 *** Delivery Incentive Bonus****** | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 80000 | 0 | 80000
23221023Da | D | DeObligation of Vend Fab Magnet Box Power Supplies Peg Point #4 *** Delivery Incentive Bonus **** | 2013-11-18 08:00 | 18-Nov-13 16:00 A | 100% | -80000 | 0 | -80000
23221023F | D | Vend Fab Magnet Box Power Supplies Peg Point #5 - ARC 7, 8, 9, 10, RSEP 8 and XSEP 10 Delivered and accepted at JLab | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 377630 | 0 | 377630
23221023G | D | Vend Fab Magnet Box Power Supplies Peg Point #5 *** Delivery Incentive Bonus****** | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 80000 | 0 | 80000
23221023Ga | D | Partial DeObligation of Vend Fab Magnet Box Power Supplies Peg Point #5 *** Delivery Incentive Bonus****** | 2014-01-20 08:00 | 21-Jan-14 16:00 A | 100% | -40000 | 0 | -40000
23221023H | D | Vend Fab Magnet Box Power Supplies Peg Point #6 - LAM 3, XSEP 8 and RSEP 9 Delivered and accepted at JLab | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 104565 | 0 | 104565
23221023J | D | Vend Fab Magnet Box Power Supplies Peg Point #6 *** Delivery Incentive Bonus****** | 2013-09-03 08:00 | 2014-03-17 | 100% | 40000 | 0 | 40000
23221023K | D | Vend Fab Magnet Box Power Supplies Peg Point #7 Acceptance Test at JLab | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 384488 | 0 | 384488
23221023L | D | Vend Fab Magnet Box Power Supplies Peg Point #8 Delivery of Spares | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 53800 | 0 | 53800
23221024 | U | Receive & Inpect Magnet System Box Power Supplies Part A FY13 (FY14 @ 23221029) | 2013-09-03 08:00 | 2013-11-18 08:43 | 100% | 0 | 0 | 486
23221024a | U | Receive & Inpect Magnet System Box Power Supplies Part B | 2013-11-18 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 2794
23221024b | U | Place/Connect Magnet System Box Power Supplies Part A Procurement | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 435 | 0 | 435
23221024ba | U | Place/Connect Magnet System Box Power Supplies Part B | 2013-11-18 08:00 | 19-May-14 16:00 A | 100% | 0 | 7764 | 90524
23221024c | U | Place/Connect Magnet System Box Power Supplies Part A Labor/Expenses FY13 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 1256 | 15142
23221024d | U | Place/Connect Magnet System Box Power Supplies Part A Labor/Expenses FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 2721 | 32810
23221029 | U | Receive & Inpect Magnet System Box Power Supplies Part A FY14 (FY13 @ 23221024) | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 1054
23221127 | U | Production & Delivery of Arc 1 and Hall A PS | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 70875 | 0 | 70875
23221133 | U | Receive, Inspect and Install Arc 1 and Hall A PS FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 1703
23221133a | U | Receive, Inspect and Install Arc 1 and Hall A PS FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 3427
23221140LOE | E | Proj Admin ongoing FY14 Part A | 2013-10-01 08:00 | 27-Nov-13 16:00 A | 100% | 0 | 0 | 9002
23221140LOEa | E | Proj Admin ongoing FY14 Part B | 2013-12-02 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 37349
23222030 | U | Installation and Testing - Single Channel Shunt Chassis FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 414
23222030a | U | Installation and Testing - Single Channel Shunt Chassis FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 513
23222035 | H | Data Entry / Paperwork - Single Channel Shunt Chassis FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 109
23222035a | H | Data Entry / Paperwork - Single Channel Shunt Chassis FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 135
23222064 | U | Installation - Shunt Resistor Plates Part A FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 260
23222064a | U | Installation - Shunt Resistor Plates Part B | 2014-04-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 411
23222065 | U | Installation - Shunt Resistor Plates Part A FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 564
23222067 | H | Update Machine Documentation - Shunt Resistor Plates Part A FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 223
23222067a | H | Update Machine Documentation - Shunt Resistor Plates Part B | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 352
23222068 | H | Update Machine Documentation - Shunt Resistor Plates Part A FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 483
23222070A | H | Engineering, Drafting and Software - Track Regulator and 30/80 Part A FY13 | 2014-05-19 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 631
23222070Aa | H | Engineering, Drafting and Software - Track Regulator and 30/80 Part B | 2014-05-19 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 1023
23222070Ab | H | Engineering, Drafting and Software - Track Regulator and 30/80 Part A FY14 | 2014-05-19 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 1367
23222075A | H | Oversight (Labor) - Track Regulator and 30/80 | 2014-05-19 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 588
23222075Aa | H | Oversight (Labor) - Track Regulator and 30/80 | 2014-05-19 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 954
23222075Ab | E | Oversight (Labor) - Track Regulator and 30/80 FY14 | 2013-10-01 08:00 | 27-Nov-13 16:00 A | 100% | 0 | 0 | 1275
23222080A | D | Procurement (Parts) - Track Regulator and 30/80 Part A - Procurement | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 12 | 0 | 12
23222080Aa | D | Procurement (Parts) - Track Regulator and 30/80 Part B | 2014-05-19 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 465 | 465
23222080Ab | D | Procurement (Parts) - Track Regulator and 30/80 Part A Expenses FY13 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 287 | 287
23222080Ac | D | Procurement (Parts) - Track Regulator and 30/80 Part A Expenses FY14 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 621 | 621
23222085A | S | Assembly and Testing - Track Regulator and 30/80 Part A FY13 | 2013-09-03 08:00 | 2014-05-19 11:15 | 100% | 0 | 0 | 2024
23222085Aa | S | Assembly and Testing - Track Regulator and 30/80 Part B | 2014-05-19 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 3284
23222085Ab | S | Assembly and Testing - Track Regulator and 30/80 Part A FY14 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 4386
23222095 | S | Installation and Testing - Track Regulator and 30/80 | 2014-05-19 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 8304
23222100A | H | Data Entry/Paperwork - Track Regulator and 30/80 | 2014-05-19 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 3426
23222142 | H | Update Machine Documentation - 75 Amp Shunt Upgrade | 2014-05-19 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 366
23222170 | U | Pull and Modify - 12GEV Shunt Shuffle FY13 | 2013-09-03 08:00 | 20-Jan-14 15:17 A | 100% | 0 | 0 | 2318
23222170a | U | Pull and Modify - 12GEV Shunt Shuffle FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2871
23222175 | U | Clean and Modify Racks - 12GEV Shunts FY13 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 3974
23222175a | U | Clean and Modify Racks - 12GEV Shunts FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 4921
23222180 | U | Reinstall Chassis' in Racks - 12GEV Shunts FY13 | 2013-09-03 08:00 | 2013-10-21 11:51 | 100% | 0 | 0 | 663
23222180a | U | Reinstall Chassis' in Racks - 12GEV Shunts FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 820
23222185 | H | New Screens for 12 GEV Shunts FY13 | 2013-09-03 08:00 | 2013-12-20 08:16 | 100% | 0 | 0 | 1231
23222185a | H | New Screens for 12 GEV Shunts FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1525
23222190 | U | Reconfiguration and Testing - 12GEV Shunts FY13 | 2013-09-03 08:00 | 2014-05-19 11:48 | 100% | 0 | 0 | 3312
23222190a | U | Reconfiguration and Testing - 12GEV Shunts FY14 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 4101
23222195 | H | Update Machine Documentation - 12GEV Shunts FY13 | 2013-09-03 08:00 | 2014-01-20 10:56 | 100% | 0 | 0 | 1609
23222195a | H | Update Machine Documentation - 12GEV Shunts FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 1993
23222220 | U | Installation and Testing - 25 Amp Shunt Upgrade FY13 | 2013-10-01 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 2152
23222220a | U | Installation and Testing - 25 Amp Shunt Upgrade FY14 | 2013-10-01 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 2665
23222230 | H | Drafting (Update Machine Drawings) FY13 | 2013-09-03 08:00 | 2014-05-19 00:56 | 100% | 0 | 0 | 2160
23222230a | H | Drafting (Update Machine Drawings) FY14 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 2675
23223015 | U | Test Trim Rack Hardware (10 ATRIMS) FY13 | 2013-09-23 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 1513
23223015a | U | Test Trim Rack Hardware (10 ATRIMS) FY14 | 2013-09-23 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 1483
23223025 | U | Assemble & Test 10 amp Trim System (10 A TRIMS) FY13 | 2013-09-03 08:00 | 21-Jan-14 16:00 A | 100% | 0 | 0 | 6619
23223025a | U | Assemble & Test 10 amp Trim System (10 A TRIMS) FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 6488
23223051H | D | Vend Fab 20 Amp Trim Power Supplies - Peg Point #7 Fifth Delivery and Acceptance of 30 units | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 77162 | 0 | 77162
23223051J | D | Vend Fab 20 Amp Trim Power Supplies - Peg Point #8 Sixth Delivery and Acceptance of 30 units | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 77162 | 0 | 77162
23223051K | D | Vend Fab 20 Amp Trim Power Supplies - Peg Point #9 Seventh Delivery and Acceptance of 30 units | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 77162 | 0 | 77162
23223051N | D | Vend Fab 20 Amp Trim Power Supplies - Peg Point #10 Eighth Delivery and Acceptance of 30 units | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 77162 | 0 | 77162
23223051P | D | Vend Fab 20 Amp Trim Power Supplies - Peg Point #11 Final Delivery and Acceptance of 20 units | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 51441 | 0 | 51441
23223051Q | D | ** Option** Vend Fab 20 Amp Trim Power Supplies - Peg Point #12 Delivery and Acceptance of 10 units | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 30776 | 0 | 30776
23223052A | U | Receive , Inspect, Test PS (20 A Trims) P1 FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 136 | 730
23223052Aa | U | Receive , Inspect, Test PS (20 A Trims) P1 FY14 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 7 | 38
23223053 | U | Receive , Inspect, Test PS (20 A Trims) P2 Procurement | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 1155 | 0 | 1155
23223053a | U | Receive , Inspect, Test PS (20 A Trims) P3 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 591 | 1555
23223054 | U | Receive , Inspect, Test PS (20 A Trims) P2 Labor/Expenses FY13 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 562 | 1833
23223054a | U | Receive , Inspect, Test PS (20 A Trims) P2 Labor/Expenses FY14 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 1217 | 3970
23223055 | U | Install PS in Racks (20 A Trims) Part A FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1851
23223055A | U | Install PS in Racks (20 A Trims) Part B | 2013-12-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 9586
23223055b | U | Install PS in Racks (20 A Trims) Part A FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1050
23223060 | U | Integration Testing of PS (20 A Trims) Part A | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 1838 | 11472
23223060a | U | Integration Testing of PS (20 A Trims) Part B | 2013-12-19 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 1410 | 8800
23223110 | D | SRCC 20 Amp PS PS Procurement | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 15380 | 0 | 15380
23223125 | S | SRCC System Q.A., Testing and Documentation Part A FY13 | 2014-05-19 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 2765
23223125a | S | SRCC System Q.A., Testing and Documentation Part B | 2014-05-19 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 606
23223125b | S | SRCC System Q.A., Testing and Documentation Part A FY14 | 2014-05-19 08:00 | 2014-07-21 08:00 | 100% | 0 | 0 | 5992
23224003LOE | E | Installation Coordination FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 2348
23224045A | U | Pull/Terminate Box PS Load Cable (Installtn) East Arc, S/R,BSY and Extraction - Procurement | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 74 | 0 | 74
23224045Aa | U | Pull/Terminate Box PS Load Cable (Installtn) East Arc, S/R,BSY and Extraction Labor/Expenses FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 213 | 1087
23224045Ab | U | Pull/Terminate Box PS Load Cable (Installtn) East Arc, S/R,BSY and Extraction Labor/Expenses FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 296 | 1514
23224055 | U | Connect Arc & Hall Mag Load & Klixon Cables (Installtn) FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 2651
23224055a | U | Connect Arc & Hall Mag Load & Klixon Cables (Installtn) FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 3692
23224085A | U | Pull/Terminate Trim Mag (Installtn) East Arc , S/R and BSY FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 2082
23224085Aa | U | Pull/Terminate Trim Mag (Installtn) East Arc , S/R and BSY FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 2363
23224087 | S | BSY Serv. Bldg Infrastructure Installation- Tray, Power, Water, Controls FY13 | 2013-09-03 08:00 | 2014-03-14 10:08 | 100% | 0 | 3571 | 9721
23224087a | S | BSY Serv. Bldg Infrastructure Installation- Tray, Power, Water, Controls FY14 | 2013-09-03 08:00 | 14-Mar-14 16:00 A | 100% | 0 | 4054 | 11034
23224100 | S | Update/Install/Test Mag Controls Software (Installtn) FY13 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 6356
23224100a | S | Update/Install/Test Mag Controls Software (Installtn) FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 8199
2331.1005 | H | Install CHL Cold Box Transfer Line to Linac Labor | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 1734 | 3066 | 4800
23411087N | D | Vend Fab Septa (S/R Dipoles) Peg Point #5 Delivery and Acceptance of ZA Spare Coil Set | 2013-09-03 08:00 | 2013-11-18 | 100% | 21500 | 0 | 21500
23411087Q | D | Vend Fab Septa (S/R Dipoles) Peg Point #7 Delivery and Acceptance of Quantity 2 ZB Coil Sets | 2013-09-03 08:00 | 2013-11-18 | 100% | 34500 | 0 | 34500
23411090M | M | Delivery Complete for Septa (S/R DIPOLES) |  | 2013-11-18 | 100% | 0 | 0 | 0
23411145 | H | Mag Measurement of Septa's (S/R Dipoles) FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 3308
23411145a | H | Mag Measurement of Septa's (S/R Dipoles) FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 4172
23417065 | H | WR - Install magnets & girders | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 7471
23417115 | H | WS - Install magnets and girders | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 9625
23417120 | S | WS - Final align | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 13506
23417130 | S | TR - Install stands | 2013-09-03 08:00 | 2013-11-18 | 100% | 0 | 0 | 17957
23417140 | S | TR - Install magnets and girders FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 39032
23417140a | S | TR - Install magnets and girders FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2014
23417145 | S | TR - Final align FY13 | 2013-10-21 08:00 | 2013-11-18 | 100% | 0 | 0 | 581
23417145a | S | TR - Final align FY14 | 2013-10-21 08:00 | 2013-11-18 | 100% | 0 | 0 | 12598
23417150 | H | Alignment complete | 2013-11-11 | 2013-11-18 | 100% | 0 | 0 | 4223
23417165 | D | Procure S/R plumbing materials | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 12255 | 12255
23417170 | D | Procure S/R Vacuum materials | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 9831 | 0 | 9831
23427016LOE | E | Installation Team Engineering Support FY13 (12 Month Down) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 9073
23427016LOEa | E | Installation Team Engineering Support FY14 (12 Month Down) | 2013-10-01 08:00 | 15-Nov-13 16:00 A | 100% | 0 | 0 | 15918
23427040 | S | Hall A - Install FY13 | 2013-09-03 08:00 | 20-Jan-14 14:11 A | 100% | 0 | 0 | 13196
23427040a | S | Hall A - Install FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 6127
23427047 | S | Hall B - Install FY13 | 2013-10-01 08:00 | 2014-03-17 | 100% | 0 | 0 | 16808
23427047a | S | Hall B - Install FY14 | 2013-10-01 08:00 | 2014-03-17 | 100% | 0 | 0 | 26015
23427052 | S | Hall C - Upstairs FY13 | 2013-09-03 08:00 | 2014-01-20 00:18 | 100% | 0 | 0 | 7560
23427052a | S | Hall C - Upstairs FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2730
23427057 | S | Hall C - Install | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 35693
23427062 | S | Material Handling costs (Vehicle) | 2013-09-03 08:00 | 2013-11-18 | 100% | 18239 | 0 | 18239
23427067 | D | Material Handling costs DeObligation | 2013-10-21 08:00 | 28-Oct-13 16:00 A | 100% | -10319 | 0 | -10319
23447010 | S | 45 MeV Dump - Re-install | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 16371
23454055 | S | 100 kW dump Modifications (ARC10/H-D Stands) Procurement | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 2999 | 0 | 2999
23454055a | S | 100 kW dump Modifications (ARC10/H-D Stands) Labor/Expenses FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 7438 | 11410
23454055b | S | 100 kW dump Modifications (ARC10/H-D Stands) Labor/Expenses FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 6524 | 10008
23458040 | S | Arc 10 Installation Completion FY13 | 2013-09-03 08:00 | 2013-12-20 00:59 | 100% | 0 | 0 | 21274
23458040a | S | Arc 10 Installation Completion FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 10976
23458045 | S | Hall D - Tagger dump installation FY13 | 2014-01-03 08:00 | 2014-03-17 | 100% | 0 | 0 | 9842
23458045a | S | Hall D - Tagger dump installation FY14 | 2014-01-03 08:00 | 2014-03-17 | 100% | 0 | 0 | 43162
23458060 | S | Hall D - Install magnets and girders FY13 | 2013-09-03 08:00 | 2014-03-17 | 100% | 0 | 0 | 6313
23458060a | S | Hall D - Install magnets and girders FY14 | 2013-09-03 08:00 | 2014-03-17 | 100% | 0 | 0 | 977
23458065 | H | Hall D - Final align FY13 | 2013-10-07 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 5321
23458065a | H | Hall D - Final align FY14 | 2013-10-07 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1373
23463035a | H | Extraction - Upstairs | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1883
23463045 | S | Extraction - Install magnets and girders | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 27554
23463050 | S | Extraction - Final align FY13 | 2013-09-16 08:00 | 2013-10-21 10:18 | 100% | 0 | 0 | 6395
23463050a | S | Extraction - Final align FY14 | 2013-09-16 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 9238
23611014B | H | Procurement Labor - SPM BPMs ELECTRONICS FY13 | 2013-09-03 08:00 | 2013-12-20 10:47 | 100% | 0 | 0 | 3055
23611014Ba | H | Procurement Labor - SPM BPMs ELECTRONICS FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 3625
23611014D | D | Prcrmnt - SPM BPMs ELECTRONICS | 2013-09-16 08:00 | 2014-03-17 | 100% | 36269 | 0 | 36269
23611014D5 | D | Prcrmnt - SPM BPMs ELECTRONICS (Previously Obligated) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 13621 | 0 | 13621
23611015A | U | Labor - Fab & Assy - SPM BPMs ELECTRONICS | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 48653
23611015B | D | Procrmnt - Fab/Assy & Testing - SPM BPMs ELECTRONICS | 2013-09-09 08:00 | 2014-03-17 | 100% | 55903 | 0 | 55903
23611025 | H | System Installation - Electronics SPM BPMs Part A | 2013-09-09 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 2272
23611025a | H | System Installation - Electronics SPM BPMs Part B | 2014-01-21 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 5897
23611025b | U | System Installation Contract Labor - Electronics SPM BPMs | 2013-09-09 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 17303 | 17303
23611025c | H | System Installation Software Support - Electronics SPM BPMs Part A | 2013-09-09 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 5365
23611025ca | S | System Installation Software Support - Electronics SPM BPMs Part B | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 18721
23611026b | H | Hook-up & Check-out Arc 10 BPMs | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 6342
23611027 | H | Hook-up & Check-out H-D B/L BPMs | 2013-09-09 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 7946
23611035M | M | SPM BPMs Comp |  | 19-May-14 16:00 A | 100% | 0 | 0 | 0
23611036 | S | First Article Cavities - nA BPM Sys | 2014-01-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 40235
23611037 | U | Procurement Labor for Cavities - nA BPM Sys | 2014-03-10 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 6413
23611037a | D | Procurement Cavities - nA BPM Sys | 2014-04-01 08:00 | 22-Sep-14 16:00 A | 100% | 180871 | 0 | 180871
23611038 | U | First Article Unit RF Receiver - nA BPM Sys | 2014-04-01 08:00 | 15-Sep-14 16:00 A | 100% | 0 | 0 | 18407
23611038a | U | First Article Unit Digital IF - nA BPM Sys | 2014-04-01 08:00 | 15-Sep-14 16:00 A | 100% | 0 | 0 | 12346
23611038b | U | First Article Enclosure nA Receiver - nA BPM Sys | 2014-04-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 11180
23611039 | D | Procurement Labor Electronics - nA BPM Sys | 2014-04-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 9903
23611040 | D | Procurements Electronics - nA BPM Sys | 2014-03-17 08:00 | 22-Sep-14 16:00 A | 100% | 35751 | 0 | 35751
23611045 | U | Assembly Electronics Labor - nA BPM Sys FY14 | 2014-05-05 08:00 | 2014-09-22 09:39 | 100% | 0 | 0 | 16513
23611045A | U | Assembly Electronics Labor - nA BPM Sys FY15 | 2014-05-05 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 4719
23611050 | D | Assembly & Testing Procurement - nA BPM Sys | 2014-05-05 08:00 | 22-Sep-14 16:00 A | 100% | 7241 | 0 | 7241
23611055 | U | System Installation Electronics - nA BPM Sytem (BPM) FY14 | 2014-05-19 08:00 | 22-Sep-14 15:48 A | 100% | 0 | 0 | 5246
23611055a | D | System Installation Electronics Contract Labor - nA BPM Sytem (BPM) | 2014-07-07 08:00 | 22-Sep-14 16:00 A | 100% | 14482 | 0 | 14482
23611055B | U | System Installation Electronics - nA BPM Sytem (BPM) FY15 | 2014-05-19 08:00 | 15-Sep-14 16:00 A | 100% | 0 | 0 | 2830
23611060 | S | Software support - nA BPMs | 2014-06-02 08:00 | 15-Sep-14 16:00 A | 100% | 0 | 0 | 38009
23611065a | H | System Documentation - BPMs FY13 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2867
23611065a5 | S | System Documentation - nA BPMs FY14 | 2014-05-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 8362
23611065a5a | S | System Documentation - nA BPMs FY15 | 2014-05-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 1108
23611065aa | H | System Documentation - BPMs FY14 | 2013-09-03 08:00 | 2014-03-17 | 100% | 0 | 0 | 4141
23611065M | M | nA BPMs Comp |  | 22-Sep-14 16:00 A | 100% | 0 | 0 | 0
23611070 | H | First Article Unit - Power Supplies/PC104/Timing Modules SPM BPMs | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 0 | 0 | 7101
23611075 | H | Procurement Labor - Power Supplies/PC104/Timing Modules SPM BPMs FY13 | 2013-09-03 08:00 | 2013-12-20 08:21 | 100% | 0 | 0 | 1469
23611075a | H | Procurement Labor - Power Supplies/PC104/Timing Modules SPM BPMs FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 3184
23611080 | D | Procurement - Power Supplies/PC104/Timing Modules SPM BPMs | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 20889 | 0 | 20889
23611085 | S | Assembly Labor - Power Supplies/PC104/Timing Modules SPM BPMs Part A | 2013-09-16 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 15623
23611085a | S | Assembly Labor - Power Supplies/PC104/Timing Modules SPM BPMs Part b | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 12284
23611090 | D | Assembly Procurement - Power Supplies/PC104/Timing Modules SPM BPMs | 2013-09-16 08:00 | 2014-03-17 | 100% | 1704 | 0 | 1704
23611095 | H | Installation Labor - Power Supplies/PC104/Timing Modules SPM BPMs Part A | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 1054
23611095a | H | Installation Labor - Power Supplies/PC104/Timing Modules SPM BPMs Part B | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 829
23611100 | D | Installation Procurement - Power Supplies/PC104/Timing Modules SPM BPMs | 2014-01-03 08:00 | 21-Apr-14 16:00 A | 100% | 1917 | 0 | 1917
23611913LOE | E | FY13 Mngmnt Effort for BPMs | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 782
23611914LOE | E | FY14 Mngmnt Effort for BPMs Part A | 2013-10-01 08:00 | 27-Nov-13 16:00 A | 100% | 0 | 0 | 1133
23611914LOEa | E | FY14 Mngmnt Effort for BPMs Part B | 2013-12-02 | 26-Aug-14 16:00 A | 100% | 0 | 0 | 4148
23612030 | S | Harp Sys Implementn Labor | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 2700 | 10722
23612035 | H | Harp Systems Software Implementn & Cmmssng | 2013-09-03 08:00 | 28-Sep-13 16:00 A | 100% | 0 | 0 | 8394
23612035M | M | Harp Sys Comp |  | 28-Sep-13 16:00 A | 100% | 0 | 0 | 0
23612913LOE | E | FY13 Mngmnt Effort for Harps | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 195
23613025a | H | Implementn of Viewer Syss Labor | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 3709
23613030 | S | Software Implementn Viewer Systems | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 16298
23613035M | M | Viewers Sys Comp |  | 20-Jan-14 16:00 A | 100% | 0 | 0 | 0
23613050 | H | SLM System Controls | 2013-09-16 08:00 | 21-Oct-13 16:00 A | 100% | 8771 | 0 | 10087
23613913LOE | E | FY13 Mngmnt Effort for Viewer Syss | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 195
23614014 | H | FFB Sys Procurement Prep | 2014-05-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 2684 | 4471
23614014A | D | FFB Sys Prcrmnts | 2014-07-01 08:00 | 22-Sep-14 13:40 A | 100% | 50215 | 916 | 51741
23614015 | S | FFB Sys Fabrication & Assy | 2014-08-04 08:00 | 17-Sep-14 16:00 A | 100% | 1059 | 4374 | 27065
23614020 | S | FFB Sys Component & VME Testing | 2014-08-12 08:00 | 17-Sep-14 16:00 A | 100% | 3283 | 0 | 11587
23614025 | H | FFB Sys Hardware Implementn | 2014-08-01 08:00 | 15-Sep-14 16:00 A | 100% | 0 | 4128 | 7323
23614030 | S | FFB Software Implementn | 2014-09-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 18757
23614035 | H | FFB Slow Lock Implementn | 2014-09-08 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 4751
23614040 | H | FFB Slow Lock & FFB Cmmssng | 2014-09-09 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 6827
23614045M | M | FFB Sys Comp |  | 22-Sep-14 16:00 A | 100% | 0 | 0 | 0
23614050LOE | E | FY14 Mngmnt Effort for FFB | 2014-03-03 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 1278
2363015aa | S | Update Hi-Level Applications Labor | 2013-09-03 08:00 | 2013-10-21 | 100% | 0 | 0 | 20056
2363913LOE | E | FY13 CSS Sys Mngmnt Effort | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 225
23641020 | S | Test/QA FSD Hardware (MPS) | 2013-09-03 08:00 | 27-Sep-13 16:00 A | 100% | 0 | 0 | 1639
23641025 | S | Install FSD Wire & Cable (MPS) FY13 | 2013-09-16 08:00 | 2014-03-14 11:32 | 100% | 0 | 0 | 2205
23641025a | S | Install FSD Wire & Cable (MPS) FY14 | 2013-09-16 08:00 | 14-Mar-14 16:00 A | 100% | 0 | 0 | 12892
23641030 | S | Install/Test FSD Hardware (MPS) FY13 | 2013-11-01 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 2506
23641030a | S | Install/Test FSD Hardware for RF Installation(MPS) FY13 | 2013-09-16 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1531
23641030aa | S | Install/Test FSD Hardware for RF Installation(MPS) FY14 | 2013-09-16 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 3305
23641030b | S | Install/Test FSD Hardware (MPS) FY14 | 2013-11-01 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 4783
23641040 | S | Develop/Install/Test FSD Software (MPS) FY13 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1752
23641040a | S | Develop/Install/Test FSD Software (MPS) FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 3781
23641045M | M | FSD Sys Comp (MPS) |  | 2014-05-02 08:00 | 100% | 0 | 0 | 0
23641055 | S | Test/QA BLM Hardware (MPS) FY13 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2272
23641055a | S | Test/QA BLM Hardware (MPS) FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 586
23641060 | S | Install BLM Wire & Cable (MPS) FY13 | 2013-10-08 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2054
23641060a | S | Install BLM Wire & Cable (MPS) FY14 | 2013-10-08 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 3920
23641065 | S | Install BLM Hardware (MPS) FY13 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1772
23641065a | S | Install BLM Hardware (MPS) FY14 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 3382
23641075 | S | Develop/Install/Test BLM Software (MPS) | 2013-12-10 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 5590
23641080M | M | BLM Sys Comp (MPS) |  | 2014-05-02 08:00 | 100% | 0 | 0 | 0
23641085 | S | Proc Tagger/Hall D Beam Loss Monitoring Hardware (MPS) | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 8000 | 0 | 8000
23641087 | S | Install BLM Wire & Cable (MPS) Tagger Hall D FY13 | 2013-10-08 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 5655
23641087a | S | Install BLM Wire & Cable (MPS) Tagger Hall D FY14 | 2013-10-08 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 18964
23641090 | S | Test/QA Tagger/Hall D Beam Loss Monitoring Hardware (MPS) FY13 | 2013-11-12 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 1249
23641090a | S | Test/QA Tagger/Hall D Beam Loss Monitoring Hardware (MPS) FY14 | 2013-11-12 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 4123
23641095 | S | Install/Test Tagger/Hall D Beam Loss Monitoring Sys (MPS) | 2013-10-11 | 15-Mar-14 16:00 A | 100% | 0 | 0 | 4322
23641100 | S | Rework FSD Cards | 2013-10-01 | 20-Jan-14 16:00 A | 100% | 4128 | 0 | 4128
23641100M | M | Beam Loss Ion Chamb Sys Comp (MPS) |  | 18-Aug-14 16:00 A | 100% | 0 | 0 | 0
23641913LOE | E | FY13 Mngmnt & Elect Dsgn Supprt Effort for MPS | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 607
23641914LOE | E | FY14 Mngmnt & Elect Dsgn Supprt Effort for MPS | 2013-10-01 08:00 | 02-Jun-14 16:00 A | 100% | 0 | 0 | 4670
23642005 | S | Develop/Install/Test BELS Software | 2013-10-01 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 10440
23642014 | S | Proc BELS Hardware | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 10663 | 0 | 11865
23642015 | S | Test/QA BELS Compnts | 2013-11-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 10524
23642019 | S | Proc Remaining BELS Hardware | 2013-11-01 08:00 | 20-Jan-14 16:00 A | 100% | 3096 | 0 | 3096
23642020 | S | Install BELS Hardware | 2014-02-10 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 5160 | 19517
23642030M | M | BELS Sys Comp |  | 18-Aug-14 16:00 A | 100% | 0 | 0 | 0
23642913LOE | E | FY13 Mngmnt & Elect Dsgn Supprt Effort for BELS | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 489
23642914LOE | E | FY14 Mngmnt & Elect Dsgn Supprt Effort for BELS | 2013-10-01 08:00 | 02-Jun-14 16:00 A | 100% | 0 | 0 | 3766
23643020b | S | Proc Remaining Cable and PLC Systems | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 4279 | 0 | 4279
23643045 | S | Install Linac Cable Conduit, Infrastructure (PSS) FY13 | 2013-09-03 08:00 | 17-Feb-14 13:03 A | 100% | 0 | 2141 | 4797
23643045a | S | Install Linac Cable Conduit, Infrastructure (PSS) FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 1325 | 2970
23643065 | S | Fab & Test Beam Transport Monitor (PSS) | 2013-11-01 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 3195
23643070 | S | Install Beam Transport Monitor (PSS) | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 23954
23643070a | S | Install Beam Transport Monitor - EPICS Interface (PSS) | 2013-12-16 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 11390
23643100 | S | Fab & Test Beam Stoppers & Diffusers (PSS) FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 8062 | 21794
23643100a | S | Fab & Test Beam Stoppers & Diffusers (PSS) FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 1664 | 4498
23643102 | S | Update Stopper/Diffuser Software (PSS) | 2013-11-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2795
23643105 | S | Install Beam Stoppers & Diffusers (PSS) FY13 | 2013-10-17 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 1223
23643105a | S | Install Beam Stoppers & Diffusers (PSS) FY14 | 2013-10-17 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2524
23643115 | S | Test/QA PSS Beam Current Monitor Compnts | 2013-12-02 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 1276
23643117 | S | Proc BCM Cavity Components- (PSS) - Procurement | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 6752 | 0 | 6752
23643117a | S | Proc BCM Cavity Components- (PSS) Expenses FY13 | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 0 | 465 | 465
23643117b | S | Proc BCM Cavity Components- (PSS) Expenses FY14 | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 0 | 552 | 552
23643120 | S | Install & Test PSS Beam Current Monitor | 2013-11-01 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 16217
23643140 | S | Upgrade MCC Console (PSS) FY13 | 2013-09-03 08:00 | 21-Apr-14 14:19 A | 100% | 0 | 0 | 4019
23643140a | S | Upgrade MCC Console (PSS) FY14 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 2281
23643145 | S | Install & Test Tagger Access Control Sys (PSS) FY13 | 2013-09-16 08:00 | 21-Apr-14 15:48 A | 100% | 0 | 0 | 2949
23643145a | S | Install & Test Tagger Access Control Sys (PSS) FY14 | 2013-09-16 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 11617
23643145b | S | Install & Test Hall D-MCC Access Control Sys (PSS) FY13 | 2013-09-16 08:00 | 2014-04-21 08:30 | 100% | 0 | 0 | 2791
23643145ba | S | Install & Test Hall D-MCC Access Control Sys (PSS) FY14 | 2013-09-16 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 13875
23643150 | S | Proc Equipment for H-A, B, C Upgrades (PSS) | 2014-02-03 08:00 | 21-Apr-14 16:00 A | 100% | 7473 | 0 | 7473
23643155 | S | Install & Test H-A, B, C Upgrades (PSS) | 2014-02-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 8644
23643160 | S | Create & Simulate PSS Logic Programs | 2013-11-20 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 9016
23643165 | S | Install & Test PSS Logic Programs | 2014-04-01 08:00 | 07-Apr-14 16:00 A | 100% | 0 | 0 | 11458
23643170M | M | Linac PSS Systems Comp |  | 30-Sep-13 16:00 A | 100% | 0 | 0 | 0
23643175M | M | Halls A, B, C PSS Systems Comp |  | 21-Apr-14 16:00 A | 100% | 0 | 0 | 0
23643180M | M | Tagger Bldng PSS Systems Comp |  | 21-Apr-14 16:00 A | 100% | 0 | 0 | 0
23643185M | M | H-D PSS Systems Comp |  | 21-Apr-14 16:00 A | 100% | 0 | 0 | 0
23643205 | S | Install Public Address Sys (PSS) | 2013-11-04 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 4209
23643280 | S | EPICS Interface Development | 2013-11-04 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 11390
23643350 | S | PSS PLC Communications - Labor FY13 | 2013-09-03 08:00 | 2014-04-21 00:35 | 100% | 0 | 0 | 1491
23643350a | S | PSS PLC Communications - Labor FY14 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 5875
23643355 | S | PSS PLC Communications - Procurements | 2013-10-03 | 20-Dec-13 16:00 A | 100% | 9803 | 0 | 9803
23643360 | S | C-100 RF Commissioning PSS Support | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 2998
23643913LOE | E | FY13 Mngmnt & Supprt Effort for PSS | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 3458
23643914LOE | E | FY14 Mngmnt & Supprt Effort for PSS | 2013-10-01 08:00 | 02-Jun-14 16:00 A | 100% | 0 | 0 | 26761
2365014 | D | HD Dump Sys Prcrmnts | 2013-09-16 08:00 | 21-Oct-13 16:00 A | 100% | 6191 | 0 | 7695
2365015 | H | HD Dump Sys Fab & Assy | 2013-10-01 08:00 | 2014-03-17 | 100% | 2502 | 516 | 10537
2365020 | H | HD Dump Component Testing | 2014-02-04 08:00 | 2014-03-17 | 100% | 0 | 0 | 5904
2365025 | S | HD Dump Sys Implementn | 2014-04-01 08:00 | 19-May-14 16:00 A | 100% | 1744 | 3236 | 11749
2365030 | H | HD Dump Software Implementn & Cmmssng | 2014-04-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 8595
2365035M | M | HD Dump Comp |  | 19-May-14 16:00 A | 100% | 0 | 0 | 0
2365045 | H | Insertable Dump Sys Fab & Assy | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 919 | 254 | 4288
2365050 | H | Insertable Dump Component Testing | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1504
2365055 | H | Insertable Dump Sys Implementn | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1128
2365060 | Z | Insertable Dump Software Implementn & Cmmssng | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 0
2365065M | M | Insertable Dump Comp |  | 23-Sep-13 16:00 A | 100% | 0 | 0 | 0
2365913LOE | E | FY13 Mngmnt Effort for Dump | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 195
2366050a | H | ARC Vac Controls Software Implementn | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 5958
2366051 | S | ARC Vac Controls Hardware Implementation & Testing | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 10930
2366055M | M | ARC Vacuum Controls Sys Comp |  | 21-Apr-14 16:00 A | 100% | 0 | 0 | 0
2367025a | S | Mag Instrmenttn Software Implementn & Cmmssng FY13 | 2013-09-03 08:00 | 17-Feb-14 14:32 A | 100% | 0 | 0 | 2258
2367025aa | S | Mag Instrmenttn Software Implementn & Cmmssng FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 9668
2367030 | H | Magnet Communication New I/O IP design - Labor FY13 | 2013-09-03 08:00 | 21-Oct-13 13:04 A | 100% | 0 | 0 | 425
2367030a | H | Magnet Communication New I/O IP design - Labor FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 702
2367035 | D | Magnet Communication New I/O IP design - Proc. | 2013-09-16 08:00 | 17-Feb-14 16:00 A | 100% | 3405 | 0 | 4600
2367040 | H | Magnet Communication New I/O IP Fabrication | 2013-09-16 08:00 | 20-Jan-14 16:00 A | 100% | 2477 | 0 | 9243
2367045 | H | Magnet Communication New I/O IP Testing | 2013-09-16 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 4690
2367050 | H | Magnet Communication New I/O IP Installation | 2013-09-16 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 4690
2367055 | H | Magnet Communication New I/O IP Software -Labor | 2013-09-16 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 6972
24152015 | S | Proc motion sys, Stands & Beam Line (COMP POLAR) Re-Baseline Obligation Split | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 12 | 0 | 12
24152020 | S | Proc motion sys, Stands & Beam Line (COMP POLAR) | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 3846 | 0 | 3846
24152025 | S | Install & Test (COMP POLAR) | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 5657
24153020 | Z | Install Rebuilt 9th Dipole in Shed (MAPPER) | 2013-10-01 08:00 | 14-Oct-13 16:00 A | 100% | 0 | 0 | 0
24211090 | D | Wang Torus Settlement | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 217518 | 0 | 217518
24211095 | D | Wang Torus Settlement Final | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 421264 | 0 | 421264
24212000 | D | Wang Solenoid Settlement | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 36925 | 0 | 36925
24212005 | D | Wang Solenoid Settlement Final | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 286076 | 0 | 286076
242211013E | E | SVT-FY13 Travel | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 4503 | 4503
242211014E | E | SVT-FY14 Travel | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 34259 | 34259
242211130 | E | HBI - SVT Engineering and Construction Oversight FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 7517
242211140 | E | HBI - SVT Engineering and Construction Oversight FY14 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 71391
242211145 | E | HBI - SVT Engineering and Construction Oversight FY15 | 2014-10-01 08:00 | 31-Oct-14 16:00 A | 100% | 0 | 0 | 12413
242211160t | D | FNAL Construction and test (Jlab/FNAL) of R1-R3 production modules (60 modules) Part A | 2013-09-03 08:00 | 16-Dec-13 16:00 A | 100% | 22828 | 0 | 22828
242211160u | D | FNAL Construction and test (Jlab/FNAL) of R1-R3 production modules (60 modules) Part B | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 222139 | 0 | 222139
242211160w | D | FNAL Construction and test (Jlab/FNAL) of R4 production 11 modules | 2013-09-03 08:00 | 2015-01-30 16:00 | 72% | 46506 | 0 | 46506
242211160w5 | D | FNAL Construction and test (Jlab/FNAL) of R4 production 11 modules | 2014-06-02 08:00 | 2015-01-30 16:00 | 72% | 63582 | 0 | 63582
242211335 | D | MECH GRP - Modules: asssembly table, mounting, and alignment fixture procurement - Proc | 2013-09-03 08:00 | 10-Sep-13 16:00 A | 100% | 1290 | 0 | 1290
242211340 | H | MECH GRP - Modules: assembly table, mounting, and alignment fixture construction - Labor | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1893
242211360 | U | HBI - Electronics HFCB R1-R4 - Proc | 2013-09-03 08:00 | 2014-11-24 16:00 | 65% | 101920 | 0 | 101920
242211361 | U | HBI - Electronics HFCB R1-R4 - Proc First Article 6 cables | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 7350 | 0 | 7350
242211365a | U | HBI - Cable assemblies: HV, LV, and data - Proc | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 80925 | 0 | 80925
242211367 | U | HBI - Cable assemblies: Pulser | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 19640 | 0 | 19640
242211370 | S | HBI - Cable assemblies: HV, LV, and data fabrication and testing R1-R4 - Labor FY13 | 2013-09-03 08:00 | 2014-01-21 08:00 | 100% | 0 | 0 | 1001
242211370a | S | HBI - Cable assemblies: HV, LV, and data fabrication and testing R1-R4 - Labor FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 8365
242211380 | H | HBI - Sloco: HV, LV, PS distribution system (fabricate) - Labor | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1410
242211390 | D | HBI - Sloco: Slow controls for monitoring and charge calibration system: component procurement - Proc | 2013-10-01 08:00 | 2014-03-24 | 100% | 67644 | 0 | 67644
242211395 | S | HBI - Sloco:Slow controls for monitoring and charge calib system: assemble, test, and debug ADC's- Labor | 2014-02-10 08:00 | 2014-12-05 16:00 | 72% | 0 | 0 | 19539
242211400a | S | HBI - Sloco:Slow controls for monitor and charge calib system: develop sloco software (1/2) - Labor | 2014-01-07 08:00 | 2014-12-05 16:00 | 16% | 0 | 0 | 28937
242211405 | S | MECH GRP - Faraday cage protective enclosure system Manufacturing Drawings - Labor | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 925 | 3911
242211405a | D | Obligated Procured Labor for Activity 242211405 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 1792 | 0 | 1792
242211410 | H | MECH GRP - Faraday cage protective enclosure system specifications and procurement prep - Labor FY13 | 2013-10-01 08:00 | 2014-03-14 | 100% | 0 | 0 | 109
242211410a | H | MECH GRP - Faraday cage protective enclosure system specifications and procurement prep - Labor FY14 | 2013-10-01 08:00 | 2014-03-14 | 100% | 0 | 0 | 485
242211415 | D | MECH GRP - Faraday cage protective enclosure system - Proc | 2014-03-13 | 20-Oct-14 16:00 A | 100% | 12973 | 0 | 12973
242211445 | S | HBI - DAq-VSCM develop program and test - Labor | 2013-10-15 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 18031
242211460 | D | MECH GRP - Cooling system: procurement - proc | 2013-10-01 08:00 | 16-Dec-13 16:00 A | 100% | 8158 | 0 | 8158
242211465 | S | MECH GRP - Support, cooling, coldplate, and alignment of stave: manufacturing Drawings - Labor | 2013-09-03 08:00 | 20-Sep-13 16:00 A | 100% | 0 | 4480 | 5927
242211470 | H | MECH GRP - Support, cooling, coldplate, and alignment of stave: procurement prep - Labor | 2013-09-16 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 579
242211475 | D | MECH GRP - Support, cooling, coldplate, and alignment of stave - Proc | 2013-12-02 08:00 | 2014-03-24 | 100% | 26129 | 0 | 26129
242211480 | S | MECH GRP - Support, cooling, coldplate, and alignment of stave Faraday Cage inner: construct and assemble - Labor | 2014-04-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 1849 | 16193
242211485 | S | MECH GRP - Mounting and aligning on support structure in lab, R1-R3 - Labor | 2014-05-12 08:00 | 2014-11-10 16:00 | 50% | 0 | 1849 | 27550
242211490 | U | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY13 | 2013-09-03 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 10580
242211490a | U | HBI - Module R1-R4 : quality assurance, test, and burn-in at FNAL - Labor FY14 | 2013-09-03 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 134831
242211495M | M | End of BST R1-R4 Production |  | 2014-12-15 16:00 | 0% | 0 | 0 | 0
242211515 | U | HBI - Electronics: HFCB Population - Proc Part A | 2013-09-03 08:00 | 2014-11-26 16:00 | 59% | 24520 | 0 | 24520
242211520 | U | HBI - Electronics: HFCB Population - Proc Part B | 2014-02-03 08:00 | 2014-12-01 16:00 | 59% | 34620 | 0 | 34620
242211530 | D | HBI - Compunetics HFCB Bend Test - Proc | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 200 | 0 | 200
242211545 | S | MECH GRP - Mounting and aligning on support structure in lab, R4 - Labor | 2015-03-02 08:00 | 2015-03-13 16:00 | 0% | 0 | 1849 | 16193
242211600 | S | HBI - Full system R4, test and burn-in in Cleanroom EEL 121 - Labor | 2015-04-13 08:00 | 2015-04-27 16:00 | 0% | 0 | 0 | 26128
242211605 | D | HBI - Bus cable PCB production - Proc | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 22550 | 0 | 22550
242211610 | H | HBI - Bus cable PCB receive and Test - Labor FY13 | 2013-09-03 08:00 | 18-Aug-14 14:37 A | 100% | 0 | 0 | 437
242211610a | H | HBI - Bus cable PCB receive and Test - Labor FY14 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 1428
242211615 | S | HBI - Full system R1-R3, test and burn-in in Cleanroom EEL 121 - Labor | 2014-07-01 08:00 | 2015-02-27 16:00 | 60% | 0 | 0 | 48337
242211620 | D | FNAL Tooling | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 6259 | 0 | 6259
242211635 | D | HBI - LV cards - Proc | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 50584 | 0 | 50584
242211645 | U | HBI - Module Reception tests at JLAB - Labor FY14 | 2014-01-03 08:00 | 2015-01-30 16:00 | 72% | 0 | 0 | 30334
242211645A | U | HBI - Module Reception tests at JLAB - Labor FY15 | 2014-01-03 08:00 | 2015-01-30 16:00 | 72% | 0 | 0 | 3600
242211655 | U | HBI - VXS crate - Proc | 2013-10-01 08:00 | 21-Apr-14 16:00 A | 100% | 11348 | 0 | 11348
242211660 | D | INFRA STR - Backup Environmental and power system for SVT Clean Room - Proc | 2014-06-02 08:00 | 16-Jun-14 16:00 A | 100% | 6448 | 0 | 6448
242211670 | D | INFRA STR - Integrated Humidity Reduction System for SVT Control room - Proc | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 4662 | 0 | 4662
242211675 | D | INFRA STR - Integrated Humidity Reduction System for SVT Control room - Proc | 2014-02-10 08:00 | 21-Jul-14 16:00 A | 100% | 8777 | 0 | 8777
242211680 | S | MECH GRP - Full system test Integration of SVT R3/R4 - Labor | 2015-02-03 08:00 | 2015-04-14 16:00 | 0% | 0 | 0 | 40041
242211685 | S | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: manufacturing Drawings - Labor | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 11095 | 18961
242211690 | H | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: procurement prep - Labor | 2014-02-17 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 597
242211695 | D | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: - Proc | 2014-05-12 08:00 | 2014-11-20 16:00 | 50% | 18378 | 0 | 18378
242211700 | S | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: construct & assemble - Labor | 2014-11-21 08:00 | 2014-12-05 16:00 | 0% | 0 | 1849 | 12407
242211705 | H | MECH GRP - Tooling for assembly and repairs: manufacturing Drawings - Labor/Expenses FY13 | 2013-09-03 08:00 | 2013-10-21 08:14 | 100% | 0 | 2312 | 3246
242211705a | H | MECH GRP - Tooling for assembly and repairs: manufacturing Drawings - Labor/Expenses FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 1312 | 1842
242211710 | H | MECH GRP - Tooling for assembly and repairs: procurement prep - Labor FY13 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 269
242211710a | H | MECH GRP - Tooling for assembly and repairs: procurement prep - Labor FY14 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 320
242211715 | D | MECH GRP - Tooling for assembly and repairs - Proc | 2013-12-02 08:00 | 16-Jun-14 16:00 A | 100% | 8309 | 0 | 8309
242211720 | S | MECH GRP - Tooling for assembly and repairs construct and assemble - Labor | 2014-02-10 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 3698 | 14256
242211725 | S | MECH GRP - Tooling for dissassembly, and repairs : manufacturing Drawings - Labor | 2013-11-04 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 12944 | 18918
242211730 | H | MECH GRP - Tooling for disassembly and repairs: procurement prep - Labor | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 1195
242211735 | D | MECH GRP - Tooling for disassembly, and repairs - Proc | 2014-04-15 08:00 | 18-Aug-14 16:00 A | 100% | 12104 | 0 | 12104
242211740 | S | MECH GRP - Tooling for disassembly and repairs Build - Labor | 2014-08-04 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 3698 | 14256
242211745 | D | MECH GRP - Environmental Control System - Proc | 2013-11-04 08:00 | 2014-12-03 16:00 | 90% | 24794 | 0 | 24794
242211755 | D | HBI - Additional HFCB - Proc | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 39100 | 0 | 39100
242211800 | S | Installation MECH GRP - Support and alignment tube, MFG Drawings - Labor | 2014-02-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 7397 | 13370
242211805 | H | Installation MECH GRP - Support & alignment tube - Proc - prep - Labor | 2014-06-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 1893
242211810 | D | Installation MECH GRP - Support and alignment tube - Proc | 2014-09-08 08:00 | 2014-12-23 16:00 | 0% | 16482 | 0 | 16482
242211815 | H | Installation MECH GRP - Support and alignment (construction) - Labor | 2015-01-05 08:00 | 2015-01-30 16:00 | 0% | 0 | 0 | 6772
242211825 | H | Installation MECH GRP - AC Distribution - proc prep - Labor | 2015-01-08 08:00 | 2015-01-22 16:00 | 0% | 0 | 0 | 1880
242211830 | D | Installation MECH GRP - AC Distribution - Proc | 2015-01-23 08:00 | 2015-02-06 16:00 | 0% | 8076 | 0 | 8076
242211860 | H | Installation MECH GRP - Purging system: procurement prep - Labor | 2014-05-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 2987
242211865 | D | Installation MECH GRP - Purging system: installation - Proc | 2014-08-04 08:00 | 2014-12-01 16:00 | 45% | 5494 | 0 | 5494
242211870 | H | Installation MECH GRP - Purging system: installation in clean room- Labor | 2015-03-16 08:00 | 2015-04-10 16:00 | 0% | 0 | 0 | 6772
242211875 | D | MECH GRP - Construct silicon module shipping containers -Proc Part A | 2013-09-16 08:00 | 18-Nov-13 16:00 A | 100% | 21893 | 0 | 21893
242211875a | D | MECH GRP - Construct silicon module shipping containers -Proc Part B | 2014-05-02 08:00 | 19-May-14 16:00 A | 100% | 30982 | 0 | 30982
242211876 | D | MECH GRP - Module shipping Charges from FNAL to Jlab - Proc | 2014-06-02 08:00 | 2015-01-30 16:00 | 72% | 13415 | 0 | 13415
242211885 | D | MECH GRP - Module inserts Copper/PEEK Part A | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 2735 | 0 | 2735
242211890 | D | MECH GRP - Module inserts Copper/PEEK Part B | 2013-11-04 08:00 | 21-Apr-14 16:00 A | 100% | 42735 | 0 | 42735
242211918M | M | SVT Ready for Installation |  | 2015-04-14 16:00 | 0% | 0 | 0 | 0
242213073 | D | ODU Contract Mount Electronics on Chambers | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 122487 | 0 | 122487
242213078 | D | De-Obligation of ODU Contract | 2013-10-01 08:00 | 19-May-14 16:00 A | 100% | -47487 | 0 | -47487
242213092 | D | ISU Contract Phase 4b - String wires and test chamber 5 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 16334 | 0 | 16334
242213097 | D | ISU Contract Phase 5b - String wires and test chamber 6 | 2013-09-03 08:00 | 2014-03-24 | 100% | 38906 | 0 | 38906
242213100 | D | ISU Contract Phase 6 - Ship chambers, fixtures and equipment to JLab | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 88172 | 0 | 88172
242213133C | H | P-#2 Build Boxes and Associated Hardware FY13 | 2013-09-03 08:00 | 2013-11-18 08:00 | 100% | 0 | 0 | 70
242213133Ca | H | P-#2 Build Boxes and Associated Hardware FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 580
242213232 | H | P-#3 Build Boxes and Associated Hardware FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 85
242213232a | H | P-#3 Build Boxes and Associated Hardware FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 534
242213330PA | D | Proc LVHV Distribution Cables and Boxes | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 65000 | 0 | 65000
242213331 | U | HV Dist Box Construction and Testing Labor | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 3900 | 0 | 3900
242213335Pa | D | P-#4 Proc Cleanroom Fixtures and Equipment Part B | 2013-09-03 08:00 | 2013-09-24 08:00 | 100% | 197 | 0 | 197
242213342 | U | P-#4 String Chambers FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 2115
242213342a | U | P-#4 String Chambers FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 6656
242213347 | S | P-#5 String Chambers FY14 | 2013-09-03 08:00 | 2014-10-20 08:53 | 100% | 0 | 0 | 165738
242213347A | S | P-#5 String Chambers FY15 | 2013-09-03 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 51492
242213355M | M | Chambers Complete |  | 20-Oct-14 16:00 A | 100% | 0 | 0 | 0
242223312 | U | Procured Labor for Modules 5 & 6 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 4375 | 0 | 4375
242223520 | U | Testing #6 FY13 | 2013-09-03 08:00 | 21-Oct-13 14:06 A | 100% | 0 | 0 | 6717
242223520a | U | Testing #6 FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 3465
242223525 | H | Disassemble #6 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1647
242223530 | H | Move #6 to storage | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1893
242223562 | Z | Store module #6 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 0
242223563M | M | PCAL Complete |  | 21-Oct-13 16:00 A | 100% | 0 | 0 | 0
242223570 | U | Repair Calorimeter PMT's | 2013-12-02 08:00 | 19-May-14 16:00 A | 100% | 10319 | 0 | 10319
242223575 | U | Forklift Rental for ESB | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 817 | 0 | 817
242231013E | E | CTOF-FY13 Travel | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 485 | 485
242231115 | U | Refurbish Laser Calibration System | 2013-12-02 08:00 | 2014-11-14 16:00 | 75% | 0 | 7135 | 24863
242231120 | U | Refurbish Laser Calibration System FY 13 Obligated Procurement | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 70 | 0 | 70
242231125 | D | Purchase UV Glue, Tooling and Materials | 2013-10-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 1347 | 1347
242231140 | H | Final Drawings of Tooling for wrapping | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 2052
242231145 | S | Fabricate Tooling for Wrapping | 2014-01-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 2564 | 4457
242231200 | D | Purchase buffing tools and materials | 2013-12-02 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 4575 | 5324
242231205 | D | Purchase 900 shts, 12 sqin, VM2002, for wrapping | 2013-11-04 08:00 | 20-Dec-13 16:00 A | 100% | 2569 | 0 | 2569
242231215 | U | Polishing/finishing LG | 2013-10-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 1156 | 11020
242231220 | U | Wrapping and Transmittance test of LG | 2013-10-04 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 16298
242231245 | U | Two-side glue Counters in Support Arm | 2013-11-04 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 21240
242231250 | U | Counter-in-rack storage and wrapping | 2013-12-09 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 23714
242231255 | S | Transmittance test of assembled Counters in Rack FY14 | 2013-11-11 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 8487
242231255A | S | Transmittance test of assembled Counters in Rack FY15 | 2013-11-11 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 3904
242231260 | S | Final Drawings of CTOF Support and Solenoid Harness | 2014-01-03 08:00 | 2014-11-14 16:00 | 0% | 0 | 0 | 8208
242231262 | S | CTOF Support and Solenoid Harness Engineer analysis | 2014-05-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 8960
242231265 | D | CTOF procure support and solenoid harness and interface rings | 2014-12-17 08:00 | 2015-04-15 16:00 | 0% | 46930 | 0 | 46930
242231270 | S | Final drawings for counter installation arm - cart and transport rack FY14 | 2014-11-17 08:00 | 2015-03-12 16:00 | 0% | 0 | 0 | 24096
242231270A | S | Final drawings for counter installation arm - cart and transport rack FY15 | 2015-03-13 08:00 | 2015-03-19 16:00 | 0% | 0 | 0 | 545
242231272 | S | Counter installation arm - cart and transport rack Engineering Analysis | 2014-11-03 08:00 | 2015-01-09 16:00 | 0% | 0 | 0 | 11947
242231275 | D | CTOF procure installation tooling and transport rack | 2015-02-20 08:00 | 2015-07-29 16:00 | 0% | 11353 | 0 | 11353
242231280 | H | Final Drawings of Magnetic Shield Compensating Coil | 2013-12-02 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 6156
242231285 | S | Final Drawings of Magnetic Shield Components | 2013-12-02 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 10260
242231287 | H | Magnetic Shield Engineering Analysis | 2013-12-02 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 8960
242231290 | D | Purchase Coil components and materials | 2014-04-07 08:00 | 2014-12-05 16:00 | 20% | 0 | 11553 | 11553
242231295 | D | Fabricate Compensating Coil Machine Shop | 2014-11-20 08:00 | 2015-03-05 16:00 | 0% | 0 | 8498 | 8498
242231300 | D | Fabricate Compensating Coil Procurement | 2014-10-06 08:00 | 2015-02-16 16:00 | 0% | 21137 | 0 | 21137
242231305 | D | Purchase/Fabricate/Ship Inner Mag. Cylinder Procurement | 2014-10-06 08:00 | 2015-03-31 16:00 | 0% | 11392 | 0 | 11392
242231320 | U | Purchase DCPS 6030A 200V/17A Ext.Magn. Shield | 2014-05-05 08:00 | 19-May-14 16:00 A | 100% | 32362 | 0 | 32362
242231325 | S | Assemble the Setup for Magnetic Shields Tests FY14 | 2014-04-07 08:00 | 2014-12-17 16:00 | 40% | 0 | 0 | 2877
242231325A | S | Assemble the Setup for Magnetic Shields Tests FY15 | 2014-04-07 08:00 | 2014-12-17 16:00 | 40% | 0 | 0 | 17812
242231335 | D | Purchase Cables and Connectors | 2014-08-06 08:00 | 2014-12-03 16:00 | 10% | 47499 | 0 | 49361
242231340 | U | Fabricate Cables LV&HV | 2014-10-06 08:00 | 2015-03-12 16:00 | 0% | 0 | 0 | 13719
242231345 | H | Final Drawings of Patch Panels for LV & HV;200 ch | 2014-01-06 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 4235
242231350 | H | Final Drawings of Splitter to TDC and ADC; 100 ch | 2014-07-18 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 4235
242231355 | U | Fabricate Patch Panels for LV&HV | 2014-10-06 08:00 | 2015-03-13 16:00 | 0% | 0 | 0 | 15632
242231360 | H | Fabricate Splitter Parts | 2014-10-06 08:00 | 2014-12-19 16:00 | 50% | 0 | 0 | 8949
242231365 | U | Assembling of the CTOF patch panels | 2015-03-16 08:00 | 2015-04-24 16:00 | 0% | 0 | 0 | 8682
242231370 | U | Assembling of the CTOF splitters | 2014-12-22 08:00 | 2015-02-26 16:00 | 0% | 0 | 0 | 11786
242231385 | U | Testing External magnetic shields | 2014-12-18 08:00 | 2015-02-03 16:00 | 0% | 0 | 0 | 24271
242231390 | U | Install PMT and check the orientation | 2014-10-06 08:00 | 2015-02-23 16:00 | 0% | 0 | 0 | 6793
242231395 | U | Install shield disks onto the Light guides FY14 | 2015-02-03 08:00 | 2015-02-24 16:00 | 0% | 0 | 0 | 2500
242231395A | U | Install shield disks onto the Light guides FY15 | 2015-02-25 08:00 | 2015-05-11 16:00 | 0% | 0 | 0 | 8705
242231400 | U | Install compensation coils and check polarity FY14 | 2015-02-16 08:00 | 2015-03-09 16:00 | 0% | 0 | 0 | 2688
242231400A | U | Install compensation coils and check polarity FY15 | 2015-03-10 08:00 | 2015-05-22 16:00 | 0% | 0 | 0 | 9361
242231405 | U | Install Middle. Mag. Shields onto PMT FY14 | 2015-02-03 08:00 | 2015-02-24 16:00 | 0% | 0 | 0 | 5376
242231405A | U | Install Middle. Mag. Shields onto PMT FY15 | 2015-02-25 08:00 | 2015-05-11 16:00 | 0% | 0 | 0 | 18723
242231410 | U | CTOF in Storage Rack cabling | 2015-04-15 08:00 | 2015-06-02 16:00 | 0% | 0 | 0 | 8160
242231415 | H | Assemble the DAQ system | 2015-04-27 08:00 | 2015-06-02 16:00 | 0% | 0 | 0 | 7448
242231420 | H | Standalone CTOF testing/optimizing | 2015-06-03 08:00 | 2015-07-14 16:00 | 0% | 0 | 0 | 5551
242231425 | S | Prepare CTOF-in-Storage-Rack for transportation | 2015-07-15 08:00 | 2015-09-01 16:00 | 0% | 0 | 0 | 17719
242231430 | D | Purchase incidentals/tools/material | 2014-07-02 08:00 | 2014-11-24 16:00 | 10% | 0 | 19093 | 19093
242231435 | U | Purchase/Fabricate/Ship Middle Mag. Disks-2 Procurement | 2014-07-07 08:00 | 2014-11-24 16:00 | 90% | 10649 | 0 | 10649
242231440 | U | Purchase/Fabricate/Ship Extern. Mag. Disks-1 Procurement | 2014-07-07 08:00 | 2014-11-24 16:00 | 60% | 10649 | 0 | 10649
242231445 | U | Purchase/Fabricate/Ship Extern. Mag. Disks-2 Procurement | 2014-07-07 08:00 | 2014-11-24 16:00 | 60% | 10649 | 0 | 10649
242231450 | U | Purchase/Fabricate/Ship Inner Mag. Cylinder #1 | 2014-10-06 08:00 | 2015-01-05 16:00 | 0% | 11392 | 0 | 11392
242231455 | U | Purchase/Fabricate/Ship Inner Non-mag. Cylinder #2 | 2014-10-06 08:00 | 2015-01-05 16:00 | 0% | 11392 | 0 | 11392
242231460 | U | Purchase stabilized dividers for H2431 PMTs | 2013-11-01 08:00 | 18-Nov-13 16:00 A | 100% | 4323 | 0 | 4323
242231465 | S | Soldering the stabilized dividers for H2431 PMTs | 2013-11-04 08:00 | 2014-07-21 | 100% | 0 | 0 | 6758
242231470M | M | CTOF Ready for Installation |  | 2015-09-01 16:00 | 0% | 0 | 0 | 0
242232180 | E | FTOF Travel FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 612 | 612
242232185 | E | FTOF Travel FY14 | 2013-10-01 08:00 | 2013-12-20 | 100% | 0 | 2268 | 2268
242232232 | D | Forward carriage patch panels procurement | 2013-09-03 08:00 | 16-Dec-13 16:00 A | 100% | 5475 | 0 | 5475
242232265a | D | High Voltage Cable Procurement (Patch Panel Plates/Brackets) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 8081 | 0 | 8081
242232320Q | D | Peg Point #11 - Counter baseline measurements complete | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 53643 | 0 | 53643
242232320R | D | Peg Point #12 - Panel-1b assembly and testing complete | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 121531 | 0 | 121531
242232320S | D | De-Obligation of USC Contract | 2013-10-01 08:00 | 17-Mar-14 16:00 A | 100% | -46531 | 0 | -46531
242232396 | D | Calibration test equipment Procurement | 2014-02-03 08:00 | 2014-03-24 | 100% | 2664 | 0 | 2664
242232546 | U | Panel 1-b QA and baseline measurements FY13 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1244
242232546a | U | Panel 1-b QA and baseline measurements FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 6288
242232560 | D | Misc. Repair Parts | 2013-12-02 08:00 | 2014-03-24 | 100% | 0 | 5494 | 5494
242232655 | D | Panel 2 Support Frame Procurement | 2013-11-04 08:00 | 16-Dec-13 16:00 A | 100% | 4472 | 0 | 4472
242232685M | M | FTOF Complete |  | 17-Mar-14 16:00 A | 100% | 0 | 0 | 0
242241300 | U | Tooling manufacturing for Quality Control of combined mirror assembly | 2013-11-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 25798 | 25798
242241370 | U | Assembly, tests and QA of additional substrates (up to 10 substrates total) FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 376
242241370a | U | Assembly, tests and QA of additional substrates (up to 10 substrates total) FY14 | 2013-09-03 08:00 | 2013-09-23 | 100% | 0 | 0 | 427
242241372 | D | Precision trimming of additional substrates (up to 10 substrates total) - Labor/Expenses FY13 | 2013-09-03 08:00 | 2013-10-21 08:01 | 100% | 0 | 806 | 935
242241372a | D | Precision trimming of additional substrates (up to 10 substrates total) - Labor/Expenses FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 1748 | 2027
242241390 | U | Coating of 60 substrates with Al + MgF2 - Proc | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 13250 | 0 | 13250
242241395 | U | Quality control of 60 coated substrates - Proc | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 9037 | 0 | 9037
242241395a | U | Quality control of 60 coated substrates - Lab | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 9534
242241400 | U | UCONN Quality control of 60 coated substrates - Lab | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 2136 | 0 | 2136
242241405 | S | Dry Fit of Preformed Mirror facets into rings - Lab | 2013-12-09 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 48325
242241405b | S | Assembly of the mirror with half sectors - Lab | 2014-06-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 118287
242241410 | S | Quality control of assembled mirror half-sectors - Lab | 2014-02-17 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 73416
242241415 | H | Checks of geometry of mirror half-sectors - Expenses FY13 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 49 | 49
242241415a | H | Checks of geometry of mirror half-sectors - Expenses FY14 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 465 | 465
242241417 | H | Manufacturing of modified HV-dividers for the 5" PMTs (50 units)-Lab | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1880
242241425 | S | Quality control of the final mirror assembly - Lab FY14 | 2014-07-07 08:00 | 2014-10-20 09:19 | 100% | 0 | 0 | 48135
242241425A | S | Quality control of the final mirror assembly - Lab FY15 | 2014-07-07 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 16557
242241430 | U | Procurement of HEPA filters for the HTCC Clean Room | 2013-11-01 08:00 | 18-Nov-13 16:00 A | 100% | 5572 | 0 | 5572
242241435 | U | Change Out of HEPA filters for the HTCC Clean Room FY14 | 2013-11-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 1304
242241435A | U | Change Out of HEPA filters for the HTCC Clean Room FY15 | 2013-11-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 999
242241450aa | D | Manufacturing of top level assembly parts of the CV construction FY13 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 5556 | 5556
242241450aaa | D | Manufacturing of top level assembly parts of the CV construction FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 9746 | 9746
242241450b | S | Assembly of the CV FY13 | 2013-09-03 08:00 | 2014-12-05 16:00 | 85% | 0 | 0 | 5433
242241450ba | S | Assembly of the CV FY14 | 2013-09-03 08:00 | 2014-12-05 16:00 | 85% | 0 | 0 | 30831
242241452 | D | Vend Fab HTCC Support Cart | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 16273 | 0 | 16273
242241455 | S | Quality control fo the CV construction - Lab FY13 | 2013-12-02 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 947
242241455a | S | Quality control fo the CV construction - Lab FY14 | 2013-12-02 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 12608
242241457 | D | HTCC Winston Cone Fabricate finals | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 3300 | 0 | 3300
242241462 | D | HTCC Consumables | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 305 | 0 | 305
242241528 | S | Assembly of the HTCC Gas System | 2014-11-13 08:00 | 2015-03-10 16:00 | 0% | 0 | 0 | 11519
242241580 | D | Procurement of miscellaneous parts - Proc | 2013-11-04 08:00 | 18-Aug-14 16:00 A | 100% | 5775 | 0 | 5775
242241580a | D | Procurement of miscellaneous parts - Expenses FY13 | 2013-11-04 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 1308 | 1308
242241580b | D | Procurement of miscellaneous parts - Expenses FY14 | 2013-11-04 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 5873 | 5873
242241585 | U | Assembly of the photo tube housing unit (PMT, HV divider, Winston Cone, Magnetic Shield) - Lab FY14 | 2013-12-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 10227
242241585A | U | Assembly of the photo tube housing unit (PMT, HV divider, Winston Cone, Magnetic Shield) - Lab FY15 | 2013-12-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 198
242241590 | S | Installation of 48 housing units - Lab | 2014-04-07 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 14464
242241595 | H | Quality control of the housing unit assembly and installation - Lab | 2014-07-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 7056
242241600 | H | Assembly of the composite carbon cone - Lab | 2013-12-02 08:00 | 31-Dec-13 16:00 A | 100% | 0 | 0 | 3786
242241605 | S | Installation of the assembled carbon cone - Lab | 2013-12-09 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 6783
242241610 | S | Installation of the composite exit window - Lab | 2014-05-02 08:00 | 2015-02-13 16:00 | 55% | 0 | 0 | 3786
242241630 | H | Installation of a temporary CO2 gas supply system - Lab | 2014-11-14 08:00 | 2015-01-29 16:00 | 0% | 0 | 0 | 6625
242241640 | S | Installation ofthe ellipsoidal mirror - Lab | 2014-11-03 08:00 | 2015-01-09 16:00 | 0% | 0 | 0 | 50452
242241645 | H | Optical tests of mirror geometry in situ - Lab | 2015-01-13 08:00 | 2015-02-11 16:00 | 0% | 0 | 0 | 10845
242241647a | D | Proc of components for the HTCC Light Monitoring System | 2013-11-04 08:00 | 16-Jun-14 16:00 A | 100% | 2967 | 0 | 2967
242241647d | S | Installation of LMS | 2014-11-03 08:00 | 2015-01-15 16:00 | 0% | 0 | 0 | 5920
242241647d5 | S | Quality control of the installed items | 2014-11-03 08:00 | 2015-04-14 16:00 | 0% | 0 | 0 | 36305
242241650M | M | HTCC Ready for Installation in the Hall |  | 2015-04-14 16:00 | 0% | 0 | 0 | 0
242242030 | Z | Quality Control of PMTs | 2014-05-02 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 0
242242031 | U | Quality Control of Existing PMTs FY13 | 2013-10-01 08:00 | 2014-11-13 16:00 | 80% | 0 | 0 | 332
242242031a | U | Quality Control of Existing PMTs FY14 | 2013-10-01 08:00 | 2014-11-17 16:00 | 80% | 0 | 0 | 3854
242242036 | H | Wavelength Shifting tests Labor/Expenses FY13 | 2013-09-03 08:00 | 17-Feb-14 14:03 A | 100% | 0 | 1290 | 2606
242242036a | H | Wavelength Shifting tests Labor/Expenses FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 732 | 1480
242242040 | D | Wavelength Shifting Procurement (Temple) | 2014-04-01 08:00 | 2014-11-14 16:00 | 80% | 61914 | 0 | 61914
242242045 | D | Procurement Lasers - Procurement | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 1651 | 0 | 1651
242242045a | D | Procurement Lasers - Labor FY13 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 37
242242045b | D | Procurement Lasers - Labor FY14 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 142
242242050 | D | Alignment Tool Manufacturing Labor/Expenses FY13 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 534 | 752
242242050a | D | Alignment Tool Manufacturing Labor/Expenses FY14 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 4093 | 5761
242242055 | S | Alignment Tool and Lasers Installation | 2013-11-04 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 2494
242242076 | D | Support Frame Fabrication for 1S in TED | 2014-11-03 08:00 | 2014-12-01 16:00 | 0% | 0 | 1032 | 2925
242242077 | D | Infrastructure Consumables | 2013-12-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 16717 | 16717
242242085 | S | Quality Control of Elliptical/Hyperbolic mirrors | 2013-11-04 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 10197
242242090 | U | Dimensions check of Elliptical/Hyperbolic mirrors FY14 | 2014-03-03 08:00 | 22-Sep-14 15:14 A | 100% | 0 | 0 | 9613
242242090A | U | Dimensions check of Elliptical/Hyperbolic mirrors FY15 | 2014-03-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 53
242242092 | U | Al/Mg Deposit Procurement WC Labor FY14 | 2014-05-02 08:00 | 2014-11-14 16:00 | 60% | 0 | 0 | 5725
242242092A | U | Al/Mg Deposit Procurement WC Labor FY15 | 2014-05-02 08:00 | 2014-11-14 16:00 | 60% | 0 | 0 | 919
242242092B | U | Al/Mg Deposit Procurement WC Procurement | 2014-05-02 08:00 | 2014-11-14 16:00 | 0% | 53241 | 0 | 53241
242242095 | H | Create Manufacturing Drawings FY13 | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 125
242242095a | H | Create Manufacturing Drawings FY14 | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 52
242242105 | H | Al/Mg Deposit Procurement Prep FY13 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 448
242242105a | H | Al/Mg Deposit Procurement Prep FY14 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 139
242242107 | H | Al/Mg Lexan/Acrylic Re-Coating Test Procurement Labor FY13 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 583
242242107a | H | Al/Mg Lexan/Acrylic Re-Coating Test Procurement Labor FY14 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1203
242242108 | U | Lexan/Acrylic/Over- Coating Procurement (all sectors) FY14 | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 2064 | 5056
242242108A | U | Lexan/Acrylic/Over- Coating Procurement (all sectors) FY15 | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 326
242242110 | D | Al/Mg Deposit Procurement (Lexan Strips) | 2014-04-14 08:00 | 21-Jul-14 16:00 A | 100% | 53241 | 0 | 53241
242242115 | H | Installation of Elliptical mirrors FY14 | 2014-11-04 08:00 | 2014-12-02 16:00 | 0% | 0 | 0 | 829
242242115A | H | Installation of Elliptical mirrors FY15 | 2014-11-04 08:00 | 2014-12-02 16:00 | 0% | 0 | 0 | 236
242242137 | D | Glue Procurement | 2013-12-02 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 2080 | 2381
242242145a | H | Complete Design Box Walls FY13 | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 162
242242145aa | H | Complete Design Box Walls FY14 | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 134
242242152 | D | Window Procurement | 2013-11-12 08:00 | 2014-11-10 16:00 | 30% | 2800 | 0 | 2800
242242152a | D | Window Procurement - Labor FY13 | 2013-11-12 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 335
242242152b | D | Window Procurement -Labor FY14 | 2013-11-12 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2060
242242155 | H | Walls Manufacturing and Installation | 2014-05-02 08:00 | 2014-12-10 16:00 | 50% | 0 | 0 | 2494
242242161 | H | HV Cables Catalog and Tagging | 2013-10-14 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 757
242242162 | H | Divider Modifications Design and Test | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 1032 | 1633
242242163 | D | Divider Modifications Labor FY14 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 1771
242242163A | D | Divider Modifications Labor FY15 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 655
242242163B | D | Divider Modifications Procurement | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 3612 | 0 | 3612
242242164 | U | Divider Modifications Implementation FY14 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 8555
242242164A | U | Divider Modifications Implementation FY15 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 2343
242242165b | D | Procure Cables Procurement | 2014-02-03 08:00 | 20-Oct-14 16:00 A | 100% | 21835 | 0 | 24241
242242169 | D | New Patch Panel Fabrication | 2014-04-07 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 3028
242242170 | D | Patch Panel Connectors Procurement | 2014-02-03 08:00 | 21-Apr-14 16:00 A | 100% | 12943 | 0 | 15115
242242185 | D | Procure Gas Line | 2014-06-02 08:00 | 18-Aug-14 16:00 A | 100% | 12778 | 0 | 13398
242242190 | H | Install Gas Line (1S) | 2014-12-01 08:00 | 2014-12-16 16:00 | 0% | 0 | 0 | 977
242242195 | H | Gas Line Quality Control | 2014-12-15 08:00 | 2014-12-19 16:00 | 0% | 0 | 0 | 391
242242205 | S | Mirrors Laser Alignments FY14 | 2014-09-15 08:00 | 2014-12-16 16:00 | 10% | 0 | 0 | 14167
242242205A | S | Mirrors Laser Alignments FY15 | 2014-09-15 | 2014-12-16 16:00 | 10% | 0 | 0 | 4584
242242215 | H | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | 2014-10-13 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 621
242242220a | S | Online Calibration Design FY13 | 2013-10-01 08:00 | 2015-02-10 16:00 | 25% | 0 | 0 | 289
242242220aa | S | Online Calibration Design FY14 | 2013-10-01 08:00 | 2015-02-10 16:00 | 25% | 0 | 0 | 2709
242242222 | S | Online HV Matching Design FY13 | 2013-10-01 08:00 | 2015-02-16 16:00 | 25% | 0 | 0 | 318
242242222a | S | Online HV Matching Design FY14 | 2013-10-01 08:00 | 2015-02-16 16:00 | 25% | 0 | 0 | 2980
242242223 | S | Online HV Matching Test FY14 | 2015-01-27 08:00 | 2015-02-12 12:00 | 0% | 0 | 0 | 2625
242242223A | S | Online HV Matching Test FY15 | 2015-02-12 12:00 | 2015-03-02 16:00 | 0% | 0 | 0 | 1016
242242225 | H | Online Calibration Test | 2015-01-28 08:00 | 2015-03-02 16:00 | 0% | 0 | 0 | 1241
242242230 | H | PMT Installation FY14 | 2014-11-18 08:00 | 2014-11-24 16:00 | 0% | 0 | 0 | 860
242242230A | H | PMT Installation FY15 | 2014-11-25 08:00 | 2014-12-03 16:00 | 0% | 0 | 0 | 204
242242235 | U | Windows Installation 6 sectors FY14 | 2014-11-18 08:00 | 2015-01-15 16:00 | 0% | 0 | 0 | 7110
242242235A | U | Windows Installation 6 sectors FY15 | 2015-01-16 08:00 | 2015-03-04 16:00 | 0% | 0 | 0 | 2429
242242240 | S | Gas Leak Check 6 sectors FY14 | 2014-11-03 08:00 | 2014-11-13 16:00 | 0% | 0 | 0 | 7215
242242240A | S | Gas Leak Check 6 sectors FY15 | 2014-11-14 08:00 | 2014-11-26 16:00 | 0% | 0 | 0 | 6948
242242245 | H | Simulation of Sagging Test | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1804
242242255 | D | Procurement Sagging Test Tools | 2013-12-09 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 601
242242260 | H | Manufacture Sagging Test Tools | 2013-11-04 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1893
242242270 | S | Sagging Test | 2013-12-09 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 3552
242242280 | H | Frame Support FY13 | 2014-11-04 08:00 | 2015-01-08 16:00 | 0% | 0 | 0 | 120
242242280a | H | Frame Support FY14 | 2014-11-04 08:00 | 2015-01-08 16:00 | 0% | 0 | 0 | 633
242242290 | H | Cut Line Mark | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 587
242242295 | H | Wall Cut-Off FY13 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 6
242242295a | H | Wall Cut-Off FY14 | 2013-12-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 751
242242300 | H | Rear Brace Manufacture | 2014-05-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 516 | 1273
242242305 | H | Rear Brace Installation | 2014-08-11 08:00 | 2014-12-05 16:00 | 50% | 0 | 0 | 1514
242242310 | H | PMTS, Mirrors Holes Drill | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 757
242242315 | H | Patch Panel Installation FY14 | 2014-09-08 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 598
242242315A | H | Patch Panel Installation FY15 | 2014-09-08 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 84
242242320 | H | Nose Extension Installation FY14 | 2014-07-03 08:00 | 2014-10-20 08:40 | 100% | 0 | 0 | 337
242242320A | H | Nose Extension Installation FY15 | 2014-07-03 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 43
242242325 | H | Spine Refurbish FY13 | 2013-12-02 08:00 | 2015-03-16 16:00 | 50% | 0 | 0 | 65
242242325a | H | Spine Refurbish FY14 | 2013-12-02 08:00 | 2015-03-16 16:00 | 50% | 0 | 0 | 832
242242325B | H | Spine Refusrbish FY15 | 2013-12-02 08:00 | 2015-03-16 16:00 | 50% | 0 | 0 | 49
242242330 | H | Gas Line Refurbish FY14 | 2014-08-02 08:00 | 2014-12-01 16:00 | 50% | 0 | 0 | 1141
242242330A | H | Gas Line Refurbish FY15 | 2014-08-02 08:00 | 2014-12-01 16:00 | 50% | 0 | 0 | 109
242242335 | D | Box Refurbish Consumables FY14 | 2013-11-01 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 14806 | 14806
242242335A | D | Box Refurbish Consumables FY15 | 2013-11-01 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 3888 | 3888
242242340 | S | Sector 2 Box Refurbish | 2013-12-02 08:00 | 2014-12-15 16:00 | 80% | 0 | 0 | 15142
242242350 | H | Sector 2 Mirrors Alignment | 2014-11-14 08:00 | 2014-12-01 16:00 | 0% | 0 | 0 | 3786
242242355 | H | Sector 2 Windows Installation | 2014-12-05 08:00 | 2014-12-12 16:00 | 0% | 0 | 0 | 1893
242242360 | H | Sector 2 Gas Leaks Checks | 2014-12-12 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 2271
242242365 | S | Sector 3 Box Refurbish | 2013-12-02 08:00 | 2015-01-15 16:00 | 80% | 0 | 0 | 13628
242242375 | H | Sector 3 Mirrors Alignment | 2015-01-08 08:00 | 2015-01-29 16:00 | 0% | 0 | 0 | 3786
242242380 | H | Sector 3 Windows Installation | 2015-01-13 08:00 | 2015-02-12 16:00 | 0% | 0 | 0 | 1893
242242385 | H | Sector 3 Gas Leaks Checks | 2015-01-29 08:00 | 2015-02-26 16:00 | 0% | 0 | 0 | 1950
242242390 | S | Sector 4 Box Refurbish | 2013-12-02 08:00 | 2015-02-20 16:00 | 60% | 0 | 0 | 13628
242242400 | H | Sector 4 Mirrors Alignment FY14 | 2015-02-16 08:00 | 2015-03-02 12:00 | 0% | 0 | 0 | 874
242242400A | H | Sector 4 Mirrors Alignment FY15 | 2015-03-02 12:00 | 2015-03-16 16:00 | 0% | 0 | 0 | 3005
242242405 | H | Sector 4 Windows Installation | 2015-02-20 08:00 | 2015-03-20 16:00 | 0% | 0 | 0 | 1953
242242410 | H | Sector 4 Gas Leaks Checks | 2015-02-27 08:00 | 2015-03-27 16:00 | 0% | 0 | 0 | 1953
242242415 | S | Sector 5 Box Refurbish | 2013-12-02 08:00 | 2015-03-20 16:00 | 60% | 0 | 0 | 12114
242242425 | H | Sector 5 Mirrors Alignment | 2015-03-16 08:00 | 2015-04-15 16:00 | 0% | 0 | 0 | 3906
242242430 | H | Sector 5 Windows Installation | 2015-03-20 08:00 | 2015-04-20 16:00 | 0% | 0 | 0 | 1953
242242435 | H | Sector 5 Gas Leaks Checks | 2015-03-30 08:00 | 2015-04-28 16:00 | 0% | 0 | 0 | 1953
242242440 | S | Sector 6 Box Refurbish | 2013-12-02 08:00 | 2015-04-01 16:00 | 60% | 0 | 0 | 12114
242242450 | H | Sector 6 Mirrors Alignment | 2015-04-15 08:00 | 2015-05-15 16:00 | 0% | 0 | 0 | 3906
242242455 | H | Sector 6 Windows Installation | 2015-04-20 08:00 | 2015-05-20 16:00 | 0% | 0 | 0 | 1953
242242460 | H | Sector 6 Gas Leaks Checks | 2015-04-29 08:00 | 2015-05-28 16:00 | 0% | 0 | 0 | 1953
242242500M | M | LTCC Complete |  | 2015-05-28 16:00 | 0% | 0 | 0 | 0
24231000 | U | AVAGO QSFP OPTIC TRANS | 2013-09-03 08:00 | 2013-11-18 08:00 | 100% | 1018 | 0 | 1018
24231005 | H | CTP procurement Prep | 2014-08-01 08:00 | 2015-01-12 16:00 | 50% | 0 | 0 | 6202
24231007 | U | CTP procurement (22 boards) | 2014-09-08 08:00 | 2015-04-28 16:00 | 60% | 163982 | 0 | 163982
24231045 | U | GTP procurement (2 boards) | 2013-11-12 08:00 | 02-Dec-13 16:00 A | 100% | 14447 | 0 | 14447
24232022 | U | Procure GE VME controllers (53) | 2014-09-22 08:00 | 2014-12-23 16:00 | 0% | 225741 | 0 | 225741
24232025 | S | Install GE VME controllers (22) | 2015-01-05 08:00 | 2015-05-05 16:00 | 0% | 0 | 0 | 24826
24233010 | D | Ethernet wiring inside Hall B (10Gbit) | 2015-01-06 08:00 | 2015-04-24 16:00 | 0% | 44722 | 0 | 44722
24233015 | D | Trigger system fibers wiring | 2014-07-07 08:00 | 2014-12-22 16:00 | 40.3% | 56435 | 0 | 56435
24233020 | U | Procure CISCO 2960S switches (24 Cu ports) (15) | 2014-05-01 08:00 | 2015-05-27 16:00 | 10% | 70278 | 0 | 70278
24233025 | S | Install CISCO 2960S switches (24 Cu ports) (15) | 2015-05-28 08:00 | 2015-07-27 16:00 | 0% | 0 | 0 | 12413
24233030 | U | Procure 4-port 10GBit Blades for BigIron | 2015-01-06 08:00 | 2015-04-24 16:00 | 0% | 53241 | 0 | 53241
24233035 | H | Install 4-port 10GBit Blades for BigIron | 2015-04-27 08:00 | 2015-05-22 16:00 | 0% | 0 | 0 | 3103
24233040 | D | Procure Ethernet fibers/Cu wires | 2015-01-06 08:00 | 2015-04-24 16:00 | 0% | 22361 | 0 | 22361
24233045 | H | Install Ethernet fibers/Cu wires | 2015-04-27 08:00 | 2015-06-24 16:00 | 0% | 0 | 0 | 6206
24233050 | U | Procure Terminal servers (Etherlite32) (10) | 2014-08-04 08:00 | 25-Aug-14 16:00 A | 100% | 15972 | 0 | 15972
24233055 | H | Install Terminal servers (Etherlite32) (10) | 2015-02-26 08:00 | 2015-04-23 16:00 | 0% | 0 | 0 | 3103
24233060 | D | Procure daq/online computers | 2014-08-05 08:00 | 25-Aug-14 16:00 A | 100% | 88380 | 0 | 88380
24233065 | S | Install daq/online computers | 2015-02-26 08:00 | 2015-04-22 16:00 | 0% | 0 | 0 | 21722
24233070M | M | Online computing infrastructure complete |  | 2015-07-27 16:00 | 0% | 0 | 0 | 0
24235005 | D | SLOW CNTL (EPICS software development) | 2013-10-01 08:00 | 02-Dec-13 16:00 A | 100% | 9390 | 0 | 9390
24235010a | S | SLOW CNTL (EPICS device drivers development) FY14 | 2014-07-01 08:00 | 2015-05-05 16:00 | 20% | 0 | 0 | 65808
24235010aB | S | SLOW CNTL (EPICS device drivers development) FY15 | 2014-07-01 08:00 | 2015-05-05 16:00 | 20% | 0 | 0 | 362
24235015 | S | SLOW CNTL (EPICS software development) | 2015-05-06 08:00 | 2015-10-12 16:00 | 0% | 0 | 0 | 143070
24242005 | S | CAEN v1190 (30) and v1290 (24) TDC's installation (FC) | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 26833 | 26833
24242005a | S | CAEN v1190 (1) and v1290N (7) TDC's installation (SF) | 2014-12-22 08:00 | 2015-07-02 16:00 | 0% | 0 | 5750 | 5750
24242010 | U | CAEN v1290 TDC's (1) procurement | 2013-11-04 08:00 | 20-Jan-14 16:00 A | 100% | 10648 | 0 | 10648
24242030 | S | JLab TDC Fanout (18) test/install (FC) | 2014-03-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 1917 | 1917
24242030a | S | JLab TDC Fanout (2) test/install (SF) | 2014-11-04 08:00 | 2015-05-15 16:00 | 0% | 0 | 1917 | 1917
24242040 | S | JLab Discriminator (240) and Flash FADC (240) test/install (FC) | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 32775 | 32775
24242040a | S | JLab Discriminator (12) and Flash FADC (12) test/install (SF) | 2014-11-04 08:00 | 2015-05-15 16:00 | 0% | 0 | 3715 | 3715
24242055 | S | ORTEC 935F Discriminators (24) Test/Install (SF) | 2014-11-04 08:00 | 2015-05-15 16:00 | 0% | 0 | 11145 | 11145
24242057 | D | Radial Connectors and Sockets for HV Distribution Boxes | 2014-05-01 08:00 | 19-May-14 16:00 A | 100% | 17293 | 0 | 17293
24242060M | M | TDC and Discriminators Complete |  | 2015-07-02 16:00 | 0% | 0 | 0 | 0
24243010 | U | SCALERS - Procurement/Install (SF) | 2015-01-06 08:00 | 2015-07-08 16:00 | 0% | 70278 | 0 | 70278
24244030 | S | CAEN 1527 HV mainframes install (12) (FC), (2) (SF)installation | 2014-04-07 08:00 | 2014-12-03 16:00 | 85.7% | 0 | 13002 | 13002
24244035 | U | HV mainframes SY4525 (5) Procurements | 2013-12-02 08:00 | 21-Apr-14 16:00 A | 100% | 50000 | 0 | 50000
24247005 | S | Wiener VME64x crates install (20) (FC) | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 11145 | 11145
24247005a | S | Wiener VME64x crates install (2) (SF) FY14 | 2014-11-04 08:00 | 2015-02-20 16:00 | 0% | 0 | 1035 | 1035
24247005aB | S | Wiener VME64x crates install (2) (SF) FY15 | 2015-02-23 08:00 | 2015-05-07 16:00 | 0% | 0 | 848 | 848
24247025 | S | NIM crates (10) install (FC) | 2014-02-03 08:00 | 2014-02-17 | 100% | 0 | 7430 | 7430
24247030 | S | NIM crates (2) install (SF) | 2014-11-04 08:00 | 2015-05-15 12:00 | 0% | 0 | 1857 | 1857
24247040 | D | Uninterruptible PowerSupply (16kVA) | 2013-09-03 08:00 | 11-Nov-13 16:00 A | 100% | 12383 | 0 | 12383
24247045 | S | Re-locate existing UPS to Hall B | 2014-11-03 08:00 | 2014-12-02 16:00 | 0% | 0 | 3715 | 3715
24247060M | M | Crates and Racks Complete |  | 2015-05-15 12:00 | 0% | 0 | 0 | 0
24254000 | D | Faraday Cup Materials | 2015-08-25 08:00 | 2015-11-12 16:00 | 0% | 0 | 2130 | 2130
24254005 | H | Faraday Cup Labor | 2015-11-13 08:00 | 2016-01-21 16:00 | 0% | 0 | 0 | 6980
24254010 | H | Downstream Viewer Manufacturing Design | 2015-08-25 08:00 | 2015-11-18 16:00 | 0% | 0 | 0 | 2118
24254015 | D | Downstream Viewer Procurement | 2015-11-19 08:00 | 2016-02-24 16:00 | 0% | 10648 | 0 | 10648
24254020 | H | Downstream Viewer Assembly | 2016-02-02 08:00 | 2016-04-20 16:00 | 0% | 0 | 0 | 1953
24254025 | S | Moller polarimeter upgrade Manufacturing Design | 2015-08-25 08:00 | 2015-11-18 16:00 | 0% | 0 | 0 | 11552
24254030 | D | Moller polarimeter upgrade Procurement | 2015-11-19 08:00 | 2016-02-24 16:00 | 0% | 63889 | 0 | 63889
24254035 | S | Moller polarimeter upgrade Installation | 2016-02-02 08:00 | 2016-04-20 16:00 | 0% | 0 | 0 | 16646
24254040 | S | Moller Shielding Manufacturing Design | 2015-08-25 08:00 | 2015-11-23 16:00 | 0% | 0 | 0 | 11552
24254045 | D | Moller Shielding Procurement | 2015-11-24 08:00 | 2016-02-25 16:00 | 0% | 53241 | 0 | 53241
24254050 | S | Moller Shielding Installation | 2016-02-26 08:00 | 2016-06-23 16:00 | 0% | 0 | 0 | 15626
24254055 | D | Downstream Vacuum System Procurement | 2015-10-01 08:00 | 2015-12-22 16:00 | 0% | 31945 | 0 | 31945
24254060 | H | Downstream Vacuum System Installation | 2015-12-23 08:00 | 2016-02-29 16:00 | 0% | 0 | 0 | 7813
24254065 | D | Upstream Vacuum System Procurement | 2015-10-01 08:00 | 2015-12-22 16:00 | 0% | 31945 | 0 | 31945
24254070 | H | Upstream Vacuum System Installation | 2015-12-23 08:00 | 2016-01-29 16:00 | 0% | 0 | 0 | 4071
24254075 | D | Beam Offset Monitor Procurement | 2015-10-01 08:00 | 2015-12-22 16:00 | 0% | 8519 | 0 | 8519
24254080 | H | Beam Offset Monitor Installation | 2015-12-23 08:00 | 2016-02-26 16:00 | 0% | 0 | 0 | 10273
24254085 | D | 2C24 girder move Procurement | 2015-10-01 08:00 | 2015-12-21 16:00 | 0% | 10648 | 0 | 10648
24254090 | S | 2C24 girder move Labor | 2015-10-09 08:00 | 2016-01-12 16:00 | 0% | 0 | 0 | 17579
24254095 | S | Upstream beam blocker and vacuum box Manufacturing Design | 2015-08-25 08:00 | 2015-10-21 16:00 | 0% | 0 | 0 | 11552
24254100 | D | Upstream beam blocker and vacuum box Procurement | 2015-10-22 08:00 | 2016-03-01 16:00 | 0% | 53241 | 0 | 53241
24254105 | S | Upstream beam blocker and vacuum box Installation | 2016-02-03 08:00 | 2016-06-22 16:00 | 0% | 0 | 0 | 10914
24254110 | D | Upstream Shielding Wall Procurement | 2015-10-01 08:00 | 2016-05-05 16:00 | 0% | 61276 | 0 | 61276
24254115 | H | Upstream Shielding Wall Installation | 2016-04-08 08:00 | 2016-05-05 16:00 | 0% | 0 | 0 | 10273
24254120 | D | Procurement of Beamline Devices | 2015-10-01 08:00 | 2016-07-28 16:00 | 0% | 21296 | 0 | 21296
24264002LOE | E | Installation Procurement Support FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 9955
24264003LOE | E | Installation Enginering Support FY14 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 127387
24264005LOE | E | Installation Engineering Oversight FY15-A | 2014-10-01 08:00 | 01-Oct-14 16:00 A | 100% | 0 | 0 | 1376
24264005LOEA | S | Installation Engineering Oversight FY15-B | 2014-10-01 08:00 | 2015-09-29 16:00 | 0% | 0 | 0 | 348025
24264006LOE | S | Installation Engineering Oversight FY16 | 2015-09-30 08:00 | 2016-01-28 16:00 | 0% | 0 | 0 | 156305
24264010M | M | SVT Ready For Installation | 2015-04-15 08:00 |  | 0% | 0 | 0 | 0
24264015M | M | CTOF Ready for Installation | 2015-09-02 08:00 |  | 0% | 0 | 0 | 0
24264020M | M | R3 Drift Chambers Ready for Installation | 2014-10-03 08:00 |  | 100% | 0 | 0 | 0
24264025M | M | R2 Drift Chambers Ready for Installation | 2014-03-10 08:00 |  | 100% | 0 | 0 | 0
24264030M | M | R1 Drift Chambers Ready for Installation | 2014-10-03 08:00 |  | 100% | 0 | 0 | 0
24264035M | M | ToF Panel 1a - First 3 units Ready for Installation | 2013-09-16 08:00 |  | 100% | 0 | 0 | 0
24264045M | M | ToF Panel 2 Ready for Installation | 2013-09-16 08:00 |  | 100% | 0 | 0 | 0
24264050M | M | ToF Panel 1b - First 3 units Ready for Installation | 2013-10-21 08:00 |  | 100% | 0 | 0 | 0
24264055M | M | ToF Panel 1b - Last 3 units Ready for Installation | 2013-10-21 08:00 |  | 100% | 0 | 0 | 0
24264065M | M | LTCC - Last 3 units Ready for Installation | 2015-05-29 08:00 |  | 0% | 0 | 0 | 0
24264080M | M | HTCC Ready for Installation | 2015-04-15 08:00 |  | 0% | 0 | 0 | 0
24264085M | M | First Torus Cryostat Ready | 2015-02-10 08:00 |  | 0% | 0 | 0 | 0
24264090M | M | Last Torus Cryostat Ready | 2015-04-20 08:00 |  | 0% | 0 | 0 | 0
24264095M | M | Torus Control System Ready for Installation | 2015-05-05 08:00 |  | 0% | 0 | 0 | 0
24264105 | H | SVT - Design mounts for SVT to cart | 2014-04-01 08:00 | 2014-11-19 16:00 | 50% | 0 | 0 | 8208
24264110 | H | SVT - Design Insertion/service cart and installation arm | 2014-05-05 08:00 | 2014-11-19 16:00 | 50% | 0 | 0 | 10260
24264115 | S | SVT - Design transportation cart/skid FY14 | 2014-10-06 08:00 | 2015-02-16 16:00 | 60% | 0 | 0 | 23204
24264115A | S | SVT - Design transportation cart/skid FY15 | 2014-10-06 08:00 | 2015-02-16 16:00 | 60% | 0 | 0 | 1466
24264120 | S | SVT - Cart/Skid Engineering analysis | 2015-01-08 08:00 | 2015-01-26 16:00 | 0% | 0 | 0 | 17921
24264125 | D | SVT - Procure SVT mounts and cart | 2015-02-17 08:00 | 2015-04-24 16:00 | 0% | 34194 | 0 | 34194
24264140 | D | PCAL - Procure PCAL installation stand | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 21969 | 0 | 21969
24264145 | S | HTCC - design transport cart | 2015-03-05 08:00 | 2015-05-21 16:00 | 0% | 0 | 15504 | 18586
24264160 | D | HTCC - procure transport cart | 2015-05-22 08:00 | 2015-07-22 16:00 | 0% | 37798 | 0 | 37798
24264230 | S | Subway Level 1 addition wiring Power Dist. | 2014-12-15 08:00 | 2014-12-19 16:00 | 0% | 10988 | 0 | 10988
24264270 | Z | Add AC power to Level 0 FC | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 0
24264278 | H | Install Fwd Carriage Mods | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 71953 | 0 | 71953
24264280 | S | Modify LTCC gas piping | 2014-04-01 08:00 | 2014-11-26 16:00 | 50% | 0 | 0 | 35026
24264281 | S | Install new gas lines from gas sched to the hall | 2014-05-05 08:00 | 2014-11-26 16:00 | 50% | 0 | 0 | 13250
24264282 | H | Design modifications to Lead Nose | 2014-10-06 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 6644 | 6644
24264285 | H | Modify Lead nose | 2014-10-20 08:00 | 23-Oct-14 16:00 A | 100% | 0 | 0 | 3125
24264297M | M | Start Forward Carriage Precabling | 2013-09-22 08:00 |  | 100% | 0 | 0 | 0
24264300 | S | Precable forward carriage FY13 | 2013-09-16 08:00 | 2013-12-20 09:08 | 100% | 0 | 0 | 4077
24264300a | S | Precable forward carriage FY14 | 2013-09-16 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 68158
24264340M | M | Start Beamline Modifications | 2016-02-10 08:00 |  | 0% | 0 | 0 | 0
24264345 | H | Install New Tagger Window | 2014-09-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 3516
24264350 | S | Move Moeller Quads and Table | 2014-06-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 11719
24264355 | H | Move GONI | 2014-06-09 08:00 | 23-Jun-14 16:00 A | 100% | 0 | 0 | 3906
24264360 | H | Align Goni and Moeller Quads | 2016-02-10 08:00 | 2016-02-12 16:00 | 0% | 0 | 0 | 1172
24264362 | D | Vend Fab Fwd. Detector Installation Tooling | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 21069 | 0 | 21069
24264364M | M | Start Installation of FWD Detectors | 2013-11-11 08:00 |  | 100% | 0 | 0 | 0
24264365 | S | Transport and install PCAL | 2013-11-11 08:00 | 16-Dec-13 16:00 A | 100% | 0 | 0 | 22714
24264370 | H | Check PCAL positions | 2013-12-16 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2271
24264390 | H | Cable/test/repair Preshower calorimeters | 2014-01-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 8820
24264395 | S | Cable/test/repair EC | 2013-09-09 08:00 | 2014-03-17 | 100% | 0 | 0 | 16303
24264400 | S | Transport and Install ToF 1a | 2013-12-16 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 18171
24264405 | H | Survey (as found location) TOF 1a positions | 2014-01-13 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 3407
24264410 | S | Cable/test/repair 1a's TOF's | 2014-01-13 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 12227
24264430 | S | Transport and install ToF 1b | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 18171
24264435 | H | Survey (as found location) TOF 1b's | 2014-04-01 08:00 | 02-Apr-14 16:00 A | 100% | 0 | 0 | 3407
24264440 | S | Cable/test/repair 1b's TOF's | 2014-02-03 08:00 | 2014-03-14 | 100% | 0 | 0 | 12227
24264460 | S | Transport and Install LTCC | 2015-06-10 08:00 | 2015-06-23 16:00 | 0% | 0 | 0 | 15626
24264465 | H | Survey (as found location) LTCC positions | 2015-06-24 08:00 | 2015-06-26 16:00 | 0% | 0 | 0 | 3516
24264470 | H | Cable/test/repair LTCC's | 2015-06-26 08:00 | 2015-07-06 16:00 | 0% | 0 | 0 | 8412
24264490 | H | Transport and Install TOF Panel 2 and align relative to panel 1a | 2015-06-29 08:00 | 2015-07-07 16:00 | 0% | 0 | 0 | 9375
24264495 | H | Final Survey TOF panel 2's Positions | 2015-07-08 08:00 | 2015-07-10 16:00 | 0% | 0 | 0 | 3516
24264500 | H | Cable/test/repair Panel 2 TOFs | 2015-07-13 08:00 | 2015-07-20 16:00 | 0% | 0 | 0 | 8412
24264515 | S | Mods to CRYO transfer lines | 2014-04-07 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 15142
24264517 | D | Modify Space Frame For Cryo Can | 2014-12-15 08:00 | 2015-02-23 16:00 | 0% | 20000 | 0 | 20000
24264520 | H | Modify Space Frame Level 3 deck For Torus Cryo | 2015-02-24 08:00 | 2015-03-23 16:00 | 0% | 0 | 0 | 3786
24264525 | H | Distribution Can - Transport and position distribution box | 2015-11-17 08:00 | 2015-11-18 16:00 | 0% | 0 | 0 | 3125
24264527 | H | Distribution Can - Connect cold piping with fittings and welding | 2015-11-19 08:00 | 2015-11-25 16:00 | 0% | 0 | 0 | 7813
24264529 | H | Distribution Can - Connect Instrumentation and valves | 2015-11-30 08:00 | 2015-12-04 16:00 | 0% | 0 | 0 | 7813
24264531 | H | Distribution Can - leak test system | 2015-12-07 08:00 | 2015-12-10 16:00 | 0% | 0 | 0 | 6250
24264533 | H | Distribution Can - pressure test system | 2015-12-11 08:00 | 2015-12-14 16:00 | 0% | 0 | 0 | 3125
24264535 | H | Distribution Can - final leak test system | 2015-12-15 08:00 | 2015-12-17 16:00 | 0% | 0 | 0 | 4688
24264540 | H | Distribution Can - purify system | 2015-12-18 08:00 | 2015-12-22 16:00 | 0% | 0 | 0 | 3906
24264545 | H | Install and wire up Torus PS | 2015-06-19 08:00 | 2015-06-25 16:00 | 0% | 0 | 0 | 7758
24264546 | S | Install Torus Control System | 2015-05-05 08:00 | 2015-06-03 16:00 | 0% | 0 | 0 | 20163
24264547 | S | Labor to Support The Torus Installation, Cooldown and Test FY14 | 2014-09-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 31292
24264547A | S | Labor to Support The Torus Installation, Cooldown and Test FY15 | 2014-10-01 08:00 | 2015-11-02 16:00 | 0% | 0 | 0 | 165489
24264547B | S | Labor to Support The Torus Installation, Cooldown and Test FY16 | 2015-11-03 08:00 | 2015-12-08 16:00 | 0% | 0 | 0 | 16146
24264548M | M | Start Torus Installation |  | 01-Oct-14 16:00 A | 100% | 0 | 0 | 0
24264550 | H | Install Spit in Hall B | 2014-10-01 08:00 | 2015-01-14 16:00 | 50% | 0 | 0 | 6057
24264552 | H | Pre-align frames | 2014-10-13 08:00 | 15-Oct-14 16:00 A | 100% | 0 | 0 | 4543
24264555 | H | Mount Hub to Spit | 2015-01-15 08:00 | 2015-01-15 16:00 | 0% | 0 | 0 | 1514
24264557 | H | Align Spit to Beamline | 2014-10-13 08:00 | 2015-01-23 16:00 | 50% | 0 | 0 | 2271
24264560 | H | Attach Coil A to Hub | 2015-02-10 08:00 | 2015-02-10 16:00 | 0% | 0 | 0 | 1514
24264562 | H | Rotate Assembly, attach Sector 3 beams | 2015-02-11 08:00 | 2015-02-11 16:00 | 0% | 0 | 0 | 1136
24264565 | H | Install Coil B, survey & align | 2015-03-10 08:00 | 2015-03-11 16:00 | 0% | 0 | 0 | 2271
24264567 | H | Rotate Assembly, Sector 3 to bottom, prep. | 2015-03-12 08:00 | 2015-03-12 16:00 | 0% | 0 | 0 | 1136
24264570 | S | Install hardware on Sector 3 US beam | 2015-03-13 08:00 | 2015-03-31 16:00 | 0% | 0 | 0 | 22146
24264572 | H | Install hardware on Sector 3 DS beam | 2015-03-13 08:00 | 2015-03-13 16:00 | 0% | 0 | 0 | 1136
24264575 | H | Rotate Assembly, attach Sector 4 beams | 2015-04-01 08:00 | 2015-04-01 16:00 | 0% | 0 | 0 | 1136
24264577 | H | Install Coil C, survey & align | 2015-04-07 08:00 | 2015-04-08 16:00 | 0% | 0 | 0 | 4543
24264580 | H | Rotate Assembly, Sector 4 to bottom, prep. | 2015-04-09 08:00 | 2015-04-09 16:00 | 0% | 0 | 0 | 1136
24264582 | S | Install hardware on Sector 4 US beam FY14 | 2015-04-10 08:00 | 2015-04-17 16:00 | 0% | 0 | 0 | 10221
24264582A | S | Install hardware on Sector 4 US beam FY15 | 2015-04-20 08:00 | 2015-04-23 16:00 | 0% | 0 | 0 | 7032
24264585 | H | Install hardware on Sector 4 DS beam | 2015-04-10 08:00 | 2015-04-10 16:00 | 0% | 0 | 0 | 757
24264587 | H | Rotate Assembly, attach Sector 5 beams | 2015-04-24 08:00 | 2015-04-24 16:00 | 0% | 0 | 0 | 1172
24264590 | H | Install Coil D, survey & align | 2015-04-27 08:00 | 2015-04-28 16:00 | 0% | 0 | 0 | 4688
24264592 | H | Rotate Assembly, Sector 5 to bottom, prep. | 2015-04-29 08:00 | 2015-04-29 16:00 | 0% | 0 | 0 | 1172
24264595 | S | Install hardware on Sector 5 US beam | 2015-04-30 08:00 | 2015-05-12 16:00 | 0% | 0 | 0 | 15821
24264597 | H | Install hardware on Sector 5 DS beam | 2015-04-30 08:00 | 2015-04-30 16:00 | 0% | 0 | 0 | 781
24264600 | H | Rotate Assembly, attach Sector 6 beams | 2015-05-13 08:00 | 2015-05-13 16:00 | 0% | 0 | 0 | 1172
24264605 | H | Install Coil E, survey & align | 2015-07-02 08:00 | 2015-07-06 16:00 | 0% | 0 | 0 | 4688
24264607 | H | Rotate Assembly, Sector 6 to bottom, prep. | 2015-07-07 08:00 | 2015-07-07 16:00 | 0% | 0 | 0 | 1172
24264610 | S | Install hardware on Sector 6 US beam | 2015-07-08 08:00 | 2015-07-20 16:00 | 0% | 0 | 0 | 15821
24264612 | H | Install hardware on Sector 6 DS beam | 2015-07-08 08:00 | 2015-07-08 16:00 | 0% | 0 | 0 | 781
24264615 | H | Rotate Assembly, attach Sector 1 beams | 2015-07-21 08:00 | 2015-07-21 16:00 | 0% | 0 | 0 | 1172
24264617 | H | Install Coil F, survey & align | 2015-07-24 08:00 | 2015-07-27 16:00 | 0% | 0 | 0 | 4688
24264620 | H | Rotate Assembly, attach Sector 2 beams | 2015-07-28 08:00 | 2015-07-29 16:00 | 0% | 0 | 0 | 4688
24264622 | H | Survey and align entire assembly | 2015-07-30 08:00 | 2015-07-30 16:00 | 0% | 0 | 0 | 2344
24264625 | H | Rotate Assembly, Sector 1 to bottom, prep. | 2015-07-31 08:00 | 2015-07-31 16:00 | 0% | 0 | 0 | 1172
24264627 | S | Install hardware on Sector 1 US beam | 2015-08-03 08:00 | 2015-08-13 16:00 | 0% | 0 | 0 | 15821
24264630 | H | Install hardware on Sector 1 DS beam | 2015-08-03 08:00 | 2015-08-03 16:00 | 0% | 0 | 0 | 781
24264632 | H | Rotate Assembly, Sector 2 to bottom, prep. | 2015-08-14 08:00 | 2015-08-14 16:00 | 0% | 0 | 0 | 1172
24264635 | S | Install hardware on Sector 2 US beam | 2015-08-17 08:00 | 2015-08-27 16:00 | 0% | 0 | 0 | 15821
24264637 | H | Install hardware on Sector 2 DS beam | 2015-08-17 08:00 | 2015-08-17 16:00 | 0% | 0 | 0 | 781
24264645 | S | Pressure/leak test. Electrical test. | 2015-08-28 08:00 | 2015-09-11 16:00 | 0% | 0 | 0 | 15598
24264650 | H | Install cold to warm supports | 2015-09-14 08:00 | 2015-09-15 16:00 | 0% | 0 | 0 | 1563
24264655 | H | Insulate cold to warm supports | 2015-09-16 08:00 | 2015-09-21 16:00 | 0% | 0 | 0 | 3125
24264660 | H | Complete shields on hex and hub | 2015-09-22 08:00 | 2015-09-22 16:00 | 0% | 0 | 0 | 781
24264665 | S | Install MLI on hex beam to coil connections | 2015-09-23 08:00 | 2015-09-30 16:00 | 0% | 0 | 0 | 11719
24264670 | H | Complete 4K and 80K shields on coil-to-coil gaps at hub | 2015-10-01 08:00 | 2015-10-08 16:00 | 0% | 0 | 0 | 7032
24264675 | S | Install U-shape vacumm jacket sections, skip weld | 2015-10-09 08:00 | 2015-10-22 16:00 | 0% | 0 | 0 | 18751
24264680 | H | Install plates to complete vacuum jacket at hub, skip weld | 2015-10-23 08:00 | 2015-10-30 16:00 | 0% | 0 | 0 | 7032
24264685 | H | Survey assembly for symmetry | 2015-11-02 08:00 | 2015-11-03 16:00 | 0% | 0 | 0 | 4688
24264690 | S | Route instrumentation wires, make electrical connections at feedthroughs | 2015-11-04 08:00 | 2015-11-17 16:00 | 0% | 0 | 0 | 18685
24264695 | S | Install brackets to complete vacuum jacket welding | 2015-11-18 08:00 | 2015-11-25 16:00 | 0% | 0 | 0 | 14063
24264700 | H | Final leak check, final electrical tests | 2015-11-30 08:00 | 2015-12-02 16:00 | 0% | 0 | 0 | 3508
24264705 | H | Install and tack weld closure plates on hex | 2015-12-03 08:00 | 2015-12-10 16:00 | 0% | 0 | 0 | 9375
24264710 | H | Install LN2 Thermosiphon Jumpers | 2015-12-11 08:00 | 2015-12-16 16:00 | 0% | 0 | 0 | 6250
24264712 | S | Complete all welding to finsih vacuum jacket | 2015-12-17 08:00 | 2016-01-29 16:00 | 0% | 0 | 0 | 58596
24264715 | H | Orient assembly, survey, and lock rotation | 2016-02-01 08:00 | 2016-02-02 16:00 | 0% | 0 | 0 | 4688
24264717 | S | Construct legs in Hall B | 2016-02-03 08:00 | 2016-02-15 16:00 | 0% | 0 | 0 | 15626
24264720 | H | Run Wires, Connect instruments, verify OOPS operation | 2016-02-16 08:00 | 2016-02-17 16:00 | 0% | 0 | 0 | 3114
24264722 | H | Pre-load vertical supports | 2016-02-18 08:00 | 2016-02-19 16:00 | 0% | 0 | 0 | 2344
24264725 | H | Adjust OOPS loads | 2016-02-22 08:00 | 2016-02-24 16:00 | 0% | 0 | 0 | 3516
24264727 | H | Using threaded holes adjust coil locations | 2016-02-25 08:00 | 2016-03-01 16:00 | 0% | 0 | 0 | 5860
24264730 | H | Locate/install cryotower | 2016-03-02 08:00 | 2016-03-02 16:00 | 0% | 0 | 0 | 1172
24264732 | S | Torus Cryotower - Connect cold piping with fittings and welding | 2016-03-03 08:00 | 2016-03-17 16:00 | 0% | 0 | 0 | 14063
24264737 | H | Leak check, electrical tests | 2016-03-18 08:00 | 2016-03-24 16:00 | 0% | 0 | 0 | 7799
24264740 | H | Final pressure test | 2016-03-25 08:00 | 2016-03-28 16:00 | 0% | 0 | 0 | 1563
24264742 | H | Close 1-8" holes, close vacuum jacket | 2016-03-29 08:00 | 2016-03-31 16:00 | 0% | 0 | 0 | 4688
24264745 | H | Pump vacuum | 2016-04-01 08:00 | 2016-04-07 16:00 | 0% | 0 | 0 | 1953
24264747 | H | Leak tests while pumping | 2016-04-08 08:00 | 2016-04-11 16:00 | 0% | 0 | 0 | 1563
24264750 | H | Pump down vacuum | 2016-04-12 08:00 | 2016-04-25 16:00 | 0% | 0 | 0 | 3906
24264760 | H | IInstall Vacuum pumping system | 2016-03-03 08:00 | 2016-03-04 16:00 | 0% | 0 | 0 | 5524
24264762 | H | Design Warm Gas Panel and Piping | 2015-11-16 08:00 | 2015-12-08 16:00 | 0% | 0 | 0 | 9246
24264762A | H | Cut Back the warm piping | 2015-12-09 08:00 | 2015-12-09 16:00 | 0% | 0 | 0 | 781
24264762B | D | Procure warm gas valves and fittings | 2015-12-10 08:00 | 2016-01-15 16:00 | 0% | 0 | 10648 | 22976
24264762C | H | Install New warm gas Piping | 2016-01-19 08:00 | 2016-02-01 16:00 | 0% | 0 | 0 | 7813
24264762D | H | Leak Test new warm Piping | 2016-02-02 08:00 | 2016-02-05 16:00 | 0% | 0 | 0 | 3125
24264762F | H | Pressure Test warm Piping | 2016-02-08 08:00 | 2016-02-08 16:00 | 0% | 0 | 0 | 781
24264762G | H | Final Leak Test system | 2016-02-09 08:00 | 2016-02-12 16:00 | 0% | 0 | 0 | 3125
24264762H | H | Purify Entire System | 2016-04-12 08:00 | 2016-04-14 16:00 | 0% | 0 | 0 | 1953
24264770 | S | Install mounting adapters for drift chambers | 2016-04-01 08:00 | 2016-04-14 16:00 | 0% | 0 | 0 | 25243
24264788M | M | Torus Assembled and Tested |  | 2016-06-27 16:00 | 0% | 0 | 0 | 0
24264790 | H | Solenoid - design adjustment system for solenoid and HTCC rails | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 10260
24264791 | D | Solenoid - procure rails and adjustment components for solenoid and HTCC rails | 2014-04-03 08:00 | 16-Jun-14 16:00 A | 100% | 22783 | 0 | 22783
24264792 | Z | Solenoid - Install and Align rails and adjustment components for solenoid and HTCC rails | 2014-09-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 0
24264793 | H | Solenoid - design motion system | 2014-03-10 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 10260
24264794 | D | Solenoid - procure motion system | 2014-07-07 08:00 | 20-Oct-14 16:00 A | 100% | 3580 | 0 | 3580
24264794a | H | Solenoid - Install motion system | 2014-11-03 08:00 | 2014-11-07 16:00 | 0% | 0 | 0 | 3786
24264795 | S | Solenoid - design cart | 2014-03-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 12878 | 12878
24264796 | S | Solenoid - cart Engineering Analysis | 2014-03-17 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 11947
24264797 | D | Solenoid - procure cart | 2014-09-08 08:00 | 2014-12-05 16:00 | 0% | 54762 | 0 | 54762
24264798M | M | Start Installation of Solenoid | 2016-03-04 08:00 |  | 0% | 0 | 0 | 0
24264800 | S | Receive and inspect solenoid magnet from Vendor | 2016-03-04 08:00 | 2016-03-08 16:00 | 0% | 0 | 0 | 17856
24264805 | H | Install Solenoid cart | 2014-12-08 08:00 | 2015-01-16 16:00 | 0% | 0 | 0 | 1514
24264810 | S | Assemble Solenoid and Piping | 2016-03-09 08:00 | 2016-04-19 16:00 | 0% | 0 | 9071 | 20790
24264815 | H | Solenoid instrumentation and current leads | 2016-04-19 08:00 | 2016-05-02 16:00 | 0% | 0 | 0 | 7758
24264820 | H | Align Solenoid | 2016-05-02 08:00 | 2016-05-03 16:00 | 0% | 0 | 0 | 781
24264825 | Z | Connect Solenoid Cryo lines | 2016-05-04 08:00 | 2016-06-01 16:00 | 0% | 0 | 0 | 0
24264830 | Z | Install CND | 2016-07-20 08:00 | 2016-07-21 16:00 | 0% | 0 | 0 | 0
24264845 | S | Mount, assemble and cable CTOF system | 2016-07-22 08:00 | 2016-08-04 16:00 | 0% | 0 | 0 | 21832
24264850 | H | Align CTOF | 2016-08-05 08:00 | 2016-08-08 16:00 | 0% | 0 | 0 | 2344
24264855 | S | Mount, cable and check SVT system | 2016-09-28 08:00 | 2016-10-18 16:00 | 0% | 0 | 0 | 21832
24264860 | H | Align SVT | 2016-10-18 08:00 | 2016-10-31 16:00 | 0% | 0 | 0 | 2344
24264860M | M | Central Detector Ready |  | 2016-08-08 16:00 | 0% | 0 | 0 | 0
24264868 | S | Design and install HTCC gas system | 2015-04-08 08:00 | 2015-08-14 16:00 | 0% | 0 | 0 | 18072
24264870 | H | Rig and Transport HTCC to Hall | 2016-07-22 08:00 | 2016-07-25 16:00 | 0% | 0 | 0 | 1953
24264872 | H | Install HTCC cart | 2016-07-26 08:00 | 2016-07-29 16:00 | 0% | 0 | 0 | 977
24264874 | H | Install HTCC | 2016-08-01 08:00 | 2016-08-02 16:00 | 0% | 0 | 0 | 5860
24264876 | H | HTCC verify mirror alignment and align detector to beam | 2016-08-03 08:00 | 2016-08-05 16:00 | 0% | 0 | 0 | 6068
24264878 | H | Cable HTCC | 2016-08-08 08:00 | 2016-08-11 16:00 | 0% | 0 | 0 | 1563
24264880 | D | Vend Fab Drift Chambers Installation tooling | 2014-07-07 08:00 | 21-Jul-14 16:00 A | 100% | 21732 | 0 | 21732
24264882 | S | Install DC signal cable trays and gas lines | 2016-01-21 08:00 | 2016-03-09 16:00 | 0% | 4829 | 20182 | 56263
24264884 | S | Route DC Signal Cables | 2016-01-21 08:00 | 2016-03-09 16:00 | 0% | 0 | 0 | 23438
24264886 | H | Install DC HV/LV Racks and cable trays | 2015-11-19 08:00 | 2015-12-22 16:00 | 0% | 0 | 0 | 9375
24264888 | S | Reroute DC gas lines to the distribution panel | 2014-04-01 08:00 | 2015-01-21 16:00 | 0% | 0 | 0 | 11357
24264890 | S | DC - design mounts and adjusters for DC to Torus | 2014-01-13 08:00 | 2015-01-12 16:00 | 70% | 0 | 25756 | 25756
24264895 | S | DC - mounts and adjusters Engineering Analysis | 2014-03-10 08:00 | 2014-11-12 16:00 | 75% | 0 | 0 | 17921
24264900 | D | DC - procure mounts and adjusters for DC to Torus | 2015-01-13 08:00 | 2015-03-11 16:00 | 0% | 78000 | 0 | 78000
24264905 | S | DC - design cable trays and gas system mounts FY14 | 2014-03-10 08:00 | 2015-02-20 16:00 | 30% | 0 | 28393 | 28393
24264905A | S | DC - design cable trays and gas system mounts FY15 | 2014-11-03 08:00 | 2015-03-25 16:00 | 0% | 0 | 1709 | 1709
24264910 | S | DC - cable trays and gas system mounts Engineering Analysis | 2015-01-15 08:00 | 2015-02-17 16:00 | 0% | 0 | 0 | 14934
24264915 | D | DC - procure cable trays and gas system mounts | 2015-02-26 08:00 | 2015-05-08 16:00 | 0% | 35638 | 0 | 35638
24264920 | S | DC - design maintenance platforms | 2014-10-04 08:00 | 2015-01-15 16:00 | 30% | 0 | 11074 | 11074
24264925 | H | DC - maintenance platforms Engineering Analysis | 2014-12-01 08:00 | 2014-12-19 16:00 | 0% | 0 | 0 | 9246
24264930 | D | DC - procure maintenance platforms | 2015-03-02 08:00 | 2015-04-27 16:00 | 0% | 20469 | 0 | 20469
24264935 | H | Widen the corners of the Hall access walls to allow R3 to pass through horizontal | 2014-01-06 08:00 | 17-Mar-14 16:00 A | 100% | 8255 | 0 | 8255
24264960M | M | Start Installation of Drift Chambers | 2016-06-28 08:00 |  | 0% | 0 | 0 | 0
24264965 | S | Install Region 2 Drift Chamber | 2016-06-28 08:00 | 2016-07-12 16:00 | 0% | 0 | 0 | 26564
24264970 | S | Survey/align R2 Drift chambers | 2016-07-06 08:00 | 2016-07-12 16:00 | 0% | 0 | 0 | 11719
24264975 | S | Install Region 1 Drift Chamber | 2016-07-12 08:00 | 2016-07-25 16:00 | 0% | 0 | 0 | 26564
24264980 | S | Survey/align R1 Drift chambers | 2016-07-15 08:00 | 2016-07-21 16:00 | 0% | 0 | 0 | 11719
24264985 | S | Install Region 3 Drift Chamber | 2016-07-21 08:00 | 2016-08-03 16:00 | 0% | 0 | 0 | 26564
24264990 | S | Survey/align R3 Drift chambers | 2016-07-27 08:00 | 2016-08-02 16:00 | 0% | 0 | 0 | 11719
24264995 | H | Connect / Cable Drift Chambers | 2016-08-03 08:00 | 2016-08-16 16:00 | 0% | 0 | 0 | 10086
242710.1 | S | Solenoid - Instrumentation Magnet Protection System Design | 2015-01-09 08:00 | 2015-06-30 16:00 | 0% | 0 | 0 | 93323
242710.1005 | H | Solenoid - Instrumentation Magnet Protection System Procurement Prep | 2014-02-03 08:00 | 2014-12-23 16:00 | 50% | 0 | 0 | 3005
242710.101 | S | Solenoid - Instrumentation Magnet Protection System Procurement | 2015-01-05 08:00 | 2015-03-30 16:00 | 0% | 100854 | 0 | 100854
242710.1015 | S | Solenoid - Instrumentation Controls Design FY13 | 2013-12-02 08:00 | 2015-01-08 16:00 | 20% | 0 | 0 | 6600
242710.1015a | S | Solenoid - Instrumentation Controls Design FY14 | 2014-06-02 08:00 | 2015-01-08 16:00 | 20% | 0 | 0 | 17707
242710.102 | H | Solenoid - Instrumentation Controls Procurement Prep | 2015-01-09 08:00 | 2015-01-15 16:00 | 0% | 0 | 0 | 3005
242710.1025 | D | Solenoid - Instrumentation Controls Procurement | 2015-01-16 08:00 | 2015-05-07 16:00 | 0% | 36117 | 0 | 36117
242710.103 | S | Solenoid - Instrumentation Controls Assembly FY14 | 2015-05-08 08:00 | 2015-08-19 16:00 | 0% | 0 | 0 | 59113
242710.1030A | S | Solenoid - Instrumentation Controls Assembly FY15 | 2015-08-20 08:00 | 2016-01-05 16:00 | 0% | 0 | 0 | 76466
242710.1035 | D | Solenoid - Vend Fab Power Supply - Peg Point #1 - Approval of Design | 2014-05-01 08:00 | 27-Jun-14 16:00 A | 100% | 59715 | 0 | 59715
242710.104 | D | Solenoid - Vend Fab Power Supply - Peg Point #2 - Materials Received and Inspected at Vendor/Fabrication Start | 2014-05-01 08:00 | 2014-11-26 16:00 | 0% | 59715 | 0 | 59715
242710.1045 | D | Solenoid - Vend Fab Power Supply - Peg Point #3 - Factory Test Completed and Accepted/Shipment | 2014-05-01 08:00 | 2015-03-31 16:00 | 0% | 59715 | 0 | 59715
242710.105 | D | Solenoid - Vend Fab Power Supply - Peg Point #4 - Acceptance Test at JLab | 2014-05-01 08:00 | 2016-07-19 16:00 | 0% | 19905 | 0 | 19905
242710.1055 | D | Solenoid - Vend Fab Power Supply - Peg Point #5 - Receipt of Spares | 2014-05-01 08:00 | 2015-03-31 16:00 | 0% | 13020 | 0 | 13020
242711.1 | E | Additional FNAL Oversight FY14 | 2014-07-01 08:00 | 2014-09-30 11:59 | 100% | 0 | 0 | 39984
242711.1000A | E | Additional FNAL Oversight FY15 | 2014-10-01 08:00 | 2014-11-07 16:00 | 82.14% | 0 | 0 | 18337
242711.1005 | D | FNAL: Materials and Supplies for Prototype CCM and CCM #7 (FNAL CCM #1 and CCM #8) | 2014-01-02 08:00 | 17-Mar-14 16:00 A | 100% | 42840 | 0 | 42840
242711.1005A | D | FNAL: Transfer and Clean Cable for CCM #8 (FNAL CCM #10) | 2014-01-02 08:00 | 2015-03-25 16:00 | 0% | 26238 | 0 | 26238
242711.1005B | D | FNAL: Wind, Test and Compress for CCM #8 (FNAL CCM #10) | 2014-01-02 08:00 | 2015-04-27 16:00 | 0% | 46302 | 0 | 46302
242711.1005C | D | FNAL: Solder Copper Shields for CCM #8 (FNAL CCM #10) | 2014-01-02 08:00 | 2015-05-28 16:00 | 0% | 60058 | 0 | 60058
242711.1005D | D | FNAL: Impregnate, cure and clean-up for CCM #8 (FNAL CCM #10) | 2014-01-02 08:00 | 2015-05-22 16:00 | 0% | 41269 | 0 | 41269
242711.1005F | D | FNAL:Pot coil in case and ship for Prototype CCM (FNAL CCM #10) | 2014-01-02 08:00 | 2015-06-18 16:00 | 0% | 20668 | 0 | 20668
242711.101 | D | FNAL: Transfer and Clean Cable for CCM#7 (FNAL CCM #9) | 2014-01-02 08:00 | 2015-02-23 16:00 | 0% | 22696 | 0 | 22696
242711.1010A | D | FNAL: Wind, Test and Compress for CCM#7 (FNAL CCM #9) | 2014-01-02 08:00 | 2015-04-27 16:00 | 0% | 30162 | 0 | 30162
242711.1010B | D | FNAL: Solder Copper Shields for CCM#7 (FNAL CCM #9) | 2014-01-02 08:00 | 2015-05-08 16:00 | 0% | 22696 | 0 | 22696
242711.1010C | D | FNAL: Impregnate, cure and clean-up for CCM#7 (FNAL CCM #9) | 2014-01-02 08:00 | 2015-05-01 16:00 | 0% | 24829 | 0 | 24829
242711.1010D | D | FNAL:Pot coil in case and ship for CCM#7 (FNAL CCM #9) | 2014-01-02 08:00 | 2015-05-29 16:00 | 0% | 17822 | 0 | 17822
242711.2005 | D | Vend Fab 1 Set of Additional Hardware for Cryostat (Cold Mass Shiled, OOPS, Axial Support, MLI, Vacuum Jacket) | 2013-10-01 08:00 | 01-May-14 16:00 A | 100% | 45350 | 0 | 45350
242711.201 | D | Reverse Entry Per CR 14-015 | 2014-05-01 08:00 | 01-May-14 16:00 A | 100% | -45350 | 0 | -45350
242711.3 | S | LN2 TEST - Procurements Preperation FY13 | 2013-12-02 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 3017
242711.3000a | S | LN2 TEST - Procurements Preperation FY14 | 2013-12-02 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 3580
242711.3005 | D | LN2 TEST - Preliminary system set up and integration (One coil LN2 Test) Procurements | 2013-11-04 | 17-Mar-14 16:00 A | 100% | 30441 | 0 | 30441
242711.301 | S | LN2 TEST - Mounting of Q heaters and wiring | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 15264
242711.3015 | S | LN2 TEST - Instrumentation general and wiring layout and cabling | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 10978
242711.302 | S | LN2 TEST - HV/LV Feedthrough and wirng | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 19024
242711.3025 | S | LN2 TEST - Preliminary system set up and integration (One coil LN2 Test) Labor | 2013-12-04 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 21430
242711.303 | S | LN2 TEST - LN2 Testing of Prototype Coil | 2014-02-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 2064 | 14922
242711.3035 | S | LN2 TEST - LN2 Testing of CCM #1 | 2014-03-17 08:00 | 2014-12-04 16:00 | 20% | 0 | 2064 | 14922
242711.304 | S | LN2 TEST - LN2 Testing of CCM #2 | 2014-03-17 08:00 | 2015-01-22 16:00 | 10% | 0 | 2064 | 14922
242711.3045 | S | LN2 TEST - LN2 Testing of CCM #3 | 2014-03-17 08:00 | 2015-02-16 16:00 | 10% | 0 | 2064 | 14922
242711.305 | S | LN2 TEST - LN2 Testing of CCM #4 | 2014-03-17 08:00 | 2015-03-16 16:00 | 10% | 0 | 2064 | 14922
242711.3055 | S | LN2 TEST - LN2 Testing of CCM #5 | 2014-03-17 08:00 | 2015-04-13 16:00 | 10% | 0 | 2064 | 14922
242711.306 | S | LN2 TEST - LN2 Testing of CCM #6 | 2014-03-17 08:00 | 2015-05-05 16:00 | 10% | 0 | 2064 | 14922
242711.3065 | S | LN2 TEST - LN2 Testing of CCM #7 FY14 | 2014-03-17 08:00 | 2015-05-22 16:00 | 10% | 0 | 413 | 2984
242711.3065A | S | LN2 TEST - LN2 Testing of CCM #7 FY15 | 2014-03-17 08:00 | 2015-05-22 16:00 | 10% | 0 | 1704 | 12318
242711.4005 | D | Solder conductor for Torus Coil #7 Coil - Procurement | 2014-01-03 08:00 | 23-Jun-14 16:00 A | 100% | 51498 | 0 | 51498
242711.4005a | H | Solder conductor for Torus Coil #7 and #8 Coil Labor FY13 | 2014-01-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 1625
242711.4005b | H | Solder conductor for Torus Coil #7 and #8 Coil Labor FY14 | 2014-01-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 2096
242711.401 | D | Solder conductor for Torus Coil #8 | 2014-01-03 08:00 | 23-Jun-14 16:00 A | 100% | 53141 | 0 | 58028
242711.4015 | H | Reverse Entry Per CR 14-015 | 2014-05-01 08:00 | 23-Jun-14 16:00 A | 100% | -104639 | 0 | -104639
242711.5 | H | Cold Tests - Contract Preparation | 2013-11-04 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 9328
242711.5005 | S | Cold Tests - Kickoff Meeting | 2014-11-03 08:00 | 2014-12-01 16:00 | 0% | 0 | 10319 | 19945
242711.501 | E | Cold Tests - Oversight Expenses and Labor FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 1754 | 3936
242711.5010a | E | Cold Tests - Oversight Expenses and Labor FY14 | 2013-10-01 08:00 | 31-Mar-14 16:00 A | 100% | 0 | 10772 | 24168
242711.5010b | P | Cold Tests - Planning Package FY14 | 2015-10-01 08:00 | 2016-01-07 16:00 | 0% | 575800 | 0 | 575800
242711.5015 | P | Cold Tests - Planning Package FY15 | 2015-10-01 08:00 | 2015-11-30 16:00 | 0% | 138426 | 18961 | 180972
242711.502 | D | DUMMY | 2014-11-03 08:00 | 2014-11-03 16:00 | 0% | 0 | 0 | 0
242711.5025 | D | DUMMY | 2014-11-03 08:00 | 2014-11-03 16:00 | 0% | 0 | 0 | 0
242711.503 | D | DUMMY | 2014-11-03 08:00 | 2014-11-03 16:00 | 0% | 0 | 0 | 0
24271665 | D | FNAL: Tooling Fabrication and Installation at FNAL Part B | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 2467 | 0 | 2467
24271680 | D | FNAL: Prototype CCM winding and tests | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 35234 | 0 | 35234
24271685 | D | FNAL: Update design with lessons learned from prototype | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 46567 | 0 | 46567
24271690 | D | FNAL: Production CCM readiness review | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 24836 | 0 | 24836
24271695 | D | FNAL: Materials and Supplies for CCM#1 Thru CCM#6 (FNAL CCM #2 thru CCM#7) | 2014-01-02 08:00 | 20-Oct-14 16:00 A | 100% | 42840 | 0 | 42840
24271695A | D | FNAL: Transfer and Clean Cable for CCM#1 Part A (FNAL CCM #3) | 2014-01-02 08:00 | 17-Feb-14 16:00 A | 100% | 21565 | 0 | 21565
24271695B | D | FNAL: Transfer and Clean Cable for CCM#1 Part B (FNAL CCM #3) | 2014-01-02 08:00 | 17-Feb-14 16:00 A | 100% | 3710 | 0 | 3710
24271695C | D | FNAL: Wind, Test and Compress for CCM#1 (FNAL CCM #3) | 2014-01-02 08:00 | 17-Mar-14 16:00 A | 100% | 37316 | 0 | 37316
24271695D | D | FNAL: Solder Copper Shields for CCM#1 (FNAL CCM #3) | 2014-01-02 08:00 | 13-Oct-14 16:00 A | 100% | 46946 | 0 | 46946
24271695F | D | FNAL: Impregnate, cure and clean-up for CCM#1 (FNAL CCM #3) | 2014-01-02 08:00 | 15-Oct-14 16:00 A | 100% | 30089 | 0 | 30089
24271695G | D | FNAL:Pot coil in case and ship for CCM#1 (FNAL CCM #3) | 2014-01-02 08:00 | 2014-11-17 16:00 | 50% | 19854 | 0 | 19854
24271700 | D | FNAL: Transfer and Clean Cable for CCM#2 (FNAL CCM #4) | 2014-01-02 08:00 | 17-Mar-14 16:00 A | 100% | 24553 | 0 | 24553
24271700A | D | FNAL: Wind, Test and Compress for CCM#2 (FNAL CCM #4) | 2014-01-02 08:00 | 20-Oct-14 16:00 A | 100% | 32703 | 0 | 32703
24271700B | D | FNAL: Solder Copper Shields for CCM#2 (FNAL CCM #4) | 2014-01-02 08:00 | 2014-12-08 16:00 | 0% | 24553 | 0 | 24553
24271700C | D | FNAL: Impregnate, cure and clean-up for CCM#2 (FNAL CCM #4) | 2014-01-02 08:00 | 2014-11-24 16:00 | 30% | 26882 | 0 | 26882
24271700D | D | FNAL:Pot coil in case and ship for CCM#2 (FNAL CCM #4) | 2014-01-02 08:00 | 2015-01-05 16:00 | 0% | 19288 | 0 | 19288
24271705 | D | FNAL: Transfer and Clean Cable for CCM#3 (FNAL CCM #5) | 2014-01-02 08:00 | 2014-11-11 16:00 | 60% | 23946 | 0 | 23946
24271705A | D | FNAL: Wind, Test and Compress for CCM#3 (FNAL CCM #5) | 2014-01-02 08:00 | 2014-12-04 16:00 | 0% | 31873 | 0 | 31873
24271705B | D | FNAL: Solder Copper Shields for CCM#3 (FNAL CCM #5) | 2014-01-02 08:00 | 2015-01-16 16:00 | 0% | 23946 | 0 | 23946
24271705C | D | FNAL: Impregnate, cure and clean-up for CCM#3 (FNAL CCM #5) | 2014-01-02 08:00 | 2015-01-13 16:00 | 0% | 26211 | 0 | 26211
24271705D | D | FNAL:Pot coil in case and ship for CCM#3 (FNAL CCM #5) | 2014-01-02 08:00 | 2015-01-29 16:00 | 0% | 18809 | 0 | 18809
24271710 | D | FNAL: Transfer and Clean Cable for CCM#4 (FNAL CCM #6) | 2014-01-02 08:00 | 2014-12-16 16:00 | 0% | 23548 | 0 | 23548
24271710A | D | FNAL: Wind, Test and Compress for CCM#4 (FNAL CCM #6) | 2014-01-02 08:00 | 2015-01-26 16:00 | 0% | 31328 | 0 | 31328
24271710B | D | FNAL: Solder Copper Shields for CCM#4 (FNAL CCM #6) | 2014-01-02 08:00 | 2015-02-13 16:00 | 0% | 23548 | 0 | 23548
24271710C | D | FNAL: Impregnate, cure and clean-up for CCM#4 (FNAL CCM #6) | 2014-01-02 08:00 | 2015-02-09 16:00 | 0% | 25771 | 0 | 25771
24271710D | D | FNAL:Pot coil in case and ship for CCM#4 (FNAL CCM #6) | 2014-01-02 08:00 | 2015-02-26 16:00 | 0% | 18495 | 0 | 18495
24271715 | D | FNAL: Transfer and Clean Cable for CCM#5 (FNAL CCM #7) | 2014-01-02 08:00 | 2015-01-08 16:00 | 0% | 23328 | 0 | 23328
24271715A | D | FNAL: Wind, Test and Compress for CCM#5 (FNAL CCM #7) | 2014-01-02 08:00 | 2015-02-26 16:00 | 0% | 31028 | 0 | 31028
24271715B | D | FNAL: Solder Copper Shields for CCM#5 (FNAL CCM #7) | 2014-01-02 08:00 | 2015-03-06 16:00 | 0% | 23328 | 0 | 23328
24271715C | D | FNAL: Impregnate, cure and clean-up for CCM#5 (FNAL CCM #7) | 2014-01-02 08:00 | 2015-03-02 16:00 | 0% | 25528 | 0 | 25528
24271715D | D | FNAL:Pot coil in case and ship for CCM#5 (FNAL CCM #7) | 2014-01-02 08:00 | 2015-03-26 16:00 | 0% | 18321 | 0 | 18321
24271720 | D | FNAL: Transfer and Clean Cable for CCM#6 (FNAL CCM #8) | 2014-01-02 08:00 | 2015-02-09 16:00 | 0% | 23062 | 0 | 23062
24271720A | D | FNAL: Wind, Test and Compress for CCM#6 (FNAL CCM #8) | 2014-01-02 08:00 | 2015-03-09 16:00 | 0% | 30663 | 0 | 30663
24271720B | D | FNAL: Solder Copper Shields for CCM#6 (FNAL CCM #8) | 2014-01-02 08:00 | 2015-03-25 16:00 | 0% | 23062 | 0 | 23062
24271720C | D | FNAL: Impregnate, cure and clean-up for CCM#6 (FNAL CCM #8) | 2014-01-02 08:00 | 2015-03-18 16:00 | 0% | 25233 | 0 | 25233
24271720D | D | FNAL:Pot coil in case and ship for CCM#6 (FNAL CCM #8) | 2014-01-02 08:00 | 2015-04-17 16:00 | 0% | 18111 | 0 | 18111
24271722 | D | FNAL:Break down tooling and ship to JLab | 2014-01-02 08:00 | 2015-06-22 16:00 | 0% | 50539 | 0 | 50539
24271724 | U | Prepare Shipping Containers | 2014-02-10 08:00 | 17-Mar-14 16:00 A | 100% | 7500 | 0 | 30214
24271724A | D | Shipping of First 4 CCMs | 2014-11-18 08:00 | 2015-02-25 16:00 | 0% | 18800 | 0 | 18800
24271724B | D | Shipping of Last 4 CCMs | 2015-03-27 08:00 | 2015-06-22 16:00 | 0% | 18800 | 0 | 18800
24271725 LOE | E | Consultant Fees WS LQ | 2013-09-03 08:00 | 30-Sep-14 16:00 A | 100% | 22950 | 0 | 22950
24271730 | D | Existing Coil Case Storage | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 2106 | 0 | 2106
24271730LOE | E | JLab support of FNAL Torus CCM effort FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 16042
24271735 | D | Contractor Training TW | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 266 | 0 | 266
24271735LOE | E | JLab support of FNAL Torus CCM effort FY14 | 2013-10-01 08:00 | 01-Jul-14 16:00 A | 100% | 0 | 0 | 152325
24271740 | D | Additional Torus Copper Stabilizer and SSC Cable tests for Coil #7 | 2013-09-03 08:00 | 01-Nov-13 16:00 A | 100% | 24035 | 0 | 24035
24271740M | M | FNAL Torus work complete |  | 2015-06-22 16:00 | 0% | 0 | 0 | 0
24272075 | D | Vend Fab Solenoid - Peg Point #2 - Intermediate Design Review (Frozen Per CR14-007) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 49772 | 0 | 49772
24272075a | D | Vend Fab Solenoid - Peg Point #3 - Final Design Review (Frozen Per CR14-007) | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 99543 | 0 | 99543
24272075b | D | Vend Fab Solenoid - Final Design Review Incetive Fee (Frozen Per CR14-007) | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 200000 | 0 | 200000
24272075ba | D | De-Obligation of Vend Fab Solenoid - Final Design Review Incetive Fee (Frozen Per CR14-007) | 2014-02-17 08:00 | 17-Feb-14 16:00 A | 100% | -135000 | 0 | -135000
24272075ba5 | D | Reverse Entry/DeObligation per Contract Mod CR14-007 | 2014-02-17 08:00 | 17-Feb-14 16:00 A | 100% | -267939 | 0 | -267939
24272075ba55 | D | Original Obligation (Frozen Per CR14-007) | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 178053 | 0 | 178053
24272075c | P | Vend Fab Solenoid - Line Item #4 Additional Design Work (Trim-coils, Temp-margin & ANSYS analysis) | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 293050 | 0 | 293050
24272075d | P | Vend Fab Solenoid - Line Item #5 - Epoxy Coil Stack Samples for Mechanical Testing | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 16916 | 0 | 16916
24272075f | P | Vend Fab Solenoid - Line Item #6 Magnetic Design & Analysis Complete | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 3069 | 0 | 3069
24272075g | P | Vend Fab Solenoid - Line Item #7 - Quench Design & Analysis Complete | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 0
24272075h | P | Vend Fab Solenoid - Line Item #8 - Cryogenic Design & Analysis Complete | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 6477 | 0 | 6477
24272075j | P | Vend Fab Solenoid - Line Item #9 - Structural Design & Analysis Complete | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 7467 | 0 | 7467
24272075k | P | Vend Fab Solenoid - Line Item #10 - Correction Coil Design & Analysis Complete | 2013-09-03 08:00 | 2015-01-12 16:00 | 100% | 0 | 0 | 0
24272075n | P | Vend Fab Solenoid - Line Item #11 - Final Design Review (FDR)---{All presentation material provide two weeks prior} | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 24886 | 0 | 24886
24272075p | P | Vend Fab Solenoid - Line Item #12 - Practice Winding Complete (1/2 height - Inner Coil) | 2013-09-03 08:00 | 2014-12-17 16:00 | 0% | 138058 | 0 | 138058
24272075q | P | Vend Fab Solenoid - Line Item #13 - Pre-MRR (Review manufacturing and QA for prototype coil winding) | 2013-09-03 08:00 | 2015-01-12 16:00 | 0% | 0 | 0 | 0
24272075r | P | Vend Fab Solenoid - Line Item #14 - Prototype Inner Coil Winding Setup (PSMM) | 2013-09-03 08:00 | 2015-01-12 16:00 | 0% | 19909 | 0 | 19909
24272075s | P | Vend Fab Solenoid - Line Item #15 - Winding and Potting Tooling - Inner Coils | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 15927 | 0 | 15927
24272075t | P | Vend Fab Solenoid - Line Item #16 - Materials for Cold Mass Received (Bobbin, Coils, Thermal Shield, etc.) | 2013-09-03 08:00 | 2015-07-10 16:00 | 0% | 326055 | 0 | 326055
24272075u | P | Vend Fab Solenoid - Line Item #17 - QA/QC Plan Acceptance | 2013-09-03 08:00 | 2015-04-17 16:00 | 0% | 0 | 0 | 0
24272075v | P | Vend Fab Solenoid - Line Item #18 - Prototype Inner Coil Winding Complete (PSMM) | 2013-09-03 08:00 | 2015-02-27 16:00 | 0% | 79634 | 0 | 79634
24272075w | P | Vend Fab Solenoid - Line Item #19 - MRR (Review manufacturing and QA for all coils, assembly and testing) | 2013-09-03 08:00 | 2015-04-01 16:00 | 0% | 0 | 0 | 0
24272075x | P | Vend Fab Solenoid - Line Item #20 - Materials for Final Assembly Received | 2013-09-03 08:00 | 2015-07-10 16:00 | 0% | 218994 | 0 | 218994
24272075y | P | Vend Fab Solenoid - Line Item #21 - Winding and Potting Tooling - Intermediate Coils | 2013-09-03 08:00 | 2015-04-01 16:00 | 0% | 19909 | 0 | 19909
24272075z | P | Vend Fab Solenoid - Line Item #22 - Inner Coils Wound & Potted | 2013-09-03 08:00 | 2015-06-10 16:00 | 0% | 99543 | 0 | 99543
24272075za | P | Vend Fab Solenoid - Line Item #23 - Winding and Potting Tooling - Shield Coil | 2013-09-03 08:00 | 2015-06-17 16:00 | 0% | 29863 | 0 | 29863
24272075zb | P | Vend Fab Solenoid - Line Item #24 - Intermediate Coils Wound & Potted | 2013-09-03 08:00 | 2015-07-29 16:00 | 0% | 179177 | 0 | 179177
24272075zc | P | Vend Fab Solenoid - Line Item #25 - Shield Coil Wound & Potted | 2013-09-03 08:00 | 2015-08-12 16:00 | 0% | 179177 | 0 | 179177
24272075zd | P | Vend Fab Solenoid - Line Item #26 - Cold Mass Assembly Complete (Bobbin, Coils, Thermal Shield, etc.) | 2013-09-03 08:00 | 2015-12-02 16:00 | 0% | 136651 | 0 | 136651
24272075zf | P | Vend Fab Solenoid - Line Item #27 - Correction Coils Wound & Potted | 2013-09-03 08:00 | 2016-07-07 16:00 | 0% | 0 | 0 | 0
24272075zg | P | Vend Fab Solenoid - Line Item #28 - Solenoid Magnet Final Assembly Complete | 2013-09-03 08:00 | 2016-02-29 16:00 | 0% | 133211 | 0 | 133211
24272075zh | P | Vend Fab Solenoid - Line Item #29 - Solenoid Magnet Acceptance Testing Complete at ETI | 2013-09-03 08:00 | 2016-03-18 16:00 | 0% | 183158 | 0 | 183158
24272075zj | P | Vend Fab Solenoid - Line Item #30 - Solenoid Magnet Received on-site at Jefferson Lab | 2013-09-03 08:00 | 2016-03-03 16:00 | 0% | 0 | 0 | 0
24272075zk | P | Vend Fab Solenoid - Line Item #31 - Final Acceptance Complete at Jefferson Lab | 2013-09-03 08:00 | 2016-04-27 16:00 | 0% | 99543 | 0 | 99543
24272075zn | P | Vend Fab Solenoid - Line Item #32 - Final Documentation Package Acceptance | 2013-09-03 08:00 | 2016-08-30 16:00 | 0% | 9955 | 0 | 9955
24272080 | D | Solenoid Outside Consulting FY13 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 178380 | 0 | 178380
24272085 | D | Solenoid Outside Consulting FY14 | 2014-02-03 08:00 | 2015-04-23 16:00 | 50% | 185742 | 0 | 185742
24272090 | D | Purchase Additional Trim Coils | 2015-11-30 08:00 | 2016-06-02 16:00 | 0% | 267939 | 0 | 267939
24272125M | D | Solenoid Assembled |  | 2016-02-29 16:00 | 0% | 0 | 0 | 0
24272405 | D | Solenoid - Cable Testing | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 24000 | 0 | 24000
24272410 | D | Consultant Fees WS | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 8050 | 0 | 8050
24273007 | D | Shipping of Coductor to AES | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 8874 | 0 | 8874
24273010B | D | Vend Fab Wave Solder of Torus and Solenoid Magnets Peg Point #2-Procurement of Materials and | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 62126 | 0 | 62126
24273010H | D | Vend Fab Wave Solder of Torus and Solenoid Magnets Peg Point #6-Delivery of 2nd set of Solenoid Conductor Lengths 1-9 | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 60934 | 0 | 60934
24273010J | D | Vend Fab Wave Solder of Torus and Solenoid Magnets Peg Point #7-Delivery of 3rd set of Solenoid Conductor Lengths 1-9 | 2013-09-03 08:00 | 01-May-14 16:00 A | 100% | 60934 | 0 | 60934
24273010K | D | Vend Fab Wave Solder of Torus and Solenoid Magnets Peg Point #8-Delivery of 4th set of Solenoid Conductor Lengths 1-9 | 2013-09-03 08:00 | 01-May-14 16:00 A | 100% | 60934 | 0 | 60934
24273010N | D | Vend Fab Wave Solder of Torus and Solenoid Magnets Peg Point #9-Additional length and splicing required for Solenoid | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 107400 | 0 | 107400
24273010P | D | Vend Fab Wave Solder of Torus and Solenoid Magnets Peg Point #10-Additional Reels for Solenoid | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 79600 | 0 | 79600
24273010Q | D | Vend Fab Wave Solder of Torus and Solenoid Magnets Peg Point #10-Conductor Cleaning | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 51000 | 0 | 51000
24273010R | D | Vend Fab Wave Solder of Torus and Solenoid Magnets New Scope | 2013-09-03 08:00 | 01-May-14 16:00 A | 100% | 211309 | 0 | 211309
24273010S | D | DUMMY | 2014-05-01 08:00 | 01-May-14 16:00 A | 100% | 0 | 0 | 0
24273010T | D | DUMMY | 2014-05-01 08:00 | 01-May-14 16:00 A | 100% | 0 | 0 | 0
24273012 | S | Wave Solder of Torus and Solenoid Magnets Travel FY13 | 2013-09-03 08:00 | 11-Nov-13 16:00 A | 100% | 0 | 2401 | 5683
24273012a | S | Wave Solder of Torus and Solenoid Magnets Travel FY14 | 2013-11-11 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 12263 | 29027
24273017 | D | Twente Cable Testing | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 12272 | 0 | 12272
24273022 | D | Additional Cu for solenoid conductor - Procurment | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 15500 | 0 | 15500
24273027 | D | Consultant Fees WS | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 225 | 0 | 225
24273045 | D | Reverse Entry Per Contract Mod CR 14-012 | 2014-05-01 08:00 | 01-May-14 16:00 A | 100% | -238087 | 0 | -238087
24273050 | D | Vend Fab Solder of Solenoid Conductor Peg Point #6-Delivery of 2nd set of Solenoid Conductor Lengths 1-9 | 2014-05-01 08:00 | 21-Jul-14 16:00 A | 100% | 60934 | 0 | 60934
24273055 | D | Vend Fab Solder of Solenoid Conductor Peg Point #7-Delivery of 3rd set of Solenoid Conductor Lengths 1-9 | 2014-05-01 08:00 | 22-Sep-14 16:00 A | 100% | 60934 | 0 | 60934
24273060 | D | Vend Fab Solder of Solenoid Conductor Peg Point #8-Delivery of 4th set of Solenoid Conductor Lengths 1-9 | 2014-05-01 08:00 | 2015-02-03 16:00 | 0% | 60934 | 0 | 60934
24273065 | D | Vend Fab Solder of Longer Solenoid Conductor Peg Point #9 | 2014-05-01 08:00 | 2015-02-03 16:00 | 85% | 44000 | 0 | 44000
24273075 | D | Vend Fab Post Cleaning/Buffing of Conductor Peg Point #14 | 2014-05-01 08:00 | 2015-02-03 16:00 | 75% | 52879 | 0 | 52879
24273080 | D | Vend Fab Solder of Torus Conductor - Delivery of Torus Coil T8 - Peg Points 15, 16, 17 & 18 | 2014-05-01 08:00 | 20-Oct-14 16:00 A | 100% | 49498 | 0 | 49498
24273085 | D | Vend Fab Solder of Torus Conductor - Delivery of Torus Coil T9 - Peg Point #19 | 2014-05-01 08:00 | 2014-12-01 16:00 | 100% | 13548 | 0 | 13548
24273095 | D | POST CLEANING OF CONDUCTOR TO MEET "FILM TEST" REQUIREMENT - Peg Point #22 | 2014-05-01 08:00 | 16-Jun-14 16:00 A | 100% | 28750 | 0 | 28750
24273100 | D | MODIFY TOOLING TO 'FLIP' SOLENOID CONDUCTOR AND SHIPMENT COSTS TO VENDOR - Peg Point #23 | 2014-05-01 08:00 | 16-Jun-14 16:00 A | 100% | 11200 | 0 | 11200
24273105 | D | COMPLETE CLEANING AND BUFFING OF TORUS REEL T2 - Peg Point #24 | 2014-05-01 08:00 | 16-Jun-14 16:00 A | 100% | 12247 | 0 | 12247
242741010 | H | Cryostat Factory - Design lifting Fixtures and Procurement Prep (Historical) | 2013-09-03 08:00 | 06-Sep-13 16:00 A | 100% | 0 | 0 | 4677
242741020 | H | Cryostat Factory - Perform tests for Torus Design - labor | 2013-09-03 08:00 | 14-Sep-13 16:00 A | 100% | 0 | 0 | 462
242741030 | H | Cryostat Factory - Write, review and sign welding Procedures | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 531
242741035 | S | Cryostat Factory - Write, review and sign Incoming material QA Procedures FY13 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 2021
242741035a | S | Cryostat Factory - Write, review and sign Incoming material QA Procedures FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1251
242741040 | H | Cryostat Factory - Write, review and sign material handling Procedures FY13 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 260
242741040a | H | Cryostat Factory - Write, review and sign material handling Procedures FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 161
242741045 | H | Cryostat Factory - Write, review and sign MLI application Procedures | 2013-09-03 08:00 | 14-Sep-13 16:00 A | 100% | 0 | 0 | 415
242741050 | S | Cryostat Factory - Write, review and sign OSP FY13 | 2013-09-03 08:00 | 16-Dec-13 13:24 A | 100% | 0 | 0 | 591
242741050a | S | Cryostat Factory - Write, review and sign OSP FY14 | 2013-09-03 08:00 | 16-Dec-13 16:00 A | 100% | 0 | 0 | 1036
242741055 | S | Cryostat Factory - Write, review and sign assembly procedures FY13 | 2013-09-03 08:00 | 17-Feb-14 13:15 A | 100% | 0 | 0 | 714
242741055a | S | Cryostat Factory - Write, review and sign assembly procedures FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 442
242741065 | D | Cryostat Factory - Orderfixtures, tables, tools, etc. for assembly Procurement | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 37877 | 0 | 37877
242741070 | D | Cryostat Stand and Axle | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 5814 | 0 | 5814
242741070M | M | Cryostat factory fixtures and tooling in-house |  | 17-Feb-14 16:00 A | 100% | 0 | 0 | 0
242741075M | M | Torus Cryostat Factory Procedures In-place |  | 17-Feb-14 16:00 A | 100% | 0 | 0 | 0
242742000 | S | Cryostat Factory - Test Lifting Fixtures and Procedures with Wang Coil Case FY13 | 2013-09-03 08:00 | 2013-10-21 09:36 | 100% | 0 | 2188 | 18440
242742005 | S | Cryostat Factory - Layout Assembly area for equipment and fixtures | 2013-09-16 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 13117
242742010 | S | Cryostat Factory - Install equipment and fixtures in factory area | 2013-09-16 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 2477 | 61221
242742015 | S | Cryostat Factory - Test Lifting Fixtures and Procedures with Wang Coil Case FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 1354 | 11417
242742015M | M | Cryostat Factory - Receive parts for proto cryostat |  | 2014-05-05 08:00 | 100% | 0 | 0 | 0
242742020 | E | Cryostat Factory - Engineering oversight (Legg) FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 19597
242742020a | E | Cryostat Factory - Engineering oversight (Legg) FY14 | 2013-10-01 08:00 | 03-Mar-14 16:00 A | 100% | 0 | 0 | 100098
242742025 | S | Cryostat Factory - Mock-up of one quarter CCM | 2013-09-16 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 39540
242742030 | S | Cryostat Factory - Pre-assembly of CCM using Wang Coil case FY13 | 2013-09-03 08:00 | 21-Oct-13 15:47 A | 100% | 0 | 0 | 13436
242742030a | S | Cryostat Factory - Pre-assembly of CCM using Wang Coil case FY14 | 2013-09-03 08:00 | 2013-11-18 | 100% | 0 | 0 | 15597
242742035 | S | Cryostat Factory - Initial reciept inspection of Coil Case MLI | 2014-04-07 | 19-May-14 16:00 A | 100% | 0 | 0 | 2440
242742040 | S | Cryostat Factory - Initial receipt inspection (QA) of Coil case shields | 2014-01-02 08:00 | 2014-04-21 | 100% | 0 | 0 | 7319
242742045 | S | Cryostat Factory - Pre-Assemble Seven Coil case shields | 2014-02-10 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 85393
242742050 | S | Cryostat Factory - Initial receipt inspection (QA) of Vacuum Vessel Parts | 2014-03-03 08:00 | 2014-04-21 | 100% | 0 | 0 | 5678
242742055 | S | Cryostat Factory - Pre-Assemble Seven Vacuum Jackets | 2014-04-08 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 67533
242742060M | M | Cryostat Factory - Receive 1st Article (CCM #1) coil cold case | 2014-12-05 08:00 |  | 0% | 0 | 0 | 0
242742065 | S | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Receive, QA and Pre-assembly) | 2014-09-08 08:00 | 2014-12-11 16:00 | 15% | 0 | 3440 | 57122
242742070 | S | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (MLI and LN2 shield assembly) | 2014-09-08 08:00 | 2015-01-15 16:00 | 10% | 0 | 3439 | 71762
242742075 | S | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Vac jacket weld up) | 2014-07-21 08:00 | 2015-02-09 16:00 | 20% | 0 | 3439 | 62001
242742080 | E | Cryostat Factory - Rewrite procedures and lessons learned from Proto | 2013-10-17 08:00 | 04-Mar-14 16:00 A | 100% | 0 | 0 | 55093
242743000M | M | Cryostat Factory - Receive production coil case #2 | 2015-01-23 08:00 |  | 0% | 0 | 0 | 0
242743005 | S | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Receive, QA and Pre-assembly) | 2014-09-08 08:00 | 2015-01-23 16:00 | 15% | 0 | 10319 | 66944
242743010 | S | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (MLI and LN2 shield assembly) | 2014-09-08 08:00 | 2015-02-17 16:00 | 10% | 0 | 0 | 48072
242743015 | S | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Vac jacket weld up) | 2014-08-04 08:00 | 2015-03-09 16:00 | 20% | 0 | 0 | 23185
242743020M | M | Cryostat Factory - Receive production coil case #3 | 2015-02-17 08:00 |  | 0% | 0 | 0 | 0
242743025 | S | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Receive, QA and Pre-assembly) | 2014-09-08 08:00 | 2015-02-17 16:00 | 15% | 0 | 10319 | 59452
242743030 | S | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (MLI and LN2 shield assembly) | 2014-09-08 08:00 | 2015-03-12 16:00 | 10% | 0 | 0 | 42964
242743035 | S | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Vac jacket weld up) | 2014-10-13 08:00 | 2015-04-06 16:00 | 20% | 0 | 0 | 23185
242743040M | M | Cryostat Factory - Receive production coil case #4 | 2015-03-17 08:00 |  | 0% | 0 | 0 | 0
242743045 | S | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Receive, QA and Pre-assembly) | 2014-09-08 08:00 | 2015-03-18 16:00 | 15% | 0 | 10319 | 59452
242743050 | S | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (MLI and LN2 shield assembly) | 2014-09-08 08:00 | 2015-04-09 16:00 | 10% | 0 | 0 | 42964
242743055 | S | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY14 | 2014-10-14 08:00 | 2015-04-22 16:00 | 20% | 0 | 0 | 13911
242743055A | S | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) FY15 | 2014-10-14 08:00 | 2015-04-22 16:00 | 20% | 0 | 0 | 9570
242743060M | M | Cryostat Factory - Receive production coil case #5 | 2015-04-14 08:00 |  | 0% | 0 | 0 | 0
242743065 | S | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Receive, QA and Pre-assembly) | 2014-09-08 08:00 | 2015-05-18 16:00 | 15% | 0 | 10319 | 59452
242743070 | S | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY14 | 2014-09-08 08:00 | 2015-06-10 16:00 | 10% | 0 | 0 | 25778
242743070A | S | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) FY15 | 2014-09-08 08:00 | 2015-06-10 16:00 | 10% | 0 | 0 | 17734
242743075 | S | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Vac jacket weld up) | 2015-06-11 08:00 | 2015-07-01 16:00 | 0% | 0 | 0 | 23924
242743080M | M | Cryostat Factory - Receive production coil case #6 | 2015-05-06 08:00 |  | 0% | 0 | 0 | 0
242743085 | S | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY14 | 2014-09-08 08:00 | 2015-06-10 16:00 | 15% | 0 | 5503 | 31708
242743085A | S | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) FY15 | 2014-09-08 08:00 | 2015-06-10 16:00 | 15% | 0 | 4969 | 28630
242743090 | S | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (MLI and LN2 shield assembly) | 2014-09-08 08:00 | 2015-07-01 16:00 | 10% | 0 | 0 | 44335
242743095 | S | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Vac jacket weld up) | 2015-07-02 08:00 | 2015-07-23 16:00 | 0% | 0 | 0 | 23924
242743100M | M | Cryostat Factory - Receive production coil case #7 | 2015-05-26 08:00 |  | 0% | 0 | 0 | 0
242743105 | S | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Receive, QA and Pre-assembly) | 2014-09-08 08:00 | 2015-06-24 16:00 | 15% | 0 | 10648 | 61349
242743110 | S | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (MLI and LN2 shield assembly) | 2014-09-08 08:00 | 2015-07-22 16:00 | 10% | 0 | 0 | 44335
242743115 | S | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Vac jacket weld up) | 2015-07-24 08:00 | 2015-08-13 16:00 | 0% | 0 | 0 | 23924
242743120 | U | Cryostat Factory - Clean up And ship to site | 2015-07-17 08:00 | 2015-09-11 16:00 | 0% | 0 | 0 | 50970
242743125 | E | Cryostat Factory - Rework FY14 | 2014-03-03 08:00 | 2014-09-30 00:30 | 100% | 0 | 0 | 57487
242743125A | E | Cryostat Factory - Rework FY15 | 2014-10-01 08:00 | 2015-05-26 16:00 | 14.56% | 0 | 0 | 63329
242751000LOE | E | Torus - Engineering Oversight FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 21911
242751005LOE | E | Torus - Engineering Oversight FY14 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 283955
242751010 | D | Vend Fab Additional Coil Case for Coil # 7 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 25220 | 0 | 25220
242751010LOE | E | Torus - Engineering Oversight FY15 | 2014-10-01 08:00 | 21-Oct-14 16:00 A | 100% | 0 | 0 | 23590
242751020 | D | Torus - 1st Article Coil Case Procurement | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 20370 | 0 | 20370
242751045 | D | Torus - 6 Production Coil Cases Procurement | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 146130 | 0 | 146130
242751050 | H | Torus - 4K MLI Modeling and Drafting | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 994
242751080 | H | Torus - Vacuum Vessel Instrumentation Drafting | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 1074
242751090 | D | Torus - Vacuum Vessel Assembly Parts Procurement | 2013-10-21 08:00 | 18-Aug-14 16:00 A | 100% | 257975 | 0 | 257975
242751110 | H | Torus - Coil Case Shields Procurement Prep FY13 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 789
242751110a | H | Torus - Coil Case Shields Procurement Prep FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 977
242751115 | D | Torus - Coil Case Shields Procurement | 2013-10-21 08:00 | 17-Feb-14 16:00 A | 100% | 149223 | 0 | 149223
242751120 | H | Torus - Coil Case MLI Procurement Prep FY13 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 658
242751120a | H | Torus - Coil Case MLI Procurement Prep FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 2308
242751125 | D | Torus - Coil Case MLI Procurement | 2014-02-03 08:00 | 21-Apr-14 16:00 A | 100% | 21670 | 0 | 21670
242751145 | D | Torus - Out Of Plane Supports - OOPS Procurement | 2013-10-21 08:00 | 21-Apr-14 16:00 A | 100% | 144466 | 0 | 144466
242751150 | S | Torus - Cold Hub - Magnet construction analysis | 2013-09-09 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2509
242751155 | H | Torus - Cold Hub - Hub analysis with off design loads | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 3473
242751160 | H | Torus - Cold Hub - Hub Shield Modeling FY13 | 2013-09-03 08:00 | 17-Mar-14 14:02 A | 100% | 0 | 0 | 514
242751160a | H | Torus - Cold Hub - Hub Shield Modeling FY14 | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 903
242751165 | H | Torus - Cold Hub - Hub Shield straping for cooling design FY13 | 2013-09-03 08:00 | 20-Oct-14 15:30 A | 100% | 0 | 0 | 187
242751165a | H | Torus - Cold Hub - Hub Shield straping for cooling design FY14 | 2013-09-03 08:00 | 20-Oct-14 15:30 A | 100% | 0 | 0 | 405
242751170 | H | Torus - Cold Hub - Hub shield final drafting | 2014-02-18 08:00 | 2014-12-03 15:30 | 50% | 0 | 0 | 2987
242751175 | H | Torus - Cold Hub Procurement Prep | 2014-02-18 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 2987
242751180 | D | Torus - Cold Hub Procurement | 2014-03-24 08:00 | 19-May-14 16:00 A | 100% | 19792 | 0 | 19792
242751185 | H | Torus - Upstream Hex - 4K Beam Stress Analysis | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 2894
242751190 | H | Torus - Upstream Hex - Piping mounting design FY13 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 795
242751190a | H | Torus - Upstream Hex - Piping mounting design FY14 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 1231
242751195 | H | Torus - Upstream Hex - Coil to Coil lead force analysis and flexibility analysis | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 0 | 0 | 1447
242751200 | H | Torus - Upstream Hex - Recooler final design FY13 | 2013-09-03 08:00 | 18-Nov-13 14:11 A | 100% | 0 | 0 | 1265
242751200a | H | Torus - Upstream Hex - Recooler final design FY14 | 2013-09-03 08:00 | 18-Nov-13 14:11 A | 100% | 0 | 0 | 1567
242751205 | H | Torus - Upstream Hex - Recooler Mounting FY13 | 2013-09-03 08:00 | 18-Nov-13 14:11 A | 100% | 0 | 0 | 326
242751205a | H | Torus - Upstream Hex - Recooler Mounting FY14 | 2013-09-03 08:00 | 18-Nov-13 14:11 A | 100% | 0 | 0 | 403
242751210 | H | Torus - Upstream Hex - Recooler Drafting | 2013-11-11 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 1847
242751215 | H | Torus - Upstream Hex - Splice design and tooling design FY13 | 2013-09-03 08:00 | 2014-12-05 16:00 | 50% | 0 | 0 | 1060
242751215a | H | Torus - Upstream Hex - Splice design and tooling design FY14 | 2013-09-03 08:00 | 2014-12-05 16:00 | 50% | 0 | 0 | 1861
242751220 | H | Torus - Upstream Hex - Piping flexibility analysis | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 2026
242751225 | H | Torus - Upstream Hex - Shield final design and Drafting | 2013-11-04 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 5581
242751230 | H | Torus - Upstream Hex - VJ final design and Drafting | 2013-11-04 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 5039
242751235 | H | Torus - Upstream Hex Assembly Parts Procurement Prep | 2014-03-10 08:00 | 2014-06-16 08:00 | 100% | 0 | 0 | 2987
242751240 | D | Torus - Upstream Hex Assembly Parts Procurement | 2014-04-07 08:00 | 2014-12-05 16:00 | 85% | 101618 | 0 | 101618
242751245 | H | Torus - Recooler Procurement Prep | 2014-03-17 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 2987
242751250 | D | Torus - Recooler Procurement | 2014-05-19 08:00 | 18-Aug-14 16:00 A | 100% | 66401 | 0 | 66401
242751255 | H | Torus - Upstream Hex MLI Procurement Prep | 2014-05-12 08:00 | 2014-11-20 16:00 | 50% | 0 | 0 | 2987
242751260 | D | Torus - Upstream Hex MLI Procurement | 2014-11-21 08:00 | 2014-12-22 16:00 | 0% | 6191 | 0 | 6191
242751265 | H | Torus - Downstream Hex - 4K beam Stress Analysis | 2013-11-04 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 5974
242751270 | H | Torus - Downstream Hex - 4K piping analysis | 2013-11-18 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2987
242751275 | H | Torus - Downstream Hex - Shield final design and Drafting | 2013-11-18 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 6977
242751280 | H | Torus - Downstream Hex - VJ final design and Drafting | 2013-11-18 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 5039
242751285 | H | Torus - Downstream Hex Assembly Parts Procurement Prep | 2014-03-17 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 2987
242751290 | D | Torus - Downstream Hex Assembly Parts Procurement | 2014-04-07 08:00 | 2014-12-03 16:00 | 85% | 74430 | 0 | 74430
242751295 | H | Torus - Downstream Hex MLI Procurement Prep | 2014-04-14 08:00 | 2014-12-03 16:00 | 50% | 0 | 0 | 2987
242751300 | D | Torus - Downstream Hex MLI Procurement | 2014-12-04 08:00 | 2015-01-12 16:00 | 0% | 6191 | 0 | 6191
242751305 | H | Torus - Misc Hex MLI Procurement Prep | 2014-02-03 08:00 | 2014-12-03 16:00 | 50% | 0 | 0 | 2987
242751310 | D | Torus - Misc Hex MLI Procurement | 2014-12-04 08:00 | 2015-01-12 16:00 | 0% | 6191 | 0 | 6191
242751315 | H | Torus - Supply-Return Header to DS ring - Modeling | 2014-04-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 2987
242751320 | H | Torus - Supply-Return Header to DS ring - Piping flexibility analysis | 2014-04-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 2987
242751325 | H | Torus - Supply-Return Header to DS ring - Modeling/Drafting | 2014-04-01 08:00 | 2014-12-03 16:00 | 50% | 0 | 0 | 4104
242751330 | H | Torus - Supply-Return Header Procurement Prep | 2014-11-03 08:00 | 2015-02-18 16:00 | 0% | 0 | 0 | 2987
242751335 | D | Torus - Supply-Return Header Procurement | 2015-02-19 08:00 | 2015-04-08 16:00 | 0% | 8255 | 0 | 8255
242751345 | H | Torus - Main Cold mass support system - Supports Analyses | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1158
242751350 | H | Torus - Main Cold mass support system - Supports Modeling FY13 | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 398
242751350a | H | Torus - Main Cold mass support system - Supports Modeling FY14 | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 410
242751355 | H | Torus - Main Cold mass support system - Supports Drafting FY13 | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 795
242751355a | H | Torus - Main Cold mass support system - Supports Drafting FY14 | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 821
242751360 | H | Torus - Main Cold mass support system - Attachment to Floor Engineering | 2013-09-16 08:00 | 2015-02-03 16:00 | 50% | 0 | 0 | 8960
242751365 | H | Torus - Main Cold mass support system - Attachment to Floor Modeling and Drafting | 2013-09-16 08:00 | 2015-02-03 16:00 | 50% | 0 | 0 | 8960
242751370 | H | Torus - CM Support Assembly Parts Procurement Prep | 2014-06-10 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 2987
242751375 | D | Torus - CM Support Assembly Parts Procurement | 2014-09-08 08:00 | 2014-12-23 16:00 | 0% | 68105 | 0 | 68105
242751380 | H | Torus - Torus Support to Hall floor Assembly Procurement Prep | 2015-04-22 08:00 | 2015-05-06 16:00 | 0% | 0 | 0 | 2987
242751385 | D | Torus - Torus Support to Hall floor Assembly Procurement | 2015-05-07 08:00 | 2015-07-30 16:00 | 0% | 77393 | 0 | 77393
242751390 | S | Torus - Installation Design - Develop Installation Tooling Design | 2013-09-16 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 11947
242751395 | S | Torus - Installation Design - Model Installation Tooling | 2013-09-16 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 11947
242751400 | H | Torus - Installation Design - Analyze Installation Tooling | 2013-09-16 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 5974
242751405 | H | Torus - Installation Design - Installation Tooling Drafting | 2014-05-12 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 6156
242751410 | H | Torus - Installation Design - Develop Scaffolding Design | 2014-07-07 08:00 | 2014-11-14 16:00 | 50% | 0 | 0 | 4104
242751415 | S | Torus - Installation Design - Develop procedures and safety documentation | 2014-05-02 08:00 | 2015-01-09 16:00 | 75% | 0 | 0 | 27777
242751420 | H | Torus - Installation Parts Procurement Prep | 2014-07-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 2987
242751425 | H | Torus - LOV analyses - 4K piping analysis FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1182
242751425a | H | Torus - LOV analyses - 4K piping analysis FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1767
242751430 | H | Torus - LOV analyses - LN2 Piping FY13 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 965
242751430a | H | Torus - LOV analyses - LN2 Piping FY14 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 1991
242751435 | H | Torus - LOV analyses - Service module FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 724
242751435a | H | Torus - LOV analyses - Service module FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2240
242751440 | D | Torus - Installation Parts Procurement (90K Accounted for Cryo Jumpers) | 2014-10-01 08:00 | 2014-12-18 16:00 | 17% | 185742 | 0 | 185742
242751445 | D | Torus - Engineering Procured Labor Phase 1 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 35259 | 0 | 35259
242751450 | D | Torus - Engineering Procured Labor Phase 2 | 2014-04-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 0
242751455 | D | Vend Fab 1 Set of Additional Hardware for Cryostat (Cold Mass Shiled, OOPS, Axial Support, MLI, Vacuum Jacket) | 2014-05-02 08:00 | 18-Aug-14 16:00 A | 100% | 45350 | 0 | 45350
242761000 | H | Hall B - Distribution Can - Drafting Mechanical | 2014-02-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 4374
242761005 | H | Hall B - Distribution Can - Drafting Structural | 2014-03-17 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 3181
242761010 | H | Hall B - Distribution Can - ProjectMgt FY13 | 2013-09-03 08:00 | 2014-12-04 16:00 | 50% | 0 | 0 | 556
242761010a | H | Hall B - Distribution Can - ProjectMgt FY14 | 2013-09-03 08:00 | 2014-12-04 16:00 | 50% | 0 | 0 | 6893
242761015 | H | Hall B - Distribution Can - QA | 2014-03-17 08:00 | 2014-12-03 16:00 | 50% | 0 | 0 | 7766
242761020 | H | Hall B - Distribution Can - Write Specs | 2013-09-16 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 8960
242761025 | H | Hall B - Distribution Can - Bid and select vendor | 2014-07-07 08:00 | 2015-02-13 16:00 | 50% | 0 | 0 | 5974
242761030 | D | Hall B - Distribution Can Procurement | 2015-02-16 08:00 | 2015-11-16 16:00 | 0% | 372976 | 0 | 372976
242762000 | S | Torus - Cryogenic Tower - Mechanical Engineering FY13 | 2013-09-03 08:00 | 2014-12-03 16:00 | 64% | 0 | 0 | 11578
242762000a | S | Torus - Cryogenic Tower - Mechanical Engineering FY14 | 2013-09-03 08:00 | 2014-12-03 16:00 | 64% | 0 | 0 | 32855
242762005 | H | Torus - Cryogenic Tower - Structural Engineering | 2013-10-01 08:00 | 2014-12-04 16:00 | 50% | 0 | 0 | 5974
242762010 | H | Torus - Cryogenic Tower - Electrical/Instrumentation Engineering | 2013-09-16 08:00 | 2014-12-04 16:00 | 50% | 0 | 0 | 3005
242762015 | S | Torus - Cryogenic Tower - Drafting Mechanical | 2013-09-16 08:00 | 2014-12-03 16:00 | 8.7% | 0 | 0 | 32832
242762020 | H | Torus - Cryogenic Tower - Drafting Structural | 2013-10-17 08:00 | 2014-12-03 16:00 | 50% | 0 | 0 | 6156
242762025 | H | Torus - Cryogenic Tower - ProjectMgt | 2013-10-17 08:00 | 2014-12-03 16:00 | 50% | 0 | 0 | 5974
242762030 | H | Torus - Cryogenic Tower - Drawing review and sign-off | 2014-12-04 08:00 | 2015-01-05 16:00 | 0% | 0 | 0 | 8960
242762035 | H | Torus - Cryogenic Tower - Write Specs | 2014-12-04 08:00 | 2015-01-05 16:00 | 0% | 0 | 0 | 8960
242762040 | H | Torus - Cryogenic Tower - Bid and select vendor | 2015-01-06 08:00 | 2015-01-29 16:00 | 0% | 0 | 0 | 5974
242762045 | D | Torus - Cryogenic Tower Procurement | 2015-01-30 08:00 | 2015-12-14 16:00 | 0% | 372976 | 0 | 372976
242771000 | S | Torus - Instrumentation Controls Design | 2013-11-04 08:00 | 2015-05-29 16:00 | 38% | 0 | 0 | 22474
242771005 | S | Torus - Instrumentation Magnet Protection System Design | 2013-11-04 08:00 | 2014-11-26 16:00 | 39% | 0 | 0 | 93323
242771010 | S | Torus - Instrumentation Sensors Procurement | 2013-11-05 08:00 | 22-Sep-14 16:00 A | 100% | 145500 | 0 | 145500
242771015 | H | Torus - Instrumentation Controls Procurement Prep | 2014-07-14 08:00 | 2014-11-21 16:00 | 50% | 0 | 0 | 3101
242771020 | D | Torus - Instrumentation Controls Procurement | 2014-08-18 08:00 | 2015-02-04 16:00 | 0% | 37269 | 0 | 37269
242771025 | H | Torus - Instrumentation Magnet Protection System Procurement Prep | 2014-02-03 08:00 | 2015-01-20 16:00 | 50% | 0 | 0 | 3101
242771030 | S | Torus - Instrumentation Magnet Protection System Procurement | 2014-09-08 08:00 | 2015-01-06 16:00 | 0% | 68843 | 0 | 68843
242771035 | S | Torus - Instrumentation Controls Assembly | 2014-11-03 08:00 | 2015-05-04 16:00 | 0% | 0 | 0 | 137466
242771040 | D | Torus - Vend Fab Power Supply - Peg Point #1 - Approval of Design | 2014-05-01 08:00 | 27-Jun-14 16:00 A | 100% | 59715 | 0 | 59715
242771045 | D | Torus - Vend Fab Power Supply - Peg Point #2 - Materials Received and Inspected at Vendor/Fabrication Start | 2014-05-01 08:00 | 20-Oct-14 16:00 A | 100% | 59715 | 0 | 59715
242771050 | D | Torus - Vend Fab Power Supply - Peg Point #3 - Factory Test Completed and Accepted/Shipment | 2014-05-01 08:00 | 2015-03-31 16:00 | 0% | 59715 | 0 | 59715
242771055 | D | Torus - Vend Fab Power Supply - Peg Point #4 - Acceptance Test at JLab | 2014-05-01 08:00 | 2016-06-03 16:00 | 0% | 19905 | 0 | 19905
242771060 | D | Torus - Vend Fab Power Supply - Peg Point #5 - Receipt of Spares | 2014-05-01 08:00 | 2015-03-31 16:00 | 0% | 13020 | 0 | 13020
242781000LOE | E | Solenoid - Technical Support & Oversite FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 2685 | 28353
242781005LOE | E | Solenoid - Technical Support & Oversite FY14 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 36117 | 360981
242781010LOE | E | Solenoid - Technical Support & Oversite FY15 | 2014-10-01 08:00 | 2015-01-05 16:00 | 38.98% | 0 | 10648 | 71089
242781015 | S | Solenoid - Magent Installation Design | 2013-10-01 08:00 | 2014-12-23 16:00 | 50% | 0 | 0 | 125034
242781020 | D | Solenoid - Magent Installation Procurements | 2015-03-03 08:00 | 2015-08-20 16:00 | 0% | 41276 | 0 | 41276
242781025 | S | Solenoid Commissioning - Design & Documentation FY14 | 2014-11-03 08:00 | 2015-06-12 16:00 | 0% | 0 | 0 | 19620
242781025A | S | Solenoid Commissioning - Design & Documentation FY15 | 2015-06-15 08:00 | 2015-08-12 16:00 | 0% | 0 | 0 | 5784
242791000 | S | Solenoid - Thermal Analysis FY13 | 2013-09-03 08:00 | 22-Sep-14 14:38 A | 100% | 0 | 0 | 11578
242791000a | S | Solenoid - Thermal Analysis FY14 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 29868
242791005 | S | Solenoid - Process P&Is | 2014-01-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 15116
242791010 | H | Solenoid - Cryogenic Modes of Operation | 2013-09-09 08:00 | 2015-02-03 16:00 | 50% | 0 | 0 | 8960
242791015 | H | Solenoid - PDR | 2014-01-06 08:00 | 2015-02-03 16:00 | 50% | 0 | 0 | 1792
242791020 | H | Solenoid - Evaluation of Process Components | 2013-09-09 08:00 | 2015-02-03 16:00 | 50% | 0 | 0 | 9759
242791025 | S | Solenoid - Current Leads | 2014-05-12 08:00 | 2015-02-03 16:00 | 0% | 0 | 0 | 11223
242791030 | S | Solenoid - Mechanical Design of the cryogenic can | 2014-11-11 08:00 | 2015-05-26 16:00 | 0% | 0 | 0 | 58555
242791035 | H | Solenoid - FDR | 2015-05-27 08:00 | 2015-05-27 16:00 | 0% | 0 | 0 | 597
242791040 | H | Solenoid Cryogenics - Write Specifications FY14 | 2015-04-08 08:00 | 2015-04-21 16:00 | 0% | 0 | 0 | 2987
242791040A | D | Solenoid Cryogenics - Write Specifications FY15 | 2015-04-22 08:00 | 2015-05-05 16:00 | 0% | 0 | 0 | 6164
242791045 | H | Solenoid Cryogenics - Bid cycle, review and award | 2015-05-28 08:00 | 2015-06-10 16:00 | 0% | 0 | 0 | 6164
242791050 | D | Solenoid Cryogenics - Procurement | 2015-06-11 08:00 | 2015-12-14 16:00 | 0% | 305603 | 53241 | 358844
242791055 | H | Solenoid cryogenics - Installation and Commissioning | 2015-12-15 08:00 | 2016-01-13 16:00 | 0% | 0 | 0 | 7553
242791060 | H | Solenoid cryogenics - Test of system | 2016-01-14 08:00 | 2016-02-11 16:00 | 0% | 0 | 0 | 10070
24311071 | S | HB Drawing Validation FY14 | 2015-05-18 08:00 | 2015-07-20 16:00 | 0% | 0 | 0 | 10342
24311071A | S | HB Drawing Validation FY15 | 2015-05-18 08:00 | 2015-07-20 16:00 | 0% | 0 | 0 | 14738
24311072 | U | HB Site Inspections FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 1186 | 1186
24311072a | U | HB Site Inspections FY14 | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 2458 | 2458
24311077 | H | Finducialize Magnet CL of SHMS HB Magnet | 2015-08-05 08:00 | 2015-08-05 16:00 | 0% | 0 | 0 | 1986
24311110 | D | Vend Fab HB Magnet Peg Point #10 Weld back He Vessel Plate; Shield Preassembly; Fab Vac Wall Parts | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 73821 | 0 | 73821
24311115 | D | Vend Fab HB Magnet Peg Point #11 Close He Vessel; Preassemble Cryostat Vac Wall | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 37168 | 0 | 37168
24311120 | D | Vend Fab HB Magnet Peg Point #12 NDT & Warm Testing; Assemble Shield to He Vessel | 2013-09-03 08:00 | 30-Jun-14 16:00 A | 100% | 83471 | 0 | 83471
24311125 | D | Vend Fab HB Magnet Peg Point #13 Shield Support Assy, Instrumentation & Insulation | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 19769 | 0 | 19769
24311130 | D | Vend Fab HB Magnet Peg Point #14 Suspend He Vessel/Shield; Complete Vac. Walls 2,3 | 2013-09-03 08:00 | 31-Oct-14 16:00 A | 100% | 25966 | 0 | 25966
24311135 | D | Vend Fab HB Magnet Peg Point #15 Finish Vac Wall & Support Links | 2013-09-03 08:00 | 2014-11-19 16:00 | 50% | 22977 | 0 | 22977
24311140 | D | Vend Fab HB Magnet Peg Point #16 Finish & Leak Check Cryo Header | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 15692 | 0 | 15692
24311145 | D | Vend Fab HB Magnet Peg Point #17 Assemble CCR to Magnet | 2013-09-03 08:00 | 08-Oct-14 16:00 A | 100% | 26315 | 0 | 26315
24311150 | D | Vend Fab HB Magnet Peg Point #18 Connect Leads, Instr. He Vessel, Leak Check Cryo, Finish Shield Conn. | 2014-02-03 08:00 | 2015-01-09 16:00 | 0% | 50515 | 0 | 50515
24311155 | D | Vend Fab HB Magnet Peg Point #19 Finish Insul & Vac; Leak Check; Fab shipping structure | 2014-02-03 08:00 | 2015-05-01 16:00 | 0% | 33594 | 0 | 33594
24311160 | D | Vend Fab HB Magnet Peg Point #20 Crate & Deliver HB Magnet to JLab | 2014-02-03 08:00 | 2015-05-15 16:00 | 0% | 13458 | 0 | 13458
24311165 | D | Vend Fab HB Magnet Peg Point #21 Acceptance, Setup, Testing, and Mapping at JLab | 2014-02-03 08:00 | 2015-08-04 16:00 | 0% | 35345 | 0 | 35345
24311168 | D | Vend Fab HB Magnet Contract Closeout | 2014-02-03 08:00 | 2015-06-29 16:00 | 0% | 80000 | 0 | 80000
24311170 | H | HB- Factory Mag Test of HB Mag | 2014-11-24 08:00 | 2015-01-23 16:00 | 0% | 0 | 2492 | 7531
243118P4LOE | E | HB Contract Mngmnt for HB Mag | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 624 | 3278
243118P5LOE | E | HB Contract Mngmnt for HB Mag | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 9287 | 32247
243118P6LOE | E | HB Contract Mngmnt for HB Mag | 2014-10-01 08:00 | 2015-01-05 16:00 | 38.98% | 0 | 2662 | 11908
24312040d | P | Vend Fab Q1 Completion of Cold Mass Testing | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 54294 | 0 | 54294
24312041a | P | Vend Fab Q1 Warm Testing Complete | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 54294 | 0 | 54294
24312046 | P | Vend Fab Q1 Completion of Cryostat Assembly | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 54294 | 0 | 54294
24312047 | P | Vend Fab Q1 Completion of Magnet Assembly | 2013-09-03 08:00 | 08-Sep-14 16:00 A | 100% | 54294 | 0 | 54294
24312048 | P | Vend Fab Q1 Completion of Factory Tests by Vendor | 2013-09-03 08:00 | 2014-12-18 16:00 | 0% | 54294 | 0 | 54294
24312050 | P | Vend Fab Q1 Magnet System Delivery | 2013-09-03 08:00 | 2015-01-15 16:00 | 0% | 54294 | 0 | 54294
24312050c | P | Vend Fab Q1 Magnet Acceptance | 2013-09-03 08:00 | 2015-03-19 16:00 | 0% | 108588 | 0 | 108588
24312050d | S | Q1 Drawing Validation FY14 | 2015-01-16 08:00 | 2015-04-23 16:00 | 0% | 0 | 0 | 15759
24312050dA | S | Q1 Drawing Validation FY15 | 2015-01-16 08:00 | 2015-04-23 16:00 | 0% | 0 | 0 | 9148
24312051M | M | Q1 Acceptance Test Complete |  | 2015-03-19 16:00 | 0% | 0 | 0 | 0
24312052M | M | Factory Low Current Mag Test of Q1 Complete |  | 30-Jun-14 16:00 A | 100% | 0 | 0 | 0
24312053M | M | Q1 Delivered to JLab |  | 2015-01-15 16:00 | 0% | 0 | 0 | 0
24312055 | Z | Pay Profit on Q1 | 2015-03-20 08:00 | 2015-03-20 16:00 | 0% | 0 | 0 | 0
24312060 | S | Q1 Schedule Acceleration Incentives | 2013-09-03 08:00 | 2015-01-09 16:00 | 49% | 45000 | 0 | 45000
243128P5LOE | E | Q1- P-5 Contract Mngmnt for Q1 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 998 | 3419
243128P5TLOE | E | Q1- P-5 Extra Travel for Q1 Contract Mgmt | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 698 | 698
243128P6LOE | E | Q1- P-6 Contract Mngmnt for Q1 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 20638 | 53493
243128P6LOE5 | E | Q1- P-7 Contract Mngmnt for Q1 | 2014-10-01 08:00 | 2014-12-18 16:00 | 41.82% | 0 | 0 | 8476
243128PC13LOE | E | Q1- Contract Oversight Consultant | 2013-09-03 08:00 | 31-Jan-14 16:00 A | 100% | 4000 | 0 | 4000
243128PC13LOE5 | E | Q1- Contract Oversight Consultant | 2014-02-03 08:00 | 31-Jul-14 16:00 A | 100% | 8255 | 0 | 8255
24312913LOE | E | Q1- FY13 Proj Mngmnt H-C upgrade | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 5169
24312914LOE | E | Q1- FY14 Proj Mngmnt H-C upgrade | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 66158
24312915LOE | E | Q1- FY15 Proj Mngmnt H-C upgrade | 2014-10-01 08:00 | 2015-09-30 16:00 | 9.35% | 0 | 0 | 68270
24312915LOE5 | E | Q1- FY16 Proj Mngmnt H-C upgrade | 2015-10-01 08:00 | 2015-12-22 16:00 | 0% | 0 | 0 | 9310
24313000M | P | Q2 Start Coil Winding | 2014-09-02 08:00 |  | 100% | 0 | 0 | 0
24313002M | P | Q2 Finish Coil Winding |  | 2014-12-12 16:00 | 0% | 0 | 0 | 0
24313004M | P | Q3 Start Coil Winding | 2014-12-12 08:00 |  | 0% | 0 | 0 | 0
24313006M | P | Q3 Finish Coil Winding |  | 2015-03-30 16:00 | 0% | 0 | 0 | 0
24313008M | P | Q2 Factory Assembly Complete |  | 2015-09-11 16:00 | 0% | 0 | 0 | 0
24313010M | P | Q3 Factory Assembly Complete |  | 2015-12-02 16:00 | 0% | 0 | 0 | 0
24313015 | P | Vend Fab Q2&3 Peg Point #2 Final Design Review | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 489700 | 0 | 489700
24313017 | P | Vend Fab Q2&3 Peg Point #3 Cryostat Component Complete | 2013-09-03 08:00 | 2015-05-11 16:00 | 0% | 432250 | 0 | 432250
24313019 | P | Vend Fab Q2&3 Peg Point #4 Cold Mass Fiducialitzation | 2013-09-03 08:00 | 2015-12-23 16:00 | 0% | 432250 | 0 | 432250
24313019a | P | Vend Fab Q2&3 Peg Point #5 Shipment | 2013-09-03 08:00 | 2016-02-10 16:00 | 0% | 1321000 | 0 | 1321000
24313019b | P | Vend Fab Q2&3 Peg Point #6 Final Acceptance | 2013-09-03 08:00 | 2016-05-19 16:00 | 0% | 146100 | 0 | 146100
24313030 | H | FDR Site Inspection FY13 | 2013-09-06 08:00 | 21-Oct-13 15:41 A | 100% | 0 | 7956 | 10416
24313030a | H | FDR Site Inspection FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 1449 | 1897
24313220 | H | Q2 and Q3 Coil Inspection | 2015-03-03 08:00 | 2015-04-30 16:00 | 0% | 0 | 4983 | 8065
24313230 | H | Q2 and Q3- Insp Cold Mass | 2015-11-30 08:00 | 2015-12-07 16:00 | 0% | 0 | 5142 | 8224
24313235 | H | Q2 and Q3 witness Pressure Tests | 2015-10-14 08:00 | 2015-12-04 16:00 | 0% | 0 | 5142 | 5142
24313270M | M | Q2 and Q3 Contract complete |  | 2016-06-02 16:00 | 0% | 0 | 0 | 0
24313275 | S | Q2&Q3 Drawing Validation | 2016-01-13 08:00 | 2016-06-02 16:00 | 0% | 0 | 0 | 25411
24313280 | D | Planning Package SigmaPhi Quads (second winding station) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 100000 | 0 | 100000
24313285 | D | Q2/Q3 portion of consolodation equipment and processing | 2013-11-18 08:00 | 2014-12-05 16:00 | 46% | 195211 | 0 | 195211
24313P4LOE | E | Q2&3- P-4 Contract Mngmnt for Q2-3 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 998 | 3886
24313P5LOE | E | Q2&3- P-5 Contract Mngmnt for Q2-3 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 6389 | 40270
24313P6LOE | E | Q2&3- P-6 Contract Mngmnt for Q2-3 | 2014-10-01 08:00 | 2015-10-01 16:00 | 9.31% | 0 | 21296 | 55198
24313P6LOE5 | E | Q2&3- P-7 Contract Mngmnt for Q2-3 | 2015-10-02 08:00 | 2015-12-22 16:00 | 0% | 0 | 0 | 8476
24314012 | P | Vend Fab Dipole Final Design Review Peg Point #3 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 97500 | 0 | 97500
24314015M | P | Start Coil Windings | 2014-02-17 08:00 |  | 100% | 0 | 0 | 0
24314020 | P | Vend Fab Dipole Second Coil Wind Peg Point #4 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 391930 | 0 | 391930
24314027 | P | Vend Fab Dipole Outer Vessel Completed Peg Point #5 (F-12) | 2013-09-03 08:00 | 2015-04-10 16:00 | 0% | 436875 | 0 | 436875
24314028 | P | Vend Fab Dipole Conductor 4K Testing Peg Point #5a | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 26000 | 0 | 26000
24314029 | P | Assembly Complete | 2013-09-03 08:00 | 2015-07-10 16:00 | 0% | 0 | 0 | 0
24314030 | P | Vend Fab Dipole Factory Test Completed Peg Point #6 | 2013-09-03 08:00 | 2015-08-31 16:00 | 0% | 333300 | 0 | 333300
24314030a | Z | Dipole Magnet Shipping | 2015-09-01 08:00 | 2015-11-04 16:00 | 0% | 0 | 0 | 0
24314035 | P | Vend Fab Dipole Magnet Accepted Peg Point #7 | 2013-09-03 08:00 | 2016-03-08 16:00 | 0% | 159910 | 0 | 159910
24314035a | H | Dipole HC Test | 2016-02-23 08:00 | 2016-02-29 16:00 | 0% | 0 | 0 | 8117
24314040 | S | Dipole Drawing Validation | 2015-11-05 08:00 | 2016-03-22 16:00 | 0% | 0 | 0 | 25411
24314047 | H | Dipole Inspect Coil | 2014-09-22 08:00 | 25-Sep-14 16:00 A | 100% | 0 | 4829 | 7816
24314048 | H | Dipole Inspect Cold Mass FY14 | 2015-01-16 08:00 | 2015-02-13 16:00 | 0% | 0 | 2492 | 3985
24314048A | H | Dipole Inspect Cold Mass FY15 | 2015-01-16 08:00 | 2015-02-13 16:00 | 0% | 0 | 2571 | 4112
24314049 | H | Dipole Witness Final Factory Tests | 2015-07-07 08:00 | 2015-08-31 16:00 | 0% | 0 | 5142 | 8224
24314050M | M | Dipole Ready for Installation | 2015-11-05 08:00 |  | 0% | 0 | 0 | 0
24314051M | M | Dipole Contract Complete | 2016-03-23 08:00 |  | 0% | 0 | 0 | 0
24314110 | D | SigmaPhi Phase 2 ( Coil Development, VPI ) | 2013-11-18 08:00 | 19-May-14 16:00 A | 100% | 296889 | 0 | 296889
24314P4LOE | E | Dipole- P-4 Contract Mngmnt for Dipole | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 998 | 3186
24314P4TLOE | E | Dipole- P-4 Contract Extra Travel | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 1566 | 1566
24314P5LOE | E | Dipole- P-5 Contract Mngmnt for Dipole | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 30957 | 54851
24314P5LOET | E | Dipole- P-5 Contract Extra Travel | 2013-12-02 | 30-Sep-14 16:00 A | 100% | 0 | 18005 | 41900
24314P6LOE | E | Dipole- P-6 Contract Mngmnt for Dipole | 2014-10-01 08:00 | 2015-09-30 16:00 | 9.35% | 0 | 31945 | 56601
24315007 | S | Test & Integrate DC Pwr Sys for all magnets | 2014-06-02 08:00 | 2015-06-04 16:00 | 20% | 0 | 0 | 41521
24315015Ba | D | Obtain Short-Sample SC Measurements | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 15278 | 0 | 15278
24315015Bb | D | Obtain RRR Measurement of Copper Part B FY13 | 2013-09-03 08:00 | 2014-04-21 09:16 | 100% | 0 | 0 | 1656
24315015Bba | D | Obtain RRR Measurement of Copper Part B FY14 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 2051
24315036a5 | S | Proc Instruments & Controls for Q2/3 and Dipole magnets Part B | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 15000 | 0 | 15000
24315037b | S | Assemble & Test Instruments & Controls Phase 3 FY13 | 2013-09-03 08:00 | 2014-09-22 11:21 | 100% | 0 | 0 | 15361
24315037ba | S | Assemble & Test Instruments & Controls Phase 3 FY14 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 84804
24315050LOEg | E | Procurement Oversight FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 2258
24315080 | D | Vend Fab DCPS - Arrival Test of Items 1&2 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 14000 | 0 | 14000
24315090 | D | Vend Fab DCPS - Arrival Test of Items 3,4,&5 | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 26660 | 0 | 26660
243161000 | P | Vendor wind Spare Q2/Q3 Coil | 2015-07-01 08:00 | 2015-11-16 16:00 | 0% | 212964 | 0 | 212964
243161005 | P | Vendor Prepare Tooling to wind Spare Dipole Coil | 2015-07-01 08:00 | 2015-07-22 16:00 | 0% | 26620 | 0 | 26620
243161010 | P | Vendor wind Spare Dipole Coil | 2015-07-23 08:00 | 2015-12-18 16:00 | 0% | 212964 | 0 | 212964
243161015 | P | Vendor storage of Spare Coils | 2015-12-21 08:00 | 2016-02-11 16:00 | 0% | 21296 | 0 | 21296
243161020 | P | Vendor ship spare coils to JLab | 2016-02-12 08:00 | 2016-03-10 16:00 | 0% | 26620 | 0 | 26620
243161030LOE | E | Oversight of Spare Coil Winding | 2015-07-01 08:00 | 2015-12-17 16:00 | 0% | 0 | 26620 | 99972
24321007 | D | Procure Connectors and Components | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 0
24321015M | Z | Test Wire Chambers at University |  | 14-Jul-14 16:00 A | 100% | 0 | 0 | 0
24323005b | D | Fab Noble Gas Cerenkov Procurement | 2013-09-03 08:00 | 2015-04-01 16:00 | 43% | 111881 | 0 | 111881
24323012 | D | Build Vacuum Box | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 13109 | 0 | 13109
24323025 | H | Install NGC Gas Mixer in Gas Shed | 2013-12-02 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 3786
243238P1LOEb | E | P-2 Supervise Constrctn of Noble Gas Cerenkov | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 971
24324005 | S | Assemble HGC Gas System & Leak-check tank | 2014-02-03 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 15142
24325027a | D | Procure CTP for Calorimeter Ref. Hall D 1543025 | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 4502 | 0 | 4502
24325030 | H | Fiducialize SHMS Shower Counter (Frame) | 2013-12-02 08:00 | 16-Dec-13 16:00 A | 100% | 0 | 0 | 757
24328005 | D | Calorimeter Support Frame TBP | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 15150 | 0 | 15150
24328010ba | D | Rigging Fixtures for individual Detctr's Procurement Part B | 2015-04-02 08:00 | 2015-05-20 16:00 | 0% | 31141 | 0 | 31141
2433000 | D | Buy 5 Fast PC's for Data Acq & Processing (COMP) | 2014-09-06 08:00 | 22-Sep-14 16:00 A | 100% | 19842 | 0 | 19842
2433005 | D | Buy File Servers for Data Acq System (COMP) | 2014-09-06 08:00 | 22-Sep-14 16:00 A | 100% | 12856 | 0 | 12856
2433010 | D | Buy 8 Workstations/Monitors (COMP) | 2014-09-02 08:00 | 20-Oct-14 16:00 A | 100% | 12856 | 0 | 12856
24341000 | S | DAQ Trigger Development FY13 | 2013-09-03 08:00 | 2014-03-17 10:55 | 100% | 0 | 0 | 3362
24341000a | S | DAQ Trigger Development FY14 | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 14574
24341085 | D | Proc CTP Module for DF2 | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 5181 | 0 | 5181
24342055 | D | Fab Cable Tray & Bus Support | 2014-01-03 08:00 | 21-Apr-14 16:00 A | 100% | 26620 | 0 | 26620
24351020 | H | Modify Moeller Collimator- Manufacturing Drawings | 2014-05-19 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 8208
24351030 | D | Modify Moeller Collimator - FAB/PROCURE | 2014-07-16 08:00 | 18-Aug-14 16:00 A | 100% | 24039 | 10319 | 41112
24353010 | U | Fabricate and Use New ARC Mapper FY13 | 2013-09-03 08:00 | 16-Jun-14 14:38 A | 100% | 0 | 0 | 11577
24353010a | U | Fabricate and Use New ARC Mapper FY14 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 34047
24353015 | U | Refurb Existing Harmonic Coil for SHMS Mags | 2014-02-03 08:00 | 2015-01-30 16:00 | 80% | 46158 | 33040 | 126576
24354008 | U | Evaluate Chamber Seal Options | 2014-04-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 9800
24354010 | S | Detail Replacement Seal | 2014-06-01 08:00 | 2014-12-23 16:00 | 50% | 0 | 0 | 21293
24354015a | D | Fabricate New Seals / Flanges Expenses FY14 | 2015-01-05 08:00 | 2015-03-04 16:00 | 0% | 0 | 25846 | 25846
24354015B | U | Fabricate New Seals / Flanges Expenses FY15 | 2015-03-05 08:00 | 2015-04-06 16:00 | 0% | 0 | 14605 | 14605
24354015C | U | Fabricate New Seals / Flanges Procurement | 2015-01-05 08:00 | 2015-04-06 16:00 | 0% | 40000 | 0 | 40000
24354020 | D | Procure Seal Supplies FY14 | 2015-02-04 08:00 | 2015-03-04 16:00 | 0% | 0 | 7542 | 7542
24354020A | U | Procure Seal Supplies FY15 | 2015-03-05 08:00 | 2015-04-06 16:00 | 0% | 0 | 8523 | 8523
24354022 | H | Fabricate, Install, Test Seal and Windows | 2015-04-07 08:00 | 2015-04-30 16:00 | 0% | 0 | 0 | 7813
24354030 | H | Specify & Order Valves, Adapters, Flanges, Gauges | 2015-01-05 08:00 | 2015-02-03 16:00 | 0% | 0 | 0 | 4104
24354030b | D | Procure Gate Valves, BL Adapters, Gauges, Fittings | 2015-02-04 08:00 | 2015-04-06 16:00 | 0% | 37000 | 0 | 37000
24354030b5 | S | Install Valves, Gauges, Fittings on SC | 2015-05-01 08:00 | 2015-05-28 16:00 | 0% | 0 | 0 | 7813
24355000 | S | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY14 | 2014-06-02 08:00 | 2014-11-26 16:00 | 0% | 0 | 0 | 55113
24355000A | S | Produce Manufacturing Drawings for Beam Pipe, Stands, Fittings FY15 | 2014-06-02 08:00 | 2014-11-26 16:00 | 0% | 0 | 0 | 888
24355005 | D | Proc 1st Pipe (Beam Pipe) | 2014-12-08 08:00 | 2015-03-10 16:00 | 0% | 14604 | 0 | 33145
24355010 | D | Proc 2nd Section of Beam Pipe (Beam Pipe) | 2014-12-08 08:00 | 2015-03-05 16:00 | 0% | 22549 | 0 | 45325
24355015 | D | Proc 3rd Section of Beam Pipe (Beam Pipe) | 2015-02-04 08:00 | 2015-04-22 16:00 | 0% | 27846 | 2648 | 55388
24355020 | D | Proc Windows & Window Spool (Beam Pipe) | 2015-02-26 08:00 | 2015-06-25 16:00 | 0% | 37153 | 0 | 74211
24355025 | D | Proc Beam Stands (Beam Pipe) | 2015-02-26 08:00 | 2015-06-25 16:00 | 0% | 18577 | 0 | 18577
24355030 | D | Proc Vac Fittings (Beam Pipe) | 2015-02-26 08:00 | 2015-06-25 16:00 | 0% | 15517 | 0 | 15517
24362000 | U | Engineering Consulting | 2013-09-03 08:00 | 2013-09-16 08:00 | 100% | 1520 | 0 | 1520
24363030aa | U | Assemble Cast Panels and Lead Sheets (SHIELD HOUSE) | 2013-09-03 08:00 | 2013-10-21 08:00 | 100% | 7775 | 0 | 7775
24363035 | D | Fab Doors and associated hardware for Shield House (SHIELD HOUSE) Part A | 2013-09-03 08:00 | 2013-11-18 | 100% | 15590 | 0 | 15590
24363036 | D | Fab Doors and associated hardware for Shield House (SHIELD HOUSE) Part B | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 1987 | 0 | 1987
24363037 | D | Fab Doors and associated hardware for Shield House (SHIELD HOUSE) Part C Procurement | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 8111 | 0 | 8111
24363037a | D | Fab Doors and associated hardware for Shield House (SHIELD HOUSE) Part C Labor FY13 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 779
24363037b | D | Fab Doors and associated hardware for Shield House (SHIELD HOUSE) Part C Labor FY14 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 3095
24363041 | D | Plastic Pellets | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 1949 | 0 | 1949
24363046 | D | Rental Containers for Plastic Pellets | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 336 | 0 | 336
24363060 | D | Fab Various Small Components (SHIELD HOUSE) | 2014-01-03 08:00 | 19-May-14 16:00 A | 100% | 7475 | 33438 | 46887
24364016 | S | Modify G0 Transfer Line | 2013-10-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 147019
24364030 | U | Fab SHMS Gas Manifolds (CRYO SYS) Part A - Procurement | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 10196 | 0 | 10196
24364030a | U | Fab SHMS Gas Manifolds (CRYO SYS) Part A Labor FY13 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 5140
24364030b | U | Fab SHMS Gas Manifolds (CRYO SYS) Part A Labor FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 4774
24364043 | S | Produce Drawings for Cryo System Connections & Controls FY13 | 2013-09-03 08:00 | 17-Feb-14 14:06 A | 100% | 0 | 0 | 3028
24364043a | S | Produce Drawings for Cryo System Connections & Controls FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 3594
24364065 | D | Proc Cables,panels & Pwr Supplies (CRYO SYS) | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 12857 | 0 | 22935
24364075 | D | Proc & Fab Various Connections etc (CRYO SYS) | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 58689 | 19286 | 80961
24365020 | D | Proc Valves & Plumbing and Reliefs Part A | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 20707 | 0 | 20707
24365020a | D | Proc Valves & Plumbing and Reliefs Part A Labor FY13 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 467
24365020b | D | Proc Valves & Plumbing and Reliefs Part A Labor FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1012
24365023 | H | Manufacturing Drawings for Vacuum System Parts FY13 | 2013-09-03 08:00 | 2014-01-20 08:44 | 100% | 0 | 0 | 2029
24365023a | H | Manufacturing Drawings for Vacuum System Parts FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 8166
24365025 | D | Proc Valves & Plumbing and Reliefs Part B | 2013-09-03 08:00 | 2015-04-30 16:00 | 80% | 88724 | 0 | 88724
24365030 | D | Proc Spool & Bellows for All Magnets Part A | 2013-09-03 08:00 | 2013-11-18 | 100% | 14447 | 0 | 14447
24365032 | D | Proc Spool & Bellows for All Magnets Part B | 2013-10-07 08:00 | 2015-04-30 16:00 | 41% | 20638 | 0 | 20638
24365035 | D | Proc Windows & Flanges Part A | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 18066 | 0 | 18066
24365040 | D | Proc Windows & Flanges Part B | 2015-03-05 08:00 | 2015-05-01 16:00 | 0% | 19929 | 0 | 19929
24365045 | D | Proc Sieve Slit Sys Part A | 2013-09-03 08:00 | 2013-11-18 | 100% | 29198 | 0 | 29198
24365047 | D | Proc Sieve Slit Sys Part B | 2014-01-06 08:00 | 20-Oct-14 16:00 A | 100% | 65113 | 0 | 65113
24365050 | S | Fab Slit Controls Labor FY14 | 2014-10-01 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 2328
24365050A | S | Fab Slit Controls Labor FY15 | 2014-10-01 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 3762
24365050B | D | Fab Slit Controls Procurement | 2014-10-01 08:00 | 20-Oct-14 16:00 A | 100% | 12472 | 0 | 12472
24366025 | U | Terminate Cables | 2014-09-03 08:00 | 2015-01-27 16:00 | 33% | 0 | 0 | 15037
24368015M | M | Cryogens Available from ESR or CHL | 2014-03-25 08:00 |  | 100% | 0 | 0 | 0
24368020 | Z | Cool Down HMS Dipole | 2014-04-01 08:00 | 23-Apr-14 16:00 A | 100% | 0 | 0 | 0
24368025 | Z | Cool Down HMS Q1 | 2014-04-14 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 0
24368030 | Z | Cool Down HMS Q2 | 2014-04-14 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 0
24368035 | Z | Cool Down HMS Q3 | 2014-04-14 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 0
24368040 | D | Procure SHMS Steel Platforms and Stairs (Box O Parts) Part A | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 2266 | 0 | 2266
24368045 | D | Procure SHMS Steel Platforms and Stairs (Box O Parts) Part B | 2013-12-02 08:00 | 17-Mar-14 16:00 A | 100% | 88364 | 0 | 88364
24368050 | D | Install SHMS Steel Procurement | 2013-09-03 08:00 | 2014-05-01 | 100% | 174707 | 0 | 174707
24368052 | H | Align Wheels and Bogies on Support Structure | 2013-09-16 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 3669
24368055 | D | Install SHMS Steel Platforms and Stairs | 2013-12-09 08:00 | 17-Mar-14 16:00 A | 100% | 36117 | 0 | 53629
24368060 | D | Construct REAR Access Platform & Shield Wall | 2014-02-10 08:00 | 16-Jun-14 16:00 A | 100% | 51023 | 0 | 74668
24368065 | S | Forming and Pouring Work for Concrete - Procurement | 2013-09-03 08:00 | 14-Mar-14 16:00 A | 100% | 309508 | 0 | 309508
24368065a | S | Forming and Pouring Work for Concrete - Labor FY13 | 2013-09-03 08:00 | 14-Mar-14 16:00 A | 100% | 0 | 0 | 4433
24368065b | S | Forming and Pouring Work for Concrete - Labor FY14 | 2013-09-03 08:00 | 14-Mar-14 16:00 A | 100% | 0 | 0 | 9607
24368070 | S | Procure Concrete for Shield House - Procurement | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 213025 | 0 | 213025
24368070a | S | Procure Concrete for Shield House - Labor FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1184
24368070b | S | Procure Concrete for Shield House - Labor FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2564
24368075 | H | Re-Establish Hall-C Alignment Network After SHMS Assy | 2014-05-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 3786
24368080 | Z | Concrete Hardening Period | 2013-11-03 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 0
24368085M | M | Shield House Concrete Work Complete |  | 17-Mar-14 16:00 A | 100% | 0 | 0 | 0
24368090 | D | Install Boron & Lead Shielding | 2014-01-06 08:00 | 19-May-14 16:00 A | 100% | 20638 | 29053 | 78242
24368095 | S | Install Doors in Shield House | 2014-02-03 08:00 | 2015-01-29 16:00 | 20% | 0 | 0 | 11675
24368097 | H | Establish Alignment Network inside SHMS Shield House | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 3786
24368100 | S | Install and Align Detector Frames for DC and Rear Detectors (Assemble Rear Detector Frame) | 2014-09-25 08:00 | 2015-02-13 16:00 | 50% | 0 | 0 | 10380
24368105 | D | Fab Raised Floor (SHIELD HOUSE) | 2014-02-10 08:00 | 21-Jul-14 16:00 A | 100% | 54939 | 0 | 59043
24368110 | H | Install Roof Beams and Wall Blocks in Shield House | 2016-04-19 08:00 | 2016-04-19 16:00 | 0% | 0 | 0 | 781
24368115 | S | Install LCW for Supprt Struct | 2014-04-01 08:00 | 22-Sep-14 16:00 A | 100% | 24766 | 5324 | 56536
24368120 | D | Long-lead procurements for AC Pwr for Support Structure | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 12985 | 0 | 12985
24368122 | S | Install AC Pwr for Supprt Struct | 2014-02-03 08:00 | 16-Jun-14 16:00 A | 100% | 72248 | 14140 | 104420
24368125 | S | Install Cable Trays of Supprt Struct | 2014-03-03 08:00 | 19-May-14 16:00 A | 100% | 16196 | 0 | 27871
24368130 | S | Install Fire Protection & Detection Sys of Supprt Struct | 2014-04-07 08:00 | 2015-01-30 16:00 | 60% | 23671 | 0 | 37173
24368135 | S | Install Mag Pwr Supplies & Utilities on Platform | 2014-04-07 08:00 | 16-Jun-14 16:00 A | 100% | 8995 | 0 | 24085
24368140 | S | Install Cable Tray & Conduits (SHIELD HOUSE) | 2014-06-02 08:00 | 20-Oct-14 16:00 A | 100% | 16196 | 0 | 27871
24368145 | H | Install Drift Gas Manifold | 2014-10-13 08:00 | 20-Oct-14 16:00 A | 100% | 0 | 0 | 7890
24368150 | S | Install Shield House Electrical Pwr (SHIELD HOUSE) | 2014-05-12 08:00 | 16-Jun-14 16:00 A | 100% | 37148 | 0 | 56228
24368155 | S | Install Cables & Produce Final Drawings (CABLING) FY14 | 2014-05-05 08:00 | 2015-03-18 16:00 | 23% | 0 | 5232 | 96737
24368155A | S | Install Cables & Produce Final Drawings (CABLING) FY15 | 2014-05-05 08:00 | 2015-03-18 16:00 | 23% | 0 | 836 | 15465
24368160 | S | Install Fire Protection and Flamm Gas det. (SHIELD HOUSE) | 2014-06-02 08:00 | 2015-01-29 16:00 | 80% | 39597 | 0 | 48995
24368165 | S | Install Shield House HVAC (SHIELD HOUSE) | 2014-03-03 08:00 | 16-Jun-14 16:00 A | 100% | 20967 | 0 | 33076
24368170 | H | Remove and Preserve C-Can and Lines | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 10457
24368175 | S | Install Cryo Boom Support | 2014-02-10 08:00 | 17-Mar-14 16:00 A | 100% | 15479 | 0 | 27154
24368180 | H | Pre-Alignment SHMS Cryo Supports | 2013-11-08 | 2013-11-11 | 100% | 0 | 0 | 1136
24368185 | S | Construct & Connect Cryogenic Lines | 2013-11-04 | 18-Aug-14 16:00 A | 100% | 0 | 20638 | 144258
24368190 | H | Complete Readiness Review for SHMS DCPS Testing FY13 | 2013-09-03 08:00 | 2014-06-16 09:00 | 100% | 0 | 0 | 2363
24368190a | H | Complete Readiness Review for SHMS DCPS Testing FY14 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 1585
24368195 | H | Prepare LCW for SHMS DCPS Testing | 2014-05-05 08:00 | 12-May-14 16:00 A | 100% | 0 | 5494 | 7387
24368200 | S | Prepare AC Power for SHMS DCPS Testing | 2014-02-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 10988 | 16998
24368205 | H | Connect HMS Q1 to SHMS DCPS #1 | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 1504
24368210 | H | Test Power Supply DCPS #1 | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 3584
24368215 | H | Connect HMS Q1 to SHMS DCPS #2 | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 1504
24368220 | H | Test Power Supply DCPS #2 | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 3584
24368225 | H | Connect HMS Dipole to SHMS DCPS #3 | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 1504
24368230 | H | Test Power Supply DCPS #3 | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 3584
24368235 | H | Connect HMS Dipole to SHMS DCPS #4 | 2014-06-16 08:00 | 23-Jun-14 16:00 A | 100% | 0 | 0 | 1504
24368240 | H | Test Power Supply DCPS #4 | 2014-06-16 08:00 | 23-Jun-14 16:00 A | 100% | 0 | 0 | 3584
24368245 | H | Connect HMS Dipole to SHMS DCPS #5 | 2014-07-01 08:00 | 04-Jul-14 16:00 A | 100% | 0 | 0 | 1504
24368250 | H | Test Power Supply DCPS #5 | 2014-07-05 08:00 | 07-Jul-14 16:00 A | 100% | 0 | 0 | 3584
24368255 | H | Pre-Align Magnet Stand Locations | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1514
24368260 | S | Pre-Align, Install and Assemble Lower Iron Yokes and HB, Q1 Stands | 2013-11-04 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 24285
24368265 | S | Connect Mag Pwr Supplies & instrument Controls | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 5656 | 0 | 94810
24368270 | S | Prep for Review of Hot Check-out & Mag Control systems | 2014-07-07 08:00 | 14-Jul-14 16:00 A | 100% | 0 | 0 | 14989
24368275M | Z | Comp safety Review of Hot Chkout procedures & Mag control systems |  | 14-Jul-14 16:00 A | 100% | 0 | 0 | 0
24368280 | S | Perform Hot Check-out of Mag Pwr Supplies FY14 | 2014-07-07 08:00 | 28-Jul-14 16:00 A | 100% | 0 | 0 | 42533
24368280A | S | Perform Hot Check-out of Mag Pwr Supplies FY15 | 2014-07-07 08:00 | 28-Jul-14 16:00 A | 100% | 0 | 0 | 11876
24368285M | M | Receive First Mag from vendor | 2015-01-16 08:00 |  | 0% | 0 | 0 | 0
24368290 | S | Mount Q1 on Supprt Carriage | 2014-08-11 08:00 | 2015-01-29 16:00 | 0% | 5160 | 0 | 28915
24368295 | S | Mount HB on Supprt Carriage | 2015-05-18 08:00 | 2015-05-22 16:00 | 0% | 5160 | 0 | 9104
24368300 | H | Fiducialize Magnet CL of SHMS Q1 Magnet | 2015-03-13 08:00 | 2015-03-13 16:00 | 0% | 0 | 0 | 1925
24368305 | S | Final Assemble & Mount Dipole on Supprt Carriage | 2015-11-05 08:00 | 2015-12-04 16:00 | 0% | 11181 | 0 | 69281
24368310 | S | Install & Connect Magnet Insulating Vac system | 2015-11-05 08:00 | 2015-12-18 16:00 | 0% | 15972 | 10648 | 55918
24368315 | H | Inspect & Assemble Upper Iron Yoke & Stands for Dipole magnet | 2015-12-07 08:00 | 2015-12-09 16:00 | 0% | 0 | 0 | 8853
24368325 | H | Assemble Upper Iron Yoke & Stands for Q2 magnet | 2016-01-12 08:00 | 2016-01-14 16:00 | 0% | 0 | 0 | 8853
24368335M | M | First New SC Mag Cooled Down in place | 2016-02-04 08:00 |  | 0% | 0 | 0 | 0
24368340 | S | Mount Q2 on Supprt Carriage | 2016-01-21 08:00 | 2016-01-27 16:00 | 0% | 5324 | 0 | 40482
24368350 | H | Fiducialize Magnet CL of SHMS Dipole Magnet | 2016-02-23 08:00 | 2016-02-25 16:00 | 0% | 0 | 0 | 5958
24368360 | H | Assemble Upper Iron Yoke & Stands for Q3 magnet | 2016-03-15 08:00 | 2016-03-17 16:00 | 0% | 0 | 0 | 8853
24368365 | H | Finucialize Magnet CL of SHMS Q2 Magnet | 2016-03-16 08:00 | 2016-03-16 16:00 | 0% | 0 | 0 | 1986
24368370 | S | Mount Q3 on Supprt Carriage | 2016-03-17 08:00 | 2016-03-23 16:00 | 0% | 5324 | 0 | 40482
24368390 | H | Finucialize Magnet CL of SHMS Q3 Magnet | 2016-05-13 08:00 | 2016-05-13 16:00 | 0% | 0 | 0 | 1986
24368400 | U | Stack Calorimeter Blocks (SHOWER COUNTER) | 2014-09-22 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 15142
24368405 | H | Connect PMTs & Cables (SHOWER COUNTER) | 2014-12-16 08:00 | 2015-02-13 16:00 | 0% | 0 | 0 | 3759
24368410 | S | Test Calorimeter (SHOWER COUNTER) | 2015-02-16 08:00 | 2015-03-04 16:00 | 0% | 0 | 0 | 3294
24368415 | S | Install and Prep Electronics Room DAQ Racks (SHIELD HOUSE) | 2014-06-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 5669 | 17000
24368420 | S | Install Electrnc's (FAST Electrnc's) FY14 | 2014-10-06 08:00 | 2015-04-15 16:00 | 12% | 0 | 0 | 18828
24368420A | S | Install Electrnc's (FAST Electrnc's) FY15 | 2014-10-06 08:00 | 2015-04-15 16:00 | 12% | 0 | 0 | 50395
24368425 | Z | Fiducialize SHMS Aerogel Cerenkov Counter (6GEV) | 2015-10-01 08:00 | 2015-10-01 16:00 | 0% | 0 | 0 | 0
24368430 | H | Fiducialize SHMS Drift Ch's, Hodoscopes, Cerenkovs, Preshower (front Dets) | 2015-10-01 08:00 | 2015-10-07 16:00 | 0% | 0 | 0 | 9930
24368435 | S | Install Detctr's in Shield House REAR | 2014-11-05 08:00 | 2015-11-30 16:00 | 0% | 10648 | 39802 | 93284
24368440 | S | Install Shutter Exit Window | 2016-03-01 08:00 | 2016-03-07 16:00 | 0% | 0 | 0 | 16067
24368445 | S | Install Detctr's in Shield House FWD | 2014-10-15 08:00 | 2016-04-18 16:00 | 25% | 10648 | 39802 | 93284
24368450 | S | Hot Check-out of Detctr's in Shield House | 2016-03-24 08:00 | 2016-05-18 16:00 | 0% | 0 | 0 | 11638
24368455 | S | Install QR Magnets | 2013-12-13 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 11675
24368460 | Z | Install Moeller Quad #2 (6GEV) | 2015-02-04 08:00 | 2015-04-30 16:00 | 0% | 0 | 0 | 0
24368465 | S | Install Beam Stands (Beam Pipe) | 2015-06-26 08:00 | 2015-07-02 16:00 | 0% | 0 | 0 | 28304
24368470 | S | Install Windows & Flanges | 2015-08-06 08:00 | 2015-09-17 16:00 | 0% | 0 | 0 | 18376
24368475 | Z | Beam-Dump Modifications & Upgrades (6GEV) | 2015-06-03 08:00 | 2016-01-04 16:00 | 0% | 0 | 0 | 0
24368480 | S | Install Beam Pipe and Vac Fittings | 2015-07-06 08:00 | 2015-07-10 16:00 | 0% | 0 | 13267 | 15220
24368485 | S | Connect Additional Quad for Moeller polarimeter | 2015-05-01 08:00 | 2015-05-28 16:00 | 0% | 1548 | 0 | 17776
24368490 | S | Leak Test Beam Pipe Vac Sys | 2015-07-13 08:00 | 2015-07-17 16:00 | 0% | 0 | 14463 | 22276
24368495 | S | Adjust Compton Elevation (Notebook) | 2014-04-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 5160 | 26299
24368500 | Z | Install Beam Line upstream of Target (6GeV) | 2015-07-01 08:00 | 2015-12-23 16:00 | 0% | 0 | 0 | 0
24368505 | Z | Install, Align, Leak-check Upstream Beam-Pipes & Girders (6GEV) | 2016-01-04 08:00 | 2016-03-31 16:00 | 0% | 0 | 0 | 0
24368510 | Z | Install Target Scattering Chamber (6GEV) | 2015-05-01 08:00 | 2015-05-07 16:00 | 0% | 0 | 0 | 0
24368515 | Z | Align Target Scattering Chamber (6GEV) | 2015-05-08 08:00 | 2015-05-14 16:00 | 0% | 0 | 0 | 0
24368520 | H | Prep for Vac & pressure systems Safety Review | 2015-01-13 08:00 | 2015-01-27 16:00 | 0% | 0 | 0 | 6164
24368525M | Z | Comp safety Review of Spectrometer vacuum system Implementn |  | 2015-01-27 16:00 | 0% | 0 | 0 | 0
24368530 | S | Install & Connect Spectrometer Vac system | 2016-05-16 08:00 | 2016-06-20 16:00 | 0% | 15972 | 10648 | 55918
24368535 | S | Install Spool & Bellows for All Magnets | 2016-05-16 08:00 | 2016-06-20 16:00 | 0% | 0 | 20428 | 33440
24368540 | S | Install Slit Controls | 2014-10-15 08:00 | 2016-06-13 16:00 | 40% | 0 | 0 | 11676
24368545 | S | Install Sieve Slit Sys | 2016-05-31 08:00 | 2016-06-13 16:00 | 0% | 0 | 42120 | 56878
24368550 | H | Prep Procurement of SHMS Angle Scribe Plates | 2014-03-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 8470
24368555 | D | Procure SHMS Angle Scribe Plates | 2014-04-07 08:00 | 22-Sep-14 16:00 A | 100% | 42593 | 0 | 42593
24368560 | S | Install & Align SHMS Angle Scribe Plates | 2015-05-04 08:00 | 2015-05-15 16:00 | 0% | 0 | 0 | 11719
24368565 | S | Install SHMS Position Readback System | 2014-10-01 08:00 | 2015-07-01 16:00 | 50% | 10648 | 1170 | 21557
24368570 | S | Install Rotation Controls of Supprt Struct | 2014-02-03 08:00 | 2015-09-30 16:00 | 82% | 100868 | 0 | 129851
24368575LOE | E | Installation Management P1 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 8159
24368580LOE | E | Installation Management P2 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 98789
24368585LOE | E | Installation Management P3 | 2014-10-01 08:00 | 2015-10-01 16:00 | 9.31% | 0 | 0 | 101939
24368590LOE | E | Installation Management P4 | 2015-10-02 08:00 | 2015-12-22 16:00 | 0% | 0 | 0 | 21927
251173f | S | Install solenoid vacuum manifold | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 0 | 0 | 3976
251195 | S | Repair Solenoid Vac Leaks | 2013-09-03 08:00 | 09-Sep-13 16:00 A | 100% | 0 | 0 | 3376
251250M | M | Installtn of Solenoid Comptd (SOLENOID) |  | 09-Sep-13 16:00 A | 100% | 0 | 0 | 0
251666 | D | Consultant Fee (Quench Study WS) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 6100 | 0 | 6100
25211172 | S | Resolution_studies_(FWD_Chambers) FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 4663
25211172a | S | Resolution_studies_(FWD_Chambers) FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 2406
25211175 | S | Complete Package Mechanical Assy (FWD Chambers) FY13 | 2013-09-03 08:00 | 2013-10-21 08:04 | 100% | 0 | 0 | 1508
25211175a | S | Complete Package Mechanical Assy (FWD Chambers) FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 778
25211191 | U | Procurement of Consumables for Fab (2013) (FWD Chambers) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 1094 | 1094
25211208 | U | Assemble and Electrical Test of Package R (FDC) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 2633
25211217 | S | Cooling system assembly FY13 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 2361
25211217a | S | Cooling system assembly FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 5238
25211220 | U | Final Testing (FWD Chambers) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 4722
25211250 | U | Disassembly of the construction equipment and site - labor and forklift lease | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 420 | 5541
25211255LOE | E | Pick-up Truck Lease | 2013-09-03 08:00 | 31-Mar-14 16:00 A | 100% | 2605 | 0 | 2605
25211255LOE5 | E | Blue Crab Cleaning (Previously Obligated) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 154 | 0 | 154
25211260 | S | Develop algorithm for fADC125 readout FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 5894
25211260a | S | Develop algorithm for fADC125 readout FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 20983
25212010 | S | Prepare as built drawings for CDC (CENT CHAMB) | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 15059
25212185 | S | Resolution Studies (CENT CHAMB) FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 757
25212185a | S | Resolution Studies (CENT CHAMB) FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 5233
25213005 | D | Fabricate (FIU) Start Counter (START COUNTERS) | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 28433 | 0 | 28433
25213015 | S | All Manufacturing Drawings for start counter FY13 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 1582
25213015a | S | All Manufacturing Drawings for start counter FY14 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 1306
25213020 | D | Procure start counter support frame parts | 2013-10-21 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 5263 | 5263
25213025 | S | Assemble start counter support frame | 2013-11-04 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 10558
25213030 | D | Consultant Fee (Quench Study WS) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 600 | 0 | 600
25221000 | D | Regina contract Decommissioning | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 8478 | 0 | 8478
25221005 | D | Procured Labor (Designer) | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 1142 | 0 | 1142
25221010 | D | Athens contract Completion | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 5125 | 0 | 5125
25221010LOE | E | Forklift Rental (ESB) | 2013-09-03 08:00 | 31-Oct-13 16:00 A | 100% | 817 | 0 | 817
25221057b | S | Construction BCAL Pulsing System (BarCal) Labor FY13 | 2013-09-03 08:00 | 2014-01-20 09:13 | 100% | 0 | 0 | 5608
25221057ba | S | Construction BCAL Pulsing System (BarCal) Labor FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 12152
25221057c | D | Construction BCAL Pulsing System (BarCal) Materials FY13 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 532 | 532
25221057ca | D | Construction BCAL Pulsing System (BarCal) Expenses FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 1153 | 1153
25221060 | S | Setup and Testing of BCAL Pulsing System FY13 | 2013-11-05 08:00 | 15-Mar-14 16:00 A | 100% | 0 | 0 | 9869
25221060a | S | Setup and Testing of BCAL Pulsing System FY14 | 2013-11-05 08:00 | 15-Mar-14 16:00 A | 100% | 0 | 0 | 21385
25221320 | D | Procure BCAL cooling manifold | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 9420 | 0 | 9420
25222085 | S | Fabricate and Install Monitoring Panes (FCAL) FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 564 | 4999
25222085a | S | Fabricate and Install Monitoring Panes (FCAL) FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 1977 | 17538
25222090 | D | Fabricate and Install Monitoring Panes (FCAL) (Previously Obligated) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 5520 | 0 | 5520
25231010 | E | FSU contract support and supervision FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 3319
25231010a | E | FSU contract support and supervision FY14 | 2013-10-01 08:00 | 27-Nov-13 16:00 A | 100% | 0 | 0 | 6335
25231030 | D | Proc Magnetic Shields (TOF) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 5860 | 0 | 5860
25231045 | D | Proc Supprt Struct (TOF) | 2013-10-21 08:00 | 17-Mar-14 16:00 A | 100% | 22425 | 0 | 22425
25231085 | D | FSU - Initial wrapping and fitup | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 179569 | 0 | 179569
25231090 | D | FSU - Proc Supplies (TOF) | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 2363 | 0 | 2363
25231105 | D | FSU - Mount PMT and Testing of First 30 Units | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 7683 | 0 | 7683
25231115 | D | FSU - Wrapping of Second 30 Units | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 451 | 0 | 451
25231120 | D | FSU - Mount PMT and Testing of Second 30 Units | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 9370 | 0 | 9370
25231125 | D | FSU - Polishing and Gluing of Third 30 Units | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 1147 | 0 | 1147
25231130 | D | FSU - Wrapping of Third 30 Units | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 9015 | 0 | 9015
25231135 | D | FSU - Mount PMT and Testing of Third 30 Units | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 14055 | 0 | 14055
25231140 | E | FSU - Construction Manager | 2013-09-03 08:00 | 27-Nov-13 16:00 A | 100% | 21381 | 0 | 21381
25231145 | D | FSU - Shipping of TOF | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 11940 | 0 | 11940
2531005f | D | Proc Single Board Computing Remaining items (DAQ) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 60911 | 0 | 60911
2531005fa | D | Proc Single Board Computing Remaining items (DAQ) Phase 2 | 2013-11-01 | 17-Feb-14 16:00 A | 100% | 159638 | 0 | 159638
2531022 | D | Proc EB nodes (DAQ) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 45500 | 0 | 45500
2531027 | D | Proc RAID disks (DAQ) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 25500 | 0 | 25500
2531033 | D | Proc Servers for EPICS Archiving (DAQ) | 2013-10-21 08:00 | 21-Apr-14 16:00 A | 100% | 22361 | 0 | 22361
2531047 | D | Proc Telecom Installation (DAQ) | 2013-11-04 08:00 | 18-Aug-14 16:00 A | 100% | 3150 | 0 | 3150
2531065 | H | Proc Fibers for Counting House to Hall (DAQ) PR FY13 | 2013-11-01 | 2013-11-18 | 100% | 0 | 0 | 3217
2531065a | H | Proc Fibers for Counting House to Hall (DAQ) PR FY14 | 2013-11-01 | 2013-11-18 | 100% | 0 | 0 | 1493
2531070 | D | Proc Fibers for Counting House to Hall (DAQ) | 2014-01-21 08:00 | 21-Apr-14 16:00 A | 100% | 35744 | 0 | 35744
2531077 | D | Proc Consoles (DAQ) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 400 | 0 | 400
2531088 | D | Procure and Install cameras in the hall (DAQ) | 2014-01-13 08:00 | 19-May-14 16:00 A | 100% | 20638 | 0 | 23643
2531089 | D | Procure Conference Equipment (DAQ) | 2013-11-01 | 20-Dec-13 16:00 A | 100% | 11179 | 0 | 11179
2531097 | S | Install infiniband network (DAQ) | 2013-10-21 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 19251
2531100 | D | Install DAQ fibers to switches (DAQ) | 2014-01-21 08:00 | 19-May-14 16:00 A | 100% | 19696 | 0 | 19696
2531105 | S | Install Trigger Electrnc's (DAQ) FY13 | 2014-02-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 4564
2531105a | S | Install Trigger Electrnc's (DAQ) FY14 | 2014-02-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 34380
2531115 | S | Install VME CPUs FY13 | 2013-10-21 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 4239
2531115a | S | Install VME CPUs FY14 | 2013-10-21 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 19684
2531125 | S | Check-out Trigger Electrnc's (DAQ) | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 33075
2531140 | D | Proc infiniband Hardware | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 13710 | 0 | 13710
2531165 | S | Install VME based electronic for Controls/Monitoring FY13 | 2014-01-15 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 2404
2531165a | S | Install VME based electronic for Controls/Monitoring FY14 | 2014-01-15 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 9549
2531178 | D | Software Licenses and Fees | 2013-11-01 | 17-Feb-14 16:00 A | 100% | 1857 | 0 | 1857
2531227aa | D | Proc IO Modules (DAQ) Batch 2 (Previously Obligated) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 4979 | 0 | 4979
2531227aa5 | D | Proc IO Modules (DAQ) Batch 2 | 2013-10-14 08:00 | 20-Jan-14 16:00 A | 100% | 6116 | 0 | 6116
2531310 | S | Install DAQ Equipment in Hall (DAQ) | 2013-12-16 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 12029
2531315 | S | Install Computing Infrastructure (DAQ) FY13 | 2013-10-21 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 5112
2531315a | S | Install Computing Infrastructure (DAQ) FY14 | 2013-10-21 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 13976
2531330 | D | Proc L3 Farm Infrastucture (DAQ) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 34101 | 0 | 34101
2531335 | H | Proc Accessories for Computing Cluster (DAQ) PR FY13 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1881
2531335a | H | Proc Accessories for Computing Cluster (DAQ) PR FY14 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1067
2531340 | D | Proc Accessories for Computing Cluster (DAQ) | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 10349 | 0 | 10349
2531350 | D | Proc Hardware for Microscope Voltage Control (DAQ) | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 3000 | 0 | 3000
2531360 | D | Patch Panels and Cu Cables to CH (DAQ) | 2013-11-04 08:00 | 21-Apr-14 16:00 A | 100% | 3612 | 0 | 5504
2531365 | E | Sys Admin Support (DAQ) | 2014-01-06 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 19251
2531370 | H | Check-out Online Computers (DAQ) | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 8686
2531375 | H | Check-out Counting House (DAQ) | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 6014
2531380 | S | Check-out Cabling (DAQ) | 2014-05-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 9626
2531385 | S | Check-out DAQ Hardware (DAQ) | 2014-04-07 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 9022
2531390 | E | Installation Coordination | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 1822
2531395 | S | Procure Small UPSs for Tagger Hall and Hall D Cables (DAQ) | 2014-03-03 08:00 | 16-Jun-14 16:00 A | 100% | 21648 | 0 | 21648
2531400 | D | Procure and Install Voltage Chassis Remote Reset | 2014-02-03 08:00 | 18-Aug-14 16:00 A | 100% | 2446 | 0 | 4325
2532000 | E | Purchased Labor (Sergey) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 1573 | 0 | 1573
2532005 | H | Install OS system along with network settings FY13 | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 1333
2532005a | H | Install OS system along with network settings FY14 | 2013-10-01 08:00 | 18-Nov-13 14:00 A | 100% | 0 | 0 | 1512
2532013E | E | FY13 Travel (ONLINE COMP) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 129 | 129
2532014E | E | FY14 Travel (ONLINE COMP) | 2013-10-01 08:00 | 29-Sep-14 16:00 A | 100% | 0 | 1648 | 1648
2532015 | H | Database web-server wiki installations | 2013-12-02 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 9626
2532020 | E | Coordination of online computing setup | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 874
2532030 | S | Install CODA and supporting software | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 6014
2532035 | S | Create scripts to launch and kill: CODA system, monitoring system FY13 | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 2620
2532035a | S | Create scripts to launch and kill: CODA system, monitoring system FY14 | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 9325
2532040 | S | Run bookkeeping scripts (database;data files and special events) FY13 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 2754
2532040a | S | Run bookkeeping scripts (database;data files and special events) FY14 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 15201
2532050 | S | Readout Lists FY13 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 2271
2532050a | S | Readout Lists FY14 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 15700
2532055 | S | Write COOL Config Files | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 12029
2532060 | S | Debug DAQ software | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 24058
2532070 | S | Implement Translation Tables FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 668
2532070a | S | Implement Translation Tables FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2378
2532075 | S | Farm Process Manager | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 21050
2532080 | S | ROOTSpy enabled Monitoring Processes FY13 | 2013-09-03 08:00 | 2014-08-18 00:46 | 100% | 0 | 0 | 3730
2532080a | S | ROOTSpy enabled Monitoring Processes FY14 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 15397
2532085 | S | Archiving and Retrieval of Histogram Files | 2013-10-21 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 15036
2532090 | S | Event Display | 2014-02-04 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 6014
2532100 | S | Transport from RAID to Tape Silo | 2013-11-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 19251
2532110 | S | Archiving Run Conditions | 2014-02-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 24383
2532115 | S | Archiving DAQ Configuration | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 12029
2532130 | S | FDC/CDC Gas Systems Controls | 2014-01-06 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 8960
2532135 | H | BCAL Gas System Controls | 2014-01-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 5974
2532140 | S | Controls for Chillers (FDC;BCAL;Target) | 2014-01-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 11947
2532145 | S | Temperature/Humidity monitoring | 2014-01-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 11947
2532150 | S | FCAL Dark Room Controls | 2013-11-06 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 11947
2532155 | S | Cryo Target Controls | 2014-01-06 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 14934
2532170a | S | HV Controls (FDC; CDC; TOF; FCAL; HODO) Phase 2 FY13 | 2013-09-03 08:00 | 2014-08-18 00:57 | 100% | 0 | 0 | 3618
2532170aa | S | HV Controls (FDC; CDC; TOF; FCAL; HODO) Phase 2 FY14 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 15867
2532175 | S | LV Controls (BCAl; ST; FDC) FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 744
2532175a | S | LV Controls (BCAl; ST; FDC) Phase 2 | 2013-09-16 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 21493
2532175b | S | LV Controls (BCAl; ST; FDC) FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 4605
2532180 | S | BIAS Control for Microscope | 2013-11-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 12029
2532185 | S | Tagger magnet and NMR control SWT (accel Grp) | 2014-02-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 11179
2532190 | S | Sweeping and pair spectrometer magnet control SWT (accel Grp) | 2014-02-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 5590
2532195 | S | Active collimator integration EPICS (Acceler grp) | 2014-03-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 30743
2532200 | S | Vacuum System Controls (accel Grp) | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 11179
2532205 | S | Motors (radiator, converter, collimator, tagger) FY13 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 4389
2532205a | S | Motors (radiator, converter, collimator, tagger) FY14 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 22643
2532215 | S | CSS Control GUIs FY13 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 3514
2532215a | S | CSS Control GUIs FY14 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 19760
2532220 | S | Debug EPICS Controls Sofware | 2014-05-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 19154
2532225 | S | Debug PLC Controls Sofware | 2014-05-02 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 17941
2532230 | S | Alarms (configuration,display, history) FY13 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 9437
2532230a | S | Alarms (configuration,display, history) FY14 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 12173
2532235 | S | Scaler Monitoring in EPICS | 2014-01-15 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 24058
2532240 | S | Trigger Monitoring in EPICS | 2014-01-15 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 12029
2532245 | S | DAQ monitoring Software | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 12029
2532250 | S | EPICS Archving and Restoration FY13 | 2013-11-11 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 2516
2532250a | S | EPICS Archving and Restoration FY14 | 2013-11-11 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 15447
2532255 | S | Coherent Peak Alignment Software with Goniometer | 2014-06-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 15036
2541000 | U | Vend Fab FADC-125 (Previously Obligated) | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 43318 | 0 | 43318
2541015 | U | Rework of Production FADC Modules (FE) FY13 | 2013-09-03 08:00 | 16-Jun-14 15:48 A | 100% | 0 | 0 | 2913
2541015a | U | Rework of Production FADC Modules (FE) FY14 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 28561
2541120 | U | fADC125 - Full Single-Crate Acceptance Test (FADC) FY13 | 2013-11-04 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 4151
2541120a | U | fADC125 - Full Single-Crate Acceptance Test (FADC) FY14 | 2013-11-04 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 15256
2541145 | U | fADC125 - Test (Qty 217) (FADC) FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 594
2541145a | U | fADC125 - Test (Qty 217) (FADC) FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1286
2541150 | S | FADC125 Production firmware development FY13 (Hall D EE) | 2013-09-03 08:00 | 2014-03-17 08:34 | 100% | 0 | 0 | 5312
2541150a | S | FADC125 Production firmware development FY14 (Hall D EE) | 2013-09-03 08:00 | 17-Mar-14 14:00 A | 100% | 0 | 0 | 15555
2541152 | S | Algorithm Development for DC FADC125 FY13 | 2013-11-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1707
2541152a | S | Algorithm Development for DC FADC125 FY14 | 2013-11-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 19289
2541154 | S | Code Deployment and Full Readout Tests FADC125 | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 18043
2541155 | E | FADC EE Hardware/software support in FY14 (Hall D EE) | 2013-12-02 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 60104
2542037 | U | F1TDC - Full Single-Crate Acceptance Test (TDC) | 2013-09-03 08:00 | 18-Sep-13 16:00 A | 100% | 0 | 0 | 15149
2542070 | S | F1TDC develop firmware FY13 | 2013-09-03 08:00 | 2013-10-21 09:17 | 100% | 0 | 0 | 4027
2542070a | S | F1TDC develop firmware FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 12674
2542075 | S | FPGA Coding, Hardware & Firmware Integration Tests F1TDC | 2013-12-02 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 18031
2542080 | S | Code Deployment and Full Readout Tests F1TDC | 2014-03-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 12029
2542085 | U | Rework of Production F1TDC modules | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 18796
2542090 | E | F1TDC EE Hardware/Software Support FY14 | 2014-01-06 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 27047
2543025 | D | Procument of CTP boards (FE grp) (Previously Obligated) | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 18009 | 0 | 18009
2543030 | D | Procument of CTP boards (FE grp) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 9682 | 0 | 9682
2543100 | D | Procument Fiber Optics Cable/Patch Pannel (FE grp) | 2013-10-21 | 21-Jul-14 16:00 A | 100% | 36117 | 0 | 36117
2543115 | S | Performance testing of global trigger system (FE grp) | 2014-02-10 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 29062
2543143 | S | Trigger Algorithms Performance Testing in the Hall (Hall D grp) | 2014-01-06 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 27065
2543144 | S | Study Algorithms with Test Stand (Hall D grp) FY13 | 2013-12-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 1148
2543144a | S | Study Algorithms with Test Stand (Hall D grp) FY14 | 2013-12-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 10844
2543150 | S | Develop Level-1 Monitor (Hall D grp) FY13 | 2013-10-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 3522
2543150a | S | Develop Level-1 Monitor (Hall D grp) FY14 | 2013-10-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 29441
2543155 | S | Install Level-1 Monitor (Hall D grp) | 2014-03-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 15036
2543160 | S | Trigger Board Initialization (Hall D grp) FY13 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 3408
2543160a | S | Trigger Board Initialization (Hall D grp) FY14 | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 42193
2543165 | S | Level-1 Verification and Debugging (Hall D grp) FY13 | 2013-11-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 1990
2543165a | S | Level-1 Verification and Debugging (Hall D grp) FY14 | 2013-11-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 18995
2543170 | D | Level-1 Trigger Testbed Electronics (Hall D grp) | 2013-11-04 | 22-Sep-14 16:00 A | 100% | 19864 | 0 | 19864
2543185 | D | Procument Structural Components for Trigger Modules (FE Grp) | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 1449 | 0 | 1449
2546362 | U | Assemble BCAL Readout V3, Power Dist. & SYST | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 2768
2546425 | D | Procure Pair Spectrometer Readout Board | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 3748 | 0 | 3748
2546430 | D | Procure Pair Spectrometer Transition Board | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 3226 | 0 | 3226
2546435 | D | Procure Pair Spectrometer Power Distribution | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 3220 | 0 | 3220
2546465 | D | Procure LV Cables | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 80 | 0 | 444
2546470 | U | Pair Spectrometer Integration FY13 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 2395
2546470a | U | Pair Spectrometer Integration FY14 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 8806
2546565 | D | Procure LV Cables | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 41 | 0 | 223
2546567 | U | Start Counter Integration FY13 | 2013-10-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 1338
2546567a | U | Start Counter Integration FY14 | 2013-10-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 2002
2546585 | U | Tagger Microscope PreAmp Board (37) Procurement $ now Labor | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 7500 | 0 | 7500
2546585a | U | Tagger Microscope PreAmp Board (37) Labor FY13 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2024
2546585b | U | Tagger Microscope PreAmp Board (37) Labor FY14 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 3551
2546600 | D | Tagger Hodoscope PreAmp Board (233) (Previously Obligated) | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 12865 | 0 | 12865
2546605 | D | Tagger Hodoscope PreAmp Board (233) Procurement $ now Labor | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 3135 | 0 | 3135
2546605a | U | Tagger Hodoscope PreAmp Board (233) - Labor FY13 | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 2855
2546605b | U | Tagger Hodoscope PreAmp Board (233) - Labor FY14 | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 4271
2546610 | S | BCAL/FCAL Monitoring Distribution Sys. Procurement Support FY13 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 1932
2546610a | S | BCAL/FCAL Monitoring Distribution Sys. Procurement Support FY14 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 7478
2546615 | D | BCAL/FCAL Monitoring Distribution COTS Electronics | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 16134 | 0 | 16134
2546620 | S | BCAL/FCAL Monitoring Distribution Box (10) Procurement | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 10000 | 0 | 10000
2546620a | S | BCAL/FCAL Monitoring Distribution Box (10) - Labor FY13 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 1918
2546620b | S | BCAL/FCAL Monitoring Distribution Box (10) - Labor FY4 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 7419
2546625 | D | BCAL/FCAL Monitoring Distribution Cables (64+64) (Previously Obligated) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 6012 | 0 | 6012
2546630 | D | BCAL/FCAL Monitoring Distribution Cables (64+64) | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 3588 | 0 | 3588
2546640 | D | Cables Type 1 (TAGH PS PSC COLLI) (350) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 18484 | 0 | 18484
2546645 | D | Splitter Output (TOF TAGM PSC) (630) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 31331 | 0 | 31331
2546650 | D | Install Hardware, Labels and Tie Wraps FY13 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 449 | 449
2546650a | D | Install Hardware, Labels and Tie Wraps FY14 | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 5728 | 5728
2546655 | D | Splitters Parts Boards and Assembly (10) | 2013-11-04 08:00 | 22-Sep-14 16:00 A | 100% | 13931 | 0 | 20979
2546660 | D | Twisted Pair Cables for TDCs | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 1908 | 0 | 1908
2547135 | U | Cables - HV Label and Bundle CDC (6) | 2013-11-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1880
2547165 | U | Cables - HV Label and Bundle FDC (8) FY13 | 2013-09-03 08:00 | 2013-11-18 08:12 | 100% | 0 | 0 | 1252
2547165a | U | Cables - HV Label and Bundle FDC (8) FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 587
2547170 | U | Cables - Signal Label and Bundle FDC (528) FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 2335
2547170a | U | Cables - Signal Label and Bundle FDC (528) FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 2289
2547175 | U | Cables - LV Label and Bundle BCAL (24) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1275
2547180 | U | Cables - Bias Label and Bundle BCAL (36) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1002
2547190 | U | Cables - HV Label and Bundle TOF (168) FY13 | 2013-09-03 08:00 | 20-Dec-13 13:09 A | 100% | 0 | 0 | 297
2547190a | U | Cables - HV Label and Bundle TOF (168) FY14 | 2013-09-03 08:00 | 20-Dec-13 13:09 A | 100% | 0 | 0 | 1197
2547200 | U | Cables - Signal Label and Bundle TOF (168) FY13 | 2013-09-03 08:00 | 20-Dec-13 13:09 A | 100% | 0 | 0 | 297
2547200a | U | Cables - Signal Label and Bundle TOF (168) FY14 | 2013-09-03 08:00 | 20-Dec-13 13:09 A | 100% | 0 | 0 | 1197
2548020 | U | Full Crate Check - Pre Installation,Lab,Install Mods,Test,Log&Label VXS fADC125 FY13 | 2013-12-02 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 766
2548020a | U | Full Crate Check - Pre Installation,Lab,Install Mods,Test,Log&Label VXS fADC125 FY14 | 2013-12-02 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 4095
2548025 | U | Full Crate Check - Pre Installation,Lab,Install Mods,Test,Log&Label VXS F1TDC FY13 | 2013-09-03 08:00 | 21-Oct-13 14:11 A | 100% | 0 | 0 | 1114
2548025a | U | Full Crate Check - Pre Installation,Lab,Install Mods,Test,Log&Label VXS F1TDC FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 3736
25511095 | S | Proc,Calibrate, Install NMR (TAGGING Mag) FY13 | 2013-11-04 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 3716 | 10112
25511095a | S | Proc, calibrate, Install NMR (TAGGING Mag) FY14 | 2013-11-04 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 2109 | 5739
25512005 | S | Design Hodoscope Supprt (HODOSCP) FY13 | 2013-09-03 08:00 | 2013-12-20 09:57 | 100% | 0 | 0 | 3223
25512005a | D | Construct Hodoscope Supprt (HODOSCP) Part A | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 24171 | 0 | 24171
25512005b | S | Design Hodoscope Supprt (HODOSCP) FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1830
25512010 | D | Catholic University Tagger Hodoscope Fixed Array | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 45007 | 0 | 45007
25512010a | E | Catholic University Tagger Hodoscope Fixed Array Oversight FY13 | 2013-09-03 08:00 | 2013-09-30 11:03 | 100% | 0 | 0 | 117
25512010aa | E | Catholic University Tagger Hodoscope Fixed Array Oversight FY14 | 2013-10-01 08:00 | 28-Feb-14 16:00 A | 100% | 0 | 0 | 592
25512013LOE | E | FY13 Travel (HODOSCP) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 245 | 245
25512056 | S | Manufacturing Drawings for Hodoscope mag shield (HODOSCP) | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1649
25512060 | D | Fab Hodoscope mag shields | 2013-11-04 | 17-Feb-14 16:00 A | 100% | 8255 | 0 | 8255
25512065 | S | Manufacturing Drawings for microscope cooling FY13 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 1968
25512065a | S | Manufacturing Drawings for microscope cooling FY14 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 8327
25512070 | D | Fab microscope cooling | 2014-05-02 08:00 | 22-Sep-14 16:00 A | 100% | 6088 | 1238 | 7326
25512131 | D | UConn TAGM Contract - Procurement of Supplies for Construction | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 3500 | 0 | 3500
25512136 | D | UConn TAGM Contract - Production 1st Article Opt Fib Bundle | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 3329 | 0 | 3329
25512146 | D | UConn TAGM Contract - Complete Construction of TAGM Enclosure | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 3447 | 0 | 3447
25512151 | D | UConn TAGM Contract - Testing of TAGM Electronic Boards | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 2017 | 0 | 2017
25512156 | D | UConn TAGM Contract - Complete 20 Optical Fiber Bundles | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 28938 | 0 | 28938
25512161 | D | UConn TAGM Contract - Complete Construction of Fiber Array Enclosure | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 3572 | 0 | 3572
25512166 | D | UConn TAGM Contract - Complete Assembly of Full Enclosure at UConn | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 3782 | 0 | 3782
25512171 | D | UConn TAGM Contract - Disassemble TAGM and Prepare for Shipment to JLab | 2013-09-03 08:00 | 18-Aug-14 16:00 A | 100% | 2627 | 0 | 2627
25512176 | D | UConn TAGM Contract - TAGM Delivered to JLab | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 2627 | 0 | 2627
2552001 | S | Prepare Procurements/Fabrication Packages FY13 (TARGET) | 2013-09-03 08:00 | 22-Sep-14 15:39 A | 100% | 0 | 0 | 977
2552001a | S | Prepare Procurements/Fabrication Packages FY14 (TARGET) | 2013-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 504
2552005 | D | Proc Gas Handling Sys (TARGET) - Procurement | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 7800 | 0 | 7800
2552005a | D | Proc Gas Handling Sys (TARGET) - Expenses FY13 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 3632 | 3632
2552005b | D | Proc Gas Handling Sys (TARGET) - Expenses FY14 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 5622 | 5622
2552006 | S | Install Gas Handling Sys (TARGET) | 2014-05-05 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 516 | 18427
2552007 | S | Install Gas Tank (TARGET) | 2014-03-10 08:00 | 21-Jul-14 16:00 A | 100% | 19090 | 0 | 19090
2552008 | S | Manufacturing Drawings for gas System (Target) FY13 | 2013-10-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 2247
2552008a | S | Manufacturing Drawings for gas System (Target) FY14 | 2013-10-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 5333
2552010 | D | Proc Controls (TARGET) - Procurement | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 7000 | 0 | 7000
2552010a | D | Proc Controls (TARGET) - Expenses FY13 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 231 | 231
2552010b | D | Proc Controls (TARGET) - Expenses FY14 | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 536 | 536
2552012 | S | Program Target Controls | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 11179
2552015 | D | Fab Isolation Vac Pumping Sys (TARGET) (Previously Obligated) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 11509 | 0 | 11509
2552015a | D | Fab Isolation Vac Pumping Sys (TARGET) | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 14888 | 0 | 14888
2552018a | S | Fab Outer Vac/Scattering Chamb (TARGET) | 2014-05-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 11213 | 25556
2552023aa | S | Fab Target Cells (TARGET) FY13 | 2013-09-03 08:00 | 2014-05-19 11:50 | 100% | 0 | 231 | 896
2552023aaa | S | Fab Target Cells (TARGET) FY14 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 1062 | 4112
2552028 | S | Prepare Procurements/Fabrication Packages solid target (TARGET) | 2014-02-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 27237
2552028a | D | Fabricate solid target (proc) | 2014-03-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 15272 | 15272
2552028b | S | Fabricate solid target (labor) | 2014-04-07 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 20181
2552032 | S | Manufacturing Drawings for cryo system (Target) FY13 | 2013-09-03 08:00 | 2014-03-17 00:09 | 100% | 0 | 0 | 3776
2552032a | S | Manufacturing Drawings for cryo system (Target) FY14 | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 1948
2552033 | D | Procure heat xchngr and cryo hardware | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 1650 | 0 | 1650
2552035 | D | Fab Positioning/Mounting Sys (TARGET) | 2014-04-07 08:00 | 16-Jun-14 16:00 A | 100% | 13002 | 3715 | 16717
2552040 | S | Assemble Target (TARGET) | 2014-04-14 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 23009
2553005 | D | Proc Raw Radiator Diamond Crystals (BL Compnts) | 2014-04-14 08:00 | 19-May-14 16:00 A | 100% | 38634 | 0 | 38634
2553010 | D | Thinning-Characterization-Mounting of Radiator Diamond Crystals (BL Compnts) Phase 1 | 2014-02-17 08:00 | 2015-03-30 16:00 | 0% | 55207 | 0 | 55207
2553010a | D | Thinning-Characterization-Mounting of Radiator Diamond Crystals (BL Compnts) | 2014-06-02 08:00 | 2015-03-30 16:00 | 0% | 31945 | 0 | 31945
2553011 | E | Diamond contractor and procurements support (BL Compnts) FY13 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 698
2553011a | E | Diamond contractor and procurements support (BL Compnts) FY14 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 8887
2553016 | D | Build Vacuum Housing for Goniometer (BL Compnts) | 2013-10-07 08:00 | 17-Feb-14 16:00 A | 100% | 24917 | 0 | 24917
2553017 | D | Procure vacuum gauges and valves for tagger beamline | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 3225 | 0 | 3225
2553020 | S | Write Control Software for Goniometer (BL Compnts) | 2013-10-02 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 24058
2553027 | S | Install Goniometer (BL Compnts) | 2014-02-10 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 38720
2553029 | S | Survey Goniometer (BL Compnts) | 2014-03-10 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 30789
2553035 | D | Proc Pair Spectrometer Mag Pwr Supply (BL Compnts) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 74300 | 0 | 74300
2553036 | D | Proc Parts for Pair Spectrometer | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 1360 | 0 | 1360
2553041 | D | Build PS low granularity Support Frame | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 620 | 0 | 620
2553042 | S | Fabricate PS High Granularity Counters | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 7619
2553044 | D | Build PS High granularity Support Frame | 2013-11-04 08:00 | 21-Apr-14 16:00 A | 100% | 5758 | 0 | 5758
2553050 | D | Proc Pair convertor insertion device (BL Compnts) (Previously Obligated) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 13325 | 0 | 13325
2553052 | D | Proc Pair convertor insertion device Mods (BL Compnts) | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 3702 | 0 | 3702
2553055 | S | Assemble and Test Pair convertor (BL Compnts) | 2013-09-09 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 24760
2553057 | S | Scientific support for Pair spectrometer characterization(BL Compnts) FY13 | 2014-02-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 150
2553057a | S | Scientific support for Pair spectrometer characterization(BL Compnts) FY14 | 2014-02-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 23903
2553062 | D | UConn Contract - Procure Readout Electronics for Active Collimator | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 6000 | 0 | 6000
2553063 | D | UConn Contract - Assembly and Test of Active Collimator | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 6192 | 0 | 6192
2553064 | D | UConn Contract - Delivery of Active Collimator to JLab | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 679 | 0 | 679
2553072a | S | Program & test Collimator Table (BL Components) FY13 | 2014-06-01 08:00 | 23-Jun-14 16:00 A | 100% | 0 | 0 | 2462
2553072b | S | Program & test Collimator Table (BL Components) FY14 | 2014-06-01 08:00 | 23-Jun-14 16:00 A | 100% | 0 | 0 | 6479
2553075 | H | Test Active Collimator (BL Compnts) | 2014-08-11 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 6642
2553080 | D | Proc Active Collimator Control Equipment (HallD) | 2013-11-01 | 16-Jun-14 16:00 A | 100% | 15624 | 0 | 15624
2553085 | S | Support Control Active Collimator (HallD) FY13 Assemble Halo counters | 2014-08-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 843
2553085a | S | Support Control Active Collimator (HallD) FY14 Assemble Halo counters | 2014-08-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 8132
2553090 | D | Proc Hardware for Active Collimator Control (Accelerator Grp) | 2013-11-01 | 18-Aug-14 16:00 A | 100% | 18800 | 0 | 18800
2553095 | S | Design Install Feedback System for Active Collimator (Accelerator Grp) FY13 | 2014-05-02 08:00 | 2015-03-30 16:00 | 90% | 0 | 0 | 4618
2553095a | S | Design Install Feedback System for Active Collimator (Accelerator Grp) FY14 | 2014-05-02 08:00 | 2015-03-30 16:00 | 90% | 0 | 0 | 38832
2553110 | S | Manufacturing Drawings for Goniometer vacuum chamber | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1646
2553125 | S | Install mounting frame for low granularity PS detectors | 2014-04-07 08:00 | 19-May-14 16:00 A | 100% | 0 | 90 | 7115
2553130 | S | Manufacturing Drawings of cooling system for PS detector | 2013-10-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 19032
2553135 | D | Procure cooling system for PS detector | 2014-06-02 08:00 | 18-Aug-14 16:00 A | 100% | 5779 | 0 | 5779
2553140 | S | Manufacturing Drawings of Amorphous target insertion device (E-beam) FY13 | 2013-09-03 08:00 | 2013-10-21 10:00 | 100% | 0 | 0 | 1672
2553140a | S | Manufacturing Drawings of Amorphous target insertion device (E-beam) FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 2846
2553145 | D | Fab Amorphous insertion device (e-beam) (Previously Obligated) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 15066 | 0 | 15066
2553147 | D | Fab Amorphous insertion device (e-beam) | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 4344 | 0 | 4344
2553150 | S | Manufacturing Drawings of polarimeter vacuum chamber | 2014-02-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 21272
2553155 | D | Fab polarimeter vacuum chamber | 2014-06-02 08:00 | 18-Aug-14 16:00 A | 100% | 6088 | 0 | 6088
2553157 | S | Install polarimeter | 2014-08-11 08:00 | 2015-03-13 16:00 | 32% | 0 | 206 | 6989
2553160 | S | Manufacturing Drawings of radiator holder | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 14182
2553165 | D | Fab radiator holder | 2014-07-07 08:00 | 18-Aug-14 16:00 A | 100% | 3715 | 0 | 3715
2553170 | D | Procure goniometer vacuum pump/instrumentation | 2013-09-03 08:00 | 21-Jul-14 16:00 A | 100% | 5238 | 0 | 5238
2553175 | S | Fab Tagger beamline components | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1651
2553185 | S | Manufacturing Drawings of Photon beamline to dump | 2014-02-04 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 17168
2553190 | D | Fabricate photon beamline to dump | 2014-04-14 08:00 | 21-Jul-14 16:00 A | 100% | 12589 | 0 | 12589
2553195 | S | Install photon beamline to dump | 2014-05-05 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 103 | 10071
2553200 | S | Manufacturing Drawings of Total Absorption Counter | 2014-02-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 19220
2553205 | H | Fabricate Total Absorption Counter Support | 2014-05-05 08:00 | 19-May-14 16:00 A | 100% | 6501 | 0 | 6501
2553210 | S | Install Total Absorption Counter | 2014-06-16 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 103 | 10672
2561040M | M | Delivery Complete for CDC (Assy) | 2013-11-11 08:00 |  | 100% | 0 | 0 | 0
2561050M | M | Complete FDC (Assy) | 2013-09-30 08:00 |  | 100% | 0 | 0 | 0
2561060M | M | Delivery Complete for TOF (Assy) | 2014-01-13 08:00 |  | 100% | 0 | 0 | 0
2561110 | S | Receive CDC for Storage (Assy) | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 2741 | 0 | 14400
2561140 | H | Receive FDC (Assy) | 2013-10-01 08:00 | 07-Oct-13 16:00 A | 100% | 0 | 0 | 3386
2561145 | S | Rail Mounting for FDC (Assy) FY13 | 2013-09-03 08:00 | 2013-10-21 09:17 | 100% | 0 | 338 | 5899
2561145a | S | Rail Mounting for FDC (Assy) FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 271 | 4735
2561160 | H | Receive TOF Detector Units (Assy) | 2013-11-04 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 3386
2561165 | S | Mount TOF Counters onto Detector Frame (Assy) | 2013-12-03 08:00 | 17-Mar-14 16:00 A | 100% | 11213 | 0 | 33127
2562000 | E | Procured Labor (Bill Vulcan) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 2608 | 0 | 2608
2562005LOE | E | FY13 Work Cordinator (Installtn) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 10266
2562006LOE | E | FY14 Work Cordinator (Installtn) | 2013-10-01 08:00 | 26-Sep-14 16:00 A | 100% | 0 | 0 | 131419
2562013E | E | FY13 Travel (Installtn) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 134 | 134
2562014E | E | FY14 Travel (Installtn) | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 1032 | 1032
2562035M | M | Assy of TOF (Installtn) | 2014-04-01 08:00 |  | 100% | 0 | 0 | 0
2562045 | S | Install Tagger Magnets & Chamber (Installtn) FY13 | 2013-09-03 08:00 | 20-Dec-13 13:11 A | 100% | 0 | 2934 | 7592
2562045a | S | Install Tagger Magnets & Chamber (Installtn) FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 1665 | 4309
2562050 | S | Install Tagger Pwr Supply (Installtn) FY13 | 2013-09-03 08:00 | 2013-11-18 09:20 | 100% | 0 | 1356 | 9965
2562050a | S | Install Tagger Pwr Supply (Installtn) FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 560 | 4113
2562060 | S | Survey & Align tagger beamline (Installtn) | 2014-03-10 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 2908
2562061 | S | Field Map Tagging Magnet (Installtn) | 2013-09-16 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 22972
2562063 | D | Fab field map fixture tagging magnet | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 1840 | 0 | 1840
2562065 | S | Install Pwr for Tagger Electrnc's (Installtn) | 2014-04-07 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 7225
2562080 | S | Install Hodoscope (Installtn) | 2014-03-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 3405 | 28979
2562085 | S | Racks - Install Tagger FY13 | 2014-04-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 21 | 400
2562085a | S | Racks - Install Tagger FY14 | 2014-04-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 10 | 186
2562090 | S | Install Tagger Electrnc's (Installtn) | 2014-06-09 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 4983 | 16862
2562091M | M | Tagger Ready For Beam (e+g) (Installtn) |  | 21-Jul-14 16:00 A | 100% | 0 | 0 | 0
2562095 | U | Cables - Install on Trays Detector to Racks Tagger | 2014-07-07 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 3759
2562095a | U | Cables - Route and Connect on Detector Tagger | 2014-07-14 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 3759
2562095b | U | Cables - Route on Racks Tagger | 2014-06-02 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 1880
2562095c | U | Cables - Connect to Crate Electronics Tagger | 2014-06-09 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 4885
2562098 | S | Install Tagger Quad Stand & Magnet (Installtn) | 2013-09-09 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 10494
2562099 | U | Cables - Install on Trays Detector to Racks Pair Spectrometer | 2014-05-05 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 3643
2562099a | U | Cables - Route and Connect on Detector Pair Spectrometer | 2014-07-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 3759
2562099b | U | Cables - Route on Racks Pair Spectrometer | 2014-05-12 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 1880
2562099c | U | Cables - Connect to Crate Electronics Pair Spectrometer | 2014-06-08 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 4885
2562165 | S | Install High Granularity Pair Spectrometer (Installtn) | 2014-04-07 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 310 | 12680
2562170 | S | Install Photon Beam Profiler (Installtn) | 2014-08-02 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 103 | 12564
2562175 | S | Install Hydrogen Target and Start Counter Inside Detector (Installtn) | 2014-07-03 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 6191 | 34344
2562180 | S | Install Photon BL Tag Hall (Installtn) | 2013-11-01 | 21-Jul-14 16:00 A | 100% | 1744 | 116 | 6724
2562181 | S | Install Photon BL Colli. Cave (Installtn) - Procurement | 2013-11-01 | 19-May-14 16:00 A | 100% | 1751 | 0 | 1751
2562181a | S | Install Photon BL Colli. Cave (Installtn) - Labor/Expenses FY13 | 2014-01-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 30 | 990
2562181b | S | Install Photon BL Colli. Cave (Installtn) - Labor/Expenses FY14 | 2014-01-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 89 | 2911
2562205 | U | Install NIM and CAEN Crates in Counting Room (Installtn) | 2014-07-02 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 9774
2562206 | U | Install Computers in Counting Room (Installtn) Part B | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 9774
2562210 | S | Install Supprt Electrnc's in Counting Room (Installtn) (SP) | 2014-04-07 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 12458 | 12458
2562214 | D | Fab field map fixture for PS magnet | 2013-11-02 08:00 | 20-Jan-14 16:00 A | 100% | 6594 | 0 | 6594
2562216 | S | Field Map PS magnet | 2014-02-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 12249
2562225 | S | Mount Bcal in Solenoid (Installtn) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 3000 | 17422
2562230 | S | Attach readout wedges to the BCAL modules in situ (Installtn) FY13 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 682 | 7719
2562230a | S | Attach readout wedges to the BCAL modules in situ (Installtn) FY14 | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 2005 | 22700
2562231 | S | Manufacturing Drawings of BCAL Lateral support | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 5337
2562232 | D | Fab BCAL lateral support | 2013-11-01 | 2013-11-18 | 100% | 3921 | 0 | 3921
2562233 | S | Install BCAL lateral support | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 310 | 4394
2562235 | H | Comp B-cal Assy (Installtn) | 2014-01-06 08:00 | 17-Feb-14 16:00 A | 100% | 2492 | 0 | 12074
2562245 | S | Racks - Install Hall Lower Level Upstream (U1) | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 946
2562246 | S | Racks - Install Hall Lower Level Upstream South (US1) | 2013-10-21 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 3583
2562250 | S | Install Pwr to Racks Upstream Platform (Installtn) - Procurement | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 20645 | 0 | 20645
2562250a | S | Install Pwr to Racks Upstream Platform (Installtn) - Labor FY13 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 4602
2562250b | S | Install Pwr to Racks Upstream Platform (Installtn) - Labor FY14 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 8785
2562270 | U | Install Supprt Electrnc's, Platform #1 (Installtn) | 2014-01-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 8721 | 19999
2562275 | U | Cables - Install on Trays Detector to Racks BCAL FY13 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 1828
2562275a | U | Cables - Route and Connect on Detector BCAL | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 15090
2562275b | U | Cables - Route on Racks BCAL | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 5652
2562275c | U | Cables - Connect to Crate Electronics BCAL | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 8644
2562275d | U | Cables - Install on Trays Detector to Racks BCAL FY14 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 20748
2562278 | S | BCAL DAQ Control and Trigger set-up | 2014-02-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 27065
2562280 | S | Technical Support for Bcal Testing (Installtn) | 2014-02-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 13529
2562281 | S | Analyze BCAL Performance inside solenoid | 2014-03-03 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 0 | 24058
2562290 | U | Cables - Install on Trays Detector to Racks CDC | 2014-03-31 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 9424
2562290a | U | Cables - Route and Connect on Detector CDC | 2014-04-07 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 15076
2562290b | U | Cables - Route on Racks CDC | 2014-04-07 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 3759
2562290c | U | Cables - Connect to Crate Electronics CDC | 2014-04-07 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 6764
2562300 | S | Mounting CDC on cart align and insert into solenoid (Installtn) | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 16552
2562301 | U | CDC mounting electronics and other connections in situ (Installtn) | 2014-03-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 14653
2562303 | S | Install FDC/CDC Alignment Check System (Installtn) | 2013-11-04 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 10558
2562330 | S | Racks - Install Hall Upper Level Upstream (U2) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 60 | 3994
2562335 | S | Install Pwr to Racks Platform #2 (Installtn) - Procurement | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 29338 | 0 | 29338
2562335a | S | Install Pwr to Racks Platform #2 (Installtn) - Labor FY13 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 2052
2562335b | S | Install Pwr to Racks Platform #2 (Installtn) - Labor FY14 | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 6035
2562355 | U | Install Supprt Electrnc's Platform #2 (Installtn) - Procurement | 2013-11-01 | 2013-11-18 | 100% | 8451 | 0 | 8451
2562355a | U | Install Supprt Electrnc's Platform #2 (Installtn) - Labor FY13 | 2013-11-01 | 2013-11-18 | 100% | 0 | 0 | 4892
2562355b | U | Install Supprt Electrnc's Platform #2 (Installtn) - Labor FY14 | 2013-11-01 | 2013-11-18 | 100% | 0 | 0 | 6310
2562360 | H | Install FDC on Platform (Installtn) | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 3738 | 0 | 11208
2562365 | H | Alignment of FDC (Installtn) | 2013-10-11 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 8665
2562370 | U | Cables - Install on Trays Detector to Racks FDC | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 13210
2562370a | U | Cables - Route and Connect on Detector FDC | 2013-12-02 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 11278
2562370b | U | Cables - Route on Racks FDC | 2014-01-13 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 11317
2562370c | U | Cables - Connect to Crate Electronics FDC | 2014-01-13 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 6764
2562380 | S | Insertion of FDC (Installtn) | 2014-02-03 08:00 | 17-Mar-14 16:00 A | 100% | 12458 | 0 | 30363
2562385 | H | Cooling Sys Checks for FDC (Installtn) | 2013-11-04 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 4980
2562392 | D | Procure final hardware for Drift Chamber gas systems (Previously Obligated) | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 26348 | 0 | 26348
2562392a | D | Procure final hardware for Drift Chamber gas systems | 2013-09-03 08:00 | 17-Mar-14 16:00 A | 100% | 26852 | 0 | 26852
2562393 | S | Install/test gas systems | 2013-09-16 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 545 | 65828
2562405 | S | Install Pwr to FCAL/TOF Racks (Installtn) | 2013-10-01 08:00 | 18-Nov-13 16:00 A | 100% | 19559 | 0 | 19559
2562420 | S | Install Supprt Electrnc's FCAL/TOF Racks (Installtn) | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 12458 | 23736
2562435 | E | Engineering Support for Detector Installation 2013 (Installtn) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 3953
2562440 | E | Engineering Support for Tagger Installation 2013 (Installtn) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 1990
2562445 | E | Engineering Support for Installation 2013 (Installtn) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 8123
2562445a | E | Engineering Support for Installation 2014 (Installtn) | 2013-10-01 08:00 | 03-Sep-14 16:00 A | 100% | 0 | 0 | 95563
2562450 | S | Install TOF Sys (Installtn) | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 1238 | 13254
2562455 | U | Cables - Install on Trays Detector to Racks TOF | 2014-04-07 08:00 | 14-Apr-14 16:00 A | 100% | 0 | 0 | 7518
2562455a | U | Cables - Route and Connect on Detector TOF | 2014-04-15 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 7518
2562455b | U | Cables - Route on Racks TOF | 2014-04-07 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 3759
2562455c | U | Cables - Connect to Crate Electronics TOF | 2014-04-14 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 4885
2562460 | S | Test TOF Sys (Installtn) | 2014-06-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 21047
2562466 | S | Install Dark Room for Fcal (Installtn) | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 850 | 4226
2562475 | U | Cables - Install on Trays Detector to Racks FCAL FY13 (FY14 @ 2562475d) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 6749
2562475a | U | Cables - Route and Connect on Detector FCAL FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1500
2562475aa | U | Cables - Route and Connect on Detector FCAL FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1470
2562475b | U | Cables - Route on Racks FCAL FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 950
2562475ba | U | Cables - Route on Racks FCAL FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1275
2562475c | U | Cables - Connect to Crate Electronics FCAL FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 846
2562475ca | U | Cables - Connect to Crate Electronics FCAL FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 1833
2562475d | U | Cables - Install on Trays Detector to Racks FCAL FY14 (FY13 @ 2562475) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 2089
2562478 | S | FCAL DAQ and Trigger_Setup FY13 | 2013-11-04 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 4426
2562478a | S | FCAL DAQ and Trigger_Setup FY14 | 2013-11-04 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 22149
2562480 | S | Install Pulsing Sys for Fcal (Installtn) FY13 | 2013-09-03 08:00 | 20-Jan-14 15:08 A | 100% | 0 | 1372 | 2136
2562480a | S | Install Pulsing Sys for Fcal (Installtn) FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 7716 | 12013
2562482 | S | Test and analyze FCAL detector FY13 | 2014-04-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 2217
2562482a | S | Test and analyze FCAL detector FY14 | 2014-04-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 18763
2562485 | S | Install Start Counter Onto LH Target (Installtn) | 2014-06-02 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 17846
2562490 | U | Cables - Install on Trays Detector to Racks Start Counter | 2014-09-01 08:00 | 15-Sep-14 16:00 A | 100% | 0 | 0 | 3759
2562490a | U | Cables - Route and Connect on Detector Start Counter | 2014-09-08 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 3759
2562490b | U | Cables - Route on Racks Start Counter | 2014-06-07 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 1880
2562490c | U | Cables - Connect to Crate Electronics Start Counter | 2014-06-09 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 4885
2562495 | H | Test Start Counter (Installtn) | 2014-09-03 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 9999
2562505 | S | Install Trigger Electrnc's (Installtn) | 2014-07-10 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 9398
2562510 | S | Check-out Trigger Electrnc's (Installtn) | 2014-06-09 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 7327
2562515 | U | Crates - Loaded (VME64x VXS HV LV) Install Hall Tagger | 2014-06-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 3759
2562520 | U | Crates - Loaded (VME64x VXS HV LV) Install Hall Pair Spectrometer | 2014-02-03 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 3759
2562525 | U | Crates - Loaded (VME64x VXS HV LV) Install Hall Start Counter | 2014-02-10 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 3759
2562530 | U | Crates - Loaded (VME64x VXS HV LV) Install Hall CDC | 2013-10-14 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 7518
2562535 | U | Crates - Loaded (VME64x VXS HV LV) Install Hall FDC | 2013-10-12 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 15037
2562540 | U | Crates - Loaded (VME64x VXS HV LV) Install Hall BCAL | 2013-10-10 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 15037
2562545 | U | Crates - Loaded (VME64x VXS HV LV) Install Hall TOF | 2013-11-04 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 3759
2562595a | E | Installation work space infrastructure (TW's Doublewide) | 2013-09-03 08:00 | 30-Sep-14 16:00 A | 100% | 5800 | 0 | 5800
2562610LOE | E | Electrical power engineer support 2013 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 0 | 10332
2562615LOE | E | Electrical power engineer support 2014 | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 0 | 66114
2562620a | D | Procure Electrical Power cable/conduit Part B FY13 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 24064 | 24064
2562620aa | D | Procure Electrical Power cable/conduit Part B FY14 | 2013-09-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 4966 | 4966
2562625 | S | Install Electrical Dirty Power cable/conduit from Panels | 2013-12-02 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 15376
2562626 | D | Install Transformers and Panels in Hall D | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 43349 | 0 | 43349
2562630 | S | Install nitrogen lines in hall D | 2013-11-04 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 13685
2562635 | S | Install air lines in hall D | 2013-12-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 13984
2562636 | S | Manufacture Drawing Inst Air Sys | 2013-10-07 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 24259
2562637 | D | Procure Inst Air Sys | 2013-11-04 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 4747 | 4747
2562640 | S | Procure cable trays and hardware | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 1238 | 0 | 1238
2562645 | S | Install cable trays and hardware FY13 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 1294
2562645a | S | Install cable trays and hardware FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 2269
2562685 | S | Fiducialize and survey equipment (2013) | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 449 | 2236
2562690 | S | Manufacturing Drawings of cooling system for FCAL dark room FY13 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 731
2562690a | S | Manufacturing Drawings of cooling system for FCAL dark room FY14 | 2013-10-01 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 604
2562700 | S | Install Cooling system for FCAL dark room | 2013-10-14 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 6276
2562705 | S | Manufacturing Drawings of Chilled water system for Hall D | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 8301
2562710 | D | Procure Chilled water components | 2013-09-09 08:00 | 18-Nov-13 16:00 A | 100% | 10113 | 0 | 10113
2562715 | S | Install Chilled water sytem Hall D | 2013-09-09 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 14636
2562730 | S | Install Upstream cable trays (FDC/CDC/SC) FY13 | 2013-09-03 08:00 | 20-Dec-13 14:07 A | 100% | 0 | 0 | 4747
2562730a | S | Install Upstream cable trays (FDC/CDC/SC) FY14 | 2013-09-03 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 2204
2562740 | S | Manufacturing Drawings of dry air cooling upstream racks/drift chambers | 2013-10-01 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 24578
2562745 | S | Fabricate dry air cooling system up racks/drift chambers | 2013-11-01 08:00 | 17-Mar-14 16:00 A | 100% | 8307 | 0 | 8307
2562750 | S | Install dry air cooling system up racks/drift chamber | 2013-12-05 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 14663
2562770 | S | Manufacturing Drawings of fixture for commissioning target | 2014-01-13 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 24259
2562775 | D | Fab Fixture for commissioning target | 2014-05-12 08:00 | 18-Aug-14 16:00 A | 100% | 8255 | 0 | 8255
2562780 | S | Install Commissioning target with Start Counter | 2014-08-11 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 10183
2562785 | E | Materials for install 2013 (Previously Obligated) | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 3757 | 0 | 3757
2562790 | E | Materials for install 2013 | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 2953 | 0 | 2953
2562805 | S | Manufacturing Drawings of N2 purge system FY13 | 2013-09-03 08:00 | 2013-11-18 00:57 | 100% | 0 | 0 | 8297
2562805a | S | Manufacturing Drawings of N2 purge system FY14 | 2013-09-03 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 15697
2562810 | D | Procure N2 purge system | 2013-10-15 08:00 | 18-Nov-13 16:00 A | 100% | 5572 | 0 | 5572
2562830 | S | Install BCAL cooling manifold FY13 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 3867
2562830a | S | Install BCAL cooling manifold FY14 | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 3990
2562835 | S | Install PS shielding | 2013-09-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 5047
2562840 | S | Install dirty power cable/conduit tagger | 2014-05-02 08:00 | 19-May-14 16:00 A | 100% | 0 | 1765 | 7159
2562845 | Z | Install Power cable/conduit tagger | 2014-05-02 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 0
2562850 | D | Procure UPS system for critical controls | 2014-03-03 08:00 | 16-Jun-14 16:00 A | 100% | 4747 | 0 | 4747
2562855 | S | Install UPS system for critical controls | 2014-06-09 08:00 | 23-Jun-14 16:00 A | 100% | 0 | 0 | 9464
2562860 | S | Install Electron beamline to dump | 2014-02-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 206 | 7823
2562865 | D | Procure lighting fixture under US platform | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 550 | 0 | 550
2562870 | S | Install lighting fixtures under US platform | 2014-05-02 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 4164
2562875 | S | Develop flammable gas detection system in solenoid | 2014-01-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 19446
2562880 | D | Procure flammable gas detection system | 2014-04-15 08:00 | 16-Jun-14 16:00 A | 100% | 8462 | 0 | 8462
2562885 | S | Install flammable gas detection system | 2014-05-05 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 11777
2562890 | S | Detector Readout Electronics Support Documentation and OSP FY14 | 2013-10-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 140156
2562890A | S | Detector Readout Electronics Support Documentation and OSP FY15 | 2013-10-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 586
2562895 | S | Preparing OSP ESAD documentation Rediness Review for April 14 Beam Run FY13 | 2013-09-03 08:00 | 2014-05-19 11:35 | 100% | 0 | 274 | 11916
2562895a | S | Preparing OSP ESAD documentation Rediness Review for April 14 Beam Run FY14 | 2013-09-03 08:00 | 19-May-14 16:00 A | 100% | 0 | 2117 | 92218
2562900 | S | Preparing OSP ESAD documentation Rediness Review for October 14 Beam Run | 2014-06-01 08:00 | 18-Aug-14 16:00 A | 100% | 0 | 2580 | 106747
26112011 | H | Redundant Cooling Towers Award Contract | 2014-07-01 08:00 | 2014-07-15 08:00 | 100% | 0 | 0 | 6164
26112012 | C | Redundant Cooling Towers Contract Progress | 2014-07-14 08:00 | 2015-01-30 16:00 | 45% | 412044 | 0 | 412044
26112013 | E | Redundant Cooling Towers Construction Management | 2014-08-01 08:00 | 2015-02-04 16:00 | 69.52% | 0 | 0 | 46698
26112030M | M | N&S Access LCW Upgrades Constr Comp |  | 2015-02-04 16:00 | 0% | 0 | 0 | 0
26114000M | M | Tunnel A/C Begin Constr | 2014-10-09 08:00 |  | 100% | 0 | 0 | 0
26114005 | H | Tunnel A/C Award Contract | 2014-10-09 08:00 | 2015-01-16 16:00 | 50% | 0 | 0 | 6164
26114010 | C | Tunnel A/C Constrctn Contract Progress | 2015-01-20 08:00 | 2015-07-24 16:00 | 0% | 1456866 | 0 | 1456866
26114015 | H | Tunnel A/C Bldng Cmmssng | 2015-07-27 08:00 | 2015-07-31 16:00 | 0% | 15916 | 0 | 15916
26114020 | E | Tunnel A/C Constrctn Mngmnt | 2015-01-20 08:00 | 2015-08-06 16:00 | 0% | 0 | 0 | 83687
26114025 | H | Tunnel A/C Beneficial Occupancy | 2015-08-03 08:00 | 2015-08-07 16:00 | 0% | 0 | 0 | 6164
26114030M | M | Tunnel A/C Constr Comp |  | 2015-08-07 16:00 | 0% | 0 | 0 | 0
26115025 | C | N&S Linac A/C Construction Contract Progress | 2013-09-03 08:00 | 16-Sep-13 16:00 A | 100% | 52634 | 0 | 52634
26115030 | E | N&S Linac A/C Construction Management FY13 | 2013-09-03 08:00 | 2013-09-30 10:21 | 100% | 0 | 0 | 7831
26115030a | E | N&S Linac A/C Construction Management FY14 | 2013-10-01 08:00 | 30-Oct-13 16:00 A | 100% | 0 | 0 | 11313
26115035 | H | N&S Linac A/C Building Commissioning | 2013-09-18 08:00 | 30-Oct-13 16:00 A | 100% | 0 | 0 | 2987
26115040 | H | N&S Linac A/C Beneficial Occupancy | 2013-09-18 08:00 | 27-Sep-13 16:00 A | 100% | 0 | 0 | 2987
26115045M | M | N&S Linac A/C Construction Complete |  | 31-Oct-13 16:00 A | 100% | 0 | 0 | 0
271913LOEB | E | FY13 Constrctn Proj Office Proj Mngmnt Part B | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 1280 | 348 | 69025
271914LOE | E | FY14 Constrctn Proj Office Proj Mngmnt | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 21292 | 930872
271915LOE | E | FY15 Constrctn Proj Office Proj Mngmnt | 2014-10-01 08:00 | 2015-09-30 16:00 | 9.35% | 0 | 10351 | 446422
271916LOE | E | FY16 Constrctn Proj Office Proj Mngmnt | 2015-10-01 08:00 | 2016-06-30 16:00 | 0% | 0 | 6636 | 216250
28000 | Z | Accelerator Schedule Contingency Activity | 2014-08-04 08:00 | 11-Aug-14 16:00 A | 100% | 0 | 0 | 0
28005 | Z | Hall A Schedule Contingency Activity | 2014-05-01 08:00 | 01-May-14 16:00 A | 100% | 0 | 0 | 0
28010 | Z | Hall D Schedule Contingency Activity | 2015-03-31 08:00 | 2016-03-25 16:00 | 0% | 0 | 0 | 0
28015 | Z | Hall B Schedule Contingency Activity | 2016-09-28 08:00 | 2018-04-03 16:00 | 0% | 0 | 0 | 0
28020 | Z | Hall C Schedule Contingency Activity | 2016-07-20 08:00 | 2018-01-19 16:00 | 0% | 0 | 0 | 0
28025 | Z | Civil Schedule Contingency Activity | 2015-08-10 08:00 | 2016-08-03 16:00 | 0% | 0 | 0 | 0
2811000 | S | Accel Hot Check-out | 2013-10-15 08:00 | 14-Apr-14 16:00 A | 100% | 0 | 0 | 169657
2811001 | Z | Accel ARR Process | 2013-09-03 08:00 | 31-Oct-13 16:00 A | 100% | 0 | 0 | 0
2811005 | S | Accel Beam Commisioning | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 435041
2811019 | Z | H-A ARR Process | 2014-03-03 08:00 | 10-Mar-14 16:00 A | 100% | 0 | 0 | 0
2811020 | S | H-A Beam Cmmssng | 2014-03-31 08:00 | 01-Apr-14 16:00 A | 100% | 0 | 0 | 27795
2811034 | Z | H-B ARR Process | 2016-07-18 08:00 | 2016-09-13 16:00 | 0% | 0 | 0 | 0
2811035 | S | H-B Beam Cmmssng | 2016-09-14 08:00 | 2016-09-27 16:00 | 0% | 0 | 0 | 114729
2811049 | Z | H-C ARR Process | 2016-05-16 08:00 | 2016-07-12 16:00 | 0% | 0 | 0 | 0
2811050 | S | H-C Beam Cmmssng | 2016-07-13 08:00 | 2016-07-19 16:00 | 0% | 0 | 0 | 57365
2811064 | Z | H-D ARR Process | 2014-08-02 08:00 | 28-Aug-14 16:00 A | 100% | 0 | 0 | 0
2811065 | S | H-D Beam Cmmssng | 2014-10-13 08:00 | 2014-11-21 16:00 | 0% | 0 | 0 | 172094
2812000 | S | Accel Hot Check-out Accelerator Commissioning (Utilities) | 2013-10-15 08:00 | 14-Apr-14 16:00 A | 100% | 198125 | 0 | 235442
2812005 | S | Accel Beam Commissioning (Utilities) | 2013-12-02 08:00 | 17-Feb-14 16:00 A | 100% | 609853 | 0 | 703439
2812020 | S | H-B Beam Cmmssng (Utilities) | 2016-09-14 08:00 | 2016-09-27 16:00 | 0% | 380140 | 0 | 411124
2812035 | S | H-C Beam Cmmssng (Utilities) | 2016-07-13 08:00 | 2016-07-19 16:00 | 0% | 269399 | 0 | 285269
2812050 | S | H-D Beam Cmmssng (Utilities) | 2014-10-13 08:00 | 2014-11-21 16:00 | 0% | 571807 | 0 | 618409
2812065 | S | H-A Beam Cmmssng (Utilities) | 2014-03-31 08:00 | 01-Apr-14 16:00 A | 100% | 115573 | 0 | 123140
281315015 | S | In-Tunnel Checkout and Commisioning Cryomodule #8 | 2013-10-01 08:00 | 10-Dec-13 16:00 A | 100% | 0 | 3846 | 24873
281315025 | S | In-Tunnel Checkout and Commisioning Cryomodule #10 FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 1326 | 8577
281315025a | S | In-Tunnel Checkout and Commisioning Cryomodule #10 FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 616 | 3982
281315030 | S | Installation & Test of Individual Heater Control & Piezo Operation FY13 | 2013-09-03 08:00 | 2014-01-21 10:33 | 100% | 0 | 326 | 2940
281315030a | S | Installation & Test of Individual Heater Control & Piezo Operation FY14 | 2013-09-03 08:00 | 2014-01-20 10:33 | 100% | 0 | 1648 | 14865
281321025 | H | RF Sys Tests #10 (Install & SYS COMMIS) | 2013-09-03 08:00 | 09-Sep-13 16:00 A | 100% | 0 | 156 | 6130
281321050 | H | RF Cavity Tests Cryomodule #9 (Install & SYS COMMIS) | 2013-09-03 08:00 | 11-Jan-14 16:00 A | 100% | 0 | 181 | 8264
281321055 | S | RF Cavity Tests Cryomodule #10 (Install & SYS COMMIS) | 2014-01-03 08:00 | 26-Jan-14 16:00 A | 100% | 0 | 267 | 12181
2813221000 | U | Test Magnet System Box Power Supplies w/Dummy Load FY13 | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 11285
2813221000a | U | Test Magnet System Box Power Supplies w/Dummy Load FY14 | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 0 | 131005
2813221005 | U | Test Arc 1 and Hall A PS w/ Dummy Load FY13 | 2013-09-09 08:00 | 20-Dec-13 13:38 A | 100% | 0 | 0 | 3916
2813221005a | U | Test Arc 1 and Hall A PS w/ Dummy Load FY14 | 2013-09-09 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 11617
2813224000 | U | Integration Testing- Box PS FY13 | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 114 | 1809
2813224000a | U | Integration Testing- Box PS FY14 | 2013-10-01 08:00 | 16-Jun-14 16:00 A | 100% | 0 | 2374 | 37796
2813224005 | U | Intergation Testing- Trim PS | 2013-09-30 08:00 | 19-May-14 16:00 A | 100% | 0 | 1333 | 32136
281341000 | S | Rebuild YB-1 | 2013-11-01 | 20-Dec-13 16:00 A | 100% | 0 | 4000 | 21626
281341005 | S | Rebuild YB-2 | 2013-11-01 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 17626
281341010 | S | Rebuild YB-Spare | 2013-11-01 | 2014-03-17 | 100% | 0 | 3000 | 22897
281341015 | S | Install YB1 and YB2 | 2014-02-03 08:00 | 17-Feb-14 16:00 A | 100% | 0 | 0 | 63468
281341020LOE | E | YB Oversight and Documentation | 2013-11-11 08:00 | 27-Feb-14 16:00 A | 100% | 0 | 0 | 32102
2821X000 | S | H-A PRE-OPS Cmmssn with Beam | 2014-05-01 08:00 | 01-May-14 16:00 A | 100% | 0 | 0 | 12240
28223000 | U | CTP testing of 22 boards | 2015-04-29 08:00 | 2015-07-30 16:00 | 0% | 0 | 0 | 49635
28223010 | U | GTP testing of 2 boards | 2014-03-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 12025
28223025 | S | DAQ Commissioning FY14 | 2014-11-03 08:00 | 2014-12-01 16:00 | 0% | 0 | 0 | 2568
28223025A | S | DAQ Commissioning FY15 | 2014-12-02 08:00 | 2015-12-01 16:00 | 0% | 0 | 0 | 34309
28223025B | S | DAQ Commissioning FY16 | 2015-12-02 08:00 | 2015-12-03 16:00 | 0% | 0 | 0 | 279
28223030 | S | CLAS12 DAQ/online software updates FY14 | 2014-11-03 08:00 | 2014-12-01 16:00 | 0% | 0 | 0 | 3822
28223030A | S | CLAS12 DAQ/online software updates FY15 | 2014-12-02 08:00 | 2015-12-01 16:00 | 0% | 0 | 0 | 51070
28223030B | S | CLAS12 DAQ/online software updates FY16 | 2015-12-02 08:00 | 2015-12-03 16:00 | 0% | 0 | 0 | 415
28223040 | S | Trigger system commissioning | 2015-07-31 08:00 | 2015-10-23 16:00 | 0% | 0 | 84334 | 133985
28226000 | S | Commission Cryogenic System | 2016-04-15 08:00 | 2016-04-28 16:00 | 0% | 0 | 0 | 13950
28226005 | S | Cooldown | 2016-04-29 08:00 | 2016-05-19 16:00 | 0% | 0 | 0 | 75358
28226010 | S | Torus Operational Tests | 2016-05-20 08:00 | 2016-06-03 16:00 | 0% | 0 | 0 | 36569
28226015 | S | Map CLAS12 Torus Field both polarities | 2016-06-06 08:00 | 2016-06-27 16:00 | 0% | 0 | 0 | 20226
28226020 | H | Solenoid Cool Down | 2016-06-02 08:00 | 2016-06-27 16:00 | 0% | 0 | 0 | 9063
28226025 | H | Solenoid Acceptance Tests and Mapping | 2016-06-28 08:00 | 2016-07-19 16:00 | 0% | 0 | 0 | 6042
2822X000 | S | H-B PRE-OPS Cmmssn with Beam | 2016-09-14 08:00 | 2016-09-27 16:00 | 0% | 0 | 0 | 105062
28231000 | S | HB-Acceptance Test | 2015-05-26 08:00 | 2015-08-04 16:00 | 0% | 0 | 0 | 25356
28231005 | S | Q1 Cooldown and Acceptance Test | 2015-01-30 08:00 | 2015-03-12 16:00 | 0% | 0 | 0 | 25356
28231010 | H | Q1 Harmonic Coil Test | 2015-03-13 08:00 | 2015-03-19 16:00 | 0% | 0 | 0 | 3933
28236000 | S | Cool Down Dipole Magnet | 2015-12-21 08:00 | 2016-02-03 16:00 | 0% | 0 | 0 | 13259
28236005 | H | Dipole Acceptance Test | 2016-02-04 08:00 | 2016-02-29 16:00 | 0% | 0 | 0 | 10070
28236010 | S | Q2 Cooldown and Acceptance Test | 2016-02-04 08:00 | 2016-03-16 16:00 | 0% | 0 | 0 | 26165
28236015 | H | Q2 HC & FF Test | 2016-03-10 08:00 | 2016-03-16 16:00 | 0% | 0 | 0 | 8898
28236020 | S | Q3 Cooldown and Acceptance Test | 2016-03-24 08:00 | 2016-05-13 16:00 | 0% | 0 | 0 | 26165
28236025 | H | Q3- HC & FF Test | 2016-05-09 08:00 | 2016-05-13 16:00 | 0% | 0 | 0 | 8898
28236030 | S | Power all Magnets together | 2016-05-16 08:00 | 2016-06-13 16:00 | 0% | 0 | 0 | 24086
2823X000 | S | H-C PRE-OPS Cmmssn with Beam | 2016-07-13 08:00 | 2016-07-19 16:00 | 0% | 0 | 0 | 45391
28241000 | E | Maintanence Support Solenoid FY13 | 2013-11-01 08:00 | 30-Nov-13 16:00 A | 100% | 0 | 1196 | 3539
28241000a | E | Maintanence Support Solenoid FY14 | 2013-11-01 08:00 | 2014-09-30 10:05 | 100% | 0 | 15236 | 45102
28241000aB | E | Maintanence Support Solenoid FY15 | 2014-09-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 255 | 754
282432005 | S | Check-out Monitoring | 2014-05-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 7662
282432010 | S | Check-out Alarm Sys | 2014-07-14 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 4654
282432015 | S | Check-out Archiving Sys | 2014-07-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 7662
282432025 | S | Check-out Storage Mngmnt Software | 2014-07-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 12633
282443010 | U | Acceptance test of CTP boards (FE grp) FY13 | 2013-09-03 08:00 | 20-Jan-14 14:10 A | 100% | 0 | 0 | 13294
282443010a | U | Acceptance test of CTP boards (FE grp) FY14 | 2013-09-03 08:00 | 20-Jan-14 16:00 A | 100% | 0 | 0 | 9602
282443020 | U | Acceptance test of GTP boards (FE grp) FY13 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 7154
282443020a | U | Acceptance test of GTP boards (FE grp) FY14 | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 0 | 0 | 13655
282443025a | S | Trigger Calibration (Hall D grp) | 2014-04-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 21050
282443025a5 | U | Acceptance test of TS boards (FE_grp) FY13 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 3328
282443025a5a | U | Acceptance test of TS boards (FE_grp) FY14 | 2013-10-01 08:00 | 21-Oct-13 16:00 A | 100% | 0 | 0 | 2576
282446000 | U | Test Power Distribution FY13 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 2098
282446000a | U | Test Power Distribution FY14 | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 4600
282446010 | U | Test Pair Spectrometer PS Readout Board | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 6764
282446015a | U | Test Pair Spectrometer Transition Board | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1880
282446020 | U | Test Pair Spectrometer Power Distribution | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 1880
282446025 | U | Test Pair Spectrometer System | 2013-10-01 08:00 | 20-Dec-13 16:00 A | 100% | 0 | 0 | 6764
282446030 | U | Test Start Counter Readout Board FY13 | 2013-10-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 1943
282446030a | U | Test Start Counter Readout Board FY14 | 2013-10-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 4760
282446035 | U | Test Start Counter Transition Board FY13 | 2013-10-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 991
282446035a | U | Test Start Counter Transition Board FY14 | 2013-10-01 08:00 | 19-May-14 16:00 A | 100% | 0 | 0 | 575
282446040 | U | Test Start Counter Power Distribution FY13 | 2013-10-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 619
282446040a | U | Test Start Counter Power Distribution FY14 | 2013-10-01 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 959
282453000 | S | Check Operation of Goniometer (BL Compnts) | 2014-07-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 24058
282453010 | U | Test PS High Granularity Counters FY13 | 2013-11-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 6126
282453010a | U | Test PS High Granularity Counters FY14 | 2013-11-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 7585
282462000 | S | Operational Checks CDC (Inside Solenoid) (Installtn) | 2014-05-02 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 32696
282462005 | S | Operation Checks FDC (outside Solenoid) (Installtn) | 2014-01-13 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 33547
282462010 | S | Operation Checks FDC (Inside Solenoid) (Installtn) | 2014-04-01 08:00 | 21-Jul-14 16:00 A | 100% | 0 | 0 | 60536
282462015 | S | System Check-out Install Hall Tagger | 2014-08-09 08:00 | 22-Aug-14 16:00 A | 100% | 0 | 0 | 6764
282462020 | S | System Check-out Install Hall Pair Spectrometer | 2014-06-09 08:00 | 15-Aug-14 16:00 A | 100% | 0 | 0 | 6764
282462025 | S | System Check-out Install Hall Start Counter | 2014-06-01 08:00 | 22-Sep-14 16:00 A | 100% | 0 | 0 | 6764
282462030 | S | System Check-out Install Hall CDC | 2014-03-03 08:00 | 17-Mar-14 16:00 A | 100% | 0 | 0 | 13529
282462035 | S | System Check-out Install Hall FDC | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 20293
282462040 | S | System Check-out Install Hall BCAL | 2014-03-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 20293
282462045 | S | System Check-out Install Hall TOF | 2014-04-03 08:00 | 21-Apr-14 16:00 A | 100% | 0 | 0 | 6764
282462050 | S | System Check-out Install Hall FCAL | 2013-11-04 08:00 | 18-Nov-13 16:00 A | 100% | 0 | 0 | 20293
2824X000 | S | H-D PRE-OPS Cmmssn with Beam | 2014-10-01 08:00 | 2014-11-21 16:00 | 45% | 0 | 0 | 160732
2831913LOE | E | FY13 Pre-Ops Supprt - Proj Office | 2013-09-03 08:00 | 30-Sep-13 16:00 A | 100% | 0 | 1628 | 69026
2831914LOE | E | FY14 Pre-Ops Supprt - Proj Office | 2013-10-01 08:00 | 30-Sep-14 16:00 A | 100% | 0 | 21292 | 930872
2831915LOE | E | FY15 Pre-Ops Supprt - Proj Office | 2014-10-01 08:00 | 2015-09-30 16:00 | 9.72% | 0 | 32241 | 1390533
2831916LOE | E | FY16 Pre-Ops Supprt - Proj Office | 2015-10-01 08:00 | 2016-06-29 16:00 | 0% | 0 | 35957 | 1172114
295212255 | D | Operations Test (P5 Chamber operational tests) | 2013-09-03 08:00 | 16-Jun-14 16:00 A | 100% | 56782 | 0 | 56782
295212260 | D | Phase 7 Chamber shipping | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 5000 | 0 | 5000
295222000 | D | Indiana Contract Completion | 2013-09-03 08:00 | 23-Sep-13 16:00 A | 100% | 8558 | 0 | 8558
2971000 | D | Blue Crab Cleanroom Completion | 2013-09-03 08:00 | 21-Oct-13 16:00 A | 100% | 29010 | 0 | 29010
32-05M | M | Start Accel Beam Commssng | 2013-12-02 08:00 |  | 100% | 0 | 0 | 0
3A-42M | M | MPS Installtn Comptd |  | 2014-05-02 08:00 | 100% | 0 | 0 | 0
3A-43M | M | H-A BL Installtn Comptd |  | 2014-02-03 08:00 | 100% | 0 | 0 | 0
3A-44M | M | H-B BL Installtn Comptd |  | 2014-03-17 08:00 | 100% | 0 | 0 | 0
3A-46M | M | H-C BL Installtn Comptd |  | 2014-02-17 08:00 | 100% | 0 | 0 | 0
3A-47M | M | Cryomodule Installtn Comptd |  | 2013-12-16 08:00 | 100% | 0 | 0 | 0
3A-48M | M | Trim Supply Installtn Comptd |  | 2014-08-14 08:00 | 100% | 0 | 0 | 0
3A-49M | M | PSS Installtn Comptd |  | 2014-04-21 08:00 | 100% | 0 | 0 | 0
3A-53M | M | H-D BL Installtn Comptd |  | 02-May-14 16:00 A | 100% | 0 | 0 | 0
3A-54M | M | S/R Installtn Comptd |  | 20-Jan-14 16:00 A | 100% | 0 | 0 | 0
3A-58M | M | End of Long Accel Constr Down |  | 2013-10-01 08:00 | 100% | 0 | 0 | 0
3P-12M | M | Start E-B Commssng of H-A Detctr's, Electrnc's, & BL Devices | 2014-03-24 08:00 |  | 100% | 0 | 0 | 0
3P-16M | M | Start E-B Commssng of H-D Detctr's, Electrnc's, & BL Devices | 2014-10-13 08:00 |  | 100% | 0 | 0 | 0
3P-18M | M | Start E-B Commssng of H-C Detctr's, Electrnc's, & BL Devices | 2016-07-13 08:00 |  | 0% | 0 | 0 | 0
3P-20M | M | Start E-B Commssng of H-B Detctr's, Electrnc's, & BL Devices | 2016-09-14 08:00 |  | 0% | 0 | 0 | 0
3P-21M | M | E-B Commssng of H-B Detctr's, Electrnc's, & BL Devices Comptd |  | 2016-09-27 16:00 | 0% | 0 | 0 | 0
3P-22M | M | E-B Commssng of H-C Detctr's, Electrnc's, & BL Devices Comptd |  | 2016-07-19 16:00 | 0% | 0 | 0 | 0
3P-25M | M | 10 GeV Beam to Hall D Tagger |  | 02-May-14 16:00 A | 100% | 0 | 0 | 0
3P-26M | M | Torus Assembled and Tested | 2016-06-28 08:00 |  | 0% | 0 | 0 | 0
4A-06M | M | Pwr (Mag) Installtn Comptd |  | 2014-09-15 08:00 | 100% | 0 | 0 | 0
4A-07M | M | Linac Installtn Comptd |  | 2013-12-09 08:00 | 100% | 0 | 0 | 0
4A-08M | M | Accelerator Beam Transport Comptd |  | 2014-02-10 08:00 | 100% | 0 | 0 | 0
4A-09M | M | I&C/Sfty for Accelerator Installtn Comptd |  | 2014-05-12 08:00 | 100% | 0 | 0 | 0
4A-10M | M | Start Accel Hot Chkout | 2013-10-14 08:00 |  | 100% | 0 | 0 | 0
4A-11M | M | Beam Transport to Halls Comptd |  | 2014-05-02 08:00 | 100% | 0 | 0 | 0
4A-12M | M | I&C/Sfty Installtn Comptd |  | 22-Sep-14 16:00 A | 100% | 0 | 0 | 0
9-140M | M | FY14 Funds Available | 2013-10-01 08:00 |  | 100% | 0 | 0 | 0
9-155M | M | FY15 Funds Available | 2014-10-01 08:00 |  | 100% | 0 | 0 | 0
9-160M | M | FY16 Funds Available | 01-Oct-15 08:00* |  | 0% | 0 | 0 | 0

## Final Product
Sum of Budgeted Units | EVMS Code | Activity Name | Start | Finish | Percent Complete | Budgeted Material Cost | Budgeted Non-Labor Cost (Expenses) | Budgeted Total Cost | Labor Resources in Person Weeks | [12 empty] | UP-DATED? | Comments | New Estimate
Row Labels | [8 empty] | CONTRB UNIV LBR | ELEC DES | ELEC ENG | ELEC TECH | MECH DES | MECH ENG | MECH TECH | PD UNIV STAFF | PD UNIV STUDNT | SCIENTIST | SR STAFF | VISTNG USERS | Grand Total | Y/N |  | Budgeted Material Cost | Budgeted Non-Labor Cost (Expenses) | CONTRB UNIV LBR | ELEC DES | ELEC ENG | ELEC TECH | MECH DES | MECH ENG | MECH TECH | PD UNIV STAFF | PD UNIV STUDNT | SCIENTIST | SR STAFF | VISTNG USERS | Grand Total
1.4.2.2.4.2 LOW THRESHOLD CC | [8 empty] | 6 |  |  | 4 |  |  | 72.2 |  | 4 | 14.2 |  | 8 | 108.4 | [16 empty] | 68.985
242242076 | D | Support Frame Fabrication for 1S in TED | 2014-11-03 08:00 | 2014-12-01 16:00 | 0% | 0 | 1032 | 2925 | [6 empty] | 1 | [5 empty] | 1 |  |  |  | 1032 | [6 empty] | 1 | [5 empty] | 1
242242092 | U | Al/Mg Deposit Procurement WC Labor FY14 | 2014-05-02 08:00 | 2014-11-14 16:00 | 60% | 0 | 0 | 5725 | [9 empty] | 1.9 |  |  | 1.9 | [13 empty] | 0.76 |  |  | 0.76
242242092A | U | Al/Mg Deposit Procurement WC Labor FY15 | 2014-05-02 08:00 | 2014-11-14 16:00 | 60% | 0 | 0 | 919 | [9 empty] | 0.3 |  |  | 0.3 | [13 empty] | 0.12 |  |  | 0.12
242242092B | U | Al/Mg Deposit Procurement WC Procurement | 2014-05-02 08:00 | 2014-11-14 16:00 | 0% | 53241 | 0 | 53241 | [12 empty] | 0 |  |  | 53241 | [13 empty] | 0
242242115 | H | Installation of Elliptical mirrors FY14 | 2014-11-04 08:00 | 2014-12-02 16:00 | 0% | 0 | 0 | 829 | [6 empty] | 0.3 |  |  | 0.1 |  |  | 0.4 | [10 empty] | 0.3 |  |  | 0.1 |  |  | 0.4
242242115A | H | Installation of Elliptical mirrors FY15 | 2014-11-04 08:00 | 2014-12-02 16:00 | 0% | 0 | 0 | 236 | [6 empty] | 0.1 |  |  | 0 |  |  | 0.1 | [10 empty] | 0.1 | [5 empty] | 0.1
242242152 | D | Window Procurement | 2013-11-12 08:00 | 2014-11-10 16:00 | 30% | 2800 | 0 | 2800 | [9 empty] | 0 |  |  | 0 |  |  | 1960 | [13 empty] | 0
242242155 | H | Walls Manufacturing and Installation | 2014-05-02 08:00 | 2014-12-10 16:00 | 50% | 0 | 0 | 2494 | [6 empty] | 1 |  |  | 0.2 |  |  | 1.2 | [10 empty] | 0.5 |  |  | 0.1 |  |  | 0.6
242242163 | D | Divider Modifications Labor FY14 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 1771 | [9 empty] | 0.6 |  |  | 0.6 | [13 empty] | 0.6 |  |  | 0.6
242242163A | D | Divider Modifications Labor FY15 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 655 | [9 empty] | 0.2 |  |  | 0.2 | [13 empty] | 0.2 |  |  | 0.2
242242163B | D | Divider Modifications Procurement | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 3612 | 0 | 3612 | [12 empty] | 0 |  |  | 3612 | [13 empty] | 0
242242164 | U | Divider Modifications Implementation FY14 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 8555 |  |  |  | 3.2 | [5 empty] | 0.9 |  |  | 4.1 | [7 empty] | 3.2 | [5 empty] | 0.9 |  |  | 4.1
242242164A | U | Divider Modifications Implementation FY15 | 2014-03-03 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 2343 |  |  |  | 0.8 | [5 empty] | 0.2 |  |  | 1 | [7 empty] | 0.8 | [5 empty] | 0.2 |  |  | 1
242242190 | H | Install Gas Line (1S) | 2014-12-01 08:00 | 2014-12-16 16:00 | 0% | 0 | 0 | 977 | [6 empty] | 0.5 | [5 empty] | 0.5 | [10 empty] | 0.5 | [5 empty] | 0.5
242242195 | H | Gas Line Quality Control | 2014-12-15 08:00 | 2014-12-19 16:00 | 0% | 0 | 0 | 391 | [6 empty] | 0.2 | [5 empty] | 0.2 | [10 empty] | 0.2 | [5 empty] | 0.2
242242205 | S | Mirrors Laser Alignments FY14 | 2014-09-15 08:00 | 2014-12-16 16:00 | 10% | 0 | 0 | 14167 | [6 empty] | 2.3 |  | 3 | 2 |  | 3 | 10.3 | [10 empty] | 2.07 |  | 2.7 | 1.8 |  | 2.7 | 9.27
242242205A | S | Mirrors Laser Alignments FY15 | 2014-09-15 | 2014-12-16 16:00 | 10% | 0 | 0 | 4584 | [6 empty] | 0.7 |  | 1 | 0.6 |  | 1 | 3.3 | [10 empty] | 0.63 |  | 0.9 | 0.54 |  | 0.9 | 2.97
242242215 | H | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | 2014-10-13 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 621 | [9 empty] | 0.2 |  |  | 0.2 | [13 empty] | 0.1 |  |  | 0.1
242242220a | S | Online Calibration Design FY13 | 2013-10-01 08:00 | 2015-02-10 16:00 | 25% | 0 | 0 | 289 | [9 empty] | 0.1 |  |  | 0.1 | [13 empty] | 0.075 |  |  | 0.075
242242220aa | S | Online Calibration Design FY14 | 2013-10-01 08:00 | 2015-02-10 16:00 | 25% | 0 | 0 | 2709 | [9 empty] | 0.9 |  |  | 0.9 | [13 empty] | 0.675 |  |  | 0.675
242242222 | S | Online HV Matching Design FY13 | 2013-10-01 08:00 | 2015-02-16 16:00 | 25% | 0 | 0 | 318 | [9 empty] | 0.1 |  |  | 0.1 | [13 empty] | 0.075 |  |  | 0.075
242242222a | S | Online HV Matching Design FY14 | 2013-10-01 08:00 | 2015-02-16 16:00 | 25% | 0 | 0 | 2980 | [9 empty] | 1 |  |  | 1 | [13 empty] | 0.75 |  |  | 0.75
242242223 | S | Online HV Matching Test FY14 | 2015-01-27 08:00 | 2015-02-12 12:00 | 0% | 0 | 0 | 2625 | [9 empty] | 0.9 |  |  | 0.9 | [13 empty] | 0.9 |  |  | 0.9
242242223A | S | Online HV Matching Test FY15 | 2015-02-12 12:00 | 2015-03-02 16:00 | 0% | 0 | 0 | 1016 | [9 empty] | 0.3 |  |  | 0.3 | [13 empty] | 0.3 |  |  | 0.3
242242225 | H | Online Calibration Test | 2015-01-28 08:00 | 2015-03-02 16:00 | 0% | 0 | 0 | 1241 | [9 empty] | 0.4 |  |  | 0.4 | [13 empty] | 0.4 |  |  | 0.4
242242230 | H | PMT Installation FY14 | 2014-11-18 08:00 | 2014-11-24 16:00 | 0% | 0 | 0 | 860 | [6 empty] | 0.3 |  |  | 0.1 |  |  | 0.4 | [10 empty] | 0.3 |  |  | 0.1 |  |  | 0.4
242242230A | H | PMT Installation FY15 | 2014-11-25 08:00 | 2014-12-03 16:00 | 0% | 0 | 0 | 204 | [6 empty] | 0.1 |  |  | 0 |  |  | 0.1 | [10 empty] | 0.1 | [5 empty] | 0.1
242242235 | U | Windows Installation 6 sectors FY14 | 2014-11-18 08:00 | 2015-01-15 16:00 | 0% | 0 | 0 | 7110 | [6 empty] | 3.8 | [5 empty] | 3.8 | [10 empty] | 3.8 | [5 empty] | 3.8
242242235A | U | Windows Installation 6 sectors FY15 | 2015-01-16 08:00 | 2015-03-04 16:00 | 0% | 0 | 0 | 2429 | [6 empty] | 1.2 | [5 empty] | 1.2 | [10 empty] | 1.2 | [5 empty] | 1.2
242242240 | S | Gas Leak Check 6 sectors FY14 | 2014-11-03 08:00 | 2014-11-13 16:00 | 0% | 0 | 0 | 7215 | [6 empty] | 1.6 |  |  | 1.4 |  |  | 3 | [10 empty] | 1.6 |  |  | 1.4 |  |  | 3
242242240A | S | Gas Leak Check 6 sectors FY15 | 2014-11-14 08:00 | 2014-11-26 16:00 | 0% | 0 | 0 | 6948 | [6 empty] | 1.4 |  |  | 1.3 |  |  | 2.7 | [10 empty] | 1.4 |  |  | 1.3 |  |  | 2.7
242242280 | H | Frame Support FY13 | 2014-11-04 08:00 | 2015-01-08 16:00 | 0% | 0 | 0 | 120 | [6 empty] | 0.1 | [5 empty] | 0.1 | [10 empty] | 0.1 | [5 empty] | 0.1
242242280a | H | Frame Support FY14 | 2014-11-04 08:00 | 2015-01-08 16:00 | 0% | 0 | 0 | 633 | [6 empty] | 0.3 | [5 empty] | 0.3 | [10 empty] | 0.3 | [5 empty] | 0.3
242242305 | H | Rear Brace Installation | 2014-08-11 08:00 | 2014-12-05 16:00 | 50% | 0 | 0 | 1514 | [6 empty] | 0.8 | [5 empty] | 0.8 | [10 empty] | 0.4 | [5 empty] | 0.4
242242315 | H | Patch Panel Installation FY14 | 2014-09-08 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 598 | [6 empty] | 0.2 |  |  | 0.1 |  |  | 0.3 | [10 empty] | 0.1 |  |  | 0.05 |  |  | 0.15
242242315A | H | Patch Panel Installation FY15 | 2014-09-08 08:00 | 2014-12-15 16:00 | 50% | 0 | 0 | 84 | [6 empty] | 0 |  |  | 0 |  |  | 0 | [16 empty] | 0
242242325 | H | Spine Refurbish FY13 | 2013-12-02 08:00 | 2015-03-16 16:00 | 50% | 0 | 0 | 65 | [6 empty] | 0 | [5 empty] | 0 | [16 empty] | 0
242242325a | H | Spine Refurbish FY14 | 2013-12-02 08:00 | 2015-03-16 16:00 | 50% | 0 | 0 | 832 | [6 empty] | 0.4 | [5 empty] | 0.4 | [10 empty] | 0.2 | [5 empty] | 0.2
242242325B | H | Spine Refusrbish FY15 | 2013-12-02 08:00 | 2015-03-16 16:00 | 50% | 0 | 0 | 49 | [6 empty] | 0 | [5 empty] | 0 | [16 empty] | 0
242242330 | H | Gas Line Refurbish FY14 | 2014-08-02 08:00 | 2014-12-01 16:00 | 50% | 0 | 0 | 1141 | [6 empty] | 0.5 |  |  | 0.1 |  |  | 0.6 | [10 empty] | 0.25 |  |  | 0.05 |  |  | 0.3
242242330A | H | Gas Line Refurbish FY15 | 2014-08-02 08:00 | 2014-12-01 16:00 | 50% | 0 | 0 | 109 | [6 empty] | 0 |  |  | 0 |  |  | 0 | [16 empty] | 0
242242340 | S | Sector 2 Box Refurbish | 2013-12-02 08:00 | 2014-12-15 16:00 | 80% | 0 | 0 | 15142 | [6 empty] | 8 | [5 empty] | 8 | [10 empty] | 1.6 | [5 empty] | 1.6
242242350 | H | Sector 2 Mirrors Alignment | 2014-11-14 08:00 | 2014-12-01 16:00 | 0% | 0 | 0 | 3786 | [6 empty] | 2 | [5 empty] | 2 | [10 empty] | 2 | [5 empty] | 2
242242355 | H | Sector 2 Windows Installation | 2014-12-05 08:00 | 2014-12-12 16:00 | 0% | 0 | 0 | 1893 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242360 | H | Sector 2 Gas Leaks Checks | 2014-12-12 08:00 | 2014-12-15 16:00 | 0% | 0 | 0 | 2271 | [6 empty] | 1.2 | [5 empty] | 1.2 | [10 empty] | 1.2 | [5 empty] | 1.2
242242365 | S | Sector 3 Box Refurbish | 2013-12-02 08:00 | 2015-01-15 16:00 | 80% | 0 | 0 | 13628 | [6 empty] | 7.2 | [5 empty] | 7.2 | [10 empty] | 1.44 | [5 empty] | 1.44
242242375 | H | Sector 3 Mirrors Alignment | 2015-01-08 08:00 | 2015-01-29 16:00 | 0% | 0 | 0 | 3786 | [6 empty] | 2 | [5 empty] | 2 | [10 empty] | 2 | [5 empty] | 2
242242380 | H | Sector 3 Windows Installation | 2015-01-13 08:00 | 2015-02-12 16:00 | 0% | 0 | 0 | 1893 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242385 | H | Sector 3 Gas Leaks Checks | 2015-01-29 08:00 | 2015-02-26 16:00 | 0% | 0 | 0 | 1950 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242390 | S | Sector 4 Box Refurbish | 2013-12-02 08:00 | 2015-02-20 16:00 | 60% | 0 | 0 | 13628 | [6 empty] | 7.2 | [5 empty] | 7.2 | [10 empty] | 2.88 | [5 empty] | 2.88
242242400 | H | Sector 4 Mirrors Alignment FY14 | 2015-02-16 08:00 | 2015-03-02 12:00 | 0% | 0 | 0 | 874 | [6 empty] | 0.5 | [5 empty] | 0.5 | [10 empty] | 0.5 | [5 empty] | 0.5
242242400A | H | Sector 4 Mirrors Alignment FY15 | 2015-03-02 12:00 | 2015-03-16 16:00 | 0% | 0 | 0 | 3005 | [6 empty] | 1.5 | [5 empty] | 1.5 | [10 empty] | 1.5 | [5 empty] | 1.5
242242405 | H | Sector 4 Windows Installation | 2015-02-20 08:00 | 2015-03-20 16:00 | 0% | 0 | 0 | 1953 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242410 | H | Sector 4 Gas Leaks Checks | 2015-02-27 08:00 | 2015-03-27 16:00 | 0% | 0 | 0 | 1953 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242415 | S | Sector 5 Box Refurbish | 2013-12-02 08:00 | 2015-03-20 16:00 | 60% | 0 | 0 | 12114 | [6 empty] | 6.4 | [5 empty] | 6.4 | [10 empty] | 2.56 | [5 empty] | 2.56
242242425 | H | Sector 5 Mirrors Alignment | 2015-03-16 08:00 | 2015-04-15 16:00 | 0% | 0 | 0 | 3906 | [6 empty] | 2 | [5 empty] | 2 | [10 empty] | 2 | [5 empty] | 2
242242430 | H | Sector 5 Windows Installation | 2015-03-20 08:00 | 2015-04-20 16:00 | 0% | 0 | 0 | 1953 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242435 | H | Sector 5 Gas Leaks Checks | 2015-03-30 08:00 | 2015-04-28 16:00 | 0% | 0 | 0 | 1953 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242440 | S | Sector 6 Box Refurbish | 2013-12-02 08:00 | 2015-04-01 16:00 | 60% | 0 | 0 | 12114 | [6 empty] | 6.4 | [5 empty] | 6.4 | [10 empty] | 2.56 | [5 empty] | 2.56
242242450 | H | Sector 6 Mirrors Alignment | 2015-04-15 08:00 | 2015-05-15 16:00 | 0% | 0 | 0 | 3906 | [6 empty] | 2 | [5 empty] | 2 | [10 empty] | 2 | [5 empty] | 2
242242455 | H | Sector 6 Windows Installation | 2015-04-20 08:00 | 2015-05-20 16:00 | 0% | 0 | 0 | 1953 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
242242460 | H | Sector 6 Gas Leaks Checks | 2015-04-29 08:00 | 2015-05-28 16:00 | 0% | 0 | 0 | 1953 | [6 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [5 empty] | 1
le | [25 empty] | 0 | 0 | 0 | 4 | 0 | 0 | 46.29 | 0 | 3.6 | 11.495 | 0 | 3.6 | 68.985
Formulas:
Start = VLOOKUP([Sum of Budgeted Units],'P6 Additional Raw Data'!$A:$I,4,FALSE)
Finish = VLOOKUP([Sum of Budgeted Units],'P6 Additional Raw Data'!$A:$I,5,FALSE)