## Activity List
|  | Code Value | Description
|  | C | % Effort (Civil Construction)
|  | D | % Delivered (Delivery of Contracted Items %)
|  | E | LOE (equation)
|  | H | 0/50/100% (</=$10K and </= 2Months) or <$2K with any duration
|  | P | 0-100% (Pre-Contract Peg Points, 0% until Contract CR is implemented
|  | S | Special (CAM written and PM approved plan for act bar phases)
|  | U | % Units Complete (In-house Fab, recving, install, test, or checkout of Mult units)
Activity ID | RESP - Responsibility | EVMS Reporting Codes | Activity Name | Start | Finish | BL Project Finish | Original Duration | Physical % Complete | Total Float | Earned Value Cost | Budgeted Total Cost | Calculated Remaining Total Cost | Value | Cost Budgeted | Total | Cost Calculated | Remaining | Total | Cost
1.4.2.2.4.2 LOW THRESHOLD CC |  |  |  | 2013-03-01 08:00 | 2014-12-17 16:00 | 2014-12-17 16:00 | 86 |  | 94.2 | 49727 | 568293 | 518566
242242030 | ELOUADRHIRI L | H | Quality Control of PMTs | 2013-06-01 08:00 | 2013-11-25 16:00 | 2013-09-10 16:00 | 20.8 | 10% | 95.2 | 0 | 0
242242031 | ELOUADRHIRI L | H | Quality Control of Existing PMTs | 2013-07-01 08:00 | 2013-08-12 16:00 | 2013-05-01 16:00 | 1.6 | 0% | 62.8 | 0 | 4066 | 4066
242242040 | ELOUADRHIRI L | D | Wavelength Shifting Procurement | 2013-06-01 08:00 | 2014-08-22 16:00 | 2014-07-01 16:00 | 52.6 | 10% | 59 | 7500 | 75000 | 67500
242242045 | ELOUADRHIRI L | D | Procurement Lasers | 2013-03-03 08:00 | 2013-08-29 16:00 | 2013-05-30 16:00 | 8.2 | 80% | 56.8 | 7304 | 9130 | 1826
242242050 | ELOUADRHIRI L | H | Alignment Tool Manufacturing | 2013-08-01 08:00 | 2013-08-30 16:00 | 2013-05-20 16:00 | 4.4 | 0% | 55.8 | 0 | 6334 | 6334
242242055 | ELOUADRHIRI L | H | Alignment Tool and Lasers Installation | 2013-09-03 08:00 | 2013-10-01 16:00 | 2013-06-24 16:00 | 4.2 | 0% | 55.8 | 0 | 2417 | 2417
242242060 | ELOUADRHIRI L | H | Mirrors Survey | 2013-04-01 08:00 | 2013-08-22 16:00 | 2013-06-24 16:00 | 3.2 | 75% | 61.2 | 219 | 291 | 73
242242076 | ELOUADRHIRI L | H | Support Frame Fabrication for 1S in TED | 2013-08-01 08:00 | 2013-09-03 16:00 | 2013-05-22 16:00 | 4.6 | 0% | 107 | 0 | 2834 | 2834
242242077 | ELOUADRHIRI L | D | Infrastructure Consumables | 2013-03-01 08:00 | 2014-05-01 16:00 | 2014-05-01 16:00 | 58.2 | 10% | 74.8 | 1800 | 18000 | 16200
242242085 | ELOUADRHIRI L | H | Quality Control of Elliptical/Hyperbolic mirrors | 2013-10-08 08:00 | 2014-08-07 16:00 | 2014-06-09 16:00 | 41 | 0% | 83.2 | 0 | 9881 | 9881
242242090 | ELOUADRHIRI L | S | Dimensions check of Elliptical/Hyperbolic mirrors | 2013-06-03 08:00 | 2014-05-09 16:00 | 2014-06-09 16:00 | 42.4 | 30% | 73.6 | 4014 | 13379 | 9365
242242092 | ELOUADRHIRI L | U | Al/Mg Deposit Procurement WC | 2013-10-24 08:00 | 2014-11-17 16:00 | 2014-05-13 16:00 | 52.8 | 0% | 47 | 0 | 58007 | 58007
242242095 | ELOUADRHIRI L | H | Create Manufacturing Drawings | 2013-03-01 08:00 | 2013-08-13 16:00 | 2013-04-05 16:00 | 5.2 | 80% | 57.6 | 699 | 874 | 175
242242105 | ELOUADRHIRI L | H | Al/Mg Deposit Procurement Prep | 2013-03-01 08:00 | 2013-08-08 16:00 | 2013-06-03 16:00 | 10.8 | 50% | 98.6 | 729 | 1457 | 729
242242107 | ELOUADRHIRI L | H | Al/Mg Lexon/Acrylic Re-Coating Test Procurement | 2013-08-01 08:00 | 2013-12-06 16:00 | 2013-07-05 16:00 | 17.8 | 0% | 47 | 0 | 1749 | 1749
242242108 | ELOUADRHIRI L | U | Lexan/Acrylic/Over- Coating Procurement (all sectors) | 2013-12-10 08:00 | 2014-10-14 16:00 | 2014-05-13 16:00 | 41.8 | 0% | 51.8 | 0 | 5206 | 5206
242242110 | ELOUADRHIRI L | D | Al/Mg Deposit Procurement | 2013-10-07 08:00 | 2014-11-13 16:00 | 2014-05-30 16:00 | 55 | 0% | 98.6 | 0 | 51595 | 51595
242242115 | ELOUADRHIRI L | H | Installation of Elliptical mirrors | 2013-10-25 08:00 | 2013-10-31 16:00 | 2013-05-16 16:00 | 1 | 0% | 98.6 | 0 | 1025 | 1025
242242137 | ELOUADRHIRI L | D | Glue Procurement | 2013-08-01 08:00 | 2013-09-27 16:00 | 2013-04-26 16:00 | 8.2 | 0% | 103.4 | 0 | 2307 | 2307
242242140 | ELOUADRHIRI L | H | Box Walls Simulation | 2013-05-03 08:00 | 2013-08-14 16:00 | 2013-05-03 16:00 | 9.2 | 50% | 111.8 | 583 | 1166 | 583
242242145a | ELOUADRHIRI L | H | Complete Design Box Walls | 2013-03-01 08:00 | 2013-08-12 16:00 | 2013-05-10 16:00 | 10.2 | 75% | 104.6 | 874 | 1166 | 291
242242152 | ELOUADRHIRI L | D | Window Procurement | 2013-08-01 08:00 | 2014-03-31 16:00 | 2013-11-21 16:00 | 32.2 | 0% | 53.2 | 0 | 5132 | 5132
242242155 | ELOUADRHIRI L | H | Walls Manufacturing and Installation | 2013-08-15 08:00 | 2013-09-19 16:00 | 2013-06-19 16:00 | 5 | 0% | 104.6 | 0 | 2417 | 2417
242242161 | ELOUADRHIRI L | H | HV Cables Catalog and Tagging | 2013-08-01 08:00 | 2013-08-22 16:00 | 2013-03-26 16:00 | 3.2 | 0% | 83 | 0 | 734 | 734
242242162 | ELOUADRHIRI L | H | Divider Modifications Design and Test | 2013-05-03 08:00 | 2013-08-14 16:00 | 2013-04-15 16:00 | 5 | 50% | 66.2 | 1583 | 3166 | 1583
242242163 | ELOUADRHIRI L | D | Divider Modifications Procurement | 2013-08-15 08:00 | 2014-04-10 16:00 | 2013-11-27 16:00 | 31.8 | 0% | 66.2 | 0 | 5832 | 5832
242242164 | ELOUADRHIRI L | U | Divider Modifications Implementation | 2013-09-12 08:00 | 2014-07-02 16:00 | 2014-03-04 16:00 | 39.6 | 0% | 66.2 | 0 | 10492 | 10492
242242165b | ELOUADRHIRI L | D | Procure Cables Procurement | 2013-08-01 08:00 | 2014-04-10 16:00 | 2013-11-27 16:00 | 33.8 | 0% | 77.8 | 0 | 23492 | 23492
242242169 | ELOUADRHIRI L | H | New Patch Panel Fabrication | 2013-08-01 08:00 | 2014-03-07 16:00 | 2013-12-20 16:00 | 29 | 0% | 82.6 | 0 | 2935 | 2935
242242170 | ELOUADRHIRI L | D | Patch Panel Connectors Procurement | 2013-03-01 08:00 | 2013-11-22 16:00 | 2013-11-22 16:00 | 37.6 | 30% | 95.4 | 6084 | 20278 | 14195
242242185 | ELOUADRHIRI L | D | Procure Gas Line | 2014-10-01 08:00 | 2014-11-14 16:00 | 2014-11-14 16:00 | 6.6 | 0% | 43 | 0 | 18583 | 18583
242242190 | ELOUADRHIRI L | H | Install Gas Line (1S) | 2014-11-25 08:00 | 2014-12-10 16:00 | 2014-12-10 16:00 | 2 | 0% | 43 | 0 | 917 | 917
242242195 | ELOUADRHIRI L | H | Gas Line Quality Control | 2014-12-11 08:00 | 2014-12-17 16:00 | 2014-12-17 16:00 | 1 | 0% | 43 | 0 | 367 | 367
242242205 | ELOUADRHIRI L | S | Mirrors Laser Alignments | 2013-10-03 08:00 | 2014-09-16 16:00 | 2014-06-09 16:00 | 47 | 0% | 55.8 | 0 | 18034 | 18034
242242215 | ELOUADRHIRI L | H | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | 2013-04-01 08:00 | 2013-08-29 16:00 | 2013-04-09 16:00 | 4.2 | 50% | 107.4 | 583 | 1166 | 583
242242220a | ELOUADRHIRI L | H | Online Calibration Design | 2013-08-01 08:00 | 2013-12-18 16:00 | 2013-11-08 16:00 | 19.4 | 0% | 64 | 0 | 2914 | 2914
242242222 | ELOUADRHIRI L | H | Online HV Matching Design | 2013-08-01 08:00 | 2013-12-18 16:00 | 2013-11-08 16:00 | 19.4 | 0% | 64 | 0 | 3206 | 3206
242242223 | ELOUADRHIRI L | H | Online HV Matching Test | 2013-11-26 08:00 | 2014-04-09 16:00 | 2014-03-04 16:00 | 17.2 | 0% | 64 | 0 | 3497 | 3497
242242225 | ELOUADRHIRI L | H | Online Calibration Test | 2014-04-10 08:00 | 2014-07-18 16:00 | 2014-06-11 16:00 | 14 | 0% | 64 | 0 | 1166 | 1166
242242230 | ELOUADRHIRI L | H | PMT Installation | 2013-09-19 08:00 | 2013-09-25 16:00 | 2013-05-17 16:00 | 1 | 0% | 57.6 | 0 | 1025 | 1025
242242235 | ELOUADRHIRI L | H | Windows Installation 6 sectors | 2013-09-27 08:00 | 2014-10-03 16:00 | 2014-06-23 16:00 | 50.4 | 0% | 53.2 | 0 | 9172 | 9172
242242240 | ELOUADRHIRI L | S | Gas Leak Check 6 sectors | 2013-08-01 08:00 | 2014-10-03 16:00 | 2014-06-23 16:00 | 58.4 | 0% | 53.2 | 0 | 13518 | 13518
242242245 | ELOUADRHIRI L | H | Simulation of Sagging Test | 2013-05-03 08:00 | 2013-10-03 16:00 | 2013-07-02 16:00 | 17.4 | 0% | 102.6 | 0 | 1749 | 1749
242242255 | ELOUADRHIRI L | D | Procurement Sagging Test Tools | 2013-08-01 08:00 | 2013-09-19 16:00 | 2013-05-24 16:00 | 7 | 0% | 99.4 | 0 | 583 | 583
242242260 | ELOUADRHIRI L | H | Manufacture Sagging Test Tools | 2013-08-01 08:00 | 2013-09-19 16:00 | 2013-05-24 16:00 | 7 | 0% | 99.4 | 0 | 1834 | 1834
242242265 | ELOUADRHIRI L | H | Transport Counterweght to TED | 2013-08-29 08:00 | 2013-09-25 16:00 | 2013-05-31 16:00 | 3.8 | 0% | 99.4 | 0 | 367 | 367
242242270 | ELOUADRHIRI L | H | Sagging Test | 2013-10-03 08:00 | 2013-10-25 16:00 | 2013-07-02 16:00 | 3.4 | 0% | 99.4 | 0 | 3442 | 3442
242242275 | ELOUADRHIRI L | H | Move Sector in Clean Room | 2013-04-01 08:00 | 2014-06-03 16:00 | 2014-06-03 16:00 | 62.6 | 80% | 70.4 | 1468 | 1834 | 367
242242280 | ELOUADRHIRI L | H | Frame Support | 2013-08-01 08:00 | 2013-08-07 16:00 | 2013-04-19 16:00 | 1 | 0% | 113 | 0 | 734 | 734
242242290 | ELOUADRHIRI L | H | Cut Line Mark | 2013-07-15 08:00 | 2013-08-05 16:00 | 2013-05-01 16:00 | 0.6 | 20% | 110 | 147 | 734 | 587
242242295 | ELOUADRHIRI L | H | Wall Cut-Off | 2013-08-05 08:00 | 2013-08-12 16:00 | 2013-05-08 16:00 | 1.2 | 0% | 110 | 0 | 734 | 734
242242300 | ELOUADRHIRI L | H | Rear Brace Manufacture | 2013-08-23 08:00 | 2013-08-27 16:00 | 2013-04-19 16:00 | 0.6 | 0% | 57.6 | 0 | 1234 | 1234
242242305 | ELOUADRHIRI L | H | Rear Brace Installation | 2013-08-27 08:00 | 2013-09-11 16:00 | 2013-05-03 16:00 | 2.2 | 0% | 57.6 | 0 | 1468 | 1468
242242310 | ELOUADRHIRI L | H | PMTS, Mirrors Holes Drill | 2013-09-12 08:00 | 2013-09-18 16:00 | 2013-05-10 16:00 | 1 | 0% | 57.6 | 0 | 734 | 734
242242315 | ELOUADRHIRI L | H | Patch Panel Installation | 2013-09-26 08:00 | 2013-10-07 16:00 | 2013-05-30 16:00 | 1.6 | 0% | 108 | 0 | 658 | 658
242242320 | ELOUADRHIRI L | H | Nose Extension Installation | 2013-09-26 08:00 | 2013-10-07 16:00 | 2013-05-30 16:00 | 1.6 | 0% | 108 | 0 | 367 | 367
242242325 | ELOUADRHIRI L | H | Spine Refurbish | 2013-05-06 08:00 | 2013-08-15 16:00 | 2013-06-07 16:00 | 1 | 0% | 107.4 | 0 | 917 | 917
242242330 | ELOUADRHIRI L | H | Gas Line Refurbish | 2013-08-16 08:00 | 2013-08-29 16:00 | 2013-06-21 16:00 | 2 | 0% | 107.4 | 0 | 1209 | 1209
242242335 | ELOUADRHIRI L | D | Box Refurbish Consumables | 2013-07-01 08:00 | 2014-03-12 16:00 | 2014-03-12 16:00 | 51 | 0% | 82 | 0 | 18000 | 18000
242242340 | ELOUADRHIRI L | S | Sector 2 Box Refurbish | 2013-04-01 08:00 | 2013-09-12 16:00 | 2013-09-12 16:00 | 10.4 | 20% | 94.4 | 3669 | 18344 | 14675
242242350 | ELOUADRHIRI L | H | Sector 2 Mirrors Alignment | 2013-09-12 08:00 | 2013-09-18 16:00 | 2013-09-18 16:00 | 1 | 0% | 94.4 | 0 | 3669 | 3669
242242355 | ELOUADRHIRI L | H | Sector 2 Windows Installation | 2013-09-19 08:00 | 2013-09-23 16:00 | 2013-09-23 16:00 | 0.6 | 0% | 94.4 | 0 | 1834 | 1834
242242360 | ELOUADRHIRI L | H | Sector 2 Gas Leaks Checks | 2013-09-24 08:00 | 2013-10-02 16:00 | 2013-10-02 16:00 | 1.4 | 0% | 94.4 | 0 | 2201 | 2201
242242365 | ELOUADRHIRI L | S | Sector 3 Box Refurbish | 2013-06-03 08:00 | 2013-11-20 16:00 | 2013-11-20 16:00 | 7 | 20% | 87.2 | 3302 | 16510 | 13208
242242375 | ELOUADRHIRI L | H | Sector 3 Mirrors Alignment | 2013-11-20 08:00 | 2013-11-26 16:00 | 2013-11-26 16:00 | 1 | 0% | 87.2 | 0 | 3669 | 3669
242242380 | ELOUADRHIRI L | H | Sector 3 Windows Installation | 2013-11-27 08:00 | 2013-12-05 16:00 | 2013-12-05 16:00 | 1 | 0% | 87.2 | 0 | 1834 | 1834
242242385 | ELOUADRHIRI L | H | Sector 3 Gas Leaks Checks | 2013-12-06 08:00 | 2013-12-12 16:00 | 2013-12-12 16:00 | 1 | 0% | 87.2 | 0 | 1834 | 1834
242242390 | ELOUADRHIRI L | S | Sector 4 Box Refurbish | 2013-06-03 08:00 | 2014-01-28 16:00 | 2014-01-28 16:00 | 6.6 | 20% | 81.8 | 3302 | 16510 | 13208
242242400 | ELOUADRHIRI L | H | Sector 4 Mirrors Alignment | 2014-01-29 08:00 | 2014-02-03 16:00 | 2014-02-03 16:00 | 0.8 | 0% | 81.8 | 0 | 3669 | 3669
242242405 | ELOUADRHIRI L | H | Sector 4 Windows Installation | 2014-02-04 08:00 | 2014-02-10 16:00 | 2014-02-10 16:00 | 1 | 0% | 81.8 | 0 | 1834 | 1834
242242410 | ELOUADRHIRI L | H | Sector 4 Gas Leaks Checks | 2014-02-11 08:00 | 2014-02-17 16:00 | 2014-02-17 16:00 | 1 | 0% | 81.8 | 0 | 1834 | 1834
242242415 | ELOUADRHIRI L | S | Sector 5 Box Refurbish | 2013-06-03 08:00 | 2014-03-24 16:00 | 2014-03-24 16:00 | 5 | 20% | 76 | 2935 | 14675 | 11740
242242425 | ELOUADRHIRI L | H | Sector 5 Mirrors Alignment | 2014-03-25 08:00 | 2014-03-31 16:00 | 2014-03-31 16:00 | 1 | 0% | 76 | 0 | 3669 | 3669
242242430 | ELOUADRHIRI L | H | Sector 5 Windows Installation | 2014-04-01 08:00 | 2014-04-07 16:00 | 2014-04-07 16:00 | 1 | 0% | 76 | 0 | 1834 | 1834
242242435 | ELOUADRHIRI L | H | Sector 5 Gas Leaks Checks | 2014-04-08 08:00 | 2014-04-14 16:00 | 2014-04-14 16:00 | 1 | 0% | 76 | 0 | 1834 | 1834
242242440 | ELOUADRHIRI L | S | Sector 6 Box Refurbish | 2013-06-03 08:00 | 2014-05-16 16:00 | 2014-05-16 16:00 | 4.8 | 20% | 70.2 | 2935 | 14675 | 11740
242242450 | ELOUADRHIRI L | H | Sector 6 Mirrors Alignment | 2014-05-15 08:00 | 2014-05-21 16:00 | 2014-05-21 16:00 | 1 | 0% | 70.2 | 0 | 3669 | 3669
242242455 | ELOUADRHIRI L | H | Sector 6 Windows Installation | 2014-05-22 08:00 | 2014-05-29 16:00 | 2014-05-29 16:00 | 1 | 0% | 70.2 | 0 | 1834 | 1834
242242460 | ELOUADRHIRI L | H | Sector 6 Gas Leaks Checks | 2014-05-29 08:00 | 2014-06-04 16:00 | 2014-06-04 16:00 | 1 | 0% | 70.2 | 0 | 1834 | 1834

## Steps
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242055 | Alignment Tool and Lasers Installation |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Toll assembly | 0 | 0.4 | 0
Laser table assembly | 0 | 0.15 | 0
Laser system assembly | 0 | 0.15 | 0
Sector mount on tool | 0 | 0.3 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242090 | Dimensions check of Elliptical/Hyperbolic mirrors |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Print 1:1 Drawings | 100 | 0.2 | 20
Remove Mirrors | 100 | 0.2 | 20
Align Mirror to Drawing | 0 | 0.6 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242205 | Mirrors Laser Alignments |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Laser Setup | 0 | 0.1 | 0
Laser/Box Survey | 0 | 0.3 | 0
Elliptical Alignment | 0 | 0.3 | 0
Hyperbolic Alignment | 0 | 0.3 | #REF!
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242220a | Online Calibration Design |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0 | 0.25 | 0
DAQ setup | 0 | 0.25 | 0
Software to control HV | 0 | 0.25 | 0
SPE Histos Software | 0 | 0.25 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242222 | Online HV Matching Design |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0 | 0.25 | 0
DAQ setup | 0 | 0.25 | 0
Software to control HV | 0 | 0.25 | 0
SPE Histos Software | 0 | 0.25 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242223 | Online HV Matching Test |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
1 Full sector HC connection | 0 | 0.5 | 0
DAQ setup | 0 | 0.5 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242240 | Gas Leak Check 6 sectors |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Nitrogen Fill 1/2" | 0 | 0.2 | 0
Freon Fill | 0 | 0.2 | 0
Snoop | 0 | 0.6 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242085 | Quality Control of Elliptical/Hyperbolic mirrors |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Visual Inspection of Mirrors | 0 | 0.3 | 0
Sample Mirrors Reflectivity Tests | 0 | 0.7
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242270 | Sagging Test |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Laser Mount on Box | 0 | 0.4 | 0
Reference Mount on Box | 0 | 0.2
Box rotation and reference check | 0 | 0.4
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242340 | Sector 2 Box Refurbish |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 0 | 0.05 | 0
Cut Line Mark | 0 | 0.05 | 0
Box Cut | 0 | 0.1 | 0
Wall Cut | 0 | 0.1 | 0
Box Plates Fit | 0 | 0.1 | 0
Patch Panel Fit | 0 | 0.1 | 0
Rear Brace | 0 | 0.1 | 0
Nose Installation | 0 | 0.15 | 0
PMT, Mirrors Holes | 0 | 0.05 | 0
Spine Refurbish | 0 | 0.1 | 0
Mount PMT, Mirrors, WC | 0 | 0.1 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242365 | Sector 2 Box Refurbish |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 0 | 0.05 | 0
Cut Line Mark | 0 | 0.05 | 0
Box Cut | 0 | 0.1 | 0
Wall Cut | 0 | 0.1 | 0
Box Plates Fit | 0 | 0.1 | 0
Patch Panel Fit | 0 | 0.1 | 0
Rear Brace | 0 | 0.1 | 0
Nose Installation | 0 | 0.15 | 0
PMT, Mirrors Holes | 0 | 0.05 | 0
Spine Refurbish | 0 | 0.1 | 0
Mount PMT, Mirrors, WC | 0 | 0.1 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242390 | Sector 2 Box Refurbish |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 0 | 0.05 | 0
Cut Line Mark | 0 | 0.05 | 0
Box Cut | 0 | 0.1 | 0
Wall Cut | 0 | 0.1 | 0
Box Plates Fit | 0 | 0.1 | 0
Patch Panel Fit | 0 | 0.1 | 0
Rear Brace | 0 | 0.1 | 0
Nose Installation | 0 | 0.15 | 0
PMT, Mirrors Holes | 0 | 0.05 | 0
Spine Refurbish | 0 | 0.1 | 0
Mount PMT, Mirrors, WC | 0 | 0.1 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242415 | Sector 2 Box Refurbish |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 0 | 0.05 | 0
Cut Line Mark | 0 | 0.05 | 0
Box Cut | 0 | 0.1 | 0
Wall Cut | 0 | 0.1 | 0
Box Plates Fit | 0 | 0.1 | 0
Patch Panel Fit | 0 | 0.1 | 0
Rear Brace | 0 | 0.1 | 0
Nose Installation | 0 | 0.15 | 0
PMT, Mirrors Holes | 0 | 0.05 | 0
Spine Refurbish | 0 | 0.1 | 0
Mount PMT, Mirrors, WC | 0 | 0.1 | 0
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242440 | Sector 2 Box Refurbish |  | MERZ B
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 0 | 0.05 | 0
Cut Line Mark | 0 | 0.05 | 0
Box Cut | 0 | 0.1 | 0
Wall Cut | 0 | 0.1 | 0
Box Plates Fit | 0 | 0.1 | 0
Patch Panel Fit | 0 | 0.1 | 0
Rear Brace | 0 | 0.1 | 0
Nose Installation | 0 | 0.15 | 0
PMT, Mirrors Holes | 0 | 0.05 | 0
Spine Refurbish | 0 | 0.1 | 0
Mount PMT, Mirrors, WC | 0 | 0.1 | 0