## SVT ETC Costs
CLAS12 LTCC ETC Procurement Costs
Activity ID | Activity Name | P6 total | Costpoint | Remaining CP | Reamining P6 | BOE | PRs | POs | Comments
242242040 | Wavelength Shifting Procurement | 61914 | 0 | 66000 |  | OB | 340671 |  | Contract Awarded, Waiting on Temple Signature for PO
242242110 | Al/Mg Deposit Procurement | 53240 | 0 | 53100 |  | OB
242242092 | Al/Mg Deposit Procurement WC | 53240.88 | 0 |  |  | Not OB | 338701 | 14-P0521-0
242242152 | Window Procurement | 2800 | 0 |  | 2800 | Not OB |  |  | Combined with HTCC P6, acquired 30% of the material (MYLAR)
242242163 | Divider Modifications Procurement | 2405.76 | 0 |  | 2405.76 | Not OB
242242165b | Procure Cables | 21835 | 15994.5 | 15000 |  | OB | 342616P, 342424, 342423 | 12A2609004-206, 14-M0645-0 | Signal Cables + Lemo connectors Still need to be ordered
242242170 | Patch Panel Connectors Procurement | 12542.54 | 15485.94 | 0 |  | OB | 342008, 339757 | 14-P0635-0, 14-P0348-0