## Sheet1
Activity ID | Obligated Prior to Rebaseline | Post Rebaseline | Activities with Steps | EVMS Reporting Codes | Activity Name | Start | Finish | Original Duration | Budgeted Labor Cost | Budgeted Labor Units | Budgeted Material Cost | Budgeted Total Cost | Budgeted Nonlabor Cost
1.4.2.2.4.2 LOW THRESHOLD CC | [5 empty] | 2013-09-03 08:00 | 2015-02-10 16:00 | 70.8 | 243898.57 | 143.07 | 222455.84 | 513570.41 | 47216
242242110 |  | PR |  | D | Al/Mg Deposit Procurement | 2013-11-11 08:00 | 2014-11-26 16:00 | 51.8 | 0 | 0 | 51595 | 51595 | 0
242242105 |  | PR |  | H | Al/Mg Deposit Procurement Prep | 2013-09-03 08:00 | 2013-10-08 16:00 | 5.2 | 582.88 | 0.2 | 0 | 582.88 | 0
242242092 |  | PR |  | U | Al/Mg Deposit Procurement WC | 2013-11-19 08:00 | 2014-11-14 16:00 | 49 | 6411.68 | 2.2 | 51595 | 58006.68 | 0
242242107 |  | PR |  | H | Al/Mg Laxon/Acrylic Re-Coating Test Procurement | 2013-09-10 08:00 | 2013-11-11 16:00 | 9 | 1748.64 | 0.6 | 0 | 1748.64 | 0
242242055 |  | PR | ST | S | Alignment Tool and Lasers Installation | 2013-11-01 08:00 | 2014-03-18 16:00 | 17.4 | 2417.28 | 1.2 | 0 | 2417.28 | 0
242242050 |  | PR |  | D | Alignment Tool Manufacturing | 2013-09-20 08:00 | 2013-12-13 16:00 | 11.8 | 1834.4 | 1 | 0 | 6334.4 | 4500
242242335 |  | PR |  | D | Box Refurbish Consumables | 2013-09-03 08:00 | 2014-10-20 16:00 | 56.2 | 0 | 0 | 0 | 18000 | 18000
242242145a |  | PR |  | H | Complete Design Box Walls | 2013-09-03 08:00 | 2013-10-22 16:00 | 7.2 | 291.44 | 0.1 | 0 | 291.44 | 0
242242095 |  | PR |  | H | Create Manufacturing Drawings | 2013-09-03 08:00 | 2013-10-10 16:00 | 5.6 | 174.86 | 0.06 | 0 | 174.86 | 0
242242290 |  | PR |  | H | Cut Line Mark | 2013-09-03 08:00 | 2013-09-30 16:00 | 4 | 587.01 | 0.32 | 0 | 587.01 | 0
242242090 |  | PR |  | U | Dimensions check of Elliptical/Hyperbolic mirrors | 2013-09-03 08:00 | 2014-06-09 16:00 | 37.6 | 9364.99 | 7.28 | 0 | 9364.99 | 0
242242162 |  | PR |  | H | Divider Modifications Design and Test | 2013-09-03 08:00 | 2014-02-11 16:00 | 21 | 582.88 | 0.2 | 0 | 1582.88 | 1000
242242164 |  | PR |  | U | Divider Modifications Implementation | 2014-02-12 08:00 | 2014-12-02 16:00 | 41 | 10492.24 | 5.1 | 0 | 10492.24 | 0
242242163 |  | PR |  | D | Divider Modifications Procurement | 2014-02-12 08:00 | 2014-12-23 16:00 | 44 | 2331.52 | 0.8 | 3500 | 5831.52 | 0
242242280 |  | PR |  | H | Frame Support | 2013-09-18 08:00 | 2013-12-05 16:00 | 11 | 733.76 | 0.4 | 0 | 733.76 | 0
242242240 |  | PR | ST | S | Gas Leak Check 6 sectors | 2014-05-23 08:00 | 2015-02-10 16:00 | 34.8 | 13517.8 | 5.75 | 0 | 13517.8 | 0
242242195 |  | PR |  | H | Gas Line Quality Control | 2014-12-11 08:00 | 2014-12-17 16:00 | 1 | 366.88 | 0.2 | 0 | 366.88 | 0
242242330 |  | PR |  | H | Gas Line Refurbish | 2014-02-27 08:00 | 2014-10-20 16:00 | 33 | 1208.64 | 0.6 | 0 | 1208.64 | 0
242242137 |  | PR |  | D | Glue Procurement | 2013-09-03 08:00 | 2013-10-29 16:00 | 8.2 | 291.44 | 0.1 | 0 | 2307.44 | 2016
242242161 |  | PR |  | H | HV Cables Catalog and Tagging | 2013-11-12 08:00 | 2014-04-18 16:00 | 20.6 | 733.76 | 0.4 | 0 | 733.76 | 0
242242077 |  | PR |  | D | Infrastructure Consumables | 2013-09-03 08:00 | 2014-05-01 16:00 | 32.4 | 0 | 0 | 0 | 16200 | 16200
242242190 |  | PR |  | H | Install Gas Line (1S) | 2014-11-25 08:00 | 2014-12-10 16:00 | 2 | 917.2 | 0.5 | 0 | 917.2 | 0
242242115 |  | PR |  | H | Installation of Elliptical mirrors | 2013-11-20 08:00 | 2014-12-10 16:00 | 52 | 1025.2 | 0.5 | 0 | 1025.2 | 0
242242215 |  | PR |  | H | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | 2013-09-03 08:00 | 2013-10-30 16:00 | 8.4 | 582.88 | 0.2 | 0 | 582.88 | 0
242242108 |  | PR |  | U | Lexan/Acrylic/Over- Coating Procurement (all sectors) | 2013-11-11 08:00 | 2014-10-31 16:00 | 48.2 | 3205.84 | 1.1 | 0 | 5205.84 | 2000
242242500M |  | PR |  | M | LTCC Complete |  | 2015-02-10 16:00 | 0 | 0 | 0 | 0 | 0 | 0
242242260 |  | PR |  | H | Manufacture Sagging Test Tools | 2013-10-25 08:00 | 2013-12-20 16:00 | 7.8 | 1834.4 | 1 | 0 | 1834.4 | 0
242242205 |  | PR | ST | S | Mirrors Laser Alignments | 2014-02-03 08:00 | 2014-12-16 16:00 | 44.4 | 18034.24 | 13.6 | 0 | 18034.24 | 0
242242169 |  | PR |  | D | New Patch Panel Fabrication | 2014-02-11 12:00 | 2014-07-31 12:00 | 24 | 2935.04 | 1.6 | 0 | 2935.04 | 0
242242320 |  | PR |  | H | Nose Extension Installation | 2014-01-16 08:00 | 2014-10-28 16:00 | 40 | 366.88 | 0.2 | 0 | 366.88 | 0
242242220a |  | PR | ST | S | Online Calibration Design | 2013-09-03 08:00 | 2014-06-27 16:00 | 40.4 | 2914.4 | 1 | 0 | 2914.4 | 0
242242225 |  | PR |  | H | Online Calibration Test | 2014-10-09 08:00 | 2014-11-11 16:00 | 4.8 | 1165.76 | 0.4 | 0 | 1165.76 | 0
242242222 |  | PR | ST | S | Online HV Matching Design | 2013-09-03 08:00 | 2014-06-27 16:00 | 40.4 | 3205.84 | 1.1 | 0 | 3205.84 | 0
242242223 |  | PR | ST | S | Online HV Matching Test | 2014-06-09 08:00 | 2014-11-11 16:00 | 22 | 3497.28 | 1.2 | 0 | 3497.28 | 0
242242170 | OB | PR |  | D | Patch Panel Connectors Procurement | 2013-09-03 08:00 | 2014-01-22 16:00 | 18.2 | 2040.08 | 0.7 | 12154.8 | 14194.88 | 0
242242315 |  | PR |  | H | Patch Panel Installation | 2014-02-11 08:00 | 2014-10-30 16:00 | 37 | 658.32 | 0.3 | 0 | 658.32 | 0
242242230 |  | PR |  | H | PMT Installation | 2014-01-21 08:00 | 2014-11-26 16:00 | 43.8 | 1025.2 | 0.5 | 0 | 1025.2 | 0
242242310 |  | PR |  | H | PMTS, Mirrors Holes Drill | 2013-10-08 08:00 | 2014-08-19 16:00 | 42.6 | 733.76 | 0.4 | 0 | 733.76 | 0
242242165b |  | PR |  | D | Procure Cables Procurement | 2013-11-12 08:00 | 2014-06-24 16:00 | 29.8 | 2331.52 | 0.8 | 21160 | 23491.52 | 0
242242185 |  | PR |  | D | Procure Gas Line | 2014-10-01 08:00 | 2014-11-14 16:00 | 6.6 | 582.88 | 0.2 | 18000 | 18582.88 | 0
242242045 | OB | PR |  | D | Procurement Lasers | 2013-09-03 08:00 | 2014-01-28 16:00 | 19 | 174.86 | 0.06 | 1651.04 | 1825.9 | 0
242242255 |  | PR |  | D | Procurement Sagging Test Tools | 2013-09-10 08:00 | 2013-11-11 16:00 | 9 | 582.88 | 0.2 | 0 | 582.88 | 0
242242085 |  | PR | ST | S | Quality Control of Elliptical/Hyperbolic mirrors | 2013-09-17 08:00 | 2014-06-09 16:00 | 35.6 | 9881.28 | 9.2 | 0 | 9881.28 | 0
242242031 |  | PR |  | U | Quality Control of Existing PMTs | 2013-09-10 08:00 | 2014-06-10 16:00 | 36.8 | 4066.32 | 10.3 | 0 | 4066.32 | 0
242242030 |  | PR |  | Z | Quality Control of PMTs | 2013-10-10 08:00 | 2014-06-10 16:00 | 32.4 | 0 | 3 | 0 | 0 | 0
242242305 |  | PR |  | H | Rear Brace Installation | 2014-01-17 08:00 | 2014-07-31 16:00 | 27.4 | 1467.52 | 0.8 | 0 | 1467.52 | 0
242242300 |  | PR |  | H | Rear Brace Manufacture | 2013-11-04 08:00 | 2014-02-28 16:00 | 14.8 | 733.76 | 0.4 | 0 | 1233.76 | 500
242242270 |  | PR | ST | S | Sagging Test | 2014-01-03 08:00 | 2014-05-23 16:00 | 20 | 3442.48 | 1.7 | 0 | 3442.48 | 0
242242340 |  | PR | ST | S | Sector 2 Box Refurbish | 2013-10-30 08:00 | 2013-12-10 16:00 | 5.6 | 14675.2 | 8 | 0 | 14675.2 | 0
242242360 |  | PR |  | H | Sector 2 Gas Leaks Checks | 2014-08-04 08:00 | 2014-09-09 16:00 | 5.2 | 2201.28 | 1.2 | 0 | 2201.28 | 0
242242350 |  | PR |  | H | Sector 2 Mirrors Alignment | 2014-04-15 08:00 | 2014-06-24 16:00 | 10 | 3668.8 | 2 | 0 | 3668.8 | 0
242242355 |  | PR |  | H | Sector 2 Windows Installation | 2014-06-30 08:00 | 2014-07-15 16:00 | 2.2 | 1834.4 | 1 | 0 | 1834.4 | 0
242242365 |  | PR | ST | S | Sector 3 Box Refurbish | 2014-01-21 08:00 | 2014-02-18 16:00 | 4.2 | 13207.68 | 7.2 | 0 | 13207.68 | 0
242242385 |  | PR |  | H | Sector 3 Gas Leaks Checks | 2014-09-30 08:00 | 2014-10-29 16:00 | 4.4 | 1834.4 | 1 | 0 | 1834.4 | 0
242242375 |  | PR |  | H | Sector 3 Mirrors Alignment | 2014-07-22 08:00 | 2014-08-26 16:00 | 5.2 | 3668.8 | 2 | 0 | 3668.8 | 0
242242380 |  | PR |  | H | Sector 3 Windows Installation | 2014-08-27 08:00 | 2014-09-16 16:00 | 2.8 | 1834.4 | 1 | 0 | 1834.4 | 0
242242390 |  | PR | ST | S | Sector 4 Box Refurbish | 2014-03-03 08:00 | 2014-04-08 16:00 | 5.4 | 13207.68 | 7.2 | 0 | 13207.68 | 0
242242410 |  | PR |  | H | Sector 4 Gas Leaks Checks | 2014-11-26 08:00 | 2014-12-16 16:00 | 2.6 | 1834.4 | 1 | 0 | 1834.4 | 0
242242400 |  | PR |  | H | Sector 4 Mirrors Alignment | 2014-09-23 08:00 | 2014-10-28 16:00 | 5.2 | 3668.8 | 2 | 0 | 3668.8 | 0
242242405 |  | PR |  | H | Sector 4 Windows Installation | 2014-10-29 08:00 | 2014-11-18 16:00 | 3 | 1834.4 | 1 | 0 | 1834.4 | 0
242242415 |  | PR | ST | S | Sector 5 Box Refurbish | 2014-04-14 08:00 | 2014-05-13 16:00 | 4.4 | 11740.16 | 6.4 | 0 | 11740.16 | 0
242242435 |  | PR |  | H | Sector 5 Gas Leaks Checks | 2014-12-17 08:00 | 2015-01-20 16:00 | 3.2 | 1834.4 | 1 | 0 | 1834.4 | 0
242242425 |  | PR |  | H | Sector 5 Mirrors Alignment | 2014-10-29 08:00 | 2014-11-11 16:00 | 2 | 3668.8 | 2 | 0 | 3668.8 | 0
242242430 |  | PR |  | H | Sector 5 Windows Installation | 2014-11-26 08:00 | 2014-12-16 16:00 | 2.6 | 1834.4 | 1 | 0 | 1834.4 | 0
242242440 |  | PR | ST | S | Sector 6 Box Refurbish | 2014-05-27 08:00 | 2014-06-17 16:00 | 3.2 | 11740.16 | 6.4 | 0 | 11740.16 | 0
242242460 |  | PR |  | H | Sector 6 Gas Leaks Checks | 2015-01-20 08:00 | 2015-02-10 16:00 | 3.2 | 1834.4 | 1 | 0 | 1834.4 | 0
242242450 |  | PR |  | H | Sector 6 Mirrors Alignment | 2014-11-26 08:00 | 2014-12-16 16:00 | 2.6 | 3668.8 | 2 | 0 | 3668.8 | 0
242242455 |  | PR |  | H | Sector 6 Windows Installation | 2014-12-17 08:00 | 2015-01-20 16:00 | 3.2 | 1834.4 | 1 | 0 | 1834.4 | 0
242242245 |  | PR |  | H | Simulation of Sagging Test | 2013-10-01 08:00 | 2014-03-04 16:00 | 20 | 1748.64 | 0.6 | 0 | 1748.64 | 0
242242325 |  | PR |  | H | Spine Refusrbish | 2013-09-03 08:00 | 2014-10-20 16:00 | 56.2 | 917.2 | 0.5 | 0 | 917.2 | 0
242242076 |  | PR |  | D | Support Frame Fabrication for 1S in TED | 2013-09-05 08:00 | 2013-12-02 16:00 | 12.2 | 1834.4 | 1 | 0 | 2834.4 | 1000
242242295 |  | PR |  | H | Wall Cut-Off | 2013-09-30 08:00 | 2014-04-21 16:00 | 27 | 733.76 | 0.4 | 0 | 733.76 | 0
242242155 |  | PR |  | H | Walls Manufacturing and Installation | 2013-10-15 08:00 | 2013-12-10 16:00 | 7.8 | 2417.28 | 1.2 | 0 | 2417.28 | 0
242242040 | OB | PR |  | D | Wavelength Shifting Procurement | 2013-09-03 08:00 | 2014-06-30 16:00 | 40.6 | 0 | 0 | 60000 | 60000 | 0
242242036 |  | PR |  | H | Wavelength Shifting tests | 2013-09-03 08:00 | 2013-10-15 16:00 | 6.2 | 2040.08 | 0.7 | 0 | 4040.08 | 2000
242242152 |  | PR |  | D | Window Procurement | 2013-09-03 08:00 | 2014-03-31 16:00 | 27.8 | 2331.52 | 0.8 | 2800 | 5131.52 | 0
242242235 |  | PR |  | U | Windows Installation 6 sectors | 2014-03-04 08:00 | 2014-12-10 16:00 | 39.4 | 9172 | 5 | 0 | 9172 | 0