## SVT ETC Costs
CLAS12 LTCC ETC Procurement Costs
Activity ID | Activity Name | P6 total | Costpoint | Remaining CP | Reamining P6 | BOE | PRs | POs | Comments
242242163 | Divider Modifications Procurement | 2405.76 | 0 | 2405.76 | 2405.76 | Not OB
242242152 | Window Procurement | 2800 | 0 | 20000 | 2800 | Not OB | 340915 |  | Combined with HTCC P6, acquired 30% of the material (MYLAR). Tests completed. PO about to be awarded. Costpoint is $20K instead of $2800.
242242110 | Al/Mg Deposit Procurement | 53240 | 53240 | 0 | 0 | Done
242242092 | Al/Mg Deposit Procurement WC | 53240.88 | 0 | 53240.88 | 53240.88 | OB | 338701 | 14-P0521-0 | Company received 39 WC out of 100.
242242040 | Wavelength Shifting Procurement | 61914 | 31000 | 30914 | 30914 | OB | 340671 | 14-P0589-0 | 164 PMTs done. Project completion: Nov. 15.
Total |  | 173600.64 |  | 106560.64 | 89360.64
Open Obligations: 104
Remaining Obligations: 198