## Sheet1
ID | Milestone | Activities with Steps | Predecessor | Successor | Activity Name | Duration (weeks) | Start | Finish | Budgeted Labor FTE (Mech T) | Budgeted Labor FTE (Elect. T) | Budgeted Labor FTE (Scientist) | Budgeted Labor FTE (Mech Eng) | Budgeted Labor FTE (Visiting) | Budgeted Material Cost | Comments
0 | YES |  | NA |  | TED Ready
1 |  |  | 0 | 2 | Calibration Software | 18w | 2015-01-05 | 2015-04-07 |  |  | 5 |  | 3.6 |  | Mauri + VU
2 |  |  | 1 |  | Calibration Test | 10w | 2015-04-08 | 2015-06-16 |  |  | 4 |  | 3.6 |  | Mauri + VU
3 |  |  | 0 |  | Winston Cones Testing | 6w | 2015-01-05 | 2015-01-15 | 1 |  | 0.6 |  |  |  | Tina + Mindy
4 |  |  | 0 | 5 | Winston Cones PR Extension | 6w | 2015-01-06 | 2016-03-02 | [5 empty] | 40000
5 |  |  | 4 |  | Additional WC Testing | 4w | 2015-02-17 | 2015-03-20 | 1 |  | 0.4 |  |  |  | Tina + Mindy
6 |  |  | 0 | 7 | Divider Mods PR | 8.6w | 2015-01-05 | 2015-02-15 |  |  |  | 0.43 |  | 5000 | Popov 3 days
7 |  |  | 6 |  | Divider Installation | 6.6w | 2015-01-07 | 2015-03-15 |  | 6.6 |  |  | 3.3 |  | Tina + Mindy + VU
7a |  |  | 0 |  | Divider Consumables | 5w | 2015-01-05 | 2015-03-15 | [5 empty] | 2000
8 |  |  | 0 | 10 | Frame Support Installation | 4w | 2015-01-13 | 2015-02-05 | 0.8 | [5 empty] | David + 2 techs
Sector 1
9 |  | ST | 0 | 10, 17 | Prep Box | 5.4 | 2015-01-05 | 2015-01-12 | 4 | [5 empty] | David Full Time
10 |  | ST | 8,9 | 11 | Hardware Installation | 3.4 | 2015-01-13 | 2015-02-04 | 4.2 | [5 empty] | 2 techs full time
11 |  |  | 10 | 12 | Mirror Alignment | 2 | 2015-02-05 | 2015-02-18 |  |  | 0.8 |  | 0.5
12 |  |  | 11 | 14 | Fiducialization | 0.6 | 2015-02-19 | 2015-02-23 | 0.6 |  |  | 0.6
13 |  |  | 10 | 14 | Window Seaming | 1 | 2015-02-05 | 2015-02-11 | 1.5
14 |  | ST | 12,13 | 15, 18 | Window Installation | 1 | 2015-02-24 | 2015-03-02 | 1.5 | [5 empty] | 2 techs full time
15 |  |  | 14 | 16a | Gas Leaks Checks | 1 | 2015-03-03 | 2015-03-09 | 1
16 |  |  | 0 | 16a | Consumables | 12 | 2014-12-03 | 2015-03-09 | [5 empty] | 350
16a | YES |  | 15 |  | Sector 2 Complete |  |  | 2015-03-09
Sector 2
17 |  | ST | 9 | 18, 25 | Prep Box | 5.4 | 2015-01-13 | 2015-02-18 | 4 | [5 empty] | David Full Time
18 |  | ST | 14, 17 | 19 | Hardware Installation | 3.4 | 2015-03-03 | 2015-03-24 | 4.2 | [5 empty] | 2 techs full time
19 |  |  | 18 | 20 | Mirror Alignment | 2 | 2015-03-25 | 2015-04-07 |  |  | 0.8 |  | 0.5
20 |  |  | 19 | 22 | Fiducialization | 0.6 | 2015-04-08 | 2015-04-10 | 0.6 |  |  | 0.6
21 |  |  | 18 | 22 | Window Seaming | 1 | 2015-03-25 | 2015-03-31 | 1.5
22 |  | ST | 20, 21 | 23, 26 | Window Installation | 1 | 2015-04-13 | 2015-04-17 | 1.5 | [5 empty] | 2 techs full time
23 |  |  | 22 | 24a | Gas Leaks Checks | 1 | 2015-04-20 | 2015-04-24 | 1
24 |  |  | 0 | 24a | Consumables | 12 | 2015-01-13 | 2015-04-24 | [5 empty] | 350
24a | YES |  | 23 |  | Sector 3 Complete |  |  | 2015-04-24
Sector 3
25 |  | ST | 17 | 26, 33 | Prep Box | 5.4 | 2015-02-19 | 2015-03-27 | 4 | [5 empty] | David Full Time
26 |  | ST | 22, 25 | 27 | Hardware Installation | 3.4 | 2015-04-20 | 2015-05-11 | 4.2 | [5 empty] | 2 techs full time
27 |  |  | 26 | 28 | Mirror Alignment | 2 | 2015-05-12 | 2015-05-18 |  |  | 0.8 |  | 0.5
28 |  |  | 27 | 30 | Fiducialization | 0.6 | 2015-05-19 | 2015-05-20 | 0.6 |  |  | 0.6
29 |  |  | 26 | 30 | Window Seaming | 1 | 2015-05-12 | 2015-05-18 | 1.5
30 |  | ST | 28, 29 | 31, 34 | Window Installation | 1 | 2015-05-21 | 2015-05-27 | 1.5 | [5 empty] | 2 techs full time
31 |  |  | 30 | 32a | Gas Leaks Checks | 1 | 2015-05-28 | 2015-06-03 | 1
32 |  |  | 0 | 32a | Consumables | 12 | 2015-02-19 | 2015-06-03 | [5 empty] | 350
32a | YES |  | 31 |  | Sector 4 Complete |  |  | 2015-06-03
Sector 4
33 |  | ST | 25 | 34, 41 | Prep Box | 5.4 | 2015-03-30 | 2015-05-05 | 4 | [5 empty] | David Full Time
34 |  | ST | 30, 33 | 35 | Hardware Installation | 3.4 | 2015-05-28 | 2015-06-18 | 4.2 | [5 empty] | 2 techs full time
35 |  |  | 34 | 36 | Mirror Alignment | 2 | 2015-06-19 | 2015-06-25 |  |  | 0.8 |  | 0.5
36 |  |  | 35 | 38 | Fiducialization | 0.6 | 2015-06-26 | 2015-06-29 | 0.6 |  |  | 0.6
37 |  |  | 34 | 38 | Window Seaming | 1 | 2015-06-19 | 2015-06-25 | 1.5
38 |  | ST | 36, 37 | 39, 42 | Window Installation | 1 | 2015-06-30 | 2015-07-06 | 1.5 | [5 empty] | 2 techs full time
39 |  |  | 38 | 40a | Gas Leaks Checks | 1 | 2015-07-07 | 2015-07-13 | 1
40 |  |  | 0 | 40a | Consumables | 12 | 2015-03-30 | 2015-07-13 | [5 empty] | 350
40a | YES |  | 39 |  | Sector 1 Complete |  |  | 2015-07-13
Sector 5
41 |  | ST | 33 | 42, 49 | Prep Box | 5.4 | 2015-05-06 | 2015-06-11 | 4 | [5 empty] | David Full Time
42 |  | ST | 38, 41 | 43 | Hardware Installation | 3.4 | 2015-07-07 | 2015-07-28 | 4.2 | [5 empty] | 2 techs full time
43 |  |  | 42 | 44 | Mirror Alignment | 2 | 2015-07-29 | 2015-08-04 |  |  | 0.8 |  | 0.5
44 |  |  | 43 | 46 | Fiducialization | 0.6 | 2015-08-05 | 2015-08-06 | 0.6 |  |  | 0.6
45 |  |  | 42 | 46 | Window Seaming | 1 | 2015-06-26 | 2015-07-02 | 1.5
46 |  | ST | 44, 45 | 47, 50 | Window Installation | 1 | 2015-08-07 | 2015-08-13 | 1.5 | [5 empty] | 2 techs full time
47 |  |  | 46 | 48a | Gas Leaks Checks | 1 | 2015-08-14 | 2015-08-20 | 1
48 |  |  | 0 | 48a | Consumables | 12 | 2015-05-06 | 2015-08-20 | [5 empty] | 350
48a | YES |  | 47 |  | Sector 5 Complete |  |  | 2015-08-20
Sector 6
49 |  | ST | 41 | 50 | Prep Box | 5.4 | 2015-06-26 | 2015-08-03 | 4 | [5 empty] | David Full Time
50 |  | ST | 46, 49 | 51 | Hardware Installation | 3.4 | 2015-08-14 | 2015-09-04 | 4.2 | [5 empty] | 2 techs full time
51 |  |  | 50 | 52 | Mirror Alignment | 2 | 2015-09-07 | 2015-09-11 |  |  | 0.8 |  | 0.5
52 |  |  | 51 | 54 | Fiducialization | 0.6 | 2015-09-14 | 2015-09-15 | 0.6 |  |  | 0.6
53 |  |  | 50 | 54 | Window Seaming | 1 | 2015-09-07 | 2015-09-11 | 1.5
54 |  | ST | 52, 53 | 55 | Window Installation | 1 | 2015-09-16 | 2015-09-22 | 1.5 | [5 empty] | 2 techs full time
55 |  |  | 54 | 56a | Gas Leaks Checks | 1 | 2015-09-23 | 2015-09-29 | 1
56 |  |  | 0 | 56a | Consumables | 12 | 2015-06-26 | 2015-09-29 | [5 empty] | 350
56a | YES |  | 55 |  | Sector 6 Complete |  |  | 2015-09-29
[9 empty] | Budgeted Labor FTE (Mech T) | Budgeted Labor FTE (Elect. T) | Budgeted Labor FTE (Scientist) | Budgeted Labor FTE (Mech Eng) | Budgeted Labor FTE (Visiting)
[8 empty] | Total: | 79.6 | 6.6 | 14.8 | 4.03 | 13.5 | 118.53
[8 empty] | Previous P6: | 46.2 | 4 | 11 | 0 | 3.6 | 64.8
[8 empty] | Delta (mw) | 33.4 | 2.6 | 3.8 | 4.03 | 9.9 | 53.73
[8 empty] | Cost Delta (K) | 63.46 | 4.94 | 10.26 | 9.269 | 9.9 | 97.829