## Template
12 GeV September 2013 STATUS UPDATE
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID
ELOUADRHIRI L
1.4.2.2.4.2 LOW THRESHOLD CC | 242242030 | Z | Quality Control of PMTs | 2013-10-10 | 2013-10-10 |  |  | 2014-06-10 | 2014-06-10 |  |  | 0 |  | 347 | Z | 242242030
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031 | U | Quality Control of Existing PMTs | 2013-09-10 | 2013-09-10 |  |  | 2014-06-10 | 2014-06-10 |  |  | 0 |  | 248 | U | 242242031
1.4.2.2.4.2 LOW THRESHOLD CC | 242242036 | H | Wavelength Shifting tests | 2013-09-03 | 2013-09-03 |  |  | 2013-10-15 | 2013-10-15 |  |  | 0 | 30 | 252 | H | 242242036
1.4.2.2.4.2 LOW THRESHOLD CC | 242242040 | D | Wavelength Shifting Procurement | 2014-01-08 | 2014-01-08 |  |  | 2014-10-23 | 2014-10-23 |  |  | 0 |  | 252 | D | 242242040
1.4.2.2.4.2 LOW THRESHOLD CC | 242242045 | D | Procurement Lasers | 2013-09-03 | 2013-09-03 |  | 2013-11-15 | 2014-01-28 | 2014-01-28 |  |  | 0 |  | 216 | D | 242242045
1.4.2.2.4.2 LOW THRESHOLD CC | 242242050 | D | Alignment Tool Manufacturing | 2013-09-20 | 2013-09-20 |  | 2013-11-15 | 2013-12-13 | 2013-12-13 |  |  | 0 |  | 217 | D | 242242050
1.4.2.2.4.2 LOW THRESHOLD CC | 242242055 | S | Alignment Tool and Lasers Installation | 2013-11-01 | 2013-11-01 |  |  | 2014-03-18 | 2014-03-18 |  |  | 0 |  | 216 | S | 242242055
1.4.2.2.4.2 LOW THRESHOLD CC | 242242076 | D | Support Frame Fabrication for 1S in TED | 2014-01-07 | 2014-01-07 |  |  | 2014-04-02 | 2014-04-02 |  |  | 0 |  | 395 | D | 242242076
1.4.2.2.4.2 LOW THRESHOLD CC | 242242077 | D | Infrastructure Consumables | 2014-01-07 | 2014-01-07 |  |  | 2014-08-25 | 2014-08-25 |  |  | 0 |  | 294 | D | 242242077
1.4.2.2.4.2 LOW THRESHOLD CC | 242242085 | S | Quality Control of Elliptical/Hyperbolic mirrors | 2013-10-31 | 2013-10-31 |  |  | 2014-07-24 | 2014-07-24 |  |  | 0 |  | 348 | S | 242242085
1.4.2.2.4.2 LOW THRESHOLD CC | 242242090 | U | Dimensions check of Elliptical/Hyperbolic mirrors | 2014-01-07 | 2014-01-07 |  |  | 2014-10-01 | 2014-10-01 |  |  | 0 |  | 268 | U | 242242090
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092 | U | Al/Mg Deposit Procurement WC | 2013-11-19 | 2013-11-19 |  |  | 2014-11-14 | 2014-11-14 |  |  | 0 |  | 236 | U | 242242092
1.4.2.2.4.2 LOW THRESHOLD CC | 242242095 | H | Create Manufacturing Drawings | 2013-09-03 | 2013-09-03 |  |  | 2013-10-10 | 2013-10-10 |  |  | 0 |  | 249 | H | 242242095
1.4.2.2.4.2 LOW THRESHOLD CC | 242242105 | H | Al/Mg Deposit Procurement Prep | 2013-09-03 | 2013-09-03 |  | 2013-11-15 | 2013-10-08 | 2013-10-08 |  |  | 0 |  | 220 | H | 242242105
1.4.2.2.4.2 LOW THRESHOLD CC | 242242107 | H | Al/Mg Laxon/Acrylic Re-Coating Test Procurement | 2013-09-10 | 2013-09-10 |  | 2013-11-15 | 2013-11-11 | 2013-11-11 |  |  | 0 |  | 236 | H | 242242107
1.4.2.2.4.2 LOW THRESHOLD CC | 242242108 | U | Lexan/Acrylic/Over- Coating Procurement (all sectors) | 2013-11-11 | 2013-11-11 |  |  | 2014-10-31 | 2014-10-31 |  |  | 0 |  | 246 | U | 242242108
1.4.2.2.4.2 LOW THRESHOLD CC | 242242110 | D | Al/Mg Deposit Procurement | 2013-11-11 | 2013-11-11 |  |  | 2014-11-26 | 2014-11-26 |  |  | 0 |  | 220 | D | 242242110
1.4.2.2.4.2 LOW THRESHOLD CC | 242242115 | H | Installation of Elliptical mirrors | 2014-01-21 | 2014-01-21 |  |  | 2014-12-10 | 2014-12-10 |  |  | 0 |  | 220 | H | 242242115
1.4.2.2.4.2 LOW THRESHOLD CC | 242242137 | D | Glue Procurement | 2013-12-05 | 2013-12-05 |  |  | 2014-03-31 | 2014-03-31 |  |  | 0 |  | 397 | D | 242242137
1.4.2.2.4.2 LOW THRESHOLD CC | 242242145a | H | Complete Design Box Walls | 2013-09-03 | 2013-09-03 |  |  | 2013-10-22 | 2013-10-22 |  |  | 0 |  | 467 | H | 242242145a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242152 | D | Window Procurement | 2013-09-03 | 2013-09-03 |  | 2013-11-15 | 2014-03-31 | 2014-03-31 |  |  | 0 |  | 185 | D | 242242152
1.4.2.2.4.2 LOW THRESHOLD CC | 242242155 | H | Walls Manufacturing and Installation | 2013-10-15 | 2013-10-15 |  |  | 2013-12-10 | 2013-12-10 |  |  | 0 |  | 467 | H | 242242155
1.4.2.2.4.2 LOW THRESHOLD CC | 242242161 | H | HV Cables Catalog and Tagging | 2013-11-12 | 2013-11-12 |  |  | 2014-04-18 | 2014-04-18 |  |  | 0 |  | 311.5 | H | 242242161
1.4.2.2.4.2 LOW THRESHOLD CC | 242242162 | H | Divider Modifications Design and Test | 2013-11-12 | 2013-11-12 |  |  | 2014-02-11 | 2014-02-11 |  |  | 0 |  | 226 | H | 242242162
1.4.2.2.4.2 LOW THRESHOLD CC | 242242163 | D | Divider Modifications Procurement | 2014-02-12 | 2014-02-12 |  |  | 2014-12-23 | 2014-12-23 |  |  | 0 |  | 226 | D | 242242163
1.4.2.2.4.2 LOW THRESHOLD CC | 242242164 | U | Divider Modifications Implementation | 2014-02-12 | 2014-02-12 |  |  | 2014-12-02 | 2014-12-02 |  |  | 0 |  | 226 | U | 242242164
1.4.2.2.4.2 LOW THRESHOLD CC | 242242165b | D | Procure Cables Procurement | 2013-11-12 | 2013-11-12 |  |  | 2014-06-24 | 2014-06-24 |  |  | 0 |  | 337 | D | 242242165b
1.4.2.2.4.2 LOW THRESHOLD CC | 242242169 | D | New Patch Panel Fabrication | 2014-02-11 | 2014-02-11 |  |  | 2014-07-31 | 2014-07-31 |  |  | 0 |  | 311.5 | D | 242242169
1.4.2.2.4.2 LOW THRESHOLD CC | 242242170 | D | Patch Panel Connectors Procurement | 2014-10-01 | 2014-10-01 |  |  | 2015-01-30 | 2015-01-30 |  |  | 0 |  | 192 | D | 242242170
1.4.2.2.4.2 LOW THRESHOLD CC | 242242185 | D | Procure Gas Line | 2014-10-01 | 2014-10-01 |  |  | 2014-11-14 | 2014-11-14 |  |  | 0 |  | 215 | D | 242242185
1.4.2.2.4.2 LOW THRESHOLD CC | 242242190 | H | Install Gas Line (1S) | 2014-11-25 | 2014-11-25 |  |  | 2014-12-10 | 2014-12-10 |  |  | 0 |  | 215 | H | 242242190
1.4.2.2.4.2 LOW THRESHOLD CC | 242242195 | H | Gas Line Quality Control | 2014-12-11 | 2014-12-11 |  |  | 2014-12-17 | 2014-12-17 |  |  | 0 |  | 215 | H | 242242195
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205 | S | Mirrors Laser Alignments | 2014-02-03 | 2014-02-03 |  |  | 2014-12-16 | 2014-12-16 |  |  | 0 |  | 216 | S | 242242205
1.4.2.2.4.2 LOW THRESHOLD CC | 242242215 | H | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | 2014-10-01 | 2014-10-01 |  |  | 2014-12-01 | 2014-12-01 |  |  | 0 |  | 227 | H | 242242215
1.4.2.2.4.2 LOW THRESHOLD CC | 242242220a | S | Online Calibration Design | 2013-09-03 | 2013-09-03 |  |  | 2014-06-27 | 2014-06-27 |  |  | 0 |  | 239 | S | 242242220a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242222 | S | Online HV Matching Design | 2013-09-03 | 2013-09-03 |  |  | 2014-06-27 | 2014-06-27 |  |  | 0 |  | 239 | S | 242242222
1.4.2.2.4.2 LOW THRESHOLD CC | 242242223 | S | Online HV Matching Test | 2014-06-09 | 2014-06-09 |  |  | 2014-11-11 | 2014-11-11 |  |  | 0 |  | 239 | S | 242242223
1.4.2.2.4.2 LOW THRESHOLD CC | 242242225 | H | Online Calibration Test | 2014-10-09 | 2014-10-09 |  |  | 2014-11-11 | 2014-11-11 |  |  | 0 |  | 239 | H | 242242225
1.4.2.2.4.2 LOW THRESHOLD CC | 242242230 | H | PMT Installation | 2014-01-21 | 2014-01-21 |  |  | 2014-11-26 | 2014-11-26 |  |  | 0 |  | 248 | H | 242242230
1.4.2.2.4.2 LOW THRESHOLD CC | 242242235 | U | Windows Installation 6 sectors | 2014-03-04 | 2014-03-04 |  |  | 2014-12-10 | 2014-12-10 |  |  | 0 |  | 185 | U | 242242235
1.4.2.2.4.2 LOW THRESHOLD CC | 242242240 | S | Gas Leak Check 6 sectors | 2014-05-23 | 2014-05-23 |  |  | 2015-02-10 | 2015-02-10 |  |  | 0 |  | 185 | S | 242242240
1.4.2.2.4.2 LOW THRESHOLD CC | 242242245 | H | Simulation of Sagging Test | 2013-10-01 | 2013-10-01 |  |  | 2014-03-04 | 2014-03-04 |  |  | 0 |  | 383 | H | 242242245
1.4.2.2.4.2 LOW THRESHOLD CC | 242242255 | D | Procurement Sagging Test Tools | 2014-01-03 | 2014-01-03 |  |  | 2014-03-18 | 2014-03-18 |  |  | 0 |  | 383 | D | 242242255
1.4.2.2.4.2 LOW THRESHOLD CC | 242242260 | H | Manufacture Sagging Test Tools | 2014-01-03 | 2014-01-03 |  |  | 2014-03-18 | 2014-03-18 |  |  | 0 |  | 383 | H | 242242260
1.4.2.2.4.2 LOW THRESHOLD CC | 242242270 | S | Sagging Test | 2014-03-19 | 2014-03-19 |  |  | 2014-04-18 | 2014-04-18 |  |  | 0 |  | 383 | S | 242242270
1.4.2.2.4.2 LOW THRESHOLD CC | 242242280 | H | Frame Support | 2013-09-18 | 2013-09-18 |  |  | 2013-12-05 | 2013-12-05 |  |  | 0 |  | 943 | H | 242242280
1.4.2.2.4.2 LOW THRESHOLD CC | 242242290 | H | Cut Line Mark | 2013-09-03 | 2013-09-03 |  |  | 2013-09-30 | 2013-09-30 |  |  | 0 |  | 382 | H | 242242290
1.4.2.2.4.2 LOW THRESHOLD CC | 242242295 | H | Wall Cut-Off | 2013-09-30 | 2013-09-30 |  |  | 2014-04-21 | 2014-04-21 |  |  | 0 |  | 382 | H | 242242295
1.4.2.2.4.2 LOW THRESHOLD CC | 242242300 | H | Rear Brace Manufacture | 2013-11-04 | 2013-11-04 |  |  | 2014-02-28 | 2014-02-28 |  |  | 0 |  | 249 | H | 242242300
1.4.2.2.4.2 LOW THRESHOLD CC | 242242305 | H | Rear Brace Installation | 2014-01-17 | 2014-01-17 |  |  | 2014-07-31 | 2014-07-31 |  |  | 0 |  | 249 | H | 242242305
1.4.2.2.4.2 LOW THRESHOLD CC | 242242310 | H | PMTS, Mirrors Holes Drill | 2013-10-08 | 2013-10-08 |  |  | 2014-08-19 | 2014-08-19 |  |  | 0 |  | 249 | H | 242242310
1.4.2.2.4.2 LOW THRESHOLD CC | 242242315 | H | Patch Panel Installation | 2014-02-11 | 2014-02-11 |  |  | 2014-10-30 | 2014-10-30 |  |  | 0 |  | 255 | H | 242242315
1.4.2.2.4.2 LOW THRESHOLD CC | 242242320 | H | Nose Extension Installation | 2014-01-21 | 2014-01-21 |  |  | 2014-10-30 | 2014-10-30 |  |  | 0 |  | 255 | H | 242242320
1.4.2.2.4.2 LOW THRESHOLD CC | 242242325 | H | Spine Refusrbish | 2013-09-03 | 2013-09-03 |  |  | 2014-10-20 | 2014-10-20 |  |  | 0 |  | 255 | H | 242242325
1.4.2.2.4.2 LOW THRESHOLD CC | 242242330 | H | Gas Line Refurbish | 2014-02-27 | 2014-02-27 |  |  | 2014-10-20 | 2014-10-20 |  |  | 0 |  | 255 | H | 242242330
1.4.2.2.4.2 LOW THRESHOLD CC | 242242335 | D | Box Refurbish Consumables | 2013-11-01 | 2013-11-01 |  |  | 2014-12-22 | 2014-12-22 |  |  | 0 |  | 212 | D | 242242335
1.4.2.2.4.2 LOW THRESHOLD CC | 242242340 | S | Sector 2 Box Refurbish | 2013-10-30 | 2013-10-30 |  |  | 2013-12-10 | 2013-12-10 |  |  | 0 |  | 185 | S | 242242340
1.4.2.2.4.2 LOW THRESHOLD CC | 242242350 | H | Sector 2 Mirrors Alignment | 2014-04-15 | 2014-04-15 |  |  | 2014-06-24 | 2014-06-24 |  |  | 0 |  | 185 | H | 242242350
1.4.2.2.4.2 LOW THRESHOLD CC | 242242355 | H | Sector 2 Windows Installation | 2014-06-30 | 2014-06-30 |  |  | 2014-07-15 | 2014-07-15 |  |  | 0 |  | 185 | H | 242242355
1.4.2.2.4.2 LOW THRESHOLD CC | 242242360 | H | Sector 2 Gas Leaks Checks | 2014-08-04 | 2014-08-04 |  |  | 2014-09-09 | 2014-09-09 |  |  | 0 |  | 293 | H | 242242360
1.4.2.2.4.2 LOW THRESHOLD CC | 242242365 | S | Sector 3 Box Refurbish | 2014-01-21 | 2014-01-21 |  |  | 2014-02-18 | 2014-02-18 |  |  | 0 |  | 293 | S | 242242365
1.4.2.2.4.2 LOW THRESHOLD CC | 242242375 | H | Sector 3 Mirrors Alignment | 2014-07-22 | 2014-07-22 |  |  | 2014-08-26 | 2014-08-26 |  |  | 0 |  | 185 | H | 242242375
1.4.2.2.4.2 LOW THRESHOLD CC | 242242380 | H | Sector 3 Windows Installation | 2014-08-27 | 2014-08-27 |  |  | 2014-09-16 | 2014-09-16 |  |  | 0 |  | 185 | H | 242242380
1.4.2.2.4.2 LOW THRESHOLD CC | 242242385 | H | Sector 3 Gas Leaks Checks | 2014-09-30 | 2014-09-30 |  |  | 2014-10-29 | 2014-10-29 |  |  | 0 |  | 301 | H | 242242385
1.4.2.2.4.2 LOW THRESHOLD CC | 242242390 | S | Sector 4 Box Refurbish | 2014-03-03 | 2014-03-03 |  |  | 2014-04-08 | 2014-04-08 |  |  | 0 |  | 301 | S | 242242390
1.4.2.2.4.2 LOW THRESHOLD CC | 242242400 | H | Sector 4 Mirrors Alignment | 2014-09-23 | 2014-09-23 |  |  | 2014-10-28 | 2014-10-28 |  |  | 0 |  | 185 | H | 242242400
1.4.2.2.4.2 LOW THRESHOLD CC | 242242405 | H | Sector 4 Windows Installation | 2014-10-29 | 2014-10-29 |  |  | 2014-11-18 | 2014-11-18 |  |  | 0 |  | 302 | H | 242242405
1.4.2.2.4.2 LOW THRESHOLD CC | 242242410 | H | Sector 4 Gas Leaks Checks | 2014-11-26 | 2014-11-26 |  |  | 2014-12-16 | 2014-12-16 |  |  | 0 |  | 302 | H | 242242410
1.4.2.2.4.2 LOW THRESHOLD CC | 242242415 | S | Sector 5 Box Refurbish | 2014-04-14 | 2014-04-14 |  |  | 2014-05-13 | 2014-05-13 |  |  | 0 |  | 302 | S | 242242415
1.4.2.2.4.2 LOW THRESHOLD CC | 242242425 | H | Sector 5 Mirrors Alignment | 2014-10-29 | 2014-10-29 |  |  | 2014-11-11 | 2014-11-11 |  |  | 0 |  | 185 | H | 242242425
1.4.2.2.4.2 LOW THRESHOLD CC | 242242430 | H | Sector 5 Windows Installation | 2014-11-26 | 2014-11-26 |  |  | 2014-12-16 | 2014-12-16 |  |  | 0 |  | 300 | H | 242242430
1.4.2.2.4.2 LOW THRESHOLD CC | 242242435 | H | Sector 5 Gas Leaks Checks | 2014-12-17 | 2014-12-17 |  |  | 2015-01-20 | 2015-01-20 |  |  | 0 |  | 300 | H | 242242435
1.4.2.2.4.2 LOW THRESHOLD CC | 242242440 | S | Sector 6 Box Refurbish | 2014-05-27 | 2014-05-27 |  |  | 2014-06-17 | 2014-06-17 |  |  | 0 |  | 300 | S | 242242440
1.4.2.2.4.2 LOW THRESHOLD CC | 242242450 | H | Sector 6 Mirrors Alignment | 2014-11-26 | 2014-11-26 |  |  | 2014-12-16 | 2014-12-16 |  |  | 0 |  | 185 | H | 242242450
1.4.2.2.4.2 LOW THRESHOLD CC | 242242455 | H | Sector 6 Windows Installation | 2014-12-17 | 2014-12-17 |  |  | 2015-01-20 | 2015-01-20 |  |  | 0 |  | 185 | H | 242242455
1.4.2.2.4.2 LOW THRESHOLD CC | 242242460 | H | Sector 6 Gas Leaks Checks | 2015-01-20 | 2015-01-20 |  |  | 2015-02-10 | 2015-02-10 |  |  | 0 |  | 185 | H | 242242460
1.4.2.2.4.2 LOW THRESHOLD CC | 242242500M | M | LTCC Complete |  |  |  |  | 2015-02-10 | 2015-02-10 |  |  | 0 |  | 185 | M | 242242500M