## Template
12 GeV Rebaseline August 2013 STATUS UPDATE
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID | Comments
1.4.2.2.4.2 LOW THRESHOLD CC | 242242030 |  | Quality Control of PMTs | 2013-04-15 | 2013-06-01 | 2013-06-01 | 2013-10-10 | 2013-09-10 | 2013-11-25 |  | 2014-06-10 16:00 | 10 |  | 476 | 0 | 242242030
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031 |  | Quality Control of Existing PMTs | 2013-04-22 | 2013-07-01 | 2013-07-01 | 2013-09-10 | 2013-05-01 | 2013-08-12 |  | 2014-06-10 16:00 | 0 |  | 314 | 0 | 242242031
| 242242036 |  | Wavelength Shifting tests |  |  |  | 2013-09-01 |  |  |  | 2013-10-15 16:00 |  |  |  |  | 242242036 | this activity was claimed 100% by mistake and removed, please add again
1.4.2.2.4.2 LOW THRESHOLD CC | 242242040 |  | Wavelength Shifting Procurement | 2013-06-10 | 2013-06-01 | 2013-06-01 | 2013-10-02 | 2014-07-01 | 2014-08-22 |  | 2014-06-30 | 10 | 20 | 295 | 0 | 242242040
1.4.2.2.4.2 LOW THRESHOLD CC | 242242045 |  | Procurement Lasers | 2013-04-03 | 2013-03-03 | 2013-03-03 |  | 2013-05-30 | 2013-08-29 |  | 2014-01-28 | 80 |  | 284 | 0 | 242242045
1.4.2.2.4.2 LOW THRESHOLD CC | 242242050 |  | Alignment Tool Manufacturing | 2013-04-19 | 2013-08-01 |  | 2013-09-20 | 2013-05-20 | 2013-08-30 |  | 2014-12-15 | 0 |  | 279 | 0 | 242242050
1.4.2.2.4.2 LOW THRESHOLD CC | 242242055 |  | Alignment Tool and Lasers Installation | 2013-05-24 | 2013-09-03 |  | 2013-11-01 | 2013-06-24 | 2013-10-01 |  | 2014-03-18 | 0 |  | 279 | 0 | 242242055
1.4.2.2.4.2 LOW THRESHOLD CC | 242242060 |  | Mirrors Survey | 2013-06-03 | 2013-04-01 | 2013-04-01 |  | 2013-06-24 | 2013-08-22 |  |  | 75 | 100 | 306 | 0 | 242242060
1.4.2.2.4.2 LOW THRESHOLD CC | 242242076 |  | Support Frame Fabrication for 1S in TED | 2013-04-22 | 2013-08-01 |  | 2013-09-05 | 2013-05-22 | 2013-09-03 |  | 2013-12-02 | 0 |  | 535 | 0 | 242242076
1.4.2.2.4.2 LOW THRESHOLD CC | 242242077 |  | Infrastructure Consumables | 2013-03-01 | 2013-03-01 | 2013-03-01 |  | 2014-05-01 | 2014-05-01 |  | 2014-05-01 16:00 | 10 |  | 374 | 0 | 242242077
1.4.2.2.4.2 LOW THRESHOLD CC | 242242085 |  | Quality Control of Elliptical/Hyperbolic mirrors | 2013-08-08 | 2013-10-08 |  | 2013-09-17 | 2014-06-09 | 2014-08-07 |  | 2014-06-09 16:00 | 0 |  | 416 | 0 | 242242085
1.4.2.2.4.2 LOW THRESHOLD CC | 242242090 |  | Dimensions check of Elliptical/Hyperbolic mirrors | 2013-07-30 | 2013-06-03 | 2013-06-03 | 2013-07-30 08:00 | 2014-06-09 | 2014-05-09 |  | 2014-06-09 16:00 | 30 |  | 368 | 0 | 242242090
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092 |  | Al/Mg Deposit Procurement WC | 2013-04-19 | 2013-10-24 |  | 2013-11-10 | 2014-05-13 | 2014-11-17 |  | 2014-11-14 | 0 |  | 235 | 0 | 242242092
1.4.2.2.4.2 LOW THRESHOLD CC | 242242095 |  | Create Manufacturing Drawings | 2013-03-01 | 2013-03-01 | 2013-03-01 |  | 2013-04-05 | 2013-08-13 |  | 2013-10-10 | 80 |  | 288 | 0 | 242242095
1.4.2.2.4.2 LOW THRESHOLD CC | 242242105 |  | Al/Mg Deposit Procurement Prep | 2013-03-19 | 2013-03-01 | 2013-03-01 |  | 2013-06-03 | 2013-08-08 |  | 2013-10-08 | 50 | 60 | 493 | 0 | 242242105
1.4.2.2.4.2 LOW THRESHOLD CC | 242242107 |  | Al/Mg Lexon/Acrylic Re-Coating Test Procurement | 2013-03-01 | 2013-08-01 |  | 2013-09-10 | 2013-07-05 | 2013-12-06 |  | 2013-11-10 | 0 |  | 235 | 0 | 242242107
1.4.2.2.4.2 LOW THRESHOLD CC | 242242108 |  | Lexan/Acrylic/Over- Coating Procurement (all sectors) | 2013-07-09 | 2013-12-10 |  | 2013-11-10 | 2014-05-13 | 2014-10-14 |  | 2014-10-14 | 0 |  | 259 | 0 | 242242108
1.4.2.2.4.2 LOW THRESHOLD CC | 242242110 |  | Al/Mg Deposit Procurement | 2013-04-22 | 2013-10-07 |  | 2013-11-10 | 2014-05-30 | 2014-11-13 |  | 2014-11-14 | 0 |  | 493 | 0 | 242242110
1.4.2.2.4.2 LOW THRESHOLD CC | 242242115 |  | Installation of Elliptical mirrors | 2013-05-10 | 2013-10-25 |  | 2013-11-20 | 2013-05-16 | 2013-10-31 |  | 2014-12-10 | 0 |  | 493 | 0 | 242242115
1.4.2.2.4.2 LOW THRESHOLD CC | 242242137 |  | Glue Procurement | 2013-03-01 | 2013-08-01 |  | 2013-08-25 | 2013-04-26 | 2013-09-27 |  | 2013-10-01 | 0 |  | 517 | 0 | 242242137
1.4.2.2.4.2 LOW THRESHOLD CC | 242242140 |  | Box Walls Simulation | 2013-03-01 | 2013-05-03 | 2013-05-03 |  | 2013-05-03 | 2013-08-14 |  |  | 50 | 100 | 559 | 0 | 242242140
1.4.2.2.4.2 LOW THRESHOLD CC | 242242145a |  | Complete Design Box Walls | 2013-03-01 | 2013-03-01 | 2013-03-01 |  | 2013-05-10 | 2013-08-12 |  | 2013-10-22 | 75 |  | 523 | 0 | 242242145a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242152 |  | Window Procurement | 2013-04-08 | 2013-08-01 |  |  | 2013-11-21 | 2014-03-31 |  |  | 0 |  | 266 | 0 | 242242152
1.4.2.2.4.2 LOW THRESHOLD CC | 242242155 |  | Walls Manufacturing and Installation | 2013-05-15 | 2013-08-15 |  | 2013-10-15 | 2013-06-19 | 2013-09-19 |  | 2014-12-10 | 0 |  | 523 | 0 | 242242155
1.4.2.2.4.2 LOW THRESHOLD CC | 242242161 |  | HV Cables Catalog and Tagging | 2013-03-05 | 2013-08-01 |  | 2013-11-12 | 2013-03-26 | 2013-08-22 |  | 2014-04-18 | 0 |  | 415 | 0 | 242242161
1.4.2.2.4.2 LOW THRESHOLD CC | 242242162 |  | Divider Modifications Design and Test | 2013-03-12 | 2013-05-03 | 2013-05-03 | 2013-09-25 | 2013-04-15 | 2013-08-14 |  | 2014-02-11 | 50 |  | 331 | 0 | 242242162
1.4.2.2.4.2 LOW THRESHOLD CC | 242242163 |  | Divider Modifications Procurement | 2013-04-16 | 2013-08-15 |  | 2014-02-11 | 2013-11-27 | 2014-04-10 |  | 2014-12-02 | 0 |  | 331 | 0 | 242242163
1.4.2.2.4.2 LOW THRESHOLD CC | 242242164 |  | Divider Modifications Implementation | 2013-05-13 | 2013-09-12 |  | 2014-02-11 | 2014-03-04 | 2014-07-02 |  | 2014-12-02 | 0 |  | 331 | 0 | 242242164
1.4.2.2.4.2 LOW THRESHOLD CC | 242242165b |  | Procure Cables Procurement | 2013-04-02 | 2013-08-01 |  | 2013-11-12 | 2013-11-27 | 2014-04-10 |  | 2014-06-24 | 0 |  | 389 | 0 | 242242165b
1.4.2.2.4.2 LOW THRESHOLD CC | 242242169 |  | New Patch Panel Fabrication | 2013-05-28 | 2013-08-01 |  | 2014-02-11 | 2013-12-20 | 2014-03-07 |  | 2014-07-08 | 0 |  | 413 | 0 | 242242169
1.4.2.2.4.2 LOW THRESHOLD CC | 242242170 |  | Patch Panel Connectors Procurement | 2013-03-01 | 2013-03-01 | 2013-03-01 | 2013-09-05 | 2013-11-22 | 2013-11-22 |  | 2014-01-22 | 30 |  | 477 | 0 | 242242170
1.4.2.2.4.2 LOW THRESHOLD CC | 242242185 |  | Procure Gas Line | 2014-10-01 | 2014-10-01 |  |  | 2014-11-14 | 2014-11-14 |  |  | 0 |  | 215 | 0 | 242242185
1.4.2.2.4.2 LOW THRESHOLD CC | 242242190 |  | Install Gas Line (1S) | 2014-11-25 | 2014-11-25 |  |  | 2014-12-10 | 2014-12-10 |  |  | 0 |  | 215 | 0 | 242242190
1.4.2.2.4.2 LOW THRESHOLD CC | 242242195 |  | Gas Line Quality Control | 2014-12-11 | 2014-12-11 |  |  | 2014-12-17 | 2014-12-17 |  |  | 0 |  | 215 | 0 | 242242195
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205 |  | Mirrors Laser Alignments | 2013-06-26 | 2013-10-03 |  | 2014-02-02 | 2014-06-09 | 2014-09-16 |  | 2014-12-16 | 0 |  | 279 | 0 | 242242205
1.4.2.2.4.2 LOW THRESHOLD CC | 242242215 |  | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | 2013-03-12 | 2013-04-01 | 2013-04-01 |  | 2013-04-09 | 2013-08-29 |  | 2013-10-30 | 50 |  | 537 | 0 | 242242215
1.4.2.2.4.2 LOW THRESHOLD CC | 242242220a |  | Online Calibration Design | 2013-06-25 | 2013-08-01 |  |  | 2013-11-08 | 2013-12-18 |  | 2014-06-28 | 0 |  | 320 | 0 | 242242220a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242222 |  | Online HV Matching Design | 2013-06-25 | 2013-08-01 |  |  | 2013-11-08 | 2013-12-18 |  | 2014-06-28 | 0 |  | 320 | 0 | 242242222
1.4.2.2.4.2 LOW THRESHOLD CC | 242242223 |  | Online HV Matching Test | 2013-10-21 | 2013-11-26 |  |  | 2014-03-04 | 2014-04-09 |  | 2014-11-11 | 0 |  | 320 | 0 | 242242223
1.4.2.2.4.2 LOW THRESHOLD CC | 242242225 |  | Online Calibration Test | 2014-03-05 | 2014-04-10 |  |  | 2014-06-11 | 2014-07-18 |  | 2014-11-11 | 0 |  | 320 | 0 | 242242225
1.4.2.2.4.2 LOW THRESHOLD CC | 242242230 |  | PMT Installation | 2013-05-13 | 2013-09-19 |  | 2014-01-20 | 2013-05-17 | 2013-09-25 |  | 2014-11-30 | 0 |  | 288 | 0 | 242242230
1.4.2.2.4.2 LOW THRESHOLD CC | 242242235 |  | Windows Installation 6 sectors | 2013-06-17 | 2013-09-27 |  | 2014-03-01 | 2014-06-23 | 2014-10-03 |  | 2014-12-10 | 0 |  | 266 | 0 | 242242235
1.4.2.2.4.2 LOW THRESHOLD CC | 242242240 |  | Gas Leak Check 6 sectors | 2013-04-19 | 2013-08-01 |  | 2014-05-25 | 2014-06-23 | 2014-10-03 |  | 2015-02-10 | 0 |  | 266 | 0 | 242242240
1.4.2.2.4.2 LOW THRESHOLD CC | 242242245 |  | Simulation of Sagging Test | 2013-03-01 | 2013-05-03 | 2013-05-03 | 2013-10-01 | 2013-07-02 | 2013-10-03 |  | 2014-03-04 | 0 |  | 513 | 0 | 242242245
1.4.2.2.4.2 LOW THRESHOLD CC | 242242255 |  | Procurement Sagging Test Tools | 2013-04-08 | 2013-08-01 |  | 2013-09-10 | 2013-05-24 | 2013-09-19 |  | 2013-11-10 | 0 |  | 497 | 0 | 242242255
1.4.2.2.4.2 LOW THRESHOLD CC | 242242260 |  | Manufacture Sagging Test Tools | 2013-04-08 | 2013-08-01 |  | 2013-10-25 | 2013-05-24 | 2013-09-19 |  | 2013-12-20 | 0 |  | 497 | 0 | 242242260
1.4.2.2.4.2 LOW THRESHOLD CC | 242242265 |  | Transport Counterweght to TED | 2013-05-06 | 2013-08-29 |  |  | 2013-05-31 | 2013-09-25 |  |  | 0 | 100 | 497 | 0 | 242242265
1.4.2.2.4.2 LOW THRESHOLD CC | 242242270 |  | Sagging Test | 2013-06-10 | 2013-10-03 |  | 2014-01-01 | 2013-07-02 | 2013-10-25 |  | 2014-05-25 | 0 |  | 497 | 0 | 242242270
1.4.2.2.4.2 LOW THRESHOLD CC | 242242275 |  | Move Sector in Clean Room | 2013-03-01 | 2013-04-01 | 2013-04-01 |  | 2014-06-03 | 2014-06-03 |  |  | 80 | 100 | 352 | 0 | 242242275
1.4.2.2.4.2 LOW THRESHOLD CC | 242242280 |  | Frame Support | 2013-04-15 | 2013-08-01 |  | 2013-09-20 | 2013-04-19 | 2013-08-07 |  | 2013-12-05 | 0 |  | 565 | 0 | 242242280
1.4.2.2.4.2 LOW THRESHOLD CC | 242242290 |  | Cut Line Mark | 2013-04-29 | 2013-07-15 | 2013-07-15 | 2013-08-20 | 2013-05-01 | 2013-08-05 |  | 2013-09-30 | 20 |  | 550 | 0 | 242242290
1.4.2.2.4.2 LOW THRESHOLD CC | 242242295 |  | Wall Cut-Off | 2013-05-01 | 2013-08-05 |  | 2013-09-30 | 2013-05-08 | 2013-08-12 |  | 2014-04-20 | 0 |  | 550 | 0 | 242242295
1.4.2.2.4.2 LOW THRESHOLD CC | 242242300 |  | Rear Brace Manufacture | 2013-04-17 | 2013-08-23 |  | 2013-09-30 | 2013-04-19 | 2013-08-27 |  | 2014-09-30 | 0 |  | 288 | 0 | 242242300
1.4.2.2.4.2 LOW THRESHOLD CC | 242242305 |  | Rear Brace Installation | 2013-04-19 | 2013-08-27 |  | 2013-10-22 | 2013-05-03 | 2013-09-11 |  | 2014-07-22 | 0 |  | 288 | 0 | 242242305
1.4.2.2.4.2 LOW THRESHOLD CC | 242242310 |  | PMTS, Mirrors Holes Drill | 2013-05-06 | 2013-09-12 |  | 2013-09-05 | 2013-05-10 | 2013-09-18 |  | 2014-08-19 | 0 |  | 288 | 0 | 242242310
1.4.2.2.4.2 LOW THRESHOLD CC | 242242315 |  | Patch Panel Installation | 2013-05-20 | 2013-09-26 |  | 2014-02-11 | 2013-05-30 | 2013-10-07 |  | 2014-10-30 | 0 |  | 540 | 0 | 242242315
1.4.2.2.4.2 LOW THRESHOLD CC | 242242320 |  | Nose Extension Installation | 2013-05-20 | 2013-09-26 |  | 2014-01-20 | 2013-05-30 | 2013-10-07 |  | 2014-10-30 | 0 |  | 540 | 0 | 242242320
1.4.2.2.4.2 LOW THRESHOLD CC | 242242325 |  | Spine Refurbish | 2013-06-03 | 2013-05-06 | 2013-05-06 |  | 2013-06-07 | 2013-08-15 |  | 2014-10-20 | 0 |  | 537 | 0 | 242242325
1.4.2.2.4.2 LOW THRESHOLD CC | 242242330 |  | Gas Line Refurbish | 2013-06-10 | 2013-08-16 |  | 2014-02-25 | 2013-06-21 | 2013-08-29 |  | 2014-10-20 | 0 |  | 537 | 0 | 242242330
1.4.2.2.4.2 LOW THRESHOLD CC | 242242335 |  | Box Refurbish Consumables | 2013-03-01 | 2013-07-01 | 2013-07-01 |  | 2014-03-12 | 2014-03-12 |  | 2014-10-20 | 0 |  | 410 | 0 | 242242335
1.4.2.2.4.2 LOW THRESHOLD CC | 242242340 |  | Sector 2 Box Refurbish | 2013-07-01 | 2013-04-01 | 2013-04-01 | 2013-10-30 | 2013-09-12 | 2013-09-12 |  | 2013-12-10 | 20 |  | 472 | 0 | 242242340 | Box refurbishment a requirement for each sector activities
1.4.2.2.4.2 LOW THRESHOLD CC | 242242350 |  | Sector 2 Mirrors Alignment | 2013-09-12 | 2013-09-12 |  | 2014-04-15 | 2013-09-18 | 2013-09-18 |  | 2014-06-24 | 0 |  | 472 | 0 | 242242350
1.4.2.2.4.2 LOW THRESHOLD CC | 242242355 |  | Sector 2 Windows Installation | 2013-09-19 | 2013-09-19 |  | 2014-06-30 | 2013-09-23 | 2013-09-23 |  | 2014-07-15 | 0 |  | 472 | 0 | 242242355
1.4.2.2.4.2 LOW THRESHOLD CC | 242242360 |  | Sector 2 Gas Leaks Checks | 2013-09-24 | 2013-09-24 |  | 2014-08-04 | 2013-10-02 | 2013-10-02 |  | 2014-09-09 | 0 |  | 472 | 0 | 242242360
1.4.2.2.4.2 LOW THRESHOLD CC | 242242365 |  | Sector 3 Box Refurbish | 2013-10-03 | 2013-06-03 | 2013-06-03 | 2014-01-21 | 2013-11-20 | 2013-11-20 |  | 2014-02-18 | 20 |  | 436 | 0 | 242242365 | Box refurbishment a requirement for each sector activities
1.4.2.2.4.2 LOW THRESHOLD CC | 242242375 |  | Sector 3 Mirrors Alignment | 2013-11-20 | 2013-11-20 |  | 2014-07-21 | 2013-11-26 | 2013-11-26 |  | 2014-08-26 | 0 |  | 436 | 0 | 242242375
1.4.2.2.4.2 LOW THRESHOLD CC | 242242380 |  | Sector 3 Windows Installation | 2013-11-27 | 2013-11-27 |  | 2014-08-26 | 2013-12-05 | 2013-12-05 |  | 2014-09-16 | 0 |  | 436 | 0 | 242242380
1.4.2.2.4.2 LOW THRESHOLD CC | 242242385 |  | Sector 3 Gas Leaks Checks | 2013-12-06 | 2013-12-06 |  | 2014-09-30 | 2013-12-12 | 2013-12-12 |  | 2014-10-29 | 0 |  | 436 | 0 | 242242385
1.4.2.2.4.2 LOW THRESHOLD CC | 242242390 |  | Sector 4 Box Refurbish | 2013-12-02 | 2013-06-03 | 2013-06-03 | 2014-03-03 | 2014-01-28 | 2014-01-28 |  | 2014-04-08 | 20 |  | 409 | 0 | 242242390 | Box refurbishment a requirement for each sector activities
1.4.2.2.4.2 LOW THRESHOLD CC | 242242400 |  | Sector 4 Mirrors Alignment | 2014-01-29 | 2014-01-29 |  | 2014-09-23 | 2014-02-03 | 2014-02-03 |  | 2014-10-28 | 0 |  | 409 | 0 | 242242400
1.4.2.2.4.2 LOW THRESHOLD CC | 242242405 |  | Sector 4 Windows Installation | 2014-02-04 | 2014-02-04 |  | 2014-10-28 | 2014-02-10 | 2014-02-10 |  | 2014-11-18 | 0 |  | 409 | 0 | 242242405
1.4.2.2.4.2 LOW THRESHOLD CC | 242242410 |  | Sector 4 Gas Leaks Checks | 2014-02-11 | 2014-02-11 |  | 2014-11-25 | 2014-02-17 | 2014-02-17 |  | 2014-12-16 | 0 |  | 409 | 0 | 242242410
1.4.2.2.4.2 LOW THRESHOLD CC | 242242415 |  | Sector 5 Box Refurbish | 2014-02-18 | 2013-06-03 | 2013-06-03 | 2014-04-14 | 2014-03-24 | 2014-03-24 |  | 2014-05-13 | 20 |  | 380 | 0 | 242242415 | Box refurbishment a requirement for each sector activities
1.4.2.2.4.2 LOW THRESHOLD CC | 242242425 |  | Sector 5 Mirrors Alignment | 2014-03-25 | 2014-03-25 |  | 2014-10-28 | 2014-03-31 | 2014-03-31 |  | 2014-11-11 | 0 |  | 380 | 0 | 242242425
1.4.2.2.4.2 LOW THRESHOLD CC | 242242430 |  | Sector 5 Windows Installation | 2014-04-01 | 2014-04-01 |  | 2014-11-25 | 2014-04-07 | 2014-04-07 |  | 2014-12-16 | 0 |  | 380 | 0 | 242242430
1.4.2.2.4.2 LOW THRESHOLD CC | 242242435 |  | Sector 5 Gas Leaks Checks | 2014-04-08 | 2014-04-08 |  | 2014-12-16 | 2014-04-14 | 2014-04-14 |  | 2015-01-20 | 0 |  | 380 | 0 | 242242435
1.4.2.2.4.2 LOW THRESHOLD CC | 242242440 |  | Sector 6 Box Refurbish | 2014-04-15 | 2013-06-03 | 2013-06-03 | 2014-05-27 | 2014-05-16 | 2014-05-16 |  | 2014-06-17 | 20 |  | 351 | 0 | 242242440 | Box refurbishment a requirement for each sector activities
1.4.2.2.4.2 LOW THRESHOLD CC | 242242450 |  | Sector 6 Mirrors Alignment | 2014-05-15 | 2014-05-15 |  | 2014-11-25 | 2014-05-21 | 2014-05-21 |  | 2014-12-16 | 0 |  | 351 | 0 | 242242450
1.4.2.2.4.2 LOW THRESHOLD CC | 242242455 |  | Sector 6 Windows Installation | 2014-05-22 | 2014-05-22 |  | 2014-12-16 | 2014-05-29 | 2014-05-29 |  | 2015-01-20 | 0 |  | 351 | 0 | 242242455
1.4.2.2.4.2 LOW THRESHOLD CC | 242242460 |  | Sector 6 Gas Leaks Checks | 2014-05-29 | 2014-05-29 |  | 2015-01-20 | 2014-06-04 | 2014-06-04 |  | 2015-02-10 | 0 |  | 351 | 0 | 242242460
1.4.2.2.4.2 LOW THRESHOLD CC | 242242500M | M | LTCC Complete |  |  |  | 2015-02-10 | 2014-12-17 | 2014-12-17 |  | 2015-02-10 | 0 |  | 215 | M | 242242500M