## Template
12 GeV July 2014 STATUS UPDATE
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID
ELOUADRHIRI L
1.4.2.2.4.2 LOW THRESHOLD CC | 242242030 | Z | Quality Control of PMTs | 2014-05-02 | 2014-05-02 | 2014-05-02 |  | 2014-05-19 | 2014-05-19 | 2014-05-19 |  | 100 |  |  | Z | 242242030
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031 | U | Quality Control of Existing PMTs FY13 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2014-11-10 | 2014-11-10 |  |  | 20 |  | 127 | U | 242242031 | We are setting up QA for first article. There are no issue with this activity.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242031a | U | Quality Control of Existing PMTs FY14 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2014-11-10 | 2014-11-10 |  |  | 20 |  | 127 | U | 242242031a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242036 | H | Wavelength Shifting tests Labor/Expenses FY13 | 2013-09-03 | 2013-09-03 | 2013-09-03 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | H | 242242036
1.4.2.2.4.2 LOW THRESHOLD CC | 242242036a | H | Wavelength Shifting tests Labor/Expenses FY14 | 2013-09-03 | 2013-09-03 | 2013-09-03 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | H | 242242036a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242040 | D | Wavelength Shifting Procurement (Temple) | 2014-04-01 | 2014-04-01 | 2014-04-01 |  | 2014-11-07 | 2014-11-07 |  |  | 10 | 20 | 276 | D | 242242040 | We are setting up QA for first article. There are no issue with this activity.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242045 | D | Procurement Lasers - Procurement | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-10-21 | 2013-10-21 | 2013-10-21 |  | 100 |  |  | D | 242242045
1.4.2.2.4.2 LOW THRESHOLD CC | 242242045a | D | Procurement Lasers - Labor FY13 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-10-21 | 2013-10-21 | 2013-10-21 |  | 100 |  |  | D | 242242045a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242045b | D | Procurement Lasers - Labor FY14 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-10-21 | 2013-10-21 | 2013-10-21 |  | 100 |  |  | D | 242242045b
1.4.2.2.4.2 LOW THRESHOLD CC | 242242050 | D | Alignment Tool Manufacturing Labor/Expenses FY13 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | D | 242242050
1.4.2.2.4.2 LOW THRESHOLD CC | 242242050a | D | Alignment Tool Manufacturing Labor/Expenses FY14 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | D | 242242050a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242055 | S | Alignment Tool and Lasers Installation | 2013-11-04 | 2013-11-04 | 2013-11-04 |  | 2014-07-14 | 2014-07-14 |  | 2014-10-26 | 15 |  | 169 | S | 242242055 | The laser is ready, waiting for LTCC frame support fabrication.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242076 | D | Support Frame Fabrication for 1S in TED | 2014-07-01 | 2014-07-01 |  |  | 2014-09-25 | 2014-09-25 |  |  | 0 |  | 307 | D | 242242076 | Drawing in progress (J. Guerra).
1.4.2.2.4.2 LOW THRESHOLD CC | 242242077 | D | Infrastructure Consumables | 2013-12-03 | 2013-12-03 | 2013-12-03 |  | 2014-08-25 | 2014-08-25 |  |  | 70 | 80 | 329 | D | 242242077
1.4.2.2.4.2 LOW THRESHOLD CC | 242242085 | S | Quality Control of Elliptical/Hyperbolic mirrors | 2013-11-04 | 2013-11-04 | 2013-11-04 |  | 2014-08-25 | 2014-08-25 |  |  | 30 | 50 | 463 | S | 242242085 | No issues.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242090 | U | Dimensions check of Elliptical/Hyperbolic mirrors | 2014-03-03 | 2014-03-03 | 2014-03-03 |  | 2014-10-30 | 2014-10-30 |  |  | 50 |  | 282 | U | 242242090 | No issues.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242092 | U | Al/Mg Deposit Procurement WC | 2014-05-02 | 2014-05-02 | 2014-05-02 |  | 2014-07-31 | 2014-07-31 |  | 2014-11-21 | 0 |  | 346 | U | 242242092 | Setup for testing completed. WC re-coating production expected to start 8/11. Reason for delay: looked for several setup, all busy/unavailable. Will use HTCC setup, available in July.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242095 | H | Create Manufacturing Drawings FY13 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-11-18 | 2013-11-18 | 2013-11-18 |  | 100 |  |  | H | 242242095
1.4.2.2.4.2 LOW THRESHOLD CC | 242242095a | H | Create Manufacturing Drawings FY14 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-11-18 | 2013-11-18 | 2013-11-18 |  | 100 |  |  | H | 242242095a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242105 | H | Al/Mg Deposit Procurement Prep FY13 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | H | 242242105
1.4.2.2.4.2 LOW THRESHOLD CC | 242242105a | H | Al/Mg Deposit Procurement Prep FY14 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | H | 242242105a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242107 | H | Al/Mg Lexan/Acrylic Re-Coating Test Procurement Labor FY13 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | H | 242242107
1.4.2.2.4.2 LOW THRESHOLD CC | 242242107a | H | Al/Mg Lexan/Acrylic Re-Coating Test Procurement Labor FY14 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | H | 242242107a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242108 | U | Lexan/Acrylic/Over- Coating Procurement (all sectors) | 2014-02-03 | 2014-02-03 | 2014-02-03 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | U | 242242108
1.4.2.2.4.2 LOW THRESHOLD CC | 242242110 | D | Al/Mg Deposit Procurement (Lexan Strips) | 2014-04-14 | 2014-04-14 | 2014-04-14 |  | 2015-06-18 | 2015-06-18 |  |  | 20 | 80 | 143 | D | 242242110 | Some quality issue being addressed by the company. Other than that, this project has no issue.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242115 | H | Installation of Elliptical mirrors | 2014-07-29 | 2014-07-29 |  | 2014-09-02 | 2015-05-29 | 2015-05-29 |  |  | 0 |  | 143 | H | 242242115 | Box not assembled yet.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242137 | D | Glue Procurement | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-07-30 | 2014-07-30 |  | 2014-10-17 | 40 | 80 | 347 | D | 242242137 | We have most of the glue.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242145a | H | Complete Design Box Walls FY13 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-11-18 | 2013-11-18 | 2013-11-18 |  | 100 |  |  | H | 242242145a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242145aa | H | Complete Design Box Walls FY14 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-11-18 | 2013-11-18 | 2013-11-18 |  | 100 |  |  | H | 242242145aa
1.4.2.2.4.2 LOW THRESHOLD CC | 242242152 | D | Window Procurement | 2013-11-12 | 2013-11-12 | 2013-11-12 |  | 2014-08-04 | 2014-08-04 |  | 2014-10-12 | 30 |  | 132 | D | 242242152 | Vendor is identified, we have several communications. Quote expected on 7/31/2014
1.4.2.2.4.2 LOW THRESHOLD CC | 242242152a | D | Window Procurement - Labor FY13 | 2013-11-12 | 2013-11-12 | 2013-11-12 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | D | 242242152a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242152b | D | Window Procurement -Labor FY14 | 2013-11-12 | 2013-11-12 | 2013-11-12 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | D | 242242152b
1.4.2.2.4.2 LOW THRESHOLD CC | 242242155 | H | Walls Manufacturing and Installation | 2014-05-02 | 2014-05-02 | 2014-05-02 |  | 2014-07-25 | 2014-07-25 |  |  | 50 |  | 350 | H | 242242155 | Vendor delivered some parts (1 sector). Waiting for more parts, vendor may be busy with Torus.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242161 | H | HV Cables Catalog and Tagging | 2013-10-14 | 2013-10-14 | 2013-10-14 |  | 2014-05-19 | 2014-05-19 | 2014-05-19 |  | 100 |  |  | H | 242242161
1.4.2.2.4.2 LOW THRESHOLD CC | 242242162 | H | Divider Modifications Design and Test | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | H | 242242162
1.4.2.2.4.2 LOW THRESHOLD CC | 242242163 | D | Divider Modifications Procurement | 2014-03-03 | 2014-03-03 | 2014-03-03 |  | 2015-02-04 | 2015-02-04 |  |  | 0 |  | 315 | D | 242242163 | Waiting on Popov availability.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242164 | U | Divider Modifications Implementation | 2014-03-03 | 2014-03-03 | 2014-03-03 |  | 2015-01-13 | 2015-01-13 |  |  | 0 |  | 239 | U | 242242164
1.4.2.2.4.2 LOW THRESHOLD CC | 242242165b | D | Procure Cables Procurement | 2014-02-03 | 2014-02-03 | 2014-02-03 |  | 2014-09-30 | 2014-09-30 |  |  | 80 |  | 304 | D | 242242165b | Nemo connectors last thing to be bought.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242169 | D | New Patch Panel Fabrication | 2014-04-07 | 2014-04-07 | 2014-04-07 |  | 2014-10-20 | 2014-10-20 | 2014-07-16 |  | 10 | 100 | 290 | D | 242242169 | All six sectors patch panel received.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242170 | D | Patch Panel Connectors Procurement | 2014-02-03 | 2014-02-03 | 2014-02-03 |  | 2014-04-21 | 2014-04-21 | 2014-04-21 |  | 100 |  |  | D | 242242170
1.4.2.2.4.2 LOW THRESHOLD CC | 242242185 | D | Procure Gas Line | 2014-06-02 | 2014-06-02 | 2014-06-02 |  | 2014-11-14 | 2014-11-14 |  | 2014-11-16 | 50 |  | 250 | D | 242242185
1.4.2.2.4.2 LOW THRESHOLD CC | 242242190 | H | Install Gas Line (1S) | 2014-11-25 | 2014-11-25 |  |  | 2014-12-10 | 2014-12-10 |  |  | 0 |  | 250 | H | 242242190
1.4.2.2.4.2 LOW THRESHOLD CC | 242242195 | H | Gas Line Quality Control | 2014-12-11 | 2014-12-11 |  |  | 2014-12-17 | 2014-12-17 |  |  | 0 |  | 250 | H | 242242195
1.4.2.2.4.2 LOW THRESHOLD CC | 242242205 | S | Mirrors Laser Alignments | 2014-07-01 | 2014-07-01 |  | 2014-10-06 | 2015-05-26 | 2015-05-26 |  |  | 0 |  | 146 | S | 242242205 | Contingent on box assembly
1.4.2.2.4.2 LOW THRESHOLD CC | 242242215 | H | Installation of FADC, DAQ, Computer, Electronics for 1 Sector | 2014-10-01 | 2014-10-01 |  | 2014-09-08 | 2014-12-01 | 2014-12-01 |  |  | 0 |  | 262 | H | 242242215
1.4.2.2.4.2 LOW THRESHOLD CC | 242242220a | S | Online Calibration Design FY13 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2014-11-26 | 2014-11-26 |  |  | 0 |  | 168 | S | 242242220a | Project Started. M. Ungaro responsible for it. Project will pick up in September.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242220aa | S | Online Calibration Design FY14 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2014-11-26 | 2014-11-26 |  |  | 0 |  | 168 | S | 242242220aa
1.4.2.2.4.2 LOW THRESHOLD CC | 242242222 | S | Online HV Matching Design FY13 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2014-11-26 | 2014-11-26 |  |  | 0 |  | 168 | S | 242242222
1.4.2.2.4.2 LOW THRESHOLD CC | 242242222a | S | Online HV Matching Design FY14 | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2014-11-26 | 2014-11-26 |  |  | 0 |  | 168 | S | 242242222a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242223 | S | Online HV Matching Test | 2014-11-06 | 2014-11-06 |  |  | 2015-04-23 | 2015-04-23 |  |  | 0 |  | 168 | S | 242242223
1.4.2.2.4.2 LOW THRESHOLD CC | 242242225 | H | Online Calibration Test | 2015-03-23 | 2015-03-23 |  |  | 2015-04-23 | 2015-04-23 |  |  | 0 |  | 168 | H | 242242225
1.4.2.2.4.2 LOW THRESHOLD CC | 242242230 | H | PMT Installation | 2014-08-29 | 2014-08-29 |  | 2014-10-06 | 2015-07-23 | 2015-07-23 |  |  | 0 |  | 127 | H | 242242230 | Contingent on box assembly
1.4.2.2.4.2 LOW THRESHOLD CC | 242242235 | U | Windows Installation 6 sectors | 2014-07-15 | 2014-07-15 |  | 2014-11-10 | 2015-05-04 | 2015-05-04 |  |  | 0 |  | 127 | U | 242242235 | Contingent on box assembly, PMTs and Mirrors mounted.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242240 | S | Gas Leak Check 6 sectors | 2014-10-06 | 2014-10-06 |  |  | 2015-06-24 | 2015-06-24 |  |  | 0 |  | 127 | S | 242242240
1.4.2.2.4.2 LOW THRESHOLD CC | 242242245 | H | Simulation of Sagging Test | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | H | 242242245
1.4.2.2.4.2 LOW THRESHOLD CC | 242242255 | D | Procurement Sagging Test Tools | 2013-12-09 | 2013-12-09 | 2013-12-09 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | D | 242242255
1.4.2.2.4.2 LOW THRESHOLD CC | 242242260 | H | Manufacture Sagging Test Tools | 2013-11-04 | 2013-11-04 | 2013-11-04 |  | 2014-02-17 | 2014-02-17 | 2014-02-17 |  | 100 |  |  | H | 242242260
1.4.2.2.4.2 LOW THRESHOLD CC | 242242270 | S | Sagging Test | 2013-12-09 | 2013-12-09 | 2013-12-09 |  | 2014-05-19 | 2014-05-19 | 2014-05-19 |  | 100 |  |  | S | 242242270
1.4.2.2.4.2 LOW THRESHOLD CC | 242242280 | H | Frame Support FY13 | 2015-01-05 | 2015-01-05 |  |  | 2015-03-05 | 2015-03-05 |  |  | 0 |  | 203 | H | 242242280
1.4.2.2.4.2 LOW THRESHOLD CC | 242242280a | H | Frame Support FY14 | 2015-01-05 | 2015-01-05 |  |  | 2015-03-05 | 2015-03-05 |  |  | 0 |  | 203 | H | 242242280a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242290 | H | Cut Line Mark | 2013-10-01 | 2013-10-01 | 2013-10-01 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | H | 242242290
1.4.2.2.4.2 LOW THRESHOLD CC | 242242295 | H | Wall Cut-Off FY13 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | H | 242242295
1.4.2.2.4.2 LOW THRESHOLD CC | 242242295a | H | Wall Cut-Off FY14 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2013-12-20 | 2013-12-20 | 2013-12-20 |  | 100 |  |  | H | 242242295a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242300 | H | Rear Brace Manufacture | 2014-05-02 | 2014-05-02 | 2014-05-02 |  | 2014-08-14 | 2014-08-14 |  |  | 50 |  | 260 | H | 242242300 | Parts being fabricated at Vision (Hampton). Production slowed down.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242305 | H | Rear Brace Installation | 2014-08-15 | 2014-08-15 |  |  | 2015-03-11 | 2015-03-11 |  |  | 0 |  | 260 | H | 242242305
1.4.2.2.4.2 LOW THRESHOLD CC | 242242310 | H | PMTS, Mirrors Holes Drill | 2013-09-03 | 2013-09-03 | 2013-09-03 |  | 2014-03-17 | 2014-03-17 | 2014-03-17 |  | 100 |  |  | H | 242242310
1.4.2.2.4.2 LOW THRESHOLD CC | 242242315 | H | Patch Panel Installation | 2014-08-28 | 2014-08-28 |  |  | 2015-03-10 | 2015-03-10 |  |  | 0 |  | 370 | H | 242242315
1.4.2.2.4.2 LOW THRESHOLD CC | 242242320 | H | Nose Extension Installation | 2014-07-01 | 2014-07-01 |  | 2014-07-02 | 2015-01-08 | 2015-01-08 |  |  | 0 |  | 411 | H | 242242320 | Parts being fabricated at Vision (Hampton). Production slowed down.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242325 | H | Spine Refurbish FY13 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-10-17 | 2014-10-17 |  |  | 50 |  | 312 | H | 242242325
1.4.2.2.4.2 LOW THRESHOLD CC | 242242325a | H | Spine Refurbish FY14 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-10-17 | 2014-10-17 |  |  | 50 |  | 312 | H | 242242325a
1.4.2.2.4.2 LOW THRESHOLD CC | 242242330 | H | Gas Line Refurbish | 2014-07-01 | 2014-07-01 |  |  | 2015-02-04 | 2015-02-04 |  |  | 0 |  | 224 | H | 242242330
1.4.2.2.4.2 LOW THRESHOLD CC | 242242335 | D | Box Refurbish Consumables | 2013-11-01 | 2013-11-01 | 2013-11-01 |  | 2014-03-17 | 2014-03-17 | 2014-03-17 |  | 100 |  |  | D | 242242335
1.4.2.2.4.2 LOW THRESHOLD CC | 242242340 | S | Sector 2 Box Refurbish | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-07-30 | 2014-07-30 |  |  | 25 |  | 85 | S | 242242340 | Parts being fabricated at Vision (Hampton). Production slowed down.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242350 | H | Sector 2 Mirrors Alignment | 2014-10-24 | 2014-10-24 |  |  | 2015-01-15 | 2015-01-15 |  |  | 0 |  | 85 | H | 242242350
1.4.2.2.4.2 LOW THRESHOLD CC | 242242355 | H | Sector 2 Windows Installation | 2015-01-22 | 2015-01-22 |  |  | 2015-02-05 | 2015-02-05 |  |  | 0 |  | 85 | H | 242242355
1.4.2.2.4.2 LOW THRESHOLD CC | 242242360 | H | Sector 2 Gas Leaks Checks | 2015-02-25 | 2015-02-25 |  |  | 2015-04-01 | 2015-04-01 |  |  | 0 |  | 280 | H | 242242360
1.4.2.2.4.2 LOW THRESHOLD CC | 242242365 | S | Sector 3 Box Refurbish | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-07-30 | 2014-07-30 |  |  | 25 |  | 214 | S | 242242365 | Parts being fabricated at Vision (Hampton). Production slowed down.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242375 | H | Sector 3 Mirrors Alignment | 2015-02-12 | 2015-02-12 |  |  | 2015-03-19 | 2015-03-19 |  |  | 0 |  | 85 | H | 242242375
1.4.2.2.4.2 LOW THRESHOLD CC | 242242380 | H | Sector 3 Windows Installation | 2015-03-20 | 2015-03-20 |  |  | 2015-04-08 | 2015-04-08 |  |  | 0 |  | 85 | H | 242242380
1.4.2.2.4.2 LOW THRESHOLD CC | 242242385 | H | Sector 3 Gas Leaks Checks | 2015-04-22 | 2015-04-22 |  |  | 2015-05-21 | 2015-05-21 |  |  | 0 |  | 540 | H | 242242385
1.4.2.2.4.2 LOW THRESHOLD CC | 242242390 | S | Sector 4 Box Refurbish | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-07-25 | 2014-07-25 |  |  | 25 |  | 260 | S | 242242390 | Parts being fabricated at Vision (Hampton). Production slowed down.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242400 | H | Sector 4 Mirrors Alignment | 2015-04-15 | 2015-04-15 |  |  | 2015-05-20 | 2015-05-20 |  |  | 0 |  | 85 | H | 242242400
1.4.2.2.4.2 LOW THRESHOLD CC | 242242405 | H | Sector 4 Windows Installation | 2015-05-21 | 2015-05-21 |  |  | 2015-06-12 | 2015-06-12 |  |  | 0 |  | 544 | H | 242242405
1.4.2.2.4.2 LOW THRESHOLD CC | 242242410 | H | Sector 4 Gas Leaks Checks | 2015-06-22 | 2015-06-22 |  |  | 2015-07-09 | 2015-07-09 |  |  | 0 |  | 544 | H | 242242410
1.4.2.2.4.2 LOW THRESHOLD CC | 242242415 | S | Sector 5 Box Refurbish | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-07-11 | 2014-07-11 |  |  | 25 |  | 296 | S | 242242415 | Parts being fabricated at Vision (Hampton). Production slowed down.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242425 | H | Sector 5 Mirrors Alignment | 2015-05-21 | 2015-05-21 |  |  | 2015-06-05 | 2015-06-05 |  |  | 0 |  | 85 | H | 242242425
1.4.2.2.4.2 LOW THRESHOLD CC | 242242430 | H | Sector 5 Windows Installation | 2015-06-22 | 2015-06-22 |  |  | 2015-07-09 | 2015-07-09 |  |  | 0 |  | 538 | H | 242242430
1.4.2.2.4.2 LOW THRESHOLD CC | 242242435 | H | Sector 5 Gas Leaks Checks | 2015-07-10 | 2015-07-10 |  |  | 2015-07-31 | 2015-07-31 |  |  | 0 |  | 538 | H | 242242435
1.4.2.2.4.2 LOW THRESHOLD CC | 242242440 | S | Sector 6 Box Refurbish | 2013-12-02 | 2013-12-02 | 2013-12-02 |  | 2014-07-18 | 2014-07-18 |  |  | 25 |  | 313 | S | 242242440 | Parts being fabricated at Vision (Hampton). Production slowed down.
1.4.2.2.4.2 LOW THRESHOLD CC | 242242450 | H | Sector 6 Mirrors Alignment | 2015-06-22 | 2015-06-22 |  |  | 2015-07-09 | 2015-07-09 |  |  | 0 |  | 85 | H | 242242450
1.4.2.2.4.2 LOW THRESHOLD CC | 242242455 | H | Sector 6 Windows Installation | 2015-07-10 | 2015-07-10 |  |  | 2015-07-31 | 2015-07-31 |  |  | 0 |  | 85 | H | 242242455
1.4.2.2.4.2 LOW THRESHOLD CC | 242242460 | H | Sector 6 Gas Leaks Checks | 2015-07-31 | 2015-07-31 |  |  | 2015-08-21 | 2015-08-21 |  |  | 0 |  | 85 | H | 242242460
1.4.2.2.4.2 LOW THRESHOLD CC | 242242500M | M | LTCC Complete |  |  |  |  | 2015-08-21 | 2015-08-21 |  |  | 0 |  | 85 | M | 242242500M