## Template
12 GeV December 2015 STATUS UPDATE
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID
YOUNG G
1.4.2.2.4.2 LOW THRESHOLD CC | 242242750 | H | Sector 5 - Window Installation | 2015-08-07 | 2015-12-01 | 2015-12-02 |  | 2015-08-12 | 2015-12-03 | 2015-12-15 |  | 0 | 100 | 389 | H | 242242750
1.4.2.2.4.2 LOW THRESHOLD CC | 242242755 | H | Sector 5 - Window Gas Leaks Checks | 2015-08-13 | 2015-12-04 | 2015-12-15 |  | 2015-08-19 | 2015-12-08 | 2015-12-22 |  | 0 | 100 | 389 | H | 242242755
1.4.2.2.4.2 LOW THRESHOLD CC | 242242765 | M | Sector 5 Complete |  |  |  |  | 2015-08-19 | 2015-12-08 | 2015-12-23 |  | 0 | 100 | 389 | M | 242242765
1.4.2.2.4.2 LOW THRESHOLD CC | 242242775 | S | Sector 6 - Hardware Installation | 2015-08-13 | 2015-11-17 | 2015-11-17 |  | 2015-09-03 | 2015-12-08 | 2015-12-17 |  | 23.5 | 100 | 381 | S | 242242775
1.4.2.2.4.2 LOW THRESHOLD CC | 242242780 | H | Sector 6 - Mirror Alignment | 2015-09-04 | 2015-12-09 | 2015-12-17 |  | 2015-09-11 | 2015-12-14 | 2015-12-23 |  | 0 | 100 | 381 | H | 242242780
1.4.2.2.4.2 LOW THRESHOLD CC | 242242785 | H | Sector 6 - Fiducialization | 2015-09-14 | 2015-12-09 | 2015-12-22 |  | 2015-09-15 | 2015-12-10 | 2015-12-23 |  | 0 | 100 | 381 | H | 242242785
1.4.2.2.4.2 LOW THRESHOLD CC | 242242795 | H | Sector 6 - Window Installation | 2015-09-16 | 2015-12-11 | 2016-01-04 |  | 2015-09-21 | 2015-12-16 |  | 2015-01-12 | 0 |  | 381 | H | 242242795
1.4.2.2.4.2 LOW THRESHOLD CC | 242242800 | H | Sector 6 - Window Gas Leaks Checks | 2015-09-22 | 2015-12-17 |  | 2015-01-12 | 2015-09-28 | 2015-12-18 |  | 2015-01-15 | 0 |  | 381 | H | 242242800
1.4.2.2.4.2 LOW THRESHOLD CC | 242242805 | U | Sector 6 - Consumables | 2015-06-12 | 2015-07-07 | 2015-07-07 |  | 2015-09-24 | 2015-12-21 |  | 2015-12-23 | 90 | 100 | 380 | U | 242242805
1.4.2.2.4.2 LOW THRESHOLD CC | 242242810 | M | Sector 6 Complete |  |  |  |  | 2015-09-28 | 2015-12-21 |  |  | 0 |  | 380 | M | 242242810
1.4.2.2.4.2 LOW THRESHOLD CC | 242242900M | M | LTCC Complete |  |  |  |  | 2015-09-28 | 2015-12-21 |  |  | 0 |  | 380 | M | 242242900M