## Template
12 GeV July 2015 STATUS UPDATE
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID
YOUNG G
1.4.2.2.4.2 LOW THRESHOLD CC | 242242505 | H | Wait (Wait Period from Funding Milestone) | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | 2014-12-23 | 2014-12-23 | 2014-12-23 |  | 100 |  |  | H | 242242505
1.4.2.2.4.2 LOW THRESHOLD CC | 242242510 | H | Reverse Entry (Per CR15-004 FY15 ETC) | 2015-01-05 | 2015-01-05 | 2015-01-05 |  | 2015-01-05 | 2015-01-05 | 2015-01-05 |  | 100 |  |  | H | 242242510
1.4.2.2.4.2 LOW THRESHOLD CC | 242242512 | U | Al/Mg Deposit Procurement WC Procurement | 2015-01-05 | 2015-01-05 | 2015-01-05 |  | 2015-02-13 | 2015-08-20 |  |  | 90 |  | 433 | U | 242242512
1.4.2.2.4.2 LOW THRESHOLD CC | 242242515 | H | Wait (Wait Period from Funding Milestone) | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | 2015-01-30 | 2015-01-30 | 2015-01-30 |  | 100 |  |  | H | 242242515
1.4.2.2.4.2 LOW THRESHOLD CC | 242242517 | U | Additional Al/Mg Deposit WC Procurement | 2015-02-02 | 2015-04-01 | 2015-04-01 |  | 2015-03-31 | 2015-09-21 |  |  | 0 |  | 433 | U | 242242517
1.4.2.2.4.2 LOW THRESHOLD CC | 242242522 | H | Wait (Wait Period from Funding Milestone) | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | 2015-02-16 | 2015-02-16 | 2015-02-16 |  | 100 |  |  | H | 242242522
1.4.2.2.4.2 LOW THRESHOLD CC | 242242525 | H | Additional WC Testing | 2015-02-17 | 2015-04-21 | 2015-04-21 |  | 2015-03-20 | 2015-09-21 |  |  | 50 |  | 433 | H | 242242525
1.4.2.2.4.2 LOW THRESHOLD CC | 242242530 | U | Divider Installation | 2015-01-05 | 2015-04-01 | 2015-04-01 |  | 2015-03-16 | 2015-07-30 |  | 2015-08-15 | 82 | 90 | 469 | U | 242242530
1.4.2.2.4.2 LOW THRESHOLD CC | 242242535 | U | Divider Consumables | 2015-01-05 | 2015-02-02 | 2015-02-02 |  | 2015-03-16 | 2015-03-16 | 2015-03-16 |  | 100 |  |  | U | 242242535
1.4.2.2.4.2 LOW THRESHOLD CC | 242242537 | H | Wait (Wait Period from Funding Milestone) | 2014-10-01 | 2014-10-01 | 2014-10-01 |  | 2015-01-12 | 2015-01-12 | 2015-01-12 |  | 100 |  |  | H | 242242537
1.4.2.2.4.2 LOW THRESHOLD CC | 242242540 | H | Frame Support Installation | 2015-01-13 | 2015-01-05 | 2015-01-05 |  | 2015-02-05 | 2015-01-19 | 2015-01-19 |  | 100 |  |  | H | 242242540
1.4.2.2.4.2 LOW THRESHOLD CC | 242242545 | H | Sector 1 - Prep Box | 2015-01-05 | 2015-01-05 | 2015-01-05 |  | 2015-01-12 | 2015-01-09 | 2015-01-09 |  | 100 |  |  | H | 242242545
1.4.2.2.4.2 LOW THRESHOLD CC | 242242550 | S | Sector 1 - Hardware Installation | 2015-01-13 | 2015-01-23 | 2015-01-23 |  | 2015-02-04 | 2015-06-15 | 2015-06-15 |  | 100 |  |  | S | 242242550
1.4.2.2.4.2 LOW THRESHOLD CC | 242242555 | H | Sector 1 - Mirror Alignment | 2015-02-05 | 2015-05-25 | 2015-05-25 |  | 2015-02-18 | 2015-06-16 | 2015-06-16 |  | 100 |  |  | H | 242242555
1.4.2.2.4.2 LOW THRESHOLD CC | 242242560 | H | Sector 1 - Fiducialization | 2015-02-19 | 2015-04-13 | 2015-04-13 |  | 2015-02-23 | 2015-05-18 | 2015-05-18 |  | 100 |  |  | H | 242242560
1.4.2.2.4.2 LOW THRESHOLD CC | 242242565 | H | Sector 1 - Window Seaming | 2015-02-05 | 2015-02-23 | 2015-02-23 |  | 2015-02-11 | 2015-03-16 | 2015-03-16 |  | 100 |  |  | H | 242242565
1.4.2.2.4.2 LOW THRESHOLD CC | 242242570 | H | Sector 1 - Window Installation | 2015-02-24 | 2015-06-17 | 2015-06-17 |  | 2015-03-02 | 2015-06-21 | 2015-06-21 |  | 100 |  |  | H | 242242570
1.4.2.2.4.2 LOW THRESHOLD CC | 242242575 | H | Sector 1 - Window Gas Leaks Checks | 2015-03-03 | 2015-07-01 |  |  | 2015-03-09 | 2015-07-17 | 2015-07-31 |  | 0 | 100 | 478 | H | 242242575
1.4.2.2.4.2 LOW THRESHOLD CC | 242242580 | U | Sector 1 - Consumables | 2015-01-05 | 2015-01-05 | 2015-01-05 |  | 2015-03-09 | 2015-01-28 | 2015-01-28 |  | 100 |  |  | U | 242242580
1.4.2.2.4.2 LOW THRESHOLD CC | 242242582 | U | Sector 1 - Consumables Obligated at time of ETC | 2015-01-05 | 2015-01-05 | 2015-01-05 |  | 2015-01-30 | 2015-01-19 | 2015-01-19 |  | 100 |  |  | U | 242242582
1.4.2.2.4.2 LOW THRESHOLD CC | 242242585 | M | Sector 1 Complete |  |  |  |  | 2015-03-09 | 2015-07-17 |  |  | 0 |  | 478 | M | 242242585
1.4.2.2.4.2 LOW THRESHOLD CC | 242242590 | S | Sector 2 - Prep Box | 2015-01-13 | 2015-01-23 | 2015-01-23 |  | 2015-02-18 | 2015-06-29 | 2015-06-29 |  | 100 |  |  | S | 242242590
1.4.2.2.4.2 LOW THRESHOLD CC | 242242595 | S | Sector 2 - Hardware Installation | 2015-03-03 | 2015-07-01 |  |  | 2015-03-24 | 2015-07-24 | 2015-07-31 |  | 0 | 59 | 397 | S | 242242595
1.4.2.2.4.2 LOW THRESHOLD CC | 242242600 | H | Sector 2 - Mirror Alignment | 2015-03-25 | 2015-07-27 |  |  | 2015-04-07 | 2015-08-07 |  |  | 0 |  | 397 | H | 242242600
1.4.2.2.4.2 LOW THRESHOLD CC | 242242605 | H | Sector 2 - Fiducialization | 2015-04-08 | 2015-08-10 |  |  | 2015-04-10 | 2015-08-12 |  |  | 0 |  | 397 | H | 242242605
1.4.2.2.4.2 LOW THRESHOLD CC | 242242610 | H | Sector 2 - Window Seaming | 2015-03-25 | 2015-04-10 | 2015-04-10 |  | 2015-03-31 | 2015-04-16 | 2015-04-16 |  | 100 |  |  | H | 242242610
1.4.2.2.4.2 LOW THRESHOLD CC | 242242615 | H | Sector 2 - Window Installation | 2015-04-13 | 2015-08-13 |  |  | 2015-04-17 | 2015-08-19 |  |  | 0 |  | 397 | H | 242242615
1.4.2.2.4.2 LOW THRESHOLD CC | 242242620 | H | Sector 2 - Window Gas Leaks Checks | 2015-04-20 | 2015-08-20 |  |  | 2015-04-24 | 2015-08-26 |  |  | 0 |  | 450 | H | 242242620
1.4.2.2.4.2 LOW THRESHOLD CC | 242242625 | U | Sector 2 - Consumables | 2015-01-13 | 2015-01-05 | 2015-01-05 |  | 2015-04-24 | 2015-01-19 | 2015-01-19 |  | 100 |  |  | U | 242242625
1.4.2.2.4.2 LOW THRESHOLD CC | 242242630 | M | Sector 2 Complete |  |  |  |  | 2015-04-24 | 2015-08-26 |  |  | 0 |  | 450 | M | 242242630
1.4.2.2.4.2 LOW THRESHOLD CC | 242242635 | S | Sector 3 - Prep Box | 2015-02-19 | 2015-02-19 | 2015-02-19 |  | 2015-03-27 | 2015-07-31 |  |  | 91.8 |  | 390 | S | 242242635
1.4.2.2.4.2 LOW THRESHOLD CC | 242242640 | S | Sector 3 - Hardware Installation | 2015-04-20 | 2015-08-20 |  |  | 2015-05-11 | 2015-09-11 |  |  | 0 |  | 397 | S | 242242640
1.4.2.2.4.2 LOW THRESHOLD CC | 242242645 | H | Sector 3 - Mirror Alignment | 2015-05-12 | 2015-09-14 |  |  | 2015-05-18 | 2015-09-18 |  |  | 0 |  | 397 | H | 242242645
1.4.2.2.4.2 LOW THRESHOLD CC | 242242650 | H | Sector 3 - Fiducialization | 2015-05-19 | 2015-09-21 |  |  | 2015-05-20 | 2015-09-22 |  |  | 0 |  | 397 | H | 242242650
1.4.2.2.4.2 LOW THRESHOLD CC | 242242655 | H | Sector 3 - Window Seaming | 2015-05-12 | 2015-04-13 | 2015-04-13 |  | 2015-05-18 | 2015-04-27 | 2015-04-27 |  | 100 |  |  | H | 242242655
1.4.2.2.4.2 LOW THRESHOLD CC | 242242660 | H | Sector 3 - Window Installation | 2015-05-21 | 2015-09-23 |  |  | 2015-05-27 | 2015-09-28 |  |  | 0 |  | 397 | H | 242242660
1.4.2.2.4.2 LOW THRESHOLD CC | 242242665 | H | Sector 3 - Window Gas Leaks Checks | 2015-05-28 | 2015-09-29 |  |  | 2015-06-03 | 2015-10-02 |  |  | 0 |  | 424 | H | 242242665
1.4.2.2.4.2 LOW THRESHOLD CC | 242242670 | U | Sector 3 - Consumables | 2015-02-19 | 2015-01-05 | 2015-01-05 |  | 2015-06-03 | 2015-01-19 | 2015-01-19 |  | 100 |  |  | U | 242242670
1.4.2.2.4.2 LOW THRESHOLD CC | 242242675 | M | Sector 3 Complete |  |  |  |  | 2015-06-03 | 2015-10-02 |  |  | 0 |  | 424 | M | 242242675
1.4.2.2.4.2 LOW THRESHOLD CC | 242242680 | S | Sector 4 - Prep Box | 2015-03-30 | 2015-02-23 | 2015-02-23 |  | 2015-05-05 | 2015-08-31 |  |  | 87.7 |  | 390 | S | 242242680
1.4.2.2.4.2 LOW THRESHOLD CC | 242242685 | S | Sector 4 - Hardware Installation | 2015-05-28 | 2015-09-29 |  |  | 2015-06-18 | 2015-10-19 |  |  | 0 |  | 397 | S | 242242685
1.4.2.2.4.2 LOW THRESHOLD CC | 242242690 | H | Sector 4 - Mirror Alignment | 2015-06-19 | 2015-10-20 |  |  | 2015-06-25 | 2015-10-26 |  |  | 0 |  | 397 | H | 242242690
1.4.2.2.4.2 LOW THRESHOLD CC | 242242695 | H | Sector 4 - Fiducialization | 2015-06-26 | 2015-10-27 |  |  | 2015-06-29 | 2015-10-28 |  |  | 0 |  | 397 | H | 242242695
1.4.2.2.4.2 LOW THRESHOLD CC | 242242700 | H | Sector 4 - Window Seaming | 2015-06-19 | 2015-04-13 | 2015-04-13 |  | 2015-06-25 | 2015-04-27 | 2015-04-27 |  | 100 |  |  | H | 242242700
1.4.2.2.4.2 LOW THRESHOLD CC | 242242705 | H | Sector 4 - Window Installation | 2015-06-30 | 2015-10-29 |  |  | 2015-07-06 | 2015-11-03 |  |  | 0 |  | 397 | H | 242242705
1.4.2.2.4.2 LOW THRESHOLD CC | 242242710 | H | Sector 4 - Window Gas Leaks Checks | 2015-07-07 | 2015-11-04 |  |  | 2015-07-13 | 2015-11-10 |  |  | 0 |  | 397 | H | 242242710
1.4.2.2.4.2 LOW THRESHOLD CC | 242242715 | U | Sector 4 - Consumables | 2015-03-30 | 2015-02-02 | 2015-02-02 |  | 2015-07-13 | 2015-02-23 | 2015-02-23 |  | 100 |  |  | U | 242242715
1.4.2.2.4.2 LOW THRESHOLD CC | 242242720 | M | Sector 4 Complete |  |  |  |  | 2015-07-13 | 2015-11-10 |  |  | 0 |  | 397 | M | 242242720
1.4.2.2.4.2 LOW THRESHOLD CC | 242242725 | S | Sector 5 - Prep Box | 2015-05-06 | 2015-02-16 | 2015-02-16 |  | 2015-06-11 | 2015-10-06 |  |  | 79.5 |  | 390 | S | 242242725
1.4.2.2.4.2 LOW THRESHOLD CC | 242242730 | S | Sector 5 - Hardware Installation | 2015-07-07 | 2015-10-07 |  |  | 2015-07-28 | 2015-10-28 |  |  | 0 |  | 390 | S | 242242730
1.4.2.2.4.2 LOW THRESHOLD CC | 242242735 | H | Sector 5 - Mirror Alignment | 2015-07-29 | 2015-10-29 |  |  | 2015-08-04 | 2015-11-04 |  |  | 0 |  | 390 | H | 242242735
1.4.2.2.4.2 LOW THRESHOLD CC | 242242740 | H | Sector 5 - Fiducialization | 2015-08-05 | 2015-11-05 |  |  | 2015-08-06 | 2015-11-06 |  |  | 0 |  | 390 | H | 242242740
1.4.2.2.4.2 LOW THRESHOLD CC | 242242745 | H | Sector 5 - Window Seaming | 2015-07-29 | 2015-04-13 | 2015-04-13 |  | 2015-08-04 | 2015-05-18 | 2015-05-18 |  | 100 |  |  | H | 242242745
1.4.2.2.4.2 LOW THRESHOLD CC | 242242750 | H | Sector 5 - Window Installation | 2015-08-07 | 2015-11-09 |  |  | 2015-08-12 | 2015-11-12 |  |  | 0 |  | 390 | H | 242242750
1.4.2.2.4.2 LOW THRESHOLD CC | 242242755 | H | Sector 5 - Window Gas Leaks Checks | 2015-08-13 | 2015-11-13 |  |  | 2015-08-19 | 2015-11-19 |  |  | 0 |  | 390 | H | 242242755
1.4.2.2.4.2 LOW THRESHOLD CC | 242242760 | U | Sector 5 - Consumables | 2015-05-06 | 2015-02-02 | 2015-02-02 |  | 2015-08-19 | 2015-02-23 | 2015-02-23 |  | 100 |  |  | U | 242242760
1.4.2.2.4.2 LOW THRESHOLD CC | 242242765 | M | Sector 5 Complete |  |  |  |  | 2015-08-19 | 2015-11-19 |  |  | 0 |  | 390 | M | 242242765
1.4.2.2.4.2 LOW THRESHOLD CC | 242242770 | S | Sector 6 - Prep Box | 2015-06-12 | 2015-02-16 | 2015-02-16 |  | 2015-07-17 | 2015-10-06 |  |  | 63.2 |  | 390 | S | 242242770
1.4.2.2.4.2 LOW THRESHOLD CC | 242242775 | S | Sector 6 - Hardware Installation | 2015-08-13 | 2015-10-07 |  |  | 2015-09-03 | 2015-10-28 |  |  | 0 |  | 390 | S | 242242775
1.4.2.2.4.2 LOW THRESHOLD CC | 242242780 | H | Sector 6 - Mirror Alignment | 2015-09-04 | 2015-10-29 |  |  | 2015-09-11 | 2015-11-04 |  |  | 0 |  | 390 | H | 242242780
1.4.2.2.4.2 LOW THRESHOLD CC | 242242785 | H | Sector 6 - Fiducialization | 2015-09-14 | 2015-11-05 |  |  | 2015-09-15 | 2015-11-06 |  |  | 0 |  | 390 | H | 242242785
1.4.2.2.4.2 LOW THRESHOLD CC | 242242790 | H | Sector 6 - Window Seaming | 2015-09-04 | 2015-05-11 | 2015-05-11 |  | 2015-09-11 | 2015-05-25 | 2015-05-25 |  | 100 |  |  | H | 242242790
1.4.2.2.4.2 LOW THRESHOLD CC | 242242795 | H | Sector 6 - Window Installation | 2015-09-16 | 2015-11-09 |  |  | 2015-09-21 | 2015-11-12 |  |  | 0 |  | 390 | H | 242242795
1.4.2.2.4.2 LOW THRESHOLD CC | 242242800 | H | Sector 6 - Window Gas Leaks Checks | 2015-09-22 | 2015-11-13 |  |  | 2015-09-28 | 2015-11-19 |  |  | 0 |  | 390 | H | 242242800
1.4.2.2.4.2 LOW THRESHOLD CC | 242242805 | U | Sector 6 - Consumables | 2015-06-12 | 2015-10-07 |  |  | 2015-09-24 | 2015-11-19 |  |  | 0 | 50 | 390 | U | 242242805
1.4.2.2.4.2 LOW THRESHOLD CC | 242242810 | M | Sector 6 Complete |  |  |  |  | 2015-09-28 | 2015-11-19 |  |  | 0 |  | 390 | M | 242242810
1.4.2.2.4.2 LOW THRESHOLD CC | 242242900M | M | LTCC Complete |  |  |  |  | 2015-09-28 | 2015-11-19 |  |  | 0 |  | 390 | M | 242242900M