## Template
12 GeV November 2015 STATUS UPDATE
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID
YOUNG G
1.4.2.2.4.2 LOW THRESHOLD CC | 242242705 | H | Sector 4 - Window Installation | 2015-06-30 | 2015-11-02 | 2015-11-04 |  | 2015-07-06 | 2015-11-12 | 2015-11-20 |  | 0 | 100 | 390 | H | 242242705
1.4.2.2.4.2 LOW THRESHOLD CC | 242242710 | H | Sector 4 - Window Gas Leaks Checks | 2015-07-07 | 2015-11-13 | 2015-11-14 |  | 2015-07-13 | 2015-11-16 | 2015-11-24 |  | 0 | 100 | 403 | H | 242242710
1.4.2.2.4.2 LOW THRESHOLD CC | 242242720 | M | Sector 4 Complete |  |  |  |  | 2015-07-13 | 2015-11-16 | 2015-11-24 |  | 0 | 100 | 403 | M | 242242720
1.4.2.2.4.2 LOW THRESHOLD CC | 242242730 | S | Sector 5 - Hardware Installation | 2015-07-07 | 2015-11-02 | 2015-11-04 |  | 2015-07-28 | 2015-11-13 | 2015-11-23 |  | 0 | 100 | 391 | S | 242242730
1.4.2.2.4.2 LOW THRESHOLD CC | 242242735 | H | Sector 5 - Mirror Alignment | 2015-07-29 | 2015-11-16 | 2015-11-24 |  | 2015-08-04 | 2015-11-20 | 2015-11-30 |  | 0 | 100 | 391 | H | 242242735
1.4.2.2.4.2 LOW THRESHOLD CC | 242242740 | H | Sector 5 - Fiducialization | 2015-08-05 | 2015-11-23 | 2015-11-23 |  | 2015-08-06 | 2015-11-24 | 2015-11-30 |  | 0 | 100 | 391 | H | 242242740
1.4.2.2.4.2 LOW THRESHOLD CC | 242242750 | H | Sector 5 - Window Installation | 2015-08-07 | 2015-11-25 |  | 2015-12-04 | 2015-08-12 | 2015-12-01 |  | 2015-12-08 | 0 |  | 391 | H | 242242750
1.4.2.2.4.2 LOW THRESHOLD CC | 242242755 | H | Sector 5 - Window Gas Leaks Checks | 2015-08-13 | 2015-12-02 |  | 2015-12-07 | 2015-08-19 | 2015-12-04 |  | 2015-12-10 | 0 |  | 391 | H | 242242755
1.4.2.2.4.2 LOW THRESHOLD CC | 242242765 | M | Sector 5 Complete |  |  |  |  | 2015-08-19 | 2015-12-04 |  | 2015-12-10 | 0 |  | 391 | M | 242242765
1.4.2.2.4.2 LOW THRESHOLD CC | 242242770 | S | Sector 6 - Prep Box | 2015-06-12 | 2015-02-16 | 2015-02-16 |  | 2015-07-17 | 2015-11-17 | 2015-11-23 |  | 87.7 | 100 | 387 | S | 242242770
1.4.2.2.4.2 LOW THRESHOLD CC | 242242775 | S | Sector 6 - Hardware Installation | 2015-08-13 | 2015-11-18 | 2015-11-24 |  | 2015-09-03 | 2015-11-30 |  | 2015-12-08 | 0 | 24 | 387 | S | 242242775
1.4.2.2.4.2 LOW THRESHOLD CC | 242242780 | H | Sector 6 - Mirror Alignment | 2015-09-04 | 2015-12-01 |  | 2015-12-09 | 2015-09-11 | 2015-12-04 |  | 2015-12-12 | 0 |  | 387 | H | 242242780
1.4.2.2.4.2 LOW THRESHOLD CC | 242242785 | H | Sector 6 - Fiducialization | 2015-09-14 | 2015-12-01 |  | 2015-12-09 | 2015-09-15 | 2015-12-02 |  | 2015-12-10 | 0 |  | 387 | H | 242242785
1.4.2.2.4.2 LOW THRESHOLD CC | 242242795 | H | Sector 6 - Window Installation | 2015-09-16 | 2015-12-03 |  | 2015-12-14 | 2015-09-21 | 2015-12-08 |  | 2015-12-17 | 0 |  | 387 | H | 242242795
1.4.2.2.4.2 LOW THRESHOLD CC | 242242800 | H | Sector 6 - Window Gas Leaks Checks | 2015-09-22 | 2015-12-09 |  | 2015-12-17 | 2015-09-28 | 2015-12-10 |  | 2015-12-20 | 0 |  | 387 | H | 242242800
1.4.2.2.4.2 LOW THRESHOLD CC | 242242805 | U | Sector 6 - Consumables | 2015-06-12 | 2015-07-07 | 2015-07-07 |  | 2015-09-24 | 2015-11-23 |  | 2015-12-20 | 75 | 90 | 398 | U | 242242805
1.4.2.2.4.2 LOW THRESHOLD CC | 242242810 | M | Sector 6 Complete |  |  |  |  | 2015-09-28 | 2015-12-10 |  | 2015-12-20 | 0 |  | 387 | M | 242242810
1.4.2.2.4.2 LOW THRESHOLD CC | 242242900M | M | LTCC Complete |  |  |  |  | 2015-09-28 | 2015-12-10 |  | 2015-12-20 | 0 |  | 387 | M | 242242900M