## Template
12 GeV September 2015 STATUS UPDATE
WBS Name | Activity ID | EVMS Code | Activity Name | BL Project Start Date | Calc Start Date | Actual Start Date | Expect to Start Date | BL Project Finish date | Calc Finish Date | Actual Finish Date | Expect To Finish Date | Prev Status % Comp | New Status % Comp | Total Float In Days | EVMS Code | Activity ID
YOUNG G
1.4.2.2.4.2 LOW THRESHOLD CC | 242242595 | S | Sector 2 - Hardware Installation | 2015-03-03 | 2015-07-03 | 2015-07-03 |  | 2015-03-24 | 2015-09-08 |  |  | 76.3 | 100 | 414 | S | 242242595
1.4.2.2.4.2 LOW THRESHOLD CC | 242242615 | H | Sector 2 - Window Installation | 2015-04-13 | 2015-09-09 |  |  | 2015-04-17 | 2015-09-15 | 2015-09-29 |  | 0 |  | 414 | H | 242242615
1.4.2.2.4.2 LOW THRESHOLD CC | 242242620 | H | Sector 2 - Window Gas Leaks Checks | 2015-04-20 | 2015-09-16 |  |  | 2015-04-24 | 2015-09-18 | 2015-10-01 |  | 0 |  | 434 | H | 242242620
1.4.2.2.4.2 LOW THRESHOLD CC | 242242630 | M | Sector 2 Complete |  |  |  |  | 2015-04-24 | 2015-09-18 | 2015-10-01 |  | 0 | 100 | 434 | M | 242242630
1.4.2.2.4.2 LOW THRESHOLD CC | 242242640 | S | Sector 3 - Hardware Installation | 2015-04-20 | 2015-08-09 | 2015-08-09 |  | 2015-05-11 | 2015-09-15 |  |  | 58.7 | 88.2 | 412 | S | 242242640
1.4.2.2.4.2 LOW THRESHOLD CC | 242242645 | H | Sector 3 - Mirror Alignment | 2015-05-12 | 2015-09-16 |  |  | 2015-05-18 | 2015-09-22 | 2015-10-01 |  | 0 | 100 | 412 | H | 242242645
1.4.2.2.4.2 LOW THRESHOLD CC | 242242650 | H | Sector 3 - Fiducialization | 2015-05-19 | 2015-09-16 |  |  | 2015-05-20 | 2015-09-16 | 2015-09-30 |  | 0 | 100 | 412 | H | 242242650
1.4.2.2.4.2 LOW THRESHOLD CC | 242242660 | H | Sector 3 - Window Installation | 2015-05-21 | 2015-09-17 |  | 2015-10-10 | 2015-05-27 | 2015-09-24 |  |  | 0 |  | 412 | H | 242242660
1.4.2.2.4.2 LOW THRESHOLD CC | 242242665 | H | Sector 3 - Window Gas Leaks Checks | 2015-05-28 | 2015-09-25 |  | 2015-10-14 | 2015-06-03 | 2015-09-28 |  |  | 0 |  | 428 | H | 242242665
1.4.2.2.4.2 LOW THRESHOLD CC | 242242675 | M | Sector 3 Complete |  |  |  |  | 2015-06-03 | 2015-09-28 |  |  | 0 |  | 428 | M | 242242675
1.4.2.2.4.2 LOW THRESHOLD CC | 242242680 | S | Sector 4 - Prep Box | 2015-03-30 | 2015-02-23 | 2015-02-23 |  | 2015-05-05 | 2015-09-15 |  | 2015-10-07 | 87.7 |  | 404 | S | 242242680
1.4.2.2.4.2 LOW THRESHOLD CC | 242242685 | S | Sector 4 - Hardware Installation | 2015-05-28 | 2015-09-16 |  |  | 2015-06-18 | 2015-09-21 |  | 2015-10-15 | 0 |  | 414 | S | 242242685
1.4.2.2.4.2 LOW THRESHOLD CC | 242242690 | H | Sector 4 - Mirror Alignment | 2015-06-19 | 2015-09-22 |  |  | 2015-06-25 | 2015-09-25 |  | 2015-10-22 | 0 |  | 414 | H | 242242690
1.4.2.2.4.2 LOW THRESHOLD CC | 242242695 | H | Sector 4 - Fiducialization | 2015-06-26 | 2015-09-22 |  |  | 2015-06-29 | 2015-09-23 |  | 2015-10-20 | 0 |  | 414 | H | 242242695
1.4.2.2.4.2 LOW THRESHOLD CC | 242242705 | H | Sector 4 - Window Installation | 2015-06-30 | 2015-09-24 |  |  | 2015-07-06 | 2015-09-25 |  | 2015-10-25 | 0 |  | 414 | H | 242242705
1.4.2.2.4.2 LOW THRESHOLD CC | 242242710 | H | Sector 4 - Window Gas Leaks Checks | 2015-07-07 | 2015-09-28 |  |  | 2015-07-13 | 2015-09-29 |  | 2015-10-29 | 0 |  | 427 | H | 242242710
1.4.2.2.4.2 LOW THRESHOLD CC | 242242720 | M | Sector 4 Complete |  |  |  |  | 2015-07-13 | 2015-09-29 |  | 2015-10-29 | 0 |  | 427 | M | 242242720
1.4.2.2.4.2 LOW THRESHOLD CC | 242242725 | S | Sector 5 - Prep Box | 2015-05-06 | 2015-02-16 | 2015-02-16 |  | 2015-06-11 | 2015-09-28 |  | 2015-10-15 | 83.6 | 87.7 | 404 | S | 242242725
1.4.2.2.4.2 LOW THRESHOLD CC | 242242730 | S | Sector 5 - Hardware Installation | 2015-07-07 | 2015-09-29 |  |  | 2015-07-28 | 2015-10-05 |  | 2015-10-22 | 0 |  | 410 | S | 242242730
1.4.2.2.4.2 LOW THRESHOLD CC | 242242735 | H | Sector 5 - Mirror Alignment | 2015-07-29 | 2015-10-06 |  |  | 2015-08-04 | 2015-10-12 |  | 2015-11-02 | 0 |  | 410 | H | 242242735
1.4.2.2.4.2 LOW THRESHOLD CC | 242242740 | H | Sector 5 - Fiducialization | 2015-08-05 | 2015-10-13 |  |  | 2015-08-06 | 2015-10-14 |  | 2015-10-28 | 0 |  | 410 | H | 242242740
1.4.2.2.4.2 LOW THRESHOLD CC | 242242750 | H | Sector 5 - Window Installation | 2015-08-07 | 2015-10-15 |  |  | 2015-08-12 | 2015-10-19 |  | 2015-11-07 | 0 |  | 410 | H | 242242750
1.4.2.2.4.2 LOW THRESHOLD CC | 242242755 | H | Sector 5 - Window Gas Leaks Checks | 2015-08-13 | 2015-10-20 |  |  | 2015-08-19 | 2015-10-22 |  | 2015-11-10 | 0 |  | 410 | H | 242242755
1.4.2.2.4.2 LOW THRESHOLD CC | 242242765 | M | Sector 5 Complete |  |  |  |  | 2015-08-19 | 2015-10-22 |  | 2015-11-15 | 0 |  | 410 | M | 242242765
1.4.2.2.4.2 LOW THRESHOLD CC | 242242770 | S | Sector 6 - Prep Box | 2015-06-12 | 2015-02-16 | 2015-02-16 |  | 2015-07-17 | 2015-10-09 |  | 2015-11-10 | 67.3 | 87.7 | 404 | S | 242242770
1.4.2.2.4.2 LOW THRESHOLD CC | 242242775 | S | Sector 6 - Hardware Installation | 2015-08-13 | 2015-10-12 |  |  | 2015-09-03 | 2015-10-20 |  | 2015-11-15 | 0 |  | 404 | S | 242242775
1.4.2.2.4.2 LOW THRESHOLD CC | 242242780 | H | Sector 6 - Mirror Alignment | 2015-09-04 | 2015-10-21 |  |  | 2015-09-11 | 2015-10-26 |  | 2015-11-20 | 0 |  | 404 | H | 242242780
1.4.2.2.4.2 LOW THRESHOLD CC | 242242785 | H | Sector 6 - Fiducialization | 2015-09-14 | 2015-10-21 |  |  | 2015-09-15 | 2015-10-22 |  | 2015-11-16 | 0 |  | 404 | H | 242242785
1.4.2.2.4.2 LOW THRESHOLD CC | 242242795 | H | Sector 6 - Window Installation | 2015-09-16 | 2015-10-23 |  |  | 2015-09-21 | 2015-10-28 |  | 2015-11-24 | 0 |  | 404 | H | 242242795
1.4.2.2.4.2 LOW THRESHOLD CC | 242242800 | H | Sector 6 - Window Gas Leaks Checks | 2015-09-22 | 2015-10-29 |  |  | 2015-09-28 | 2015-10-30 |  | 2015-11-30 | 0 |  | 404 | H | 242242800
1.4.2.2.4.2 LOW THRESHOLD CC | 242242805 | U | Sector 6 - Consumables | 2015-06-12 | 2015-07-07 | 2015-07-07 |  | 2015-09-24 | 2015-10-30 |  |  | 50 | 75 | 404 | U | 242242805
1.4.2.2.4.2 LOW THRESHOLD CC | 242242810 | M | Sector 6 Complete |  |  |  |  | 2015-09-28 | 2015-10-30 |  | 2015-11-30 | 0 |  | 404 | M | 242242810
1.4.2.2.4.2 LOW THRESHOLD CC | 242242900M | M | LTCC Complete |  |  |  |  | 2015-09-28 | 2015-10-30 |  | 2015-12-05 | 0 |  | 404 | M | 242242900M
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X050 | S | LTCC - Calibration Test | 2015-04-08 | 2015-04-21 | 2015-04-21 |  | 2015-06-16 | 2015-09-09 | 2015-09-16 |  | 75 | 100 | 441 | S | 2822X050