## report
PMK Activities with steps
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242211395 | HBI - Sloco:Slow controls for monitoring and charge calib system: assemble, test, and debug ADC's- Labor | 28% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Test sensors (temperature & humidity) | 100% | 10 | Yes
Assemble tested sensors in the silicon detector barrel | 0% | 8 | No
Assemble & Test Slow Controls patch panel and breakout blocks | 0% | 10 | No
Connect & test HFCB, RTD's, and Humidity sensors to terminal Blocks | 0% | 8 | No
Install and Test Isolated ADC's / RTD VME Modules | 100% | 10 | Yes
Install and Test Relay and DAC VME Modules | 0% | 10 | No
Test Chiller / flow sensor slow controls | 0% | 8 | No
Test ground isolation on HFCB Grounds to Isolated ADC's | 100% | 8 | Yes
Test and calibrate individual monitoring sensors | 0% | 8 | No
Debug complete SVT Slow Controls System Hardware | 0% | 20 | No
242211400a | HBI - Sloco:Slow controls for monitor and charge calib system: develop sloco software (1/2) - Labor | 7% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Write EPICS Device Driver for Isolated ADC modules | 100% | 7 | Yes
Develop User Interfaces (GUI) | 0% | 15 | No
Write support for Chiller asyn driver Interface | 0% | 4 | No
Develop EPICS record Database | 0% | 20 | No
Determine Alarm levels and responses | 0% | 5 | No
Write Alarm Handler | 0% | 5 | No
Develop SVT Channel Archiver | 0% | 5 | No
Write SVT Strip Tool plotting Interface | 0% | 2 | No
Develop Sequencer Applications | 0% | 4 | No
Develop BURT (Backup and Restore Tool) for SVT EPICS Slow Controls | 0% | 4 | No
Develop SVT Archiver interface & Histogramming | 0% | 4 | No
Test and debug Interlock levels | 0% | 8 | No
Test and debug complete SVT EPICS System | 0% | 10 | No
Integrate & Test SVT Slow Controls System into CLAS12 Systems | 0% | 7 | No
242211485 | MECH GRP - Mounting and aligning on support structure in lab, R1-R3 - Labor | 5% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Region 1 Assembly set up and survey | 100% | 5 | Yes
Insert inner shell | 0% | 5 | No
Assemble Region 1 Part A (5 modules) | 0% | 5 | No
Assemble Region 1 Part B (5 modules) | 0% | 5 | No
Region 2 assembly set up and survey | 0% | 5 | No
Assemble Region 2 Part A (5 modules) | 0% | 5 | No
Assemble Region 2 Part B (5 modules) | 0% | 5 | No
Assemble Region 2 Part C (4 modules) | 0% | 5 | No
Region 3 assembly set up and survey | 0% | 5 | No
Assemble Region 3 Part A (6 modules) | 0% | 15 | No
Assemble Region 3 Part B (6 modules) | 0% | 15 | No
Assemble Region 3 Part C (6 modules) | 0% | 15 | No
Install Faraday cage components | 0% | 10 | No
242211545 | MECH GRP - Mounting and aligning on support structure in lab, R4 - Labor | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Region 4 Assembly set-up and survey | 0% | 5 | No
Insert R4 inner shell | 0% | 5 | No
Assemble Region 4 Part A (6 modules) | 0% | 20 | No
Assemble Region 4 Part B (6 modules) | 0% | 20 | No
Assemble Region 4 Part C (6 modules) | 0% | 20 | No
Assemble Region 4 Part D (6 modules) | 0% | 20 | No
Install Region 4 Faraday cage components | 0% | 10 | No
242211600 | HBI - Full system R4, test and burn-in in Cleanroom EEL 121 - Labor | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Checkout of safety system (interlock LV/HV/cooling/gas before starting R4 | 0% | 20 | No
Checkout of the High-Voltage system and distribution R4 | 0% | 20 | No
Checkout of the Low-Voltage System R4 | 0% | 20 | No
Checkout of Front-End electronics R4 | 0% | 20 | No
Checkout of DAQ and Trigger R4 | 0% | 20 | No
242211615 | HBI - Full system R1-R3, test and burn-in in Cleanroom EEL 121 - Labor | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Checkout of DAQ and Trigger R3 | 0% | 4 | No
Checkout of safety system (interlock LV/HV/cooling/gas before starting R1+R2+R3 | 0% | 4 | No
Checkout of the High-Voltage system and distribution R1+R2+R3 | 0% | 4 | No
Checkout of the Low-Voltage System R1+R2+R3 | 0% | 4 | No
Checkout of Front-End electronics R1+R2+R3 | 0% | 4 | No
Checkout of DAQ and Trigger R1+R2+R3 | 0% | 4 | No
Checkout of safety system (interlock LV/HV/cooling/gas before starting R1 | 0% | 4 | No
Checkout of the High-Voltage system and distribution R1 | 0% | 4 | No
Checkout of the Low-Voltage System R1 | 0% | 4 | No
Checkout of Front-End electronics R1 | 0% | 4 | No
Checkout of DAQ and Trigger R1 | 0% | 4 | No
Checkout of safety system (interlock LV/HV/cooling/gas before starting R2 | 0% | 4 | No
Checkout of the High-Voltage system and distribution R2 | 0% | 4 | No
Checkout of the Low-Voltage System R2 | 0% | 4 | No
Checkout of Front-End electronics R2 | 0% | 4 | No
Checkout of DAQ and Trigger R2 | 0% | 4 | No
Checkout of safety system (interlock LV/HV/cooling/gas before starting R1+R2 | 0% | 4 | No
Checkout of the High-Voltage system and distribution R1+R2 | 0% | 4 | No
Checkout of the Low-Voltage System R1+R2 | 0% | 4 | No
Checkout of Front-End electronics R1+R2 | 0% | 4 | No
Checkout of DAQ and Trigger R1+R2 | 0% | 4 | No
Checkout of safety system (interlock LV/HV/cooling/gas before starting R3 | 0% | 4 | No
Checkout of the High-Voltage system and distribution R3 | 0% | 4 | No
Checkout of the Low-Voltage System R3 | 0% | 4 | No
Checkout of Front-End electronics R3 | 0% | 4 | No
242211680 | MECH GRP - Full system test Integration of SVT R3/R4 - Labor | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Checkout of the High-Voltage system and distribution R1-R4 | 0% | 10 | No
Checkout of the Low-Voltage System R1-R4 | 0% | 10 | No
Checkout of Front-End electronics R1-R4 | 0% | 10 | No
Checkout of DAQ and Trigger R1-R4 | 0% | 10 | No
Checkout of safety system (interlock LV/HV/cooling/gas before starting R1-R4 | 0% | 10 | No
Transport R3 and R4 to the large clean room. | 0% | 10 | No
Insert and attach R3 to R4 | 0% | 10 | No
Hook all services (cooling lines, nitrogen gas lines, power supplies, and interlocks) | 0% | 10 | No
Install Faraday cage over R4 | 0% | 10 | No
Survey position of R3 with respect to R4 | 0% | 10 | No
242211700 | MECH GRP - Region 4 Support, cooling, coldplate, and alignment structure: construct & assemble - Labor | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Inspection of parts | 0% | 50 | No
Assembly of parts | 0% | 50 | No
242211740 | MECH GRP - Tooling for disassembly and repairs Build - Labor | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Check parts | 0% | 20 | No
Assemble fixture | 0% | 80 | No
242213347 | P-#5 String Chambers | 87.1% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
String and test all SL5 sense wires on 5th RIII chamber | 100% | 8.3 | Yes
String and test all SL6 sense wires on 5th RIII chamber | 100% | 8.3 | Yes
Re-Test all wires on 5th RIII chamber | 100% | 2.8 | Yes
Pot crimp pins on 5th RIII chamber | 100% | 2.8 | Yes
Survey and fiducialize 5th RIII chamber | 100% | 2.8 | Yes
Install gas window, Instrument 5th RIII Chamber | 100% | 5.5 | Yes
Install 6th RIII chamber on stringing fixture | 100% | 2.8 | Yes
Install 6th RIII pre-tension harware | 100% | 5.5 | Yes
String and test all SL6 field wires on 6th RIII chamber | 100% | 8.3 | Yes
String and test all SL5 field wires on 6th RIII chamber | 100% | 8.3 | Yes
String and test all SL5 sense wires on 6th RIII chamber | 100% | 8.3 | Yes
String and test all SL6 sense wires on 6th RIII chamber | 100% | 8.3 | Yes
Re-Test all wires on 6th RIII chamber | 100% | 2.8 | Yes
Pot crimp pins on 6th RIII chamber | 100% | 2.8 | Yes
Survey and fiducialize 6th RIII chamber | 0% | 2.8 | No
Install gas window, Instrument 6th RIII Chamber | 0% | 5.5 | No
Survey/fiducialize all RI chambers 5&6 | 0% | 4.6 | No
Survey/fiducialize all RI chambers 1&2 | 100% | 4.6 | Yes
Survey/fiducialize all RI chambers 3&4 | 100% | 4.7 | Yes
242231145 | Fabricate Tooling for Wrapping | 20% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Complete design for tooling | 100% | 10 | Yes
Complete testing phase | 100% | 10 | Yes
Complete fabrication | 0% | 80 | No
242231255 | Transmittance test of assembled Counters in Rack | 66.8% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Test of rack 1 | 100% | 16.7 | Yes
Test of rack 2 | 100% | 16.7 | Yes
Test of rack 3 | 100% | 16.7 | Yes
Test of rack 4 | 100% | 16.7 | Yes
Test of rack 5 | 0% | 16.7 | No
Test of rack 6 | 0% | 16.7 | No
242231260 | Final Drawings of CTOF Support and Solenoid Harness | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Complete drawings of CTOF support | 0% | 50 | No
Complete drawings of CTOF solenoid harness | 0% | 50 | No
242231270 | Final drawings for counter installation arm - cart and transport rack | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Complete drawing package for cart system | 0% | 50 | No
Complete drawing package for transport rack | 0% | 50 | No
242231272 | Counter installation arm - cart and transport rack Engineering Analysis | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Fabrication of installation arm cart | 0% | 50 | No
Fabrication of CTOF counter transportation rack | 0% | 50 | No
242231285 | Final Drawings of Magnetic Shield Components | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Complete drawings for compensation coil and bayonet connector | 0% | 60 | No
Complete drawings for end-cap cones | 0% | 20 | No
Complete drawings for inner shield | 0% | 20 | No
242231325 | Assemble the Setup for Magnetic Shields Tests | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install and power SC solenoid | 0% | 40 | No
Install support for the magnetic shield | 0% | 40 | No
Install magnetic sensors | 0% | 20 | No
242231425 | Prepare CTOF-in-Storage-Rack for transportation | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Rack #1 | 0% | 16.7 | No
Rack #2 | 0% | 16.7 | No
Rack #3 | 0% | 16.7 | No
Rack #4 | 0% | 16.7 | No
Rack #5 | 0% | 16.7 | No
Rack #6 | 0% | 16.7 | No
242231465 | Soldering the stabilized dividers for H2431 PMTs | 50% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Purchase 130 PCB boards with components | 100% | 40 | Yes
Dismount PMT shields | 100% | 10 | Yes
Solder PCB board to the PMT base | 0% | 40 | No
Mount PMT shield | 0% | 10 | No
242241405b | Assembly of the mirror with half sectors - Lab | 15% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Installation of 12 Half-sectors without gluing them together | 100% | 15 | Yes
Gluing 6 Half-sectors together | 0% | 25 | No
Gluing of remaining 6 Half-sectors together | 0% | 25 | No
Gluing of the First and Second halfs together | 0% | 20 | No
Installation of the ring with bridge pieces glued to the ring | 0% | 5 | No
Gluing of the ring with bridge pieces to the mirror | 0% | 10 | No
242241410 | Quality control of assembled mirror half-sectors - Lab | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Installation of the testing equipment | 100% | 25 | Yes
Quality control and tests of all Half-sectors | 0% | 75 | No
242241425 | Quality control of the final mirror assembly - Lab | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Checks of integrity of the final assembly and fix possible problems | 0% | 50 | No
Checks of quality of attachment of the support ring to the assembled mirror | 0% | 30 | No
Gap excess glue inspection and fix possible problems | 0% | 20 | No
242241450b | Assembly of the CV FY13 | 85% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Completion of the assembly major structural members of the CV | 100% | 25 | Yes
Attachment of the outer shells of the CV | 100% | 30 | Yes
Powerwash and painting of the CV | 100% | 30 | Yes
Placement of the cleaned/painted CV inside of the clean room | 0% | 15 | No
242241450ba | Assembly of the CV FY14 | 85% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Completion of the assembly major structural members of the CV | 100% | 25 | Yes
Attachment of the outer shells of the CV | 100% | 30 | Yes
Powerwash and painting of the CV | 100% | 30 | Yes
Placement of the cleaned/painted CV inside of the clean room | 0% | 15 | No
242241528 | Assembly of the HTCC Gas System | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Modification of the existing gas lines and controls in the Hall B | 0% | 80 | No
Tests of the system without HTCC connected to it. | 0% | 20 | No
242241590 | Installation of 48 housing units - Lab | 33.3% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mount internal Brackets | 100% | 33.3 | Yes
Mount PMT housings | 0% | 33.3 | No
Mount Internal Components | 0% | 33.3 | No
242241605 | Installation of the assembled carbon cone - Lab | 50% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Dry fit and alignment of the carbon cone with spokes in CV | 100% | 50 | Yes
Final assembly of the cone in the Containment Vessel | 0% | 50 | No
242241610 | Installation of the composite exit window - Lab | 55% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Preparation of the exit window for installation | 100% | 15 | Yes
Dry fit of the exit window to the CV with carbon cone installed | 100% | 40 | Yes
Gluing of the window to the CV | 0% | 45 | No
242241640 | Installation ofthe ellipsoidal mirror - Lab | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Installation of the mounting fixtures in the CV | 0% | 5 | No
Preparation of the Mirror for lifting off the table | 0% | 5 | No
Installation of the mMirror in the CV | 0% | 70 | No
Alignment of the Mirror and geometry tests | 0% | 20 | No
242241647d | Installation of LMS | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Installation of the inside components (fiber optics, holders) | 0% | 71.4 | No
Installation of outside unit | 0% | 14.3 | No
Tests of the system before moving HTCC in the Hall | 0% | 14.3 | No
242241647d5 | Quality control of the installed items | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Light leak tests and fixing possible leaks | 0% | 15 | No
Gas leak tests of CV and fixing possible leaks | 0% | 85 | No
242242055 | Alignment Tool and Lasers Installation | 15% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Tool assembly | 0% | 40 | No
Laser table assembly | 100% | 15 | Yes
Laser system assembly | 0% | 15 | No
Sector mount on tool | 0% | 30 | No
242242085 | Quality Control of Elliptical/Hyperbolic mirrors | 30% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Visual Inspection of Mirrors | 100% | 30 | Yes
Sample Mirrors Reflectivity Tests | 0% | 70 | No
242242205 | Mirrors Laser Alignments | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Laser Setup | 0% | 10 | No
Laser/Box Survey | 0% | 30 | No
Elliptical Alignment | 0% | 30 | No
Hyperbolic Alignment | 0% | 30 | No
242242220a | Online Calibration Design FY13 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 0% | 25 | No
242242220aa | Online Calibration Design FY14 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 0% | 25 | No
242242222 | Online HV Matching Design FY13 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 0% | 25 | No
242242222a | Online HV Matching Design FY14 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 0% | 25 | No
242242223 | Online HV Matching Test | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
1 Full sector HC connection | 0% | 50 | No
DAQ setup | 0% | 50 | No
242242240 | Gas Leak Check 6 sectors | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Nitrogen Fill 1/2" | 0% | 20 | No
Freon Fill | 0% | 20 | No
Snoop | 0% | 60 | No
242242340 | Sector 2 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242365 | Sector 3 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242390 | Sector 4 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242415 | Sector 5 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242440 | Sector 6 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
24232025 | Install GE VME controllers (22) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install in crates and wire up | 0% | 40 | No
Register IP names, determine test software to be used | 0% | 20 | No
Boot one by one and run test software; send to repair if needed | 0% | 40 | No
24233025 | Install CISCO 2960S switches (24 Cu ports) (15) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install CISCO switches in racks and wire up | 0% | 50 | No
Configure all switches for corresponding subnets | 0% | 50 | No
24233065 | Install daq/online computers | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install daq/online computers hardware and wire up | 0% | 20 | No
Install operating systems and daq/online software | 0% | 20 | No
Test entire system | 0% | 60 | No
24235010a | SLOW CNTL (EPICS device drivers development) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Develop/install epics drivers for HV/LV systems | 0% | 10 | No
Develop/install epics drivers for motor systems | 0% | 10 | No
Develop/install epics drivers for magnets | 0% | 10 | No
Develop/install epics drivers for other systems | 0% | 70 | No
24235015 | SLOW CNTL (EPICS software development) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Develop/install epics iocs | 0% | 20 | No
Develop/install epics GUIs | 0% | 20 | No
Develop/install epics components (alarm, archiver etc) | 0% | 20 | No
Develop/install epics monitoring tree including communication with DAQ | 0% | 40 | No
24242005a | CAEN v1190 (1) and v1290N (7) TDC's installation (SF) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install v1190/v1290 TDC boards on Space Frame | 0% | 20 | No
Cable all TDCs on Space Frame | 0% | 40 | No
Test all TDCs running calibration procedures and obtain calibration constants | 0% | 40 | No
24242030a | JLab TDC Fanout (2) test/install (SF) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install TDC FOUT boards on Space Frame | 0% | 33.3 | No
Cable all FOUTs on Space Frame | 0% | 33.3 | No
Test all FOUTs running DAQ | 0% | 33.3 | No
24242040a | JLab Discriminator (12) and Flash FADC (12) test/install (SF) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install DSC2 and FADC boards on Space Frame | 0% | 20 | No
Cable all DSC2 and FADC on Space Frame | 0% | 20 | No
Test all DSC2 and FADC running calibration procedures and obtain calibration constants | 0% | 60 | No
24242055 | ORTEC 935F Discriminators (24) Test/Install (SF) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install ORTEC 935 boards on Space Frame | 0% | 20 | No
Cable all ORTEC 935 on Space Frame | 0% | 20 | No
Test all ORTEC 935 running calibration procedures and obtain calibration constants | 0% | 60 | No
24244030 | CAEN 1527 HV mainframes install (12) (FC), (2) (SF)installation | 85.7% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install CAEN mainframes in the Hall and populate with HV boards | 0% | 4.3 | No
Connect and configure mainframes to the network, and boards to detectors | 0% | 4.3 | No
Include mainframes into epics IOCs and test entire system | 0% | 5.7 | No
Install CAEN mainframes in the Hall and populate with HV boards FC | 100% | 25.7 | Yes
Connect and configure mainframes to the network, and boards to detectors FC | 100% | 25.7 | Yes
Include mainframes into epics IOCs and test entire system FC | 100% | 34.3 | Yes
24247005a | Wiener VME64x crates install (2) (SF) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install WIENER crates on Space Frame | 0% | 30 | No
Connect crates to the network and configure | 0% | 20 | No
Test crates with epics control | 0% | 50 | No
24247030 | NIM crates (2) install (SF) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install NIM crates on Space Frame | 0% | 30 | No
Connect crates to the network and configure | 0% | 20 | No
Test crates with epics control | 0% | 50 | No
24247045 | Re-locate existing UPS to Hall B | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Relocate UPS devices to the Pie Tower and Space Frame in Hall B | 0% | 20 | No
Replace all batteries | 0% | 50 | No
Connect to the network and emergency generator | 0% | 20 | No
Run tests | 0% | 10 | No
24264115 | SVT - Design transportation cart/skid | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Conceptual design | 0% | 30 | No
3D model | 0% | 30 | No
Drawings | 0% | 40 | No
24264120 | SVT - Cart/Skid Engineering analysis | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Hand Calculations | 0% | 25 | No
FEA Analysis | 0% | 50 | No
Report | 0% | 25 | No
24264145 | HTCC - design transport cart | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Conceptual design | 0% | 30 | No
3D model | 0% | 30 | No
Drawings | 0% | 40 | No
24264230 | Subway Level 1 addition wiring Power Dist. | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Determine required wiring | 0% | 30 | No
Install wiring | 0% | 70 | No
24264280 | Modify LTCC gas piping | 50% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Design gas piping system | 100% | 40 | Yes
Install piping for sector 1 | 100% | 10 | Yes
Install piping for sector 2 | 0% | 10 | No
Install piping for sector 3 | 0% | 10 | No
Install piping for sector 4 | 0% | 10 | No
Install piping for sector 5 | 0% | 10 | No
Install piping for sector 6 | 0% | 10 | No
24264281 | Install new gas lines from gas sched to the hall | 50% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install supply piping | 100% | 50 | Yes
Install return piping | 0% | 50 | No
24264460 | Transport and Install LTCC | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Transport and Install LTCC sector 1 | 0% | 25 | No
Transport and Install LTCC sector 2 | 0% | 15 | No
Transport and Install LTCC sector 3 | 0% | 15 | No
Transport and Install LTCC sector 4 | 0% | 15 | No
Transport and Install LTCC sector 5 | 0% | 15 | No
Transport and Install LTCC sector 6 | 0% | 15 | No
24264547 | Labor to Support The Torus Installation, Cooldown and Test | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install Spit in Hall B | 0% | 1.2 | No
Pre-align frames | 0% | 0.9 | No
Mount Hub to Spit | 0% | 0.3 | No
Align Spit to Beamline | 0% | 0.4 | No
Attach Coil A to Hub | 0% | 0.3 | No
Rotate Assembly, attach Sector 3 beams | 0% | 0.2 | No
Install Coil B, survey & align | 0% | 0.4 | No
Rotate Assembly, Sector 3 to bottom, prep. | 0% | 0.2 | No
Install hardware on Sector 3 US beam | 0% | 4.6 | No
Install hardware on Sector 3 DS beam | 0% | 0.2 | No
Rotate Assembly, attach Sector 4 beams | 0% | 0.2 | No
Install Coil C, survey & align | 0% | 0.9 | No
Rotate Assembly, Sector 4 to bottom, prep. | 0% | 0.2 | No
Install hardware on Sector 4 US beam | 0% | 3.6 | No
Install hardware on Sector 4 DS beam | 0% | 0.1 | No
Rotate Assembly, attach Sector 5 beams | 0% | 0.2 | No
Install Coil D, survey & align | 0% | 0.9 | No
Rotate Assembly, Sector 5 to bottom, prep. | 0% | 0.2 | No
Install hardware on Sector 5 US beam | 0% | 3.2 | No
Install hardware on Sector 5 DS beam | 0% | 0.1 | No
Rotate Assembly, attach Sector 6 beams | 0% | 0.2 | No
Install Coil E, survey & align | 0% | 0.9 | No
Rotate Assembly, Sector 6 to bottom, prep. | 0% | 0.2 | No
Install hardware on Sector 6 US beam | 0% | 3.2 | No
Install hardware on Sector 6 DS beam | 0% | 0.1 | No
Rotate Assembly, attach Sector 1 beams | 0% | 0.2 | No
Install Coil F, survey & align | 0% | 0.9 | No
Rotate Assembly, attach Sector 2 beams | 0% | 0.9 | No
Survey and align entire assembly | 0% | 0.4 | No
Rotate Assembly, Sector 1 to bottom, prep. | 0% | 0.2 | No
Install hardware on Sector 1 US beam | 0% | 3.2 | No
Install hardware on Sector 1 DS beam | 0% | 0.1 | No
Rotate Assembly, Sector 2 to bottom, prep. | 0% | 0.2 | No
Install hardware on Sector 2 US beam | 0% | 3.2 | No
Install hardware on Sector 2 DS beam | 0% | 0.1 | No
Pressure/leak test. Electrical test. | 0% | 3.2 | No
Install cold to warm supports | 0% | 0.3 | No
Insulate cold to warm supports | 0% | 0.6 | No
Complete shields on hex and hub | 0% | 0.1 | No
Install MLI on hex beam to coil connections | 0% | 2.4 | No
Complete 4K and 80K shields on coil-to-coil gaps at hub | 0% | 1.4 | No
Install U-shape vacumm jacket sections, skip weld | 0% | 3.8 | No
Install plates to complete vacuum jacket at hub, skip weld | 0% | 1.4 | No
Survey assembly for symmetry | 0% | 0.9 | No
Route instrumentation wires, make electrical connections at feedthroughs | 0% | 3.8 | No
Install brackets to complete vacuum jacket welding | 0% | 2.9 | No
Final leak check, final electrical tests | 0% | 0.6 | No
Install and tack weld closure plates on hex | 0% | 1.9 | No
Install LN2 Thermosiphon Jumpers | 0% | 1.2 | No
Complete all welding to finsih vacuum jacket | 0% | 12.2 | No
Orient assembly, survey, and lock rotation | 0% | 0.9 | No
Construct legs in Hall B | 0% | 3.2 | No
Run Wires, Connect instruments, verify OOPS operation | 0% | 0.6 | No
Pre-load vertical supports | 0% | 0.4 | No
Adjust OOPS loads | 0% | 0.6 | No
Using threaded holes adjust coil locations | 0% | 1.1 | No
Locate/install cryotower | 0% | 0.2 | No
Torus Cryotower - Connect cold piping with fittings and welding | 0% | 2.9 | No
Leak check, electrical tests | 0% | 1.5 | No
Final pressure test | 0% | 0.3 | No
Close 1-8 holes | close vacuum jacket" | 0% | 0.9 | No
Pump vacuum | 0% | 0.3 | No
Leak tests while pumping | 0% | 0.3 | No
Pump down vacuum | 0% | 0.7 | No
IInstall Vacuum pumping system | 0% | 1.1 | No
Design Warm Gas Panel and Piping | 0% | 1.9 | No
Cut Back the warm piping | 0% | 0.1 | No
Procure warm gas valves and fittings | 0% | 4.6 | No
Install New warm gas Piping | 0% | 1.5 | No
Leak Test new warm Piping | 0% | 0.6 | No
Pressure Test warm Piping | 0% | 0.1 | No
Final Leak Test system | 0% | 0.6 | No
Purify Entire System | 0% | 0.3 | No
Install mounting adapters for drift chambers | 0% | 5.4 | No
24264845 | Mount, assemble and cable CTOF system | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install CTOF support structure to solenoid | 0% | 20 | No
Install 48 counters | 0% | 50 | No
Install 96 magnetic shields | 0% | 20 | No
Cable detector | 0% | 10 | No
24264855 | Mount, cable and check SVT system | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install SVT cart | 0% | 30 | No
Install SVT electronics | 0% | 50 | No
Place SVT on cart | 0% | 20 | No
24264868 | Design and install HTCC gas system | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Design HTCC gas system | 0% | 40 | No
Install gas system | 0% | 60 | No
24264882 | Install DC signal cable trays and gas lines | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Connect cables to R1 cable trays | 0% | 20 | No
Install R1 cable trays | 0% | 10 | No
Connect cables to R3 cable trays | 0% | 20 | No
Install R3 cable trays | 0% | 10 | No
Install cable trays on Torus | 0% | 30 | No
Install gas lines | 0% | 10 | No
24264884 | Route DC Signal Cables | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Route cables for region 1 | 0% | 40 | No
Route cables for region 2 | 0% | 30 | No
Route cables for region 3 | 0% | 30 | No
24264888 | Reroute DC gas lines to the distribution panel | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Route gas lines for region 1 | 0% | 40 | No
Route gas lines for region 2 | 0% | 30 | No
Route gas lines for region 3 | 0% | 30 | No
24264890 | DC - design mounts and adjusters for DC to Torus | 40% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
DC - design mounts and adjusters for DC to Torus for region 1 | 100% | 40 | Yes
DC - design mounts and adjusters for DC to Torus for region 2 | 0% | 30 | No
DC - design mounts and adjusters for DC to Torus for region 3 | 0% | 30 | No
24264895 | DC - mounts and adjusters Engineering Analysis | 75% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Hand Calculations | 100% | 25 | Yes
FEA Analysis | 100% | 50 | Yes
Report | 0% | 25 | No
24264905 | DC - design cable trays and gas system mounts | 30% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Conceptual design | 100% | 30 | Yes
3D model | 0% | 30 | No
Drawings | 0% | 40 | No
24264910 | DC - cable trays and gas system mounts Engineering Analysis | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Hand Calculations | 0% | 25 | No
FEA Analysis | 0% | 50 | No
Report | 0% | 25 | No
24264920 | DC - design maintenance platforms | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Conceptual design | 0% | 30 | No
3D model | 0% | 30 | No
Drawings | 0% | 40 | No
24264965 | Install Region 2 Drift Chamber | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install Region 2 Drift Chamber Sector 1 | 0% | 25 | No
Install Region 2 Drift Chamber Sector 2 | 0% | 15 | No
Install Region 2 Drift Chamber Sector 3 | 0% | 15 | No
Install Region 2 Drift Chamber Sector 4 | 0% | 15 | No
Install Region 2 Drift Chamber Sector 5 | 0% | 15 | No
Install Region 2 Drift Chamber Sector 6 | 0% | 15 | No
24264970 | Survey/align R2 Drift chambers | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Survey/align R2 Drift chambers Sector 1 | 0% | 25 | No
Survey/align R2 Drift chambers Sector 2 | 0% | 15 | No
Survey/align R2 Drift chambers Sector 3 | 0% | 15 | No
Survey/align R2 Drift chambers Sector 4 | 0% | 15 | No
Survey/align R2 Drift chambers Sector 5 | 0% | 15 | No
Survey/align R2 Drift chambers Sector 6 | 0% | 15 | No
24264975 | Install Region 1 Drift Chamber | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install Region 1 Drift Chamber Sector 1 | 0% | 25 | No
Install Region 1 Drift Chamber Sector 2 | 0% | 15 | No
Install Region 1 Drift Chamber Sector 3 | 0% | 15 | No
Install Region 1 Drift Chamber Sector 4 | 0% | 15 | No
Install Region 1 Drift Chamber Sector 5 | 0% | 15 | No
Install Region 1 Drift Chamber Sector 6 | 0% | 15 | No
24264980 | Survey/align R1 Drift chambers | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Survey/align R1 Drift chambers Sector 1 | 0% | 25 | No
Survey/align R1 Drift chambers Sector 2 | 0% | 15 | No
Survey/align R1 Drift chambers Sector 3 | 0% | 15 | No
Survey/align R1 Drift chambers Sector 4 | 0% | 15 | No
Survey/align R1 Drift chambers Sector 5 | 0% | 15 | No
Survey/align R1 Drift chambers Sector 6 | 0% | 15 | No
24264985 | Install Region 3 Drift Chamber | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Install Region 3 Drift Chamber Sector 1 | 0% | 25 | No
Install Region 3 Drift Chamber Sector 2 | 0% | 15 | No
Install Region 3 Drift Chamber Sector 3 | 0% | 15 | No
Install Region 3 Drift Chamber Sector 4 | 0% | 15 | No
Install Region 3 Drift Chamber Sector 5 | 0% | 15 | No
Install Region 3 Drift Chamber Sector 6 | 0% | 15 | No
24264990 | Survey/align R3 Drift chambers | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Survey/align R3 Drift chambers Sector 1 | 0% | 25 | No
Survey/align R3 Drift chambers Sector 2 | 0% | 15 | No
Survey/align R3 Drift chambers Sector 3 | 0% | 15 | No
Survey/align R3 Drift chambers Sector 4 | 0% | 15 | No
Survey/align R3 Drift chambers Sector 5 | 0% | 15 | No
Survey/align R3 Drift chambers Sector 6 | 0% | 15 | No
242710.1 | Solenoid - Instrumentation Magnet Protection System Design | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Define Operational Parameters & Harware | 0% | 20 | No
Develop Process & Control Plan (Analysis, Design & Evaluation) | 0% | 20 | No
Develop Acceptance Criterion | 0% | 20 | No
Develop Receipt & Inspection Process | 0% | 20 | No
Develop Specification | 0% | 20 | No
242710.1015 | Solenoid - Instrumentation Controls Design FY13 | 20% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Define Operational Parameters & Harware | 100% | 20 | Yes
Develop Process & Control Plan (Analysis, Design & Evaluation) | 0% | 20 | No
Develop Acceptance Criterion | 0% | 20 | No
Develop Receipt & Inspection Process | 0% | 20 | No
Develop Specification | 0% | 20 | No
242710.1015a | Solenoid - Instrumentation Controls Design FY14 | 20% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Define Operational Parameters & Harware | 100% | 20 | Yes
Develop Process & Control Plan (Analysis, Design & Evaluation) | 0% | 20 | No
Develop Acceptance Criterion | 0% | 20 | No
Develop Receipt & Inspection Process | 0% | 20 | No
Develop Specification | 0% | 20 | No
242710.103 | Solenoid - Instrumentation Controls Assembly | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Receipt and Inspection | 0% | 15 | No
Assembly & Checkout | 0% | 40 | No
Validate and Finalize Protection System Design | 0% | 35 | No
Create Design History File | 0% | 10 | No
242711.3035 | LN2 TEST - LN2 Testing of CCM #1 | 20% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mounting of Temp /hall sensors | 0% | 10 | No
Mounting of Q Heaters | 100% | 10 | Yes
Mounting of strain gauges | 0% | 10 | No
Wiring/cable layout and HV/HV feed through wiring to the interconnect | 0% | 10 | No
Set up for calibration in the data logger | 100% | 10 | Yes
Set up process and data logging all together at room temperature | 0% | 10 | No
Wrap CCM in plastic bag and purge with dry nitrogen | 0% | 10 | No
Lift CCM into foam box and Connect instrumentation and plumbing to CCM in box | 0% | 10 | No
Monitor Coil temps during test | 0% | 10 | No
Disconnect from plumbing & instr | 0% | 5 | No
Crane lifted into the shipping crate | 0% | 5 | No
242711.304 | LN2 TEST - LN2 Testing of CCM #2 | 10% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mounting of Temp /hall sensors | 0% | 10 | No
Mounting of Q Heaters | 100% | 10 | Yes
Mounting of strain gauges | 0% | 10 | No
Wiring/cable layout and HV/HV feed through wiring to the interconnect | 0% | 10 | No
Set up for calibration in the data logger | 0% | 10 | No
Set up process and data logging all together at room temperature | 0% | 10 | No
Wrap CCM in plastic bag and purge with dry nitrogen | 0% | 10 | No
Lift CCM into foam box and Connect instrumentation and plumbing to CCM in box | 0% | 10 | No
Monitor Coil temps during test | 0% | 10 | No
Disconnect from plumbing & instr | 0% | 5 | No
Crane lifted into the shipping crate | 0% | 5 | No
242711.3045 | LN2 TEST - LN2 Testing of CCM #3 | 10% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mounting of Temp /hall sensors | 0% | 10 | No
Mounting of Q Heaters | 100% | 10 | Yes
Mounting of strain gauges | 0% | 10 | No
Wiring/cable layout and HV/HV feed through wiring to the interconnect | 0% | 10 | No
Set up for calibration in the data logger | 0% | 10 | No
Set up process and data logging all together at room temperature | 0% | 10 | No
Wrap CCM in plastic bag and purge with dry nitrogen | 0% | 10 | No
Lift CCM into foam box and Connect instrumentation and plumbing to CCM in box | 0% | 10 | No
Monitor Coil temps during test | 0% | 10 | No
Disconnect from plumbing & instr | 0% | 5 | No
Crane lifted into the shipping crate | 0% | 5 | No
242711.305 | LN2 TEST - LN2 Testing of CCM #4 | 10% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mounting of Temp /hall sensors | 0% | 10 | No
Mounting of Q Heaters | 100% | 10 | Yes
Mounting of strain gauges | 0% | 10 | No
Wiring/cable layout and HV/HV feed through wiring to the interconnect | 0% | 10 | No
Set up for calibration in the data logger | 0% | 10 | No
Set up process and data logging all together at room temperature | 0% | 10 | No
Wrap CCM in plastic bag and purge with dry nitrogen | 0% | 10 | No
Lift CCM into foam box and Connect instrumentation and plumbing to CCM in box | 0% | 10 | No
Monitor Coil temps during test | 0% | 10 | No
Disconnect from plumbing & instr | 0% | 5 | No
Crane lifted into the shipping crate | 0% | 5 | No
242711.3055 | LN2 TEST - LN2 Testing of CCM #5 | 10% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mounting of Temp /hall sensors | 0% | 10 | No
Mounting of Q Heaters | 100% | 10 | Yes
Mounting of strain gauges | 0% | 10 | No
Wiring/cable layout and HV/HV feed through wiring to the interconnect | 0% | 10 | No
Set up for calibration in the data logger | 0% | 10 | No
Set up process and data logging all together at room temperature | 0% | 10 | No
Wrap CCM in plastic bag and purge with dry nitrogen | 0% | 10 | No
Lift CCM into foam box and Connect instrumentation and plumbing to CCM in box | 0% | 10 | No
Monitor Coil temps during test | 0% | 10 | No
Disconnect from plumbing & instr | 0% | 5 | No
Crane lifted into the shipping crate | 0% | 5 | No
242711.306 | LN2 TEST - LN2 Testing of CCM #6 | 10% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mounting of Temp /hall sensors | 0% | 10 | No
Mounting of Q Heaters | 100% | 10 | Yes
Mounting of strain gauges | 0% | 10 | No
Wiring/cable layout and HV/HV feed through wiring to the interconnect | 0% | 10 | No
Set up for calibration in the data logger | 0% | 10 | No
Set up process and data logging all together at room temperature | 0% | 10 | No
Wrap CCM in plastic bag and purge with dry nitrogen | 0% | 10 | No
Lift CCM into foam box and Connect instrumentation and plumbing to CCM in box | 0% | 10 | No
Monitor Coil temps during test | 0% | 10 | No
Disconnect from plumbing & instr | 0% | 5 | No
Crane lifted into the shipping crate | 0% | 5 | No
242711.3065 | LN2 TEST - LN2 Testing of CCM #7 | 10% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mounting of Temp /hall sensors | 0% | 10 | No
Mounting of Q Heaters | 100% | 10 | Yes
Mounting of strain gauges | 0% | 10 | No
Wiring/cable layout and HV/HV feed through wiring to the interconnect | 0% | 10 | No
Set up for calibration in the data logger | 0% | 10 | No
Set up process and data logging all together at room temperature | 0% | 10 | No
Wrap CCM in plastic bag and purge with dry nitrogen | 0% | 10 | No
Lift CCM into foam box and Connect instrumentation and plumbing to CCM in box | 0% | 10 | No
Monitor Coil temps during test | 0% | 10 | No
Disconnect from plumbing & instr | 0% | 5 | No
Crane lifted into the shipping crate | 0% | 5 | No
24273012a | Wave Solder of Torus and Solenoid Magnets Travel FY14 | 75% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Trip 20 | 100% | 12.5 | Yes
Trip 21 | 100% | 12.5 | Yes
Trip 22 | 100% | 12.5 | Yes
Trip 23 | 100% | 12.5 | Yes
Trip 24 | 100% | 12.5 | Yes
Trip 25 | 100% | 12.5 | Yes
Trip 26 | 0% | 12.5 | No
Trip 27 | 0% | 12.5 | No
242742045 | Cryostat Factory - Pre-Assemble Seven Coil case shields | 40% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Glue and screw aluminum plates together with G10 joint | 0% | 35 | No
Weld P tube to plate assemblies | 0% | 25 | No
Weld coupler onto P tube and leak check welds | 100% | 15 | Yes
Glue Al support tubes into shield back | 100% | 25 | Yes
242742055 | Cryostat Factory - Pre-Assemble Seven Vacuum Jackets | 37.5% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Complete Pre-assembly of Vacuum Jacket 1 | 100% | 25 | Yes
Complete Pre-assembly of Vacuum Jacket 2 | 100% | 12.5 | Yes
Complete Pre-assembly of Vacuum Jacket 3 | 0% | 12.5 | No
Complete Pre-assembly of Vacuum Jacket 4 | 0% | 12.5 | No
Complete Pre-assembly of Vacuum Jacket 5 | 0% | 12.5 | No
Complete Pre-assembly of Vacuum Jacket 6 | 0% | 12.5 | No
Complete Pre-assembly of Vacuum Jacket 7 | 0% | 12.5 | No
242742065 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Receive, QA and Pre-assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Initial receipt inspection (CP-Torus-CCM-INSP-COLD) of CCM | 0% | 25 | No
Install OOPS cups, bumpers and IPS | 0% | 10 | No
Install tube extensions of He cooling lines. Leak check and pressure test | 0% | 15 | No
Install Instrumentation and Quench heater | 0% | 30 | No
Install MLI | 0% | 20 | No
242742070 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (MLI and LN2 shield assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Assemble LN2 Shield onto CCM with Threaded Inserts and IPS | 0% | 20 | No
Weld P tube couplers and leak and pressure check | 0% | 15 | No
Glue in plugs on Al spacer tubes | 0% | 20 | No
Route conductors, He tubes and Instrumentation wiring through to Hex connection | 0% | 20 | No
Wrap MLI on LN2 shield and place MLI tubes in through holes | 0% | 25 | No
242742075 | Cryostat Factory - Assemble 1st Article (CCM #1) Coil Cryostat with cold mass (Vac jacket weld up) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Lower CCM/LN2 shield assembly into vacuum jacket | 0% | 10 | No
Dress instrumentation, conductors and He lines into Hex ring connection point | 0% | 5 | No
Lift front vacuum jacket plate on assembly and weld in place | 0% | 30 | No
Lift and Weld upper vaccuum jacket in place | 0% | 20 | No
Straighten and weld on remaining side walls | 0% | 20 | No
Install OOPS supports and transport hardware. Ship to Hall B. | 0% | 15 | No
242743005 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Receive, QA and Pre-assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Initial receipt inspection (CP-Torus-CCM-INSP-COLD) of CCM | 0% | 25 | No
Install OOPS cups, bumpers and IPS | 0% | 10 | No
Install tube extensions of He cooling lines. Leak check and pressure test | 0% | 15 | No
Install Instrumentation and Quench heater | 0% | 30 | No
Install MLI | 0% | 20 | No
242743010 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (MLI and LN2 shield assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Assemble LN2 Shield onto CCM with Threaded Inserts and IPS | 0% | 20 | No
Weld P tube couplers and leak and pressure check | 0% | 15 | No
Glue in plugs on Al spacer tubes | 0% | 20 | No
Route conductors, He tubes and Instrumentation wiring through to Hex connection | 0% | 20 | No
Wrap MLI on LN2 shield and place MLI tubes in through holes | 0% | 25 | No
242743015 | Cryostat Factory - Assemble Coil Cryostat #2 with cold mass (Vac jacket weld up) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Lower CCM/LN2 shield assembly into vacuum jacket | 0% | 10 | No
Dress instrumentation, conductors and He lines into Hex ring connection point | 0% | 5 | No
Lift front vacuum jacket plate on assembly and weld in place | 0% | 30 | No
Lift and Weld upper vaccuum jacket in place | 0% | 20 | No
Straighten and weld on remaining side walls | 0% | 20 | No
Install OOPS supports and transport hardware. Ship to Hall B. | 0% | 15 | No
242743025 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Receive, QA and Pre-assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Initial receipt inspection (CP-Torus-CCM-INSP-COLD) of CCM | 0% | 25 | No
Install OOPS cups, bumpers and IPS | 0% | 10 | No
Install tube extensions of He cooling lines. Leak check and pressure test | 0% | 15 | No
Install Instrumentation and Quench heater | 0% | 30 | No
Install MLI | 0% | 20 | No
242743030 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (MLI and LN2 shield assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Assemble LN2 Shield onto CCM with Threaded Inserts and IPS | 0% | 20 | No
Weld P tube couplers and leak and pressure check | 0% | 15 | No
Glue in plugs on Al spacer tubes | 0% | 20 | No
Route conductors, He tubes and Instrumentation wiring through to Hex connection | 0% | 20 | No
Wrap MLI on LN2 shield and place MLI tubes in through holes | 0% | 25 | No
242743035 | Cryostat Factory - Assemble Coil Cryostat #3 with cold mass (Vac jacket weld up) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Lower CCM/LN2 shield assembly into vacuum jacket | 0% | 10 | No
Dress instrumentation, conductors and He lines into Hex ring connection point | 0% | 5 | No
Lift front vacuum jacket plate on assembly and weld in place | 0% | 30 | No
Lift and Weld upper vaccuum jacket in place | 0% | 20 | No
Straighten and weld on remaining side walls | 0% | 20 | No
Install OOPS supports and transport hardware. Ship to Hall B. | 0% | 15 | No
242743045 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Receive, QA and Pre-assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Initial receipt inspection (CP-Torus-CCM-INSP-COLD) of CCM | 0% | 25 | No
Install OOPS cups, bumpers and IPS | 0% | 10 | No
Install tube extensions of He cooling lines. Leak check and pressure test | 0% | 15 | No
Install Instrumentation and Quench heater | 0% | 30 | No
Install MLI | 0% | 20 | No
242743050 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (MLI and LN2 shield assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Assemble LN2 Shield onto CCM with Threaded Inserts and IPS | 0% | 20 | No
Weld P tube couplers and leak and pressure check | 0% | 15 | No
Glue in plugs on Al spacer tubes | 0% | 20 | No
Route conductors, He tubes and Instrumentation wiring through to Hex connection | 0% | 20 | No
Wrap MLI on LN2 shield and place MLI tubes in through holes | 0% | 25 | No
242743055 | Cryostat Factory - Assemble Coil Cryostat #4 with cold mass (Vac jacket weld up) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Lower CCM/LN2 shield assembly into vacuum jacket | 0% | 10 | No
Dress instrumentation, conductors and He lines into Hex ring connection point | 0% | 5 | No
Lift front vacuum jacket plate on assembly and weld in place | 0% | 30 | No
Lift and Weld upper vaccuum jacket in place | 0% | 20 | No
Straighten and weld on remaining side walls | 0% | 20 | No
Install OOPS supports and transport hardware. Ship to Hall B. | 0% | 15 | No
242743065 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Receive, QA and Pre-assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Initial receipt inspection (CP-Torus-CCM-INSP-COLD) of CCM | 0% | 25 | No
Install OOPS cups, bumpers and IPS | 0% | 10 | No
Install tube extensions of He cooling lines. Leak check and pressure test | 0% | 15 | No
Install Instrumentation and Quench heater | 0% | 30 | No
Install MLI | 0% | 20 | No
242743070 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (MLI and LN2 shield assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Assemble LN2 Shield onto CCM with Threaded Inserts and IPS | 0% | 20 | No
Weld P tube couplers and leak and pressure check | 0% | 15 | No
Glue in plugs on Al spacer tubes | 0% | 20 | No
Route conductors, He tubes and Instrumentation wiring through to Hex connection | 0% | 20 | No
Wrap MLI on LN2 shield and place MLI tubes in through holes | 0% | 25 | No
242743075 | Cryostat Factory - Assemble Coil Cryostat #5 with cold mass (Vac jacket weld up) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Lower CCM/LN2 shield assembly into vacuum jacket | 0% | 10 | No
Dress instrumentation, conductors and He lines into Hex ring connection point | 0% | 5 | No
Lift front vacuum jacket plate on assembly and weld in place | 0% | 30 | No
Lift and Weld upper vaccuum jacket in place | 0% | 20 | No
Straighten and weld on remaining side walls | 0% | 20 | No
Install OOPS supports and transport hardware. Ship to Hall B. | 0% | 15 | No
242743085 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Receive, QA and Pre-assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Initial receipt inspection (CP-Torus-CCM-INSP-COLD) of CCM | 0% | 25 | No
Install OOPS cups, bumpers and IPS | 0% | 10 | No
Install tube extensions of He cooling lines. Leak check and pressure test | 0% | 15 | No
Install Instrumentation and Quench heater | 0% | 30 | No
Install MLI | 0% | 20 | No
242743090 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (MLI and LN2 shield assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Assemble LN2 Shield onto CCM with Threaded Inserts and IPS | 0% | 20 | No
Weld P tube couplers and leak and pressure check | 0% | 15 | No
Glue in plugs on Al spacer tubes | 0% | 20 | No
Route conductors, He tubes and Instrumentation wiring through to Hex connection | 0% | 20 | No
Wrap MLI on LN2 shield and place MLI tubes in through holes | 0% | 25 | No
242743095 | Cryostat Factory - Assemble Coil Cryostat #6 with cold mass (Vac jacket weld up) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Lower CCM/LN2 shield assembly into vacuum jacket | 0% | 10 | No
Dress instrumentation, conductors and He lines into Hex ring connection point | 0% | 5 | No
Lift front vacuum jacket plate on assembly and weld in place | 0% | 30 | No
Lift and Weld upper vaccuum jacket in place | 0% | 20 | No
Straighten and weld on remaining side walls | 0% | 20 | No
Install OOPS supports and transport hardware. Ship to Hall B. | 0% | 15 | No
242743105 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Receive, QA and Pre-assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Initial receipt inspection (CP-Torus-CCM-INSP-COLD) of CCM | 0% | 25 | No
Install OOPS cups, bumpers and IPS | 0% | 10 | No
Install tube extensions of He cooling lines. Leak check and pressure test | 0% | 15 | No
Install Instrumentation and Quench heater | 0% | 30 | No
Install MLI | 0% | 20 | No
242743110 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (MLI and LN2 shield assembly) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Assemble LN2 Shield onto CCM with Threaded Inserts and IPS | 0% | 20 | No
Weld P tube couplers and leak and pressure check | 0% | 15 | No
Glue in plugs on Al spacer tubes | 0% | 20 | No
Route conductors, He tubes and Instrumentation wiring through to Hex connection | 0% | 20 | No
Wrap MLI on LN2 shield and place MLI tubes in through holes | 0% | 25 | No
242743115 | Cryostat Factory - Assemble Coil Cryostat #7 with cold mass (Vac jacket weld up) | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Lower CCM/LN2 shield assembly into vacuum jacket | 0% | 10 | No
Dress instrumentation, conductors and He lines into Hex ring connection point | 0% | 5 | No
Lift front vacuum jacket plate on assembly and weld in place | 0% | 30 | No
Lift and Weld upper vaccuum jacket in place | 0% | 20 | No
Straighten and weld on remaining side walls | 0% | 20 | No
Install OOPS supports and transport hardware. Ship to Hall B. | 0% | 15 | No
242751415 | Torus - Installation Design - Develop procedures and safety documentation | 50% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Produce list of procedures and safety documents | 100% | 25 | Yes
Write OSPs for Installation in Hall | 100% | 25 | Yes
Write Procedures for Installation in Hall | 0% | 25 | No
Complete MRR for installation in Hall | 0% | 25 | No
242762000 | Torus - Cryogenic Tower - Mechanical Engineering FY13 | 41.6% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mechanical Analysis | 0% | 9.3 | No
Sizing of Phased Seperators | 0% | 5.6 | No
Stress Analysis | 0% | 9.3 | No
Process Diagrams (P&Is) Completed | 100% | 4.6 | Yes
Final Instrumentation | 0% | 1.9 | No
Thermo Dynamic Analysis | 100% | 18.5 | Yes
FMEA | 0% | 4.6 | No
Sizing of Current Leads | 0% | 5.6 | No
Sizing of Valves and Baynonets | 0% | 5.6 | No
Sizing of Transfer Lines | 0% | 5.6 | No
Sizing of Vacuum Vessel | 0% | 5.6 | No
Sizing of Structural Components | 0% | 5.6 | No
Process Diagrams (P&Is) Initial | 100% | 18.5 | Yes
242762000a | Torus - Cryogenic Tower - Mechanical Engineering FY14 | 37% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mechanical Analysis | 0% | 9.3 | No
Sizing of Phased Seperators | 0% | 5.6 | No
Stress Analysis | 0% | 9.3 | No
Process Diagrams (P&Is) Completed | 0% | 4.6 | No
Final Instrumentation | 0% | 1.9 | No
Thermo Dynamic Analysis | 100% | 18.5 | Yes
FMEA | 0% | 4.6 | No
Sizing of Current Leads | 0% | 5.6 | No
Sizing of Valves and Baynonets | 0% | 5.6 | No
Sizing of Transfer Lines | 0% | 5.6 | No
Sizing of Vacuum Vessel | 0% | 5.6 | No
Sizing of Structural Components | 0% | 5.6 | No
Process Diagrams (P&Is) Initial | 100% | 18.5 | Yes
242762015 | Torus - Cryogenic Tower - Drafting Mechanical | 8.7% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Phased Seperators Final Drafting | 0% | 4.3 | No
Valves and Bayonets Final Drafting | 0% | 4.3 | No
Current Leads Final Drafting | 0% | 4.3 | No
Transfer lines Final Drafting | 0% | 4.3 | No
Vacuum Vessel Final Drafting | 0% | 4.3 | No
Instrumenation Final | 0% | 4.3 | No
Phased Seperators Initial Drafting | 0% | 8.7 | No
Valves and Bayonets Initial Drafting | 0% | 8.7 | No
Current Leads Initial Drafting | 0% | 8.7 | No
Transfer lines Initial Drafting | 0% | 8.7 | No
Vacuum Vessel Initial Drafting | 0% | 8.7 | No
Instrumenation Initial | 0% | 8.7 | No
Safety Components Initial | 0% | 8.7 | No
Safety Components Final | 0% | 4.3 | No
Conceptual Design | 100% | 8.7 | Yes
242771000 | Torus - Instrumentation Controls Design | 20% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Instr layout | 0% | 10 | No
P&I D | 0% | 10 | No
Basic FMEA | 100% | 20 | Yes
Safety interlocks | 0% | 10 | No
Measurement system requirement | 0% | 10 | No
Control and DAQ requirement | 0% | 10 | No
Safety hardware locks | 0% | 5 | No
Diagnostic and monitoring | 0% | 10 | No
Set design guidelines and safety | 0% | 5 | No
Layout for a set of control logic | 0% | 10 | No
242771005 | Torus - Instrumentation Magnet Protection System Design | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Fast discharge and requirement | 100% | 5 | Yes
Slow discharge and requirement | 100% | 5 | Yes
Splices and risk mitigation | 0% | 5 | No
reversal switch and breaker circuit | 100% | 5 | Yes
Dump resistor requirement and GND fault detection | 0% | 10 | No
Q detection | 0% | 10 | No
Voltage, Temp, strain, Load, flow, etc. requirement | 0% | 10 | No
Mounting and layout of the Instr components | 0% | 10 | No
GND insulation and Control QA holds | 0% | 5 | No
Q heater and Quench propagation measurement | 100% | 5 | Yes
Voltage taps and sensor mounts to live/hot wires | 0% | 5 | No
Magnet FMEA | 100% | 5 | Yes
Cryogenic FMEA with System | 0% | 5 | No
System level P&I and classified notes for interlocks | 0% | 5 | No
Splice and joint resistance test | 0% | 10 | No
242771010 | Torus - Instrumentation Sensors Procurement | 80% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Strain gauges | 100% | 10 | Yes
load cells | 0% | 10 | No
Pt100 | 100% | 10 | Yes
Cernox | 100% | 10 | Yes
Ribbon cables | 100% | 15 | Yes
Shielded twisted pair cables | 100% | 15 | Yes
Mounts for sensors | 0% | 10 | No
Solder pads | 100% | 10 | Yes
Low temp glues | 100% | 10 | Yes
242771030 | Torus - Instrumentation Magnet Protection System Procurement | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
PSU | 0% | 40 | No
Switch | 0% | 5 | No
Circuit breaker | 0% | 5 | No
Bus bars | 0% | 5 | No
Flex bus bar | 0% | 5 | No
reversal switch | 0% | 5 | No
PLC | 0% | 10 | No
Fast DAQ | 0% | 15 | No
Copper lugs for connections | 0% | 5 | No
LCW lines | 0% | 5 | No
242771035 | Torus - Instrumentation Controls Assembly | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
PLC rack built and layout | 0% | 14.3 | No
PLC programming | 0% | 14.3 | No
Fast DAQ prog | 0% | 14.3 | No
Fast DAQ wiring | 0% | 14.3 | No
PLC wiring | 0% | 14.3 | No
Interface with Cryo | 0% | 14.3 | No
interface with EPICS | 0% | 14.3 | No
242781015 | Solenoid - Magent Installation Design | 50% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Validate Initial Magnetic Design | 100% | 5 | Yes
Validate Initial Quench Design | 100% | 5 | Yes
Validate Initial Cryogenic Design | 100% | 5 | Yes
Validate Initial Structural Design | 100% | 5 | Yes
Validate Intermediate Magnetic Design | 100% | 5 | Yes
Validate Intermediate Quench Design | 100% | 5 | Yes
Validate Intermediate Cryogenic Design | 100% | 5 | Yes
Validate Intermediate Structural Design | 100% | 5 | Yes
Validate Final Magnetic Design | 0% | 5 | No
Validate Final Quench Design | 100% | 5 | Yes
Validate FinalCryogenic Design | 100% | 5 | Yes
Validate Final Structural Design | 0% | 5 | No
Develop Solenoid/Detector Interface Documentation | 0% | 5 | No
Develop Solenoid/Cryogenic Interface Documentation | 0% | 5 | No
Develop Instrumentation & Controls Interface Documentation | 0% | 5 | No
Develop Installation Interface and Plan | 0% | 5 | No
Develop Operational Parameters Documentation | 0% | 5 | No
Validate & Finalize - Interface Control Documentation | 0% | 5 | No
Validate & Finalize - Accepatnce Documentation | 0% | 5 | No
Create Design History File | 0% | 5 | No
242781025 | Solenoid Commissioning - Design & Documentation | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Develop Plan for Receipt and Acceptance Testing of Solenoid Magnet | 0% | 10 | No
Develop Solenoid Commissioning Plan | 0% | 15 | No
Complete Receipt and Acceptance Testing of Solenoid Magnet | 0% | 25 | No
Complete Solenoid Commissioning Plan | 0% | 30 | No
Develop Operational Performance Report | 0% | 20 | No
242791000 | Solenoid - Thermal Analysis FY13 | 83.3% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Analyze Shield Heat Load | 100% | 16.7 | Yes
Analyze Cold Mass Heat Load | 100% | 16.7 | Yes
Determine Thermal Distribution in Magnet | 100% | 16.7 | Yes
Initial ANSYS Analysis | 100% | 16.7 | Yes
Pressure Drops Analysis | 100% | 8.3 | Yes
Cool Down Analysis | 100% | 8.3 | Yes
Final ANSYS Thermal Analysis | 0% | 16.7 | No
242791000a | Solenoid - Thermal Analysis FY14 | 83.3% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Analyze Shield Heat Load | 100% | 16.7 | Yes
Analyze Cold Mass Heat Load | 100% | 16.7 | Yes
Determine Thermal Distribution in Magnet | 100% | 16.7 | Yes
Initial ANSYS Analysis | 100% | 16.7 | Yes
Pressure Drops Analysis | 100% | 8.3 | Yes
Cool Down Analysis | 100% | 8.3 | Yes
Final ANSYS Thermal Analysis | 0% | 16.7 | No
242791005 | Solenoid - Process P&Is | 50% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Thermosiphon Calculations | 100% | 25 | Yes
Cryo Report Claus owes | 100% | 25 | Yes
Final P&I Sign off | 0% | 50 | No
242791030 | Solenoid - Mechanical Design of the cryogenic can | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Mechanical Analysis | 0% | 7.6 | No
Sizing of Phased Seperators | 0% | 4.6 | No
Stress Analysis | 0% | 7.6 | No
Process Diagrams (P&Is) Completed | 0% | 3.8 | No
Final Instrumentation | 0% | 1.5 | No
Thermo Dynamic Analysis | 0% | 15.3 | No
FMEA | 0% | 3.8 | No
Sizing of Current Leads | 0% | 4.6 | No
Sizing of Valves and Baynonets | 0% | 4.6 | No
Sizing of Transfer Lines | 0% | 4.6 | No
Sizing of Vacuum Vessel | 0% | 4.6 | No
Sizing of Structural Components | 0% | 4.6 | No
Process Diagrams (P&Is) Initial | 0% | 15.3 | No
Phased Seperators Final Drafting | 0% | 0.8 | No
Valves and Bayonets Final Drafting | 0% | 0.8 | No
Current Leads Final Drafting | 0% | 0.8 | No
Transfer lines Final Drafting | 0% | 0.8 | No
Vacuum Vessel Final Drafting | 0% | 0.8 | No
Instrumenation Final | 0% | 0.8 | No
Phased Seperators Initial Drafting | 0% | 1.5 | No
Valves and Bayonets Initial Drafting | 0% | 1.5 | No
Current Leads Initial Drafting | 0% | 1.5 | No
Transfer lines Initial Drafting | 0% | 1.5 | No
Vacuum Vessel Initial Drafting | 0% | 1.5 | No
Instrumenation Initial | 0% | 1.5 | No
Safety Components Initial | 0% | 1.5 | No
Safety Components Final | 0% | 0.8 | No
Conceptual Design | 0% | 1.5 | No