## report
PMK Activities with steps
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242550 | Sector 1 - Hardware Installation | 41.1% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Install cables, labels, install ends and test cable. | 100% | 23.5 | Yes
Repairs and install shields | 100% | 17.6 | Yes
Install PMTS, WC, attach cable | 0% | 17.6 | No
Install Mirrors | 0% | 17.6 | No
Determine location and lengths of mirror extension, install | 0% | 11.8 | No
Mirror Support | 0% | 11.8 | No
242242590 | Sector 2 - Prep Box | 91.8% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Route Channel into backwall | 100% | 2 | Yes
Dry fit backwall assembly, mark holes | 100% | 4.1 | Yes
Drill and countersin sidewalls for bolts | 100% | 12.2 | Yes
Machine bottom plates as needed | 100% | 2 | Yes
Disassemble , clean and reassemble backwall | 100% | 20.4 | Yes
Fit top wall plates | 100% | 8.2 | Yes
Fill voides in top plates with carbon fiber, bond and taper seams | 100% | 8.2 | Yes
Fill backwall hardware | 100% | 4.1 | Yes
Elevate Box and backfill nose | 100% | 12.2 | Yes
Install gas lines | 100% | 4.1 | Yes
Install bottom nose plate | 100% | 4.1 | Yes
Pressure wash box | 100% | 4.1 | Yes
Install connectors in patch panel, install panel | 100% | 6.1 | Yes
Move to TED | 0% | 8.2 | No
242242595 | Sector 2 - Hardware Installation | 0% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Install cables, labels, install ends and test cable. | 0% | 23.5 | No
Repairs and install shields | 0% | 17.6 | No
Install PMTS, WC, attach cable | 0% | 17.6 | No
Install Mirrors | 0% | 17.6 | No
Determine location and lengths of mirror extension, install | 0% | 11.8 | No
Mirror Support | 0% | 11.8 | No
242242635 | Sector 3 - Prep Box | 75.5% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Route Channel into backwall | 0% | 2 | No
Dry fit backwall assembly, mark holes | 100% | 4.1 | Yes
Drill and countersin sidewalls for bolts | 100% | 12.2 | Yes
Machine bottom plates as needed | 100% | 2 | No
Disassemble , clean and reassemble backwall | 100% | 20.4 | No
Fit top wall plates | 100% | 8.2 | No
Fill voides in top plates with carbon fiber, bond and taper seams | 100% | 8.2 | No
Fill backwall hardware | 100% | 4.1 | No
Elevate Box and backfill nose | 100% | 12.2 | No
Install gas lines | 100% | 4.1 | No
Install bottom nose plate | 0% | 4.1 | No
Pressure wash box | 0% | 4.1 | No
Install connectors in patch panel, install panel | 0% | 6.1 | No
Move to TED | 0% | 8.2 | No
242242640 | Sector 3 - Hardware Installation | 0% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Install cables, labels, install ends and test cable. | 100% | 23.5 | Yes
Repairs and install shields | 0% | 17.6 | No
Install PMTS, WC, attach cable | 0% | 17.6 | No
Install Mirrors | 0% | 17.6 | No
Determine location and lengths of mirror extension, install | 0% | 11.8 | No
Mirror Support | 0% | 11.8 | No
242242680 | Sector 4 - Prep Box | 38.7% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Route Channel into backwall | 100% | 2 | No
Dry fit backwall assembly, mark holes | 100% | 4.1 | No
Drill and countersin sidewalls for bolts | 100% | 12.2 | No
Machine bottom plates as needed | 0% | 2 | No
Disassemble , clean and reassemble backwall | 100% | 20.4 | No
Fit top wall plates | 0% | 8.2 | No
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.2 | No
Fill backwall hardware | 0% | 4.1 | No
Elevate Box and backfill nose | 0% | 12.2 | No
Install gas lines | 0% | 4.1 | No
Install bottom nose plate | 0% | 4.1 | No
Pressure wash box | 0% | 4.1 | No
Install connectors in patch panel, install panel | 100% | 6.1 | Yes
Move to TED | 0% | 8.2 | No
242242685 | Sector 4 - Hardware Installation | 0% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Install cables, labels, install ends and test cable. | 0% | 23.5 | No
Repairs and install shields | 0% | 17.6 | No
Install PMTS, WC, attach cable | 0% | 17.6 | No
Install Mirrors | 0% | 17.6 | No
Determine location and lengths of mirror extension, install | 0% | 11.8 | No
Mirror Support | 0% | 11.8 | No
242242725 | Sector 5 - Prep Box | 6.1% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Route Channel into backwall | 0% | 2 | No
Dry fit backwall assembly, mark holes | 0% | 4.1 | No
Drill and countersin sidewalls for bolts | 0% | 12.2 | No
Machine bottom plates as needed | 0% | 2 | No
Disassemble , clean and reassemble backwall | 0% | 20.4 | No
Fit top wall plates | 0% | 8.2 | No
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.2 | No
Fill backwall hardware | 0% | 4.1 | No
Elevate Box and backfill nose | 0% | 12.2 | No
Install gas lines | 0% | 4.1 | No
Install bottom nose plate | 0% | 4.1 | No
Pressure wash box | 0% | 4.1 | No
Install connectors in patch panel, install panel | 100% | 6.1 | Yes
Move to TED | 0% | 8.2 | No
242242730 | Sector 5 - Hardware Installation | 0% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Install cables, labels, install ends and test cable. | 0% | 23.5 | No
Repairs and install shields | 0% | 17.6 | No
Install PMTS, WC, attach cable | 0% | 17.6 | No
Install Mirrors | 0% | 17.6 | No
Determine location and lengths of mirror extension, install | 0% | 11.8 | No
Mirror Support | 0% | 11.8 | No
242242770 | Sector 6 - Prep Box | 6.1% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Route Channel into backwall | 0% | 2 | No
Dry fit backwall assembly, mark holes | 0% | 4.1 | No
Drill and countersin sidewalls for bolts | 0% | 12.2 | No
Machine bottom plates as needed | 0% | 2 | No
Disassemble , clean and reassemble backwall | 0% | 20.4 | No
Fit top wall plates | 0% | 8.2 | No
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.2 | No
Fill backwall hardware | 0% | 4.1 | No
Elevate Box and backfill nose | 0% | 12.2 | No
Install gas lines | 0% | 4.1 | No
Install bottom nose plate | 0% | 4.1 | No
Pressure wash box | 0% | 4.1 | No
Install connectors in patch panel, install panel | 100% | 6.1 | Yes
Move to TED | 0% | 8.2 | No
242242775 | Sector 6 - Hardware Installation | 0% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
Install cables, labels, install ends and test cable. | 0% | 23.5 | No
Repairs and install shields | 0% | 17.6 | No
Install PMTS, WC, attach cable | 0% | 17.6 | No
Install Mirrors | 0% | 17.6 | No
Determine location and lengths of mirror extension, install | 0% | 11.8 | No
Mirror Support | 0% | 11.8 | No
2822X045 | LTCC - Calibration Software | 70% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
GUI Setup | 100% | 10 | Yes
Root Canvas Setup | 100% | 10 | Yes
CCDB I/O | 100% | 10 | Yes
Crate I/O | 0% | 10 | No
EVIO I/O | 100% | 10 | Yes
ET Ring I/O | 0% | 10 | No
Raw FADC Reader | 100% | 10 | Yes
Pulse FADC Reader | 100% | 10 | No
Integral FADC Reader | 100% | 10 | No
nphe fit | 0% | 10 | No
2822X050 | LTCC - Calibration Test | 0% | YOUNG G
Step Name | Step % Complete | Step Weight Percent | Completed
HV I/O | 0% | 25 | No
Data I/O | 0% | 25 | No
nphe reader | 0% | 25 | No
nphe fit | 0% | 25 | No