## report
PMK Activities with steps
Activity ID | Activity Name | Physical % Complete | RESP - Responsibility
242242055 | Alignment Tool and Lasers Installation | 15% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Tool assembly | 0% | 40 | No
Laser table assembly | 100% | 15 | Yes
Laser system assembly | 0% | 15 | No
Sector mount on tool | 0% | 30 | No
242242085 | Quality Control of Elliptical/Hyperbolic mirrors | 30% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Visual Inspection of Mirrors | 100% | 30 | Yes
Sample Mirrors Reflectivity Tests | 0% | 70 | No
242242205 | Mirrors Laser Alignments | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Laser Setup | 0% | 10 | No
Laser/Box Survey | 0% | 30 | No
Elliptical Alignment | 0% | 30 | No
Hyperbolic Alignment | 0% | 30 | No
242242220a | Online Calibration Design FY13 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 20% | 25 | No
242242220aa | Online Calibration Design FY14 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 20% | 25 | No
242242222 | Online HV Matching Design FY13 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 20% | 25 | No
242242222a | Online HV Matching Design FY14 | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
HV slow control access | 0% | 25 | No
DAQ setup | 0% | 25 | No
Software to control HV | 0% | 25 | No
SPE Histos Software | 20% | 25 | No
242242223 | Online HV Matching Test | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
1 Full sector HC connection | 0% | 50 | No
DAQ setup | 0% | 50 | No
242242240 | Gas Leak Check 6 sectors | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Nitrogen Fill 1/2" | 0% | 20 | No
Freon Fill | 0% | 20 | No
Snoop | 0% | 60 | No
242242270 | Sagging Test | 0% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Laser Mount on Box | 0% | 40 | No
Reference Mount on Box | 0% | 20 | No
Box rotation and reference check | 0% | 40 | No
242242340 | Sector 2 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242365 | Sector 3 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242390 | Sector 4 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242415 | Sector 5 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No
242242440 | Sector 6 Box Refurbish | 25% | ELOUADRHIRI L
Step Name | Step % Complete | Step Weight Percent | Completed
Box Frame Support | 100% | 5 | Yes
Cut Line Mark | 100% | 5 | Yes
Box Cut | 100% | 10 | Yes
Wall Cut | 0% | 10 | No
Box Plates Fit | 0% | 10 | No
Patch Panel Fit | 0% | 10 | No
Rear Brace | 0% | 10 | No
Nose Installation | 0% | 15 | No
PMT, Mirrors Holes | 100% | 5 | Yes
Spine Refurbish | 0% | 10 | No
Mount PMT, Mirrors, WC | 0% | 10 | No