## report
PMK Activities with steps
Activity ID | Activity Name | Physical % Complete | Duration (days)
1 | Box Prep S1 | 100% | 24.5
Step Name | Step % Complete | Step Weight Percent
Route Channel into backwall | 100% | 2.041% | 0.5
Dry fit backwall assembly, mark holes | 100% | 4.082% | 1
Drill and countersin sidewalls for bolts | 100% | 12.24% | 3
Machine bottom plates as needed | 100% | 2.041% | 0.5
Disassemble , clean and reassemble backwall | 100% | 20.41% | 5
Fit top wall plates | 100% | 8.163% | 2
Fill voides in top plates with carbon fiber, bond and taper seams | 100% | 8.163% | 2
Fill backwall hardware | 100% | 4.082% | 1
Elevate Box and backfill nose | 100% | 12.24% | 3
Install gas lines | 100% | 4.082% | 1
Install bottom nose plate | 100% | 4.082% | 1
Pressure wash box | 100% | 4.082% | 1
Install connectors in patch panel, install panel | 100% | 6.122% | 1.5
Move to TED | 100% | 8.163% | 2
1 | Hardware Installation S1 | 0% | 17
Step Name | Step % Complete | Step Weight Percent
Install cables, labels, install ends and test cable. | 100% | 23.53% | 4
Repairs and install shields | 0% | 17.65% | 3
Install PMTS, WC, attach cable | 0% | 17.65% | 3
Install Mirrors | 0% | 17.65% | 3
Determine location and lengths of mirror extension, install | 0% | 11.76% | 2
Mirror Support | 0% | 11.76% | 2
2 | Box Prep S2 | 0% | 24.5
Step Name | Step % Complete | Step Weight Percent
Route Channel into backwall | 100% | 2.041% | 0.5
Dry fit backwall assembly, mark holes | 100% | 4.082% | 1
Drill and countersin sidewalls for bolts | 100% | 12.24% | 3
Machine bottom plates as needed | 100% | 2.041% | 0.5
Disassemble , clean and reassemble backwall | 100% | 20.41% | 5
Fit top wall plates | 100% | 8.163% | 2
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.163% | 2
Fill backwall hardware | 0% | 4.082% | 1
Elevate Box and backfill nose | 0% | 12.24% | 3
Install gas lines | 0% | 4.082% | 1
Install bottom nose plate | 0% | 4.082% | 1
Pressure wash box | 0% | 4.082% | 1
Install connectors in patch panel, install panel | 0% | 6.122% | 1.5
Move to TED | 0% | 8.163% | 2
3 | Hardware Installation S2 | 0% | 17
Step Name | Step % Complete | Step Weight Percent
Install cables, labels, install ends and test cable. | 0% | 23.53% | 4
Repairs and install shields | 0% | 17.65% | 3
Install PMTS, WC, attach cable | 0% | 17.65% | 3
Install Mirrors | 0% | 17.65% | 3
Determine location and lengths of mirror extension, install | 0% | 11.76% | 2
Mirror Support | 0% | 11.76% | 2
4 | Box Prep S3 | 0% | 24.5
Step Name | Step % Complete | Step Weight Percent
Route Channel into backwall | 0% | 2.041% | 0.5
Dry fit backwall assembly, mark holes | 0% | 4.082% | 1
Drill and countersin sidewalls for bolts | 0% | 12.24% | 3
Machine bottom plates as needed | 0% | 2.041% | 0.5
Disassemble , clean and reassemble backwall | 0% | 20.41% | 5
Fit top wall plates | 0% | 8.163% | 2
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.163% | 2
Fill backwall hardware | 0% | 4.082% | 1
Elevate Box and backfill nose | 0% | 12.24% | 3
Install gas lines | 0% | 4.082% | 1
Install bottom nose plate | 0% | 4.082% | 1
Pressure wash box | 0% | 4.082% | 1
Install connectors in patch panel, install panel | 0% | 6.122% | 1.5
Move to TED | 0% | 8.163% | 2
5 | Hardware Installation S3 | 0% | 17
Step Name | Step % Complete | Step Weight Percent
Install cables, labels, install ends and test cable. | 0% | 23.53% | 4
Repairs and install shields | 0% | 17.65% | 3
Install PMTS, WC, attach cable | 0% | 17.65% | 3
Install Mirrors | 0% | 17.65% | 3
Determine location and lengths of mirror extension, install | 0% | 11.76% | 2
Mirror Support | 0% | 11.76% | 2
6 | Box Prep S4 | 0% | 24.5
Step Name | Step % Complete | Step Weight Percent
Route Channel into backwall | 0% | 2.041% | 0.5
Dry fit backwall assembly, mark holes | 0% | 4.082% | 1
Drill and countersin sidewalls for bolts | 0% | 12.24% | 3
Machine bottom plates as needed | 0% | 2.041% | 0.5
Disassemble , clean and reassemble backwall | 0% | 20.41% | 5
Fit top wall plates | 0% | 8.163% | 2
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.163% | 2
Fill backwall hardware | 0% | 4.082% | 1
Elevate Box and backfill nose | 0% | 12.24% | 3
Install gas lines | 0% | 4.082% | 1
Install bottom nose plate | 0% | 4.082% | 1
Pressure wash box | 0% | 4.082% | 1
Install connectors in patch panel, install panel | 0% | 6.122% | 1.5
Move to TED | 0% | 8.163% | 2
7 | Hardware Installation S4 | 0% | 17
Step Name | Step % Complete | Step Weight Percent
Install cables, labels, install ends and test cable. | 0% | 23.53% | 4
Repairs and install shields | 0% | 17.65% | 3
Install PMTS, WC, attach cable | 0% | 17.65% | 3
Install Mirrors | 0% | 17.65% | 3
Determine location and lengths of mirror extension, install | 0% | 11.76% | 2
Mirror Support | 0% | 11.76% | 2
8 | Box Prep S5 | 0% | 24.5
Step Name | Step % Complete | Step Weight Percent
Route Channel into backwall | 0% | 2.041% | 0.5
Dry fit backwall assembly, mark holes | 0% | 4.082% | 1
Drill and countersin sidewalls for bolts | 0% | 12.24% | 3
Machine bottom plates as needed | 0% | 2.041% | 0.5
Disassemble , clean and reassemble backwall | 0% | 20.41% | 5
Fit top wall plates | 0% | 8.163% | 2
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.163% | 2
Fill backwall hardware | 0% | 4.082% | 1
Elevate Box and backfill nose | 0% | 12.24% | 3
Install gas lines | 0% | 4.082% | 1
Install bottom nose plate | 0% | 4.082% | 1
Pressure wash box | 0% | 4.082% | 1
Install connectors in patch panel, install panel | 0% | 6.122% | 1.5
Move to TED | 0% | 8.163% | 2
9 | Hardware Installation S5 | 0% | 17
Step Name | Step % Complete | Step Weight Percent
Install cables, labels, install ends and test cable. | 0% | 23.53% | 4
Repairs and install shields | 0% | 17.65% | 3
Install PMTS, WC, attach cable | 0% | 17.65% | 3
Install Mirrors | 0% | 17.65% | 3
Determine location and lengths of mirror extension, install | 0% | 11.76% | 2
Mirror Support | 0% | 11.76% | 2
10 | Box Prep S6 | 0% | 24.5
Step Name | Step % Complete | Step Weight Percent
Route Channel into backwall | 0% | 2.041% | 0.5
Dry fit backwall assembly, mark holes | 0% | 4.082% | 1
Drill and countersin sidewalls for bolts | 0% | 12.24% | 3
Machine bottom plates as needed | 0% | 2.041% | 0.5
Disassemble , clean and reassemble backwall | 0% | 20.41% | 5
Fit top wall plates | 0% | 8.163% | 2
Fill voides in top plates with carbon fiber, bond and taper seams | 0% | 8.163% | 2
Fill backwall hardware | 0% | 4.082% | 1
Elevate Box and backfill nose | 0% | 12.24% | 3
Install gas lines | 0% | 4.082% | 1
Install bottom nose plate | 0% | 4.082% | 1
Pressure wash box | 0% | 4.082% | 1
Install connectors in patch panel, install panel | 0% | 6.122% | 1.5
Move to TED | 0% | 8.163% | 2
11 | Hardware Installation S6 | 0% | 17
Step Name | Step % Complete | Step Weight Percent
Install cables, labels, install ends and test cable. | 0% | 23.53% | 4
Repairs and install shields | 0% | 17.65% | 3
Install PMTS, WC, attach cable | 0% | 17.65% | 3
Install Mirrors | 0% | 17.65% | 3
Determine location and lengths of mirror extension, install | 0% | 11.76% | 2
Mirror Support | 0% | 11.76% | 2
12 | LTCC/HTCC Calibration Software | 20% | 56
Step Name | Step % Complete | Step Weight Percent
GUI Setup | 100% | 10% | 20
Root Canvas Setup | 100% | 10% | 2
CCDB I/O | 0% | 10% | 4
Crate I/O | 0% | 10% | 10
EVIO I/O | 0% | 10% | 20
ET Ring I/O | 0% | 10% | 4
Raw FADC Reader | 0% | 10% | 5
Pulse FADC Reader | 0% | 10% | 5
Integral FADC Reader | 0% | 10% | 5
nphe fit | 0% | 10% | 20
12 | LTCC/HTCC Calibration Test | 20% | 36
Step Name | Step % Complete | Step Weight Percent
HV I/O | 0% | 25% | 20
Data I/O | 0% | 25% | 2
nphe reader | 0% | 25% | 4
nphe fit | 0% | 25% | 10