## %complete
Activity ID | Physical % Complete | MONTHLY EV COST
2-32M | 0% | 0
2-33M | 0% | 0
2-34M | 100% | 0
2-35M | 0% | 0
2-36M | 0% | 0
2-37M | 0% | 0
242211280 | 100% | 0
242211282 | 100% | 0
242211290 | 100% | 0
242211290A | 100% | 0
242211295 | 100% | 0
242211295A | 100% | 0
242211300 | 100% | 0
242211300A | 100% | 0
242211305 | 100% | 0
242211337 | 100% | 0
242211339 | 100% | 0
242211339M | 100% | 0
242211345 | 100% | 0
242211350 | 100% | 0
242211352 | 100% | 0
242211355 | 100% | 5035
242211365 | 100% | 2509
242211402 | 74% | 4111
242211487 | 100% | 0
242211495M | 100% | 0
242211497 | 100% | 0
242211507 | 100% | 3518
242211517 | 100% | 0
242211535 | 100% | 0
242211540 | 100% | 6827
242211550 | 100% | 6827
242211760 | 100% | 0
242211765 | 100% | 0
242211835 | 100% | 0
242211840 | 100% | 0
242211845 | 100% | 0
242211878 | 100% | 0
242211880 | 100% | 2719
242211895 | 100% | 6988
242211900 | 100% | 0
242211918M | 0% | 0
242211950 | 25% | 0
242231000 | 100% | 0
242231005 | 70.55% | 2641
242231115 | 75% | 0
242231260 | 70% | 821
242231261 | 70% | 1271
242231265 | 0% | 0
242231270 | 50% | 3614
242231270A | 50% | 82
242231272 | 33.3% | 3978
242231273 | 100% | 0
242231275 | 0% | 0
242231290 | 100% | 0
242231295 | 100% | 850
242231300 | 13% | 0
242231325 | 80% | 1151
242231325A | 80% | 7125
242231335A | 53% | 0
242231340 | 50% | 0
242231355 | 33% | 0
242231360 | 50% | 0
242231362 | 0% | 0
242231365 | 0% | 0
242231370 | 0% | 0
242231385 | 32% | 7281
242231390 | 100% | 4891
242231395 | 100% | 0
242231395A | 100% | 0
242231400 | 100% | 0
242231400A | 100% | 0
242231405 | 100% | 0
242231405A | 100% | 0
242231410 | 50% | 0
242231415 | 50% | 0
242231420 | 0% | 0
242231425 | 0% | 0
242231430 | 38% | 0
242231470 | 100% | 0
242231470M | 0% | 0
242241200 | 100% | 0
242241205 | 100% | 0
242241450b | 100% | 0
242241450ba | 100% | 0
242241528 | 0% | 0
242241610 | 55% | 0
242241630 | 0% | 0
242241635 | 0% | 0
242241636 | 100% | 0
242241637 | 100% | 0
242241640 | 64% | 6106
242241642 | 100% | 0
242241646 | 100% | 0
242241650M | 0% | 0
242242505 | 100% | 0
242242512 | 80% | 3434
242242515 | 100% | 0
242242517 | 0% | 0
242242522 | 100% | 0
242242525 | 50% | 0
242242530 | 82% | 9676
242242535 | 100% | 0
242242537 | 100% | 0
242242540 | 100% | 0
242242545 | 100% | 0
242242550 | 88.1% | 2412
242242555 | 50% | 1454
242242560 | 100% | 1511
242242565 | 100% | 0
242242570 | 0% | 0
242242575 | 0% | 0
242242580 | 100% | 0
242242582 | 100% | 0
242242585 | 0% | 0
242242590 | 91.8% | 0
242242595 | 0% | 0
242242600 | 0% | 0
242242605 | 0% | 0
242242610 | 100% | 0
242242615 | 0% | 0
242242620 | 0% | 0
242242625 | 100% | 0
242242630 | 0% | 0
242242635 | 85.7% | 477
242242640 | 0% | 0
242242645 | 0% | 0
242242650 | 0% | 0
242242655 | 100% | 0
242242660 | 0% | 0
242242665 | 0% | 0
242242670 | 100% | 0
242242675 | 0% | 0
242242680 | 87.7% | 3195
242242685 | 0% | 0
242242690 | 0% | 0
242242695 | 0% | 0
242242700 | 100% | 0
242242705 | 0% | 0
242242710 | 0% | 0
242242715 | 100% | 0
242242720 | 0% | 0
242242725 | 55% | 3820
242242730 | 0% | 0
242242735 | 0% | 0
242242740 | 0% | 0
242242745 | 100% | 1465
242242750 | 0% | 0
242242755 | 0% | 0
242242760 | 100% | 0
242242765 | 0% | 0
242242770 | 46.8% | 3180
242242775 | 0% | 0
242242780 | 0% | 0
242242785 | 0% | 0
242242790 | 100% | 2930
242242795 | 0% | 0
242242800 | 0% | 0
242242805 | 0% | 0
242242810 | 0% | 0
242242900M | 0% | 0
24231002 | 100% | 0
24231005 | 50% | 0
24231006 | 30% | 0
24231011 | 0% | 0
24231012 | 0% | 0
24232022 | 100% | 0
24232030 | 100% | 0
24232035 | 100% | 0
24233000 | 0% | 0
24233002 | 0% | 0
24233005 | 100% | 0
24233010 | 0% | 0
24233030 | 0% | 0
24233040 | 0% | 0
24233045 | 0% | 0
24233055 | 0% | 0
24233065 | 100% | 0
24233068 | 0% | 0
24233069 | 0% | 0
24233070M | 0% | 0
24242003 | 0% | 0
24242040a | 0% | 0
24242055 | 0% | 0
24242060M | 0% | 0
24243005 | 0% | 0
24243010 | 0% | 0
24244030 | 85.7% | 0
24247005a | 0% | 0
24247005aB | 0% | 0
24247030 | 0% | 0
24247042 | 100% | 0
24247045 | 100% | 0
24247047 | 100% | 0
24247049 | 0% | 0
24247051 | 0% | 0
24247053 | 0% | 0
24247060M | 0% | 0
24254000 | 0% | 0
24254005 | 0% | 0
24254010 | 0% | 0
24254015 | 0% | 0
24254020 | 0% | 0
24254025 | 0% | 0
24254030 | 0% | 0
24254035 | 0% | 0
24254040 | 0% | 0
24254045 | 0% | 0
24254050 | 0% | 0
24254055 | 0% | 0
24254060 | 0% | 0
24254065 | 0% | 0
24254070 | 0% | 0
24254075 | 0% | 0
24254080 | 0% | 0
24254085 | 0% | 0
24254090 | 0% | 0
24254095 | 0% | 0
24254100 | 0% | 0
24254105 | 0% | 0
24254110 | 0% | 0
24254115 | 0% | 0
24254120 | 0% | 0
24254125 | 0% | 0
24265000 | 100% | 0
24265005 | 48.3% | 24733
24265010 | 0% | 0
24265015M | 100% | 0
24265020M | 0% | 0
24265025 | 0% | 0
24265030 | 0% | 0
24265035 | 0% | 0
24265040 | 0% | 0
24265045 | 0% | 0
24265050 | 0% | 0
24265055 | 0% | 0
24265060 | 0% | 0
24265075 | 100% | 0
24265080 | 100% | 0
24265085 | 100% | 0
24265086 | 100% | 0
24265086A | 100% | 0
24265086A05 | 100% | 0
24265086A10 | 100% | 0
24265086A15 | 100% | 0
24265086A20 | 100% | 0
24265086A25 | 100% | 0
24265086B | 100% | 0
24265086B03 | 100% | 0
24265086B05 | 100% | 0
24265086B08 | 100% | 0
24265086B10 | 100% | 0
24265086B15 | 100% | 0
24265086B20 | 100% | 0
24265086B25 | 100% | 0
24265086B30 | 100% | 0
24265086B35 | 100% | 0
24265086C | 100% | 0
24265086D | 100% | 13957
24265086F | 100% | 1871
24265086F05 | 100% | 1871
24265086F10 | 100% | 1871
24265086F15 | 100% | 1871
24265086F20 | 100% | 1871
24265086F25 | 100% | 1871
24265086G | 100% | 4215
24265086G05 | 50% | 2107
24265086G10 | 50% | 2107
24265086G15 | 50% | 2107
24265086G20 | 50% | 2107
24265086G25 | 50% | 2107
24265086H | 0% | 0
24265086H05 | 0% | 0
24265086H10 | 0% | 0
24265086H15 | 0% | 0
24265086H20 | 0% | 0
24265086H25 | 0% | 0
24265090 | 100% | 0
24265095 | 100% | 0
24265100 | 100% | 0
24265110 | 100% | 0
24265115 | 100% | 3485
24265120 | 100% | 0
24265135 | 100% | 0
24265140 | 100% | 0
24265150 | 100% | 0
24265155 | 100% | 3672
24265160 | 100% | 3485
24265175 | 100% | 0
24265185 | 100% | 2179
24265190 | 100% | 9647
24265200 | 100% | 2570
24265205 | 100% | 7344
24265210 | 100% | 391
24265225 | 100% | 2179
24265230 | 0% | 0
24265240 | 100% | 2570
24265245 | 0% | 0
24265250 | 100% | 6971
24265265 | 0% | 0
24265270 | 0% | 0
24265280 | 0% | 0
24265285 | 0% | 0
24265287 | 0% | 0
24265290 | 0% | 0
24265292 | 0% | 0
24265295 | 0% | 0
24265300 | 0% | 0
24265305 | 0% | 0
24265310 | 0% | 0
24265315 | 0% | 0
24265320 | 0% | 0
24265325 | 0% | 0
24265325A | 0% | 0
24265330 | 0% | 0
24265335 | 0% | 0
24265335A | 0% | 0
24265335B | 0% | 0
24265335C | 0% | 0
24265335D | 0% | 0
24265335F | 0% | 0
24265340 | 0% | 0
24265342 | 0% | 0
24265342A | 0% | 0
24265342B | 0% | 0
24265342C | 0% | 0
24265342D | 0% | 0
24265342F | 0% | 0
24265343 | 0% | 0
24265345 | 0% | 0
24265345A | 0% | 0
24265345B | 0% | 0
24265345C | 0% | 0
24265345D | 0% | 0
24265345F | 0% | 0
24265346 | 0% | 0
24265350 | 0% | 0
24265355 | 0% | 0
24265360 | 0% | 0
24265365 | 0% | 0
24265370 | 0% | 0
24265380 | 0% | 0
24265385 | 0% | 0
24265390 | 0% | 0
24265395 | 0% | 0
24265400 | 0% | 0
24265402M | 0% | 0
24265404 | 0% | 0
24265405 | 0% | 0
24265410 | 0% | 0
24265415 | 0% | 0
24265420 | 0% | 0
24265425 | 0% | 0
24265430 | 0% | 0
24265435 | 0% | 0
24265440 | 0% | 0
24265445 | 0% | 0
24265450 | 0% | 0
24265455 | 0% | 0
24266000 | 100% | 0
24266005 | 50% | 3659
24266010 | 0% | 0
24266015 | 0% | 0
24266020 | 0% | 0
24266025 | 0% | 0
24266030 | 0% | 0
24266050 | 0% | 0
24266060 | 0% | 0
24266065 | 0% | 0
24266075 | 0% | 0
24266080 | 0% | 0
24267000 | 100% | 0
24267005 | 0% | 0
24267005M | 0% | 0
24267010M | 0% | 0
24267015M | 100% | 0
24267020M | 0% | 0
24267025M | 0% | 0
24267035 | 54.79% | 11477
24267040 | 0% | 0
24267045 | 0% | 0
24267047 | 100% | 0
24267050 | 70% | 2107
24267055 | 65% | 771
24267060 | 0% | 0
24267065 | 0% | 0
24267070 | 0% | 0
24267075 | 0% | 0
24267080 | 90% | 0
24267085 | 0% | 0
24267090 | 51% | 0
24267095 | 100% | 0
24267100 | 100% | 0
24267105 | 100% | 0
24267110 | 100% | 0
24267115 | 0% | 0
24267120 | 0% | 0
24267125 | 0% | 0
24267130 | 0% | 0
24267135 | 60% | 5576
24267140 | 0% | 0
24267145 | 100% | 0
24267150 | 30% | 0
24267155 | 0% | 0
24267160 | 0% | 0
24267165 | 0% | 0
24267170 | 0% | 0
24267175 | 0% | 0
24267180 | 0% | 0
24267185 | 0% | 0
24267190 | 0% | 0
24267195 | 0% | 0
24267210 | 0% | 0
24267215 | 0% | 0
24267230 | 0% | 0
24267245M | 0% | 0
24267255 | 0% | 0
24267265M | 0% | 0
24267270 | 0% | 0
24267280 | 0% | 0
24267290 | 0% | 0
24267300 | 0% | 0
24267355 | 0% | 0
24267360 | 0% | 0
24267365 | 0% | 0
24267370 | 0% | 0
24267375 | 0% | 0
24267380 | 0% | 0
24267385 | 0% | 0
24267390 | 0% | 0
24267395M | 0% | 0
242710.1045 | 100% | 0
242710.105 | 0% | 0
242710.1055 | 100% | 0
242710.106 | 100% | 0
242710.107 | 0% | 0
242710.1075 | 0% | 0
242710.1078 | 0% | 0
242710.108 | 0% | 0
242710.1085 | 17.5% | 0
242710.1087 | 0% | 0
242710.109 | 0% | 0
242710.1095 | 50% | 0
242710.11 | 50% | 0
242710.1105 | 0% | 0
242710.111 | 0% | 0
242710.1115 | 0% | 0
242710.112 | 0% | 0
242710.1125 | 0% | 0
242710.113 | 0% | 0
242710.1135 | 0% | 0
242710.114 | 0% | 0
242710.1145 | 0% | 0
242710.115 | 0% | 0
242710.1155 | 0% | 0
242710.116 | 0% | 0
242710.1165 | 0% | 0
242710.117 | 0% | 0
242710.1173 | 0% | 0
242710.1175 | 0% | 0
242710.118 | 0% | 0
242710.1185 | 0% | 0
242710.119 | 0% | 0
242710.1195 | 0% | 0
242710.1197 | 0% | 0
242710.12 | 0% | 0
242710.1205 | 0% | 0
242710.121 | 0% | 0
242710.1215 | 0% | 0
242710.122 | 0% | 0
242710.1225 | 0% | 0
242710.123 | 0% | 0
242710.1235 | 0% | 0
242710.124 | 0% | 0
242710.1245 | 0% | 0
242710.125 | 0% | 0
242710.1255 | 0% | 0
242710.126 | 0% | 0
242710.1265 | 0% | 0
242710.127 | 0% | 0
242710.1275 | 0% | 0
242710.128 | 0% | 0
242710.1285 | 0% | 0
242710.129 | 0% | 0
242710.1295 | 0% | 0
242711.1025 | 100% | 0
242711.307 | 100% | 0
242711.308 | 100% | 0
242711.311 | 100% | 0
242711.5012 | 100% | 0
24271775 | 100% | 0
24271780 | 100% | 0
24271785 | 100% | 0
24271790 | 100% | 0
24271795 | 100% | 0
24271800 | 100% | 0
24271805 | 100% | 0
24271810 | 100% | 0
24271820 | 100% | 0
24271825 | 100% | 0
24271830 | 100% | 0
24271835 | 100% | 0
24271840 | 100% | 0
24271845 | 100% | 0
24271850 | 100% | 0
24271855 | 100% | 0
24271860 | 100% | 0
24271865 | 100% | 0
24271870 | 100% | 0
24271875 | 100% | 0
24271880 | 100% | 0
24271885 | 100% | 0
24271890 | 100% | 0
24271895 | 100% | 35423
24271900 | 100% | 34769
24271905 | 100% | 0
24271910 | 100% | 23383
24271915 | 100% | 0
24271925 | 100% | 23693
24271930 | 100% | 48440
24271935 | 20% | 0
24271940 | 0% | 0
24271945 | 20% | 7096
24271950 | 100% | 0
24271955 | 75% | 4700
24271960 | 83.74% | 24536
24271965 | 83.74% | 1190
24271970 | 100% | 0
24271975M | 0% | 0
24272125M | 0% | 0
24272415 | 100% | 0
24272485 | 0% | 0
24272490 | 100% | 0
24272500 | 0% | 0
24272505 | 0% | 0
24272510 | 100% | 0
24272515 | 0% | 0
24272520 | 0% | 0
24272525 | 0% | 0
24272530 | 0% | 0
24272535 | 0% | 0
24272536 | 100% | 0
24272537 | 43% | 48805
24272540 | 0% | 0
24272545 | 0% | 0
24272550 | 0% | 0
24272555 | 0% | 0
24272560 | 0% | 0
24272565 | 0% | 0
24272570 | 0% | 0
24272575 | 0% | 0
24272580 | 0% | 0
24272585 | 100% | 0
24272590 | 10% | 0
24272595 | 100% | 0
24273110 | 100% | 0
24273120 | 100% | 0
24273125 | 100% | 0
24273150 | 100% | 0
24273160 | 100% | 0
24273165 | 100% | 0
24273170 | 100% | 0
24273175 | 100% | 0
24273180 | 100% | 0
24273185 | 100% | 0
24273190 | 100% | 0
24273195 | 25% | 0
24273200 | 100% | 3693
242742085 | 100% | 0
242742095 | 100% | 3774
242743130 | 100% | 0
242743140 | 100% | 0
242743145 | 100% | 0
242743155 | 100% | 0
242743160 | 100% | 0
242743165M | 100% | 0
242743170 | 100% | 0
242743175 | 100% | 0
242743180 | 100% | 0
242743185M | 100% | 0
242743190 | 100% | 0
242743195 | 100% | 0
242743200 | 100% | 8364
242743205M | 100% | 0
242743210 | 100% | 0
242743215 | 100% | 9844
242743220 | 68.8% | 13168
242743225M | 100% | 0
242743230 | 100% | 12233
242743235 | 30.8% | 19560
242743240 | 0% | 0
242743245M | 100% | 0
242743250 | 55.5% | 15257
242743255 | 0% | 0
242743260 | 0% | 0
242743262 | 0% | 0
242743265 | 0% | 0
242743270 | 67.76% | 5271
242743275 | 67.76% | 1578
242743280 | 100% | 0
242751164 | 100% | 0
242751166 | 100% | 0
242751168 | 100% | 0
242751169 | 100% | 0
242751171 | 100% | 0
242751172 | 100% | 0
242751216 | 100% | 0
242751217 | 100% | 0
242751218 | 100% | 0
242751242 | 80% | 0
242751260A | 100% | 0
242751292 | 80% | 0
242751300A | 100% | 0
242751310A | 100% | 6191
242751325A | 20% | 0
242751330A | 0% | 0
242751335A | 0% | 0
242751360A | 100% | 0
242751365A | 100% | 3176
242751380A | 50% | 771
242751385A | 0% | 0
242751417 | 100% | 0
242751440A | 100% | 0
242751460 | 100% | 0
242751462 | 100% | 0
242751463 | 100% | 0
242751465 | 100% | 0
242751470 | 100% | 0
242751475 | 100% | 0
242751477 | 100% | 0
242751480 | 100% | 5000
242751485 | 100% | 0
242751487 | 100% | 0
242751490 | 100% | 0
242751500 | 100% | 0
242751505 | 100% | 0
242751510 | 100% | 6050
242761035 | 100% | 0
242761060 | 100% | 0
242761065 | 100% | 0
242761070 | 100% | 0
242761075 | 42.46% | 2176
242761081 | 100% | 0
242761082 | 0% | 0
242761083 | 0% | 0
242761084 | 0% | 0
242761089 | 0% | 0
242761090 | 100% | 0
242761095 | 0% | 0
242761100 | 0% | 0
242761145 | 0% | 0
242761150 | 0% | 0
242761155 | 0% | 0
242761160 | 0% | 0
242761165 | 0% | 0
242761166 | 0% | 0
242761167 | 0% | 0
242761170 | 0% | 0
242761175 | 0% | 0
242761180 | 0% | 0
242761185 | 0% | 0
242761190 | 0% | 0
242761200 | 0% | 0
242762050 | 100% | 0
242762060 | 100% | 0
242762065 | 100% | 0
242762070 | 100% | 0
242762075 | 100% | 0
242762080 | 0% | 0
242762085 | 100% | 0
242762090 | 50% | 0
242762095 | 100% | 0
242762100 | 100% | 3782
242762105 | 100% | 5901
242762110 | 66.8% | 6173
242762115 | 16.7% | 3086
242762120 | 0% | 0
242762200 | 0% | 0
242762205 | 100% | 0
242762210 | 100% | 0
242762215 | 50% | 0
242762220 | 50% | 18750
242762225 | 16.7% | 2059
242762230 | 10% | 5000
242762235 | 50% | 2697
242762240 | 50% | 16250
242762250 | 100% | 0
242762255 | 16.7% | 5266
242762260 | 0% | 0
242762265 | 0% | 0
242762270 | 0% | 0
242762275 | 0% | 0
242762285 | 100% | 0
242762290 | 100% | 0
242771050 | 100% | 0
242771055 | 0% | 0
242771060 | 100% | 0
242771070 | 100% | 0
242771080 | 100% | 0
242771085 | 100% | 0
242771100 | 100% | 0
242771105 | 100% | 0
242771110 | 100% | 0
242771115 | 100% | 0
242771120 | 100% | 0
242771130 | 100% | 0
242771135 | 100% | 8217
242771140 | 60% | 0
242771145 | 0% | 0
242771150 | 45% | 6292
242771155 | 50% | 0
242771160 | 100% | 0
242771165 | 0% | 0
242771170 | 50% | 0
242771175 | 40% | 12405
242771180 | 0% | 0
242771185 | 100% | 0
242771190 | 0% | 0
242771195 | 0% | 0
242771200 | 0% | 0
242771205 | 20% | 0
242771210 | 0% | 0
242771215 | 100% | 0
242771220 | 40% | 12156
242771225 | 100% | 10718
242771230 | 0% | 0
242771235 | 0% | 0
242771240 | 75% | 0
242771245 | 50% | 0
242771250 | 0% | 0
242771260 | 0% | 0
242771265 | 0% | 0
242771270 | 0% | 0
242771275 | 0% | 0
242771280 | 35% | 0
242771295 | 12% | 0
242771310 | 100% | 0
242771315 | 100% | 0
242771320 | 16% | 0
242771325 | 16% | 3523
242771330 | 0% | 0
242781045 | 100% | 0
242781050 | 55.08% | 42056
242781055 | 0% | 0
242781060 | 8% | 0
242781065 | 0% | 0
242781070 | 0% | 0
242781075 | 0% | 0
242781080 | 0% | 0
242781085 | 0% | 0
242781090 | 100% | 0
242781095 | 0% | 0
242781105 | 0% | 0
242791100 | 100% | 0
242791105 | 100% | 0
242791110 | 20% | 1220
242791115 | 0% | 0
242791120 | 0% | 0
242791125 | 0% | 0
242791130 | 0% | 0
242791135 | 0% | 0
242791140 | 0% | 0
242791145 | 0% | 0
242791150 | 0% | 0
242791155 | 0% | 0
242791160 | 0% | 0
242791165 | 0% | 0
242791170 | 0% | 0
242791175 | 0% | 0
242791180 | 100% | 0
242791185 | 100% | 0
242791190 | 0% | 0
242791195 | 0% | 0
242791200 | 0% | 0
242791205 | 0% | 0
242791210 | 0% | 0
242791215 | 0% | 0
242791225 | 100% | 0
242791230 | 0% | 0
242791235 | 0% | 0
242791240 | 0% | 0
242791245 | 0% | 0
242791255 | 100% | 0
242791260 | 100% | 0
28223000 | 0% | 0
28223025 | 100% | 0
28223025A | 43.2% | 4940
28223025B | 0% | 0
28223030 | 100% | 0
28223030A | 43.2% | 7354
28223030B | 0% | 0
28223040 | 0% | 0
28223045 | 67.92% | 0
28223050 | 0% | 0
28223055 | 0% | 0
28223060 | 100% | 0
28223065 | 0% | 0
28223070 | 0% | 0
28226000 | 0% | 0
28226001 | 0% | 0
28226002 | 0% | 0
28226002A | 0% | 0
28226002B | 0% | 0
28226002C | 0% | 0
28226002D | 0% | 0
28226002F | 0% | 0
28226003 | 0% | 0
28226004 | 0% | 0
28226005 | 0% | 0
28226010 | 0% | 0
28226011 | 0% | 0
28226015 | 0% | 0
28226020 | 0% | 0
28226025 | 0% | 0
28226030 | 0% | 0
28226035 | 0% | 0
28226040 | 0% | 0
28226045 | 0% | 0
28226050 | 0% | 0
28226055 | 0% | 0
28226175 | 0% | 0
28226180 | 0% | 0
28226185 | 0% | 0
28226190 | 0% | 0
28226195 | 0% | 0
28226200 | 0% | 0
28226205 | 0% | 0
28226210 | 0% | 0
28226235 | 0% | 0
28226240 | 0% | 0
28226245 | 0% | 0
28226250 | 0% | 0
28226255 | 0% | 0
28226260 | 0% | 0
28226265 | 0% | 0
28226270 | 0% | 0
28226275 | 0% | 0
28226280 | 100% | 0
28226285 | 100% | 0
28226290 | 100% | 0
28226295 | 100% | 13799
28226300 | 0% | 0
28226305 | 60% | 0
28226310 | 0% | 0
28226320 | 54.53% | 3321
28226325 | 0% | 0
28226330 | 0% | 0
28226335 | 0% | 0
28226340 | 0% | 0
28226345 | 27.95% | 0
28226350 | 0% | 0
2822X000 | 0% | 0
2822X005 | 100% | 0
2822X010 | 100% | 0
2822X015 | 40% | 3103
2822X020 | 40% | 5584
2822X025 | 0% | 0
2822X027 | 0% | 0
2822X030 | 60% | 0
2822X035 | 49.6% | 18007
2822X040 | 0% | 0
2822X045 | 90% | 0
2822X050 | 75% | 4644
2822X055 | 0% | 0
2822X060 | 0% | 0
2822X065 | 0% | 0
2822X070 | 0% | 0
2822X075 | 0% | 0
2822X080 | 0% | 0
2822X085 | 0% | 0
2822X090 | 0% | 0
2822X095 | 0% | 0
2822X100 | 0% | 0
2822X1005 | 0% | 0
2822X110 | 0% | 0
2822X115 | 0% | 0
3P-18M | 0% | 0
3P-20M | 0% | 0
3P-21M | 0% | 0
3P-22M | 0% | 0
3P-26M | 0% | 0

## Sheet3
LTCC Remaining Scope as of 31 May 2015
WBS Name | Activity ID | Activity Name | Activity Start | Activity Finish | Resource ID Name | Total Budgeted Units (Weeks) or Proc/Exp Cost | % Complete | Remaining Step Names | Step Weight Percent | May Progress | Rate | Cost |  | mw left | Sum MW per Box
1.4.2.2.4.2 LOW THRESHOLD CC | 242242512 | Al/Mg Deposit Procurement WC Procurement | 2015-01-05 08:00 | 2015-08-20 16:00 | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 31483 | 80% |  |  | 3434
1.4.2.2.4.2 LOW THRESHOLD CC | 242242512 | Al/Mg Deposit Procurement WC Procurement | 2015-01-05 08:00 | 2015-08-20 16:00 | PRCRMNT>$50K 69.PROCUREMENT>$50K 69 | 2857 | 80%
1.4.2.2.4.2 LOW THRESHOLD CC | 242242517 | Additional Al/Mg Deposit WC Procurement | 2015-04-01 08:00 | 2015-09-21 16:00 | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 30000 | 0% |  |  | 0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242525 | Additional WC Testing | 2015-04-21 08:00 | 2015-09-21 16:00 | SCIENTIST.SCIENTIST | 0.6 | 50% |  |  | 0 | 3.1032 | 0.93096
1.4.2.2.4.2 LOW THRESHOLD CC | 242242525 | Additional WC Testing | 2015-04-21 08:00 | 2015-09-21 16:00 | MECH TECH.MECH TECH | 1 | 50% |  |  | 0 | 1.9532 | 0.9766
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242530 | Divider Installation | 2015-04-01 08:00 | 2015-06-15 16:00 | ELEC TECH.ELEC TECH | 6.6 | 82% |  |  | 9676 | 1.9396 | 2.3042
1.4.2.2.4.2 LOW THRESHOLD CC | 242242530 | Divider Installation | 2015-04-01 08:00 | 2015-06-15 16:00 | VISTNG USERS.VISTNG USERS | 3.3 | 82% |  |  |  | 0.85 | 0.5049
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242550 | Sector 1 - Hardware Installation | 2015-01-23 08:00 | 2015-06-15 16:00 | MECH TECH.MECH TECH | 4.2 | 88.1% |  |  | 2412 | 1.9532 | 0.97621 |  | 0.4998
[8 empty] | Mirror Support | 11.8 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242555 | Sector 1 - Mirror Alignment | 2015-05-25 08:00 | 2015-06-16 16:00 | VISTNG USERS.VISTNG USERS | 0.5 | 50% |  |  | 1454 | 0.85 | 0.2125 |  | 0.25
1.4.2.2.4.2 LOW THRESHOLD CC | 242242555 | Sector 1 - Mirror Alignment | 2015-05-25 08:00 | 2015-06-16 16:00 | SCIENTIST.SCIENTIST | 0.8 | 50% |  |  |  | 3.1032 | 1.2413 |  | 0.4
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242570 | Sector 1 - Window Installation | 2015-06-17 08:00 | 2015-06-19 16:00 | MECH TECH.MECH TECH | 1.5 | 0% |  |  | 0 | 1.9532 | 2.9298 |  | 1.5
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242575 | Sector 1 - Window Gas Leaks Checks | 2015-06-22 08:00 | 2015-06-26 16:00 | MECH TECH.MECH TECH | 1 | 0% |  |  | 0 | 1.9532 | 1.9532 |  | 1
[12 empty] | 0 |  |  | 3.6498
1.4.2.2.4.2 LOW THRESHOLD CC | 242242590 | Sector 2 - Prep Box | 2015-01-23 08:00 | 2015-06-18 16:00 | MECH TECH.MECH TECH | 4 | 91.8% |  |  | 0 | 1.9532 | 0.64065 |  | 0.328
[8 empty] | Move to TED | 8.2 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242595 | Sector 2 - Hardware Installation | 2015-06-22 08:00 | 2015-07-14 16:00 | MECH TECH.MECH TECH | 4.2 | 0% |  |  | 0 | 1.9532 | 8.2034 |  | 4.2
[8 empty] | Install cables, labels, install ends and test cable. | 23.5 |  |  | 0
[8 empty] | Repairs and install shields | 17.6 |  |  | 0
[8 empty] | Install PMTS, WC, attach cable | 17.6 |  |  | 0
[8 empty] | Install Mirrors | 17.6 |  |  | 0
[8 empty] | Determine location and lengths of mirror extension, install | 11.8 |  |  | 0
[8 empty] | Mirror Support | 11.8 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242600 | Sector 2 - Mirror Alignment | 2015-07-15 08:00 | 2015-07-28 16:00 | VISTNG USERS.VISTNG USERS | 0.5 | 0% |  |  | 0 | 0.85 | 0.425 |  | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242600 | Sector 2 - Mirror Alignment | 2015-07-15 08:00 | 2015-07-28 16:00 | SCIENTIST.SCIENTIST | 0.8 | 0% |  |  | 0 | 3.1032 | 2.4826 |  | 0.8
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242605 | Sector 2 - Fiducialization | 2015-07-29 08:00 | 2015-07-31 16:00 | MECH TECH.MECH TECH | 0.6 | 0% |  |  | 0 | 1.9532 | 1.1719 |  | 0.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242605 | Sector 2 - Fiducialization | 2015-07-29 08:00 | 2015-07-31 16:00 | MECH ENG.MECH ENG | 0.6 | 0% |  |  | 0 | 3.082 | 1.8492 |  | 0.6
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242615 | Sector 2 - Window Installation | 2015-08-03 08:00 | 2015-08-07 16:00 | MECH TECH.MECH TECH | 1.5 | 0% |  |  | 0 | 1.9532 | 2.9298 |  | 1.5
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242620 | Sector 2 - Window Gas Leaks Checks | 2015-08-10 08:00 | 2015-08-14 16:00 | MECH TECH.MECH TECH | 1 | 0% |  |  | 0 | 1.9532 | 1.9532 |  | 1
[12 empty] | 0 |  |  | 9.528
1.4.2.2.4.2 LOW THRESHOLD CC | 242242635 | Sector 3 - Prep Box | 2015-02-19 08:00 | 2015-06-26 16:00 | MECH TECH.MECH TECH | 4 | 85.7% |  |  | 477 | 1.9532 | 1.1172 |  | 0.572
[8 empty] | Route Channel into backwall | 2 |  |  | 0
[8 empty] | Pressure wash box | 4.1 |  |  | 0
[8 empty] | Move to TED | 8.2 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242640 | Sector 3 - Hardware Installation | 2015-08-10 08:00 | 2015-08-31 16:00 | MECH TECH.MECH TECH | 4.2 | 0% |  |  | 0 | 1.9532 | 8.2034 |  | 4.2
[8 empty] | Install cables, labels, install ends and test cable. | 23.5 |  |  | 0
[8 empty] | Repairs and install shields | 17.6 |  |  | 0
[8 empty] | Install PMTS, WC, attach cable | 17.6 |  |  | 0
[8 empty] | Install Mirrors | 17.6 |  |  | 0
[8 empty] | Determine location and lengths of mirror extension, install | 11.8 |  |  | 0
[8 empty] | Mirror Support | 11.8 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242645 | Sector 3 - Mirror Alignment | 2015-09-01 08:00 | 2015-09-08 16:00 | VISTNG USERS.VISTNG USERS | 0.5 | 0% |  |  | 0 | 0.85 | 0.425 |  | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242645 | Sector 3 - Mirror Alignment | 2015-09-01 08:00 | 2015-09-08 16:00 | SCIENTIST.SCIENTIST | 0.8 | 0% |  |  | 0 | 3.1032 | 2.4826 |  | 0.8
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242650 | Sector 3 - Fiducialization | 2015-09-09 08:00 | 2015-09-10 16:00 | MECH TECH.MECH TECH | 0.6 | 0% |  |  | 0 | 1.9532 | 1.1719 |  | 0.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242650 | Sector 3 - Fiducialization | 2015-09-09 08:00 | 2015-09-10 16:00 | MECH ENG.MECH ENG | 0.6 | 0% |  |  | 0 | 3.082 | 1.8492 |  | 0.6
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242660 | Sector 3 - Window Installation | 2015-09-11 08:00 | 2015-09-16 16:00 | MECH TECH.MECH TECH | 1.5 | 0% |  |  | 0 | 1.9532 | 2.9298 |  | 1.5
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242665 | Sector 3 - Window Gas Leaks Checks | 2015-09-17 08:00 | 2015-09-22 16:00 | MECH TECH.MECH TECH | 1 | 0% |  |  | 0 | 1.9532 | 1.9532 |  | 1
[12 empty] | 0 |  |  | 9.772
1.4.2.2.4.2 LOW THRESHOLD CC | 242242680 | Sector 4 - Prep Box | 2015-02-23 08:00 | 2015-07-08 16:00 | MECH TECH.MECH TECH | 4 | 87.7% |  |  | 3195 | 1.9532 | 0.96097 |  | 0.492
[8 empty] | Pressure wash box | 4.1 |  |  | 0
[8 empty] | Move to TED | 8.2 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242685 | Sector 4 - Hardware Installation | 2015-09-17 08:00 | 2015-10-07 16:00 | MECH TECH.MECH TECH | 4.2 | 0% |  |  | 0 | 1.9532 | 8.2034 |  | 4.2
[8 empty] | Install cables, labels, install ends and test cable. | 23.5 |  |  | 0
[8 empty] | Repairs and install shields | 17.6 |  |  | 0
[8 empty] | Install PMTS, WC, attach cable | 17.6 |  |  | 0
[8 empty] | Install Mirrors | 17.6 |  |  | 0
[8 empty] | Determine location and lengths of mirror extension, install | 11.8 |  |  | 0
[8 empty] | Mirror Support | 11.8 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242690 | Sector 4 - Mirror Alignment | 2015-10-08 08:00 | 2015-10-14 16:00 | VISTNG USERS.VISTNG USERS | 0.5 | 0% |  |  | 0 | 0.85 | 0.425 |  | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242690 | Sector 4 - Mirror Alignment | 2015-10-08 08:00 | 2015-10-14 16:00 | SCIENTIST.SCIENTIST | 0.8 | 0% |  |  | 0 | 3.1032 | 2.4826 |  | 0.8
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242695 | Sector 4 - Fiducialization | 2015-10-15 08:00 | 2015-10-16 16:00 | MECH TECH.MECH TECH | 0.6 | 0% |  |  | 0 | 1.9532 | 1.1719 |  | 0.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242695 | Sector 4 - Fiducialization | 2015-10-15 08:00 | 2015-10-16 16:00 | MECH ENG.MECH ENG | 0.6 | 0% |  |  | 0 | 3.082 | 1.8492 |  | 0.6
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242705 | Sector 4 - Window Installation | 2015-10-19 08:00 | 2015-10-22 16:00 | MECH TECH.MECH TECH | 1.5 | 0% |  |  | 0 | 1.9532 | 2.9298 |  | 1.5
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242710 | Sector 4 - Window Gas Leaks Checks | 2015-10-23 08:00 | 2015-10-29 16:00 | MECH TECH.MECH TECH | 1 | 0% |  |  | 0 | 1.9532 | 1.9532 |  | 1
[12 empty] | 0 |  |  | 9.692
1.4.2.2.4.2 LOW THRESHOLD CC | 242242725 | Sector 5 - Prep Box | 2015-02-16 08:00 | 2015-08-12 16:00 | MECH TECH.MECH TECH | 4 | 55% |  |  | 3820 | 1.9532 | 3.5158 |  | 1.8
[8 empty] | Fill voides in top plates with carbon fiber, bond and taper seams | 8.2 |  |  | 0
[8 empty] | Fill backwall hardware | 4.1 |  |  | 0
[8 empty] | Elevate Box and backfill nose | 12.2 |  |  | 0
[8 empty] | Install gas lines | 4.1 |  |  | 0
[8 empty] | Install bottom nose plate | 4.1 |  |  | 0
[8 empty] | Pressure wash box | 4.1 |  |  | 0
[8 empty] | Move to TED | 8.2 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242730 | Sector 5 - Hardware Installation | 2015-10-23 08:00 | 2015-11-13 16:00 | MECH TECH.MECH TECH | 4.2 | 0% |  |  | 0 | 1.9532 | 8.2034 |  | 4.2
[8 empty] | Install cables, labels, install ends and test cable. | 23.5 |  |  | 0
[8 empty] | Repairs and install shields | 17.6 |  |  | 0
[8 empty] | Install PMTS, WC, attach cable | 17.6 |  |  | 0
[8 empty] | Install Mirrors | 17.6 |  |  | 0
[8 empty] | Determine location and lengths of mirror extension, install | 11.8 |  |  | 0
[8 empty] | Mirror Support | 11.8 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242735 | Sector 5 - Mirror Alignment | 2015-11-16 08:00 | 2015-11-20 16:00 | VISTNG USERS.VISTNG USERS | 0.5 | 0% |  |  | 0 | 0.85 | 0.425 |  | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242735 | Sector 5 - Mirror Alignment | 2015-11-16 08:00 | 2015-11-20 16:00 | SCIENTIST.SCIENTIST | 0.8 | 0% |  |  | 0 | 3.1032 | 2.4826 |  | 0.8
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242740 | Sector 5 - Fiducialization | 2015-11-23 08:00 | 2015-11-24 16:00 | MECH TECH.MECH TECH | 0.6 | 0% |  |  | 0 | 1.9532 | 1.1719 |  | 0.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242740 | Sector 5 - Fiducialization | 2015-11-23 08:00 | 2015-11-24 16:00 | MECH ENG.MECH ENG | 0.6 | 0% |  |  | 0 | 3.082 | 1.8492 |  | 0.6
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242750 | Sector 5 - Window Installation | 2015-11-25 08:00 | 2015-12-02 16:00 | MECH TECH.MECH TECH | 1.5 | 0% |  |  | 0 | 1.9532 | 2.9298 |  | 1.5
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242755 | Sector 5 - Window Gas Leaks Checks | 2015-12-03 08:00 | 2015-12-09 16:00 | MECH TECH.MECH TECH | 1 | 0% |  |  | 0 | 1.9532 | 1.9532 |  | 1
[12 empty] | 0 |  |  | 11
1.4.2.2.4.2 LOW THRESHOLD CC | 242242770 | Sector 6 - Prep Box | 2015-02-16 08:00 | 2015-09-17 16:00 | MECH TECH.MECH TECH | 4 | 46.8% |  |  | 3180 | 1.9532 | 4.1564 |  | 2.128
[8 empty] | Fit top wall plates | 8.2 |  |  | 0
[8 empty] | Fill voides in top plates with carbon fiber, bond and taper seams | 8.2 |  |  | 0
[8 empty] | Fill backwall hardware | 4.1 |  |  | 0
[8 empty] | Elevate Box and backfill nose | 12.2 |  |  | 0
[8 empty] | Install gas lines | 4.1 |  |  | 0
[8 empty] | Install bottom nose plate | 4.1 |  |  | 0
[8 empty] | Pressure wash box | 4.1 |  |  | 0
[8 empty] | Move to TED | 8.2 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242775 | Sector 6 - Hardware Installation | 2015-12-03 08:00 | 2016-01-04 16:00 | MECH TECH.MECH TECH | 4.2 | 0% |  |  | 0 | 1.9532 | 8.2034 |  | 4.2
[8 empty] | Install cables, labels, install ends and test cable. | 23.5 |  |  | 0
[8 empty] | Repairs and install shields | 17.6 |  |  | 0
[8 empty] | Install PMTS, WC, attach cable | 17.6 |  |  | 0
[8 empty] | Install Mirrors | 17.6 |  |  | 0
[8 empty] | Determine location and lengths of mirror extension, install | 11.8 |  |  | 0
[8 empty] | Mirror Support | 11.8 |  |  | 0
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242780 | Sector 6 - Mirror Alignment | 2016-01-05 08:00 | 2016-01-11 16:00 | VISTNG USERS.VISTNG USERS | 0.5 | 0% |  |  | 0 | 0.85 | 0.425 |  | 0.5
1.4.2.2.4.2 LOW THRESHOLD CC | 242242780 | Sector 6 - Mirror Alignment | 2016-01-05 08:00 | 2016-01-11 16:00 | SCIENTIST.SCIENTIST | 0.8 | 0% |  |  | 0 | 3.1032 | 2.4826 |  | 0.8
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242785 | Sector 6 - Fiducialization | 2016-01-12 08:00 | 2016-01-13 16:00 | MECH TECH.MECH TECH | 0.6 | 0% |  |  | 0 | 1.9532 | 1.1719 |  | 0.6
1.4.2.2.4.2 LOW THRESHOLD CC | 242242785 | Sector 6 - Fiducialization | 2016-01-12 08:00 | 2016-01-13 16:00 | MECH ENG.MECH ENG | 0.6 | 0% |  |  | 0 | 3.082 | 1.8492 |  | 0.6
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242795 | Sector 6 - Window Installation | 2016-01-14 08:00 | 2016-01-20 16:00 | MECH TECH.MECH TECH | 1.5 | 0% |  |  | 0 | 1.9532 | 2.9298 |  | 1.5
0
1.4.2.2.4.2 LOW THRESHOLD CC | 242242800 | Sector 6 - Window Gas Leaks Checks | 2016-01-21 08:00 | 2016-01-27 16:00 | MECH TECH.MECH TECH | 1 | 0% |  |  | 0 | 1.9532 | 1.9532 |  | 1
[12 empty] | 0 |  |  | 11.328
1.4.2.2.4.2 LOW THRESHOLD CC | 242242805 | Sector 6 - Consumables | 2015-08-13 08:00 | 2015-11-24 16:00 | EXPNS SUPPLS & MATLS.SUPPLIES & MATERIALS | 350 | 0% |  |  | 0 |  | 0
0
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267120 | Modify LTCC gas piping (Gas System Use) | 2015-06-05 08:00 | 2015-07-01 16:00 | MECH DES.MECH DES | 3 | 0% |  |  | 0 | 2.1176 | 6.3528
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267120 | Modify LTCC gas piping (Gas System Use) | 2015-06-05 08:00 | 2015-07-01 16:00 | MECH TECH.MECH TECH | 6 | 0% |  |  | 0 | 1.9532 | 11.7192
[8 empty] | NI (1 of 3) cRIO | 29.1 |  |  | 0
[8 empty] | NI (2 of 3) cRIO | 29.1 |  |  | 0
[8 empty] | NI (3 of 3) cRIO | 29.1 |  |  | 0
[8 empty] | Chassis 2 | 6.3 |  |  | 0
[8 empty] | Chassis 3 | 6.3 |  |  | 0
0
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267175 | Design LTCC nose mount | 2015-08-04 08:00 | 2015-08-14 16:00 | MECH ENG.MECH ENG | 1 | 0% |  |  | 0 | 3.082 | 3.082
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267175 | Design LTCC nose mount | 2015-08-04 08:00 | 2015-08-14 16:00 | MECH DES.MECH DES | 2 | 0% |  |  | 0 | 2.1176 | 4.2352
0
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267180 | Procure LTCC nose mounts | 2015-08-17 08:00 | 2015-10-16 16:00 | PRCRMNT<$50K 60.PROCUREMENT<$50K 60 | 4015 | 0% |  |  | 0 |  | 0
0
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267190 | Design LTCC installation tooling adapters | 2015-08-17 08:00 | 2015-09-04 16:00 | MECH ENG.MECH ENG | 1 | 0% |  |  | 0 | 3.082 | 3.082
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267190 | Design LTCC installation tooling adapters | 2015-08-17 08:00 | 2015-09-04 16:00 | MECH DES.MECH DES | 3 | 0% |  |  | 0 | 2.1176 | 6.3528
0
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267195 | Procure LTCC installation tooling adapters | 2015-09-08 08:00 | 2015-11-05 16:00 | PRCRMNT<$50K60NESC16.PROCUREMENT<$50K 60 NO ESCALATION FY16 | 1832 | 0% |  |  | 0 |  | 0
0
1.4.2.6.7 DETECTOR AND FIXTURES INSTALLATION | 24267215 | Transport and Install LTCC | 2016-02-08 08:00 | 2016-02-19 16:00 | MECH TECH.MECH TECH | 8 | 0% |  |  | 0 | 1.9532 | 15.6256
0
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X045 | LTCC - Calibration Software | 2015-01-05 08:00 | 2015-06-19 16:00 | SCIENTIST.SCIENTIST | 5 | 90% |  |  | 0 | 3.1032 | 1.5516
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X045 | LTCC - Calibration Software | 2015-01-05 08:00 | 2015-06-19 16:00 | VISTNG USERS.VISTNG USERS | 3.6 | 90% |  |  | 0 | 0.85 | 0.306
[8 empty] | ET Ring I/O | 10 |  |  | 0
0
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X050 | LTCC - Calibration Test | 2015-04-21 08:00 | 2015-06-29 16:00 | SCIENTIST.SCIENTIST | 5 | 75% |  |  | 4644 | 3.1032 | 3.879
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X050 | LTCC - Calibration Test | 2015-04-21 08:00 | 2015-06-29 16:00 | VISTNG USERS.VISTNG USERS | 3.6 | 75% |  |  |  | 0.85 | 0.765
[8 empty] | nphe fit | 25 |  |  | 0
0
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X065 | Survey (as found location) LTCC positions | 2016-02-22 08:00 | 2016-02-24 16:00 | MECH TECH.MECH TECH | 1.8 | 0% |  |  | 0 | 1.9532 | 3.5158
0
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X070 | Cable/test/repair LTCC's | 2016-02-24 08:00 | 2016-03-02 16:00 | MECH TECH.MECH TECH | 2.4 | 0% |  |  | 0 | 1.9532 | 4.6877
1.8.2.2.X HALL B COMMISSIONING WITH BEAM | 2822X070 | Cable/test/repair LTCC's | 2016-02-24 08:00 | 2016-03-02 16:00 | SCIENTIST.SCIENTIST | 1.2 | 0% |  |  | 0 | 3.1032 | 3.7238
[12 empty] | 186.3748 | Sum
[12 empty] | 117.4963 | Construction
[12 empty] | 50.4496 | Installation
[12 empty] | 18.4289 | Pre-ops