Project Overview:

1. Box modeled (DEC 2013)
2. Sagging Test (JAN 2013)
3. Box Modifications (Start March 2013, 2 month / sector)
4. Mirror Alignment (Start April 2013, 1 month / sector)

Project Manpower Tasks

1. Leak Tests part 1 can be done before clean room. A. Need George to show me how.
2. Leak Tests part 2 Per sector: TECH 1 day for test. TECH 5 days for leak tight. Total per sector: 6 days. Total for LTCC: 24 days.

Time frame: 6 days each month starting ~Oct. 2013.

1. Clean Room installation: 4 TECH 5 days. November opportunity?
2. Move LTCC sector in / out clean room: 3 TECH, ½ day. For 6 sectors: 20 days. Timeframe: 3 days every 2 months starting Feb.
3. Window installation: 2 TECH, 1 sector / day. Total: 2 TECH for 6 days. Timeframe: 6 days / month starting February.
4. Sagging test: 4 tech + Doug / 2 days. January.
5. Box modification implementation. Machine Shop. 15 days / sector? Starts in April.
6. Mirror Repairs: 1 TECH 2 days / sector. Total: 12 days.
7. PMT replacement 1 TECH / 5 days / sector. Total: 30 days.